Royal Borough of Greenwich RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| RBG #1a | Behaviour Change | - Improved kerbside Recycling via fortnightly collection | Complete | - The Towards Zero Waste (TZW) project was successfully implemented and introduced fortnightly residual waste collection to 72,000 kerbside properties. The service was supported by a ‘no side waste’ and stricter ‘contamination policy’. | - Overall residual tonnages fell by 4.8%. In addition to the service change it can also be attributed to the cost-of-living crisis. - kg per head reduced to 337.18 which is an overachievement by 18.74kg in comparison with the expected target. - We have committed to improving the recycling rate to 35.9% by 2024/25 as a result of the Towards Zero Waste (TZW) project. However, our (unaudited) recycling rate for 2023/24 increased to 33.0%. This was an increase of 3.8% on the previous year. This is due a combination of factors including internal changes in the waste acceptance protocol resulting in higher proportion of recycling rejected at the front end after collection and partly limiting collections to quality recyclables only as result of the contamination policy, which is believed to have reduced the tonnage for reprocessing. |
| RBG #1b | Behaviour Change | Improved Recycling in Flats - Retrofit recycling facilities in flats in line with ReLondon flats toolkit when it becomes practical and financially viable. - Develop business case to employ additional resources to tackle contamination in recycling within flats. - Explore feasibility to develop a contamination policy to charge managing agents for the collection of contaminated recycling bins. - Redesign posters for general waste, recycling and food waste for communal properties to improve signage | On track On track On hold Complete | - Due to financial constraints, Royal Greenwich adopted a targeted approach where certain estates were selected based on contamination logs and crew feedback to improve recycling by following elements of the ReLondon toolkit. - An inventory of 346 estates comprising of 11,573 properties has been developed. This includes 184 Royal Greenwich, 31 housing association and 131 private blocks. The inventory provides information about the type of blocks (high-rise or low-rise, private/council), number and condition of current facilities, and capacity to help determine actions and improvements. - Although there is a delay to rolling out improvements in private bocks as signed Service Level Agreements need to be in place, in the Council estates 205 checks were carried out under the monitoring programme between 8th April 2024 – 15th May 2024, identifying 73% of the recycling bins containing contamination. - The following interventions are being tested: - 18 x reverse lidded bins - 4 x twin stream bins - 17 x recycling bins with slam locks - Replacement of 10 x recycling bins with new containers - Fully refurbish 37 x recycling bins - Replacement of 20 x general waste bins due to their condition - Improvements are due to be rolled out in August ‘24 followed by monitoring. - Royal Greenwich also undertook a compositional analysis of its waste which will support future targeted comms campaign. - A Waste and Street Advisor was recruited for 12 months from November ‘23 – November ’24 to improve flats recycling. A bid has been submitted to extend this role until March ’25 to help with the Service Level Agreement process as well. - Due to other priority tasks, this is on hold. - Posters have been redesigned and are available on demand. General recycling leaflet is currently being redesigned. | - None agreed |
| RBG #1c | Behaviour Change | Business Waste - Appoint consultants to review business waste including consideration of commercial food waste subject to Defra consultation. | Delayed | - Appointment of a consultant is currently being progressed. - A project plan is to be developed for the delivery of commercial food waste collection service by March 2025. | - None agreed |
| RBG #1d | Behaviour Change | Schools - Junior Environment Champions registered with Royal Greenwich will receive engagement activities to promote the concept of ‘reduce and reuse’. - Creating online hubs to help Environmental Champions to facilitate events, waste minimisation and awareness activiti | Complete On track | - The ‘minimise/save money’ article featured in the Environment Champions newsletter in May ‘23. - In March ’24 a post-Covid review of Environment Champions was undertaken to refine the number actively participating in the scheme whilst increasing engagement and improve networking. - Currently working on an umbrella scheme to bring every volunteering activity in the borough together to capture volunteering activities more effectively and showcase projects to attract more volunteers. - Royal Greenwich will benefit from Veolia’s Sustainability Fund. Information has been shared with the Environment Champions and we will promote it on social media. | - The article reached 850 Environmental Champions in the network at that time. |
| RBG #1e | Behaviour Change | Community Awareness campaigns via website, social media and borough newsletter - Promote Waste Minimisation to support our TZW project, Love Food Hate Waste Campaign on tips to reduce food waste in the Council’s ‘Together 23’ event to be held in summer 2023. - Promote Olio app on food sharing - Promote ‘Good Food in Greenwich’ campaign on Royal Greenwich’s corporate website - Promote Freegle and Ferris (The Zero Waste app – currently under consideration) to encourage reuse to extend life of items - Participate in national campaigns such as National Recycling Week, seasonal activities e.g., waste reduction in Easter, Halloween and Christmas digital engagement | Complete Complete Complete On track On track | - Waste minimisation was promoted throughout the TZW campaign, which was delivered in six phases including the ‘Contamination Policy’ and ‘No Side Waste’ policy comms. - We carried out one Love Food Hate Waste session in March 2024. - Three sessions on Love Food Hate Waste training in the community have been carried out in 2024/25 so far, with five more planned over the summer. - ‘Together 23’ event was attended by 14,000 people where the TZW project was promoted, leaflets shared with some attendees. - The link to access Olio app has been added to the RBG website. - The link to ‘Good Food in Greenwich’ has been included on the Royal Greenwich’s website. It is also promoted to the Environment Champions. - Freegle diverted 42.3 tonnes of waste and reduced 21.6 tonnes of CO2 within the borough. This also benefitted the community by an estimated £30k. - Supported Recycle Week via social media in October 2023 - Supported Food Waste Action Week through social media in March ’24. | - It is not currently possible to get data to the level to see how many Royal Greenwich residents have accessed the site. however, all these initiatives are included on the website: Reduce your waste ¦ Royal Borough of Greenwich (royalgreenwich.gov.uk) |
| RBG #1f | Behaviour Change | Mindful Shopper - This guide will be promoted by adding the link The Mindful Shopper ¦ Your Guide to Living with Less Waste on Royal Greenwich’s corporate website to engage residents in the waste reduction campaign by encouraging them to adopt sustainable purchasing habits | Complete | - The link has been added to the website as part of ‘Reduce Your Waste’ theme | - The link has been added to the Royal Greenwich website: Reduce your waste ¦ Royal Borough of Greenwich (royalgreenwich.gov.uk) |
| RBG #1g | Behaviour Change | Library of Things (LoT) - Continue to promote ‘Library of things’ in Woolwich to encourage reuse | On-track | - The Woolwich LoT scheme - This is a non-Royal Greenwich initiative which continues to deliver benefits. | - A total of 8.6 tonnes of waste is prevented which resulted in a reduction of 0.07 kg/hh/annum which is an overachievement by 0.05 kg/hh/annum. |
| RBG #1h | Behaviour Change | RePurpose Shop (Royal Greenwich’s Reuse Shop) - Based on the 2021/22 performance of the RePurose shop Royal Greenwich will be able to divert 25 tonnes per annum including textiles and books through this initiative. - The RePurpose shop has also explored the avenue of online sales via ebay which is expected to facilitate diversion of 1.6 tonnes of waste per annum. | On-track | - The Royal Greenwich’s RePurpose Agreement with Greenwich and Bexley Community Hospice ended on 3rd November 2023. Between April ’23 – October ’23 a total of 3.5 tonnes were diverted. It equated to - 0.03kg/hh/annum, - 0.01 kg/head/annum and - contributed around 0.01% towards Royal Greenwich recycling rate. - Donations received reduced significantly over the period which couldn’t enable the initiative to be sustained. - Alternative arrangements being explored. | - 3.5 tonnes were diverted against the expected target of 24 tonnes which reduced contribution to recycling rate from 0.07% to 0.01% (an error occurred in calculating recycling rate at the time of submission of the RRP which recorded 0.02% of contribution towards recycling rate) |
| RBG #1i | Behaviour Change | Zero Waste Map - Maximise opportunities for Royal Greenwich residents to become waste free by developing a map of the businesses, facilities and workshops who support the circular economy agenda. | on-hold | - Initiative cannot be progressed due to the website revamp. To be reviewed in the future. - An inventory is being developed in the meantime to gather information about various venues who offer reuse, recycle and upcycle facilities. - An enquiry has been made with South London Partnership to learn from their experience and identify KPIs. | - None achieved currently |
| RBG #1j | Behaviour Change | Circular Economy Matchmaker - Embed the local economy into Royal Greenwich’s procurement activities and encourage more businesses to become part of this platform to increase their reach. | No longer progressed | - Attempts were made to collate and streamline all the information about businesses in the borough who follow the CE models but did not produce any fruitful outcomes. | - None agreed. |
| RBG #2 | Waste Reduction | - Pan-London Sustainable Food campaign (2022-24) | Complete | - Royal Greenwich contributed £5k towards the campaign. 2 x billboards were displayed in Woolwich Arsenal during September ’23 – October ’23. - This was also promoted through social media and Royal Greenwich’s newsletter ‘Greenwich Info’. - No further funding was secured to contribute towards this campaign beyond 2023/24. | - None agreed. |
| RBG #3 | Maximise Recycling | - Contamination policy | Complete | - The policy was successfully delivered which involves a three-stage process of tagging and leaving contaminated recycling bins uncollected and eventual removal of bins if they remained contaminated within a three-month period. - Waste and Street Advisors undertook over 3,000 individual proactive engagements. - The policy will continue to be followed as a permanent feature of the kerbside collection service. | - On average a 1% targeted communication was maintained with kerbside households which resulted in achieving 2.05 kg/hh/annum of recycling. This is 0.09 kg lower than the targeted 2.14 kg. As mentioned in Action 1, It is partly due to front end rejects of recycling between the baseline year and 2022/23 and partly due to the impact of the contamination policy. |
| RBG #4 | Maximise Recycling | - Review of Planning Guidance to better facilitate waste and recycling facilities | Delayed | - The review was delayed due to other priority tasks but is currently being progressed. Updated guidance notes are planned to be published later this year. | - None agreed |
| RBG #5a | Maximise Recycling | - Kerbside textile recycling | Delayed | - This has been put on hold due to resources being committed to the main service change in 2023/24. - This action is being progressed, however, the ongoing crisis in the second-hand textile industry may critically affect this action. | - None achieved currently |
| RBG #5b | Maximise Recycling | - Kerbside food waste collection service | On track | - Currently assessing food waste collection service models. - Expansion of food waste to remaining properties – Capital funding from Defra being challenged due to insufficient amount allocated to fully fund the service. | - None agreed. |
| RBG #5c | Maximise Recycling | - Maximise the range of recyclables from kerbside | On track | - New builds continue to receive food waste collection service. The Royal Greenwich Planning Guidance is currently under review. - A targeted monitoring programme is currently being undertaken. Please refer to point1b on flats improvement targeted campaign. - Please refer to point 5b regarding food expansion in the existing blocks of flats. | - None agreed |
| RBG #6 | Maximise Recycling | - Bring banks textile collection - Improved bring site facilities | On track | - A total of 117 tonnes of textile was successfully diverted from residual waste stream through eight bring bank sites. - Two sites have been upgraded and apertures on bins have been installed to reduce contamination but to no avail. DMR bins have been removed from both sites due to contamination and a service being provided at the kerbside already. - Royal Greenwich is planning to bid for grant funding offered by Recycle Your Electricals to introduce WEEE bins with housing units for improved storage and usage at two existing sites. | - This service contributed 0.12% towards the recycling rate against an agreed target of 0.07%. |
| RBG #7 | Reducing Environmental Impact | - Electric infrastructure upgradation of Birchmere | On track | - Consultants are currently working on a range of options to upgrade the site. Results are expected in November ’24 but a date when electric infrastructure will be more widely available is not yet known. | - None agreed |
| RBG #8 | Reducing Environmental Impact | - HVO driven vehicles | Complete | - c.30% HVO:Diesel mix being used to control cost increase of HVO use. | - c.30% reduction in CO2 from vehicles estimated |
| RBG #9a | Reducing Environmental Impact | - Rollout of telematics across the fleet and take action to improve overall driving performance | Complete | - All vehicles retrofitted with telematics solution - Action being taken to improve driving behaviour | - None agreed |
| RBG #9b | Reducing Environmental Impact | - Efficient collections | On track | - Route optimisation work stream completed as part of TZW project. Further route optimisation to take place over the next 18 months. | - None agreed |
| RBG #10 | Maximise local waste sites | - SE London Waste Technical Paper / RBG Local Plan, section 4.8.12 | On track | - No change | - No change |