- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 407.11 | 399 | 269.19kg Kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 379.49 | 369.67 | 332.43kg Kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 77 | 76 | 77kg Kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 28.9 | 32 | 26.8% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 23. | 23 | 20.7% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 0 | 0 | 0 | 100 | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100 | 100 | 100 | 100 | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 65 | 65 | 65 | 100 | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100 | 100 | 100 | 100 | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | n/a | n/a | 0 | 100 | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | n/a | n/a | 100 | 100 | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100 | 100 | 100 | 100 | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| COL#1 | Implementation of Circular Economy strategy to lead by example | - At time of writing, a new Circular Economy (CE) Strategy is in development – expect to launch in 2023. This replaces the CoL waste strategy 2013-2021. As the new CE strategy is in development at time of writing, specific activities have not yet been set. However, some actions are likely to include developing staff understanding of CE to enable staff to identify CE opportunities within their departments, embedding CE within policies and procedures. Additionally, tasks such as promoting reuse sharing platforms, encouraging residents to adopt CE behaviours and more are tasks which also form part of this RRP. Anticipate at least some actions from the CE strategy will be completed during the lifetime of this RRP and other actions to be ongoing. - CE strategy expected to be focussed mainly on internal operations and the influence which the CoL could have with external stakeholders, for example, through the planning process. Sites located outside the Square Mile may be contained in a subsequent CE Strategy although this will be kept under review. This is so that we can trial actions locally, before rolling out actions to more complex and operationally diverse sites ranging from Port of Tilbury, Heathrow Animal Reception Centre, wholesale markets to Hampstead Heath and more. - The CoL Responsible Business Strategy 2018 – 2023 has “waste” as a key priority – we will continue to liaise with colleagues during lifetime of the RBS. - The CoL Single Use Plastic Policy (SUP) outlines how we will work with our supply chain, employees and communities to eliminate unnecessary plastic waste and encourages the use of recycled content plastic where there are no other suitable alternatives. As part of this, we are engaging with our stationary supplier to identify where recycled content can be increased and packaging reduced. - We will continue to promote the CoL’s preferred internal reuse sharing platform, WARP-it. This sets out to keep resources such as furniture and stationery in use internally thereby keeping resources in use for longer and reducing disposal costs. Unclaimed items are then made available to the wider warp-it network such as schools and charities in our reuse network. The reuse network aspires to reduce waste, encourage reuse and reduce costs of buying items the CoL already has and avoidable disposal costs through providing reusable items to others. We will undertake at least 1 warp-it promotional campaign each to year to promote reuse internally | Ongoing | A & B) The Circular Economy Framework (CEF) was signed off by the court of common council and launched in January 2025. The framework’s vision is to transition the City of London Corporation to be a circular organisation which exemplifies, drives and innovates circular practices, leading the Square Mile as a circular city by 2040. With a mission to support and educate everyone who lives, works, learns and visits here to adopt circularity. Working groups are active across the organisation supporting the progression of key focus areas of the initial action plan running to 2027. The main focuses include: - Waste and Resources - Working towards compliance with Simpler Recycling across the corporate estate and preparation for March 2026 for residential services. - Additional textiles and WEEE waste services installed for residents to access. - Portfolio and Capital Projects - Inclusion of circular economy principles within the design standards - Heightened requirements for good waste management practices within our green lease clauses for rented properties. - Supply Chain - Inclusion of circular principles within larger tender exercises - Capturing of case studies of our suppliers where circular principles have been applied. - Training, Communication and Engagement - Webinar hosted on the CEF open to all employees - Campaign on reuse platform Warp-it The main focuses for the Square Mile plan include: - Built Environment - Par-taking in the ROMULUS pilot bringing together key stakeholders from across the construction industry to drive increased reuse of building materials. See action COL#34 for info - Retro-fit first approached included in our Sustainability SPD and Emerging City Plan. - Food and Beverage - Discussions with various stakeholders to explore the potential of a cup re-use scheme in the City - Training, Communication and Engagement - Public event held on 4 September 2025 bringing together experts from across different aspects of circularity to educate and inspire City business/residents. Other areas of progress include - Full review of the internal waste operations of the Corporation and the development of a new role to address our own challenges across our full estate which comes into action Sept 2025. We will also look to sign up to the OWL Plastics Pledge which the City Corporation supported the creation of. - The CE continues to be a key strategic pillar within the City Corporation with it being included as a key objective in the Corporate Plan along with being featured in the City Plan, Sustainability SPD, the Embodied Carbon Action Plan, the Net Zero Design Standards and the Sustainability Supply Chain work. C&D) - The Responsible Procurement Policy is now integrated into operations as Business as Usual where one of the key aims is “taking climate action and minimise environmental impacts of procurement on our operations and throughout our supply chain”. This includes sections on using resources more efficiently and producing less waste. The SUP is referenced in the Responsible Procurement Policy and additionally, the CoL has also participated in the One World Living Plastic Pledge working group which at time of writing, is still in development. There is also activity planned for 2025-2026 to look at plastic use in catering beyond at point of sale which have already been eliminated. Our stationery suppliers are also reducing plastic packaging – 4m of shrink wrap is stretched to extend to 60m - Shrink wrap is returned baled and recycled and investigating use of pallet collars which reduce plastic (but is heavier). E) We continue to promote warp-it and in March 2025 we had a promotional push which resulted in 99 new registrations and 24 new listings containing 624 items. Since March 2025, over 6tonnes of potential wasted items been listed, saving over 18,000kg of carbon. In addition to using warp-it, we are looking to introduce a Library of Things and Library of Our Things to further promote reuse both internally and externally. Please see action COL#36. Additionally, there has been a notable increase in awareness of trying to keep items in use for longer and more departments and teams are having conversations about reuse / repair options for eg furniture rather than disposing of items. This has resulted in a working group for disposal options being set up in 2025-2026 which is still in formation. | - Awareness raising has been the biggest impact of the actions of the CEF so far with various departments across the City Corporation now considering circularity within their operations. - Through the ROMULUS trial we are having a large impact by facilitating the different stakeholders who are usually competitors to come together to co-solution for the challenges of reuse of building materials. See COL#34 for further info - Over 18,000kg carbon and 6tonnes of potential waste avoided by listing 624 unwanted items on Warp-it since March 2025 |
| COL#2 | Encourage Circular Economy (CE) behaviours amongst residents to reduce waste and encourage reuse and repair | - Further to the expiry of the CoL waste strategy, we will continue to implement initiatives that encourage and support our residents to take responsibility to reduce the overall household waste they produce e.g. promote campaigns such as Love Food Hate Waste, No Junk Mail, Real Nappies etc Additionally, we will also e.g. promote refill and avoiding single use plastics to reduce waste to name a few. - We will also provide services and initiatives that encourage the reuse of items therefore diverting these materials from final disposal and also reducing waste. e.g. continue to grow our “Do more than just recycling” webpage which provides CE guidance, link with “mindful shopper” website, continue popular events such as Give and Take Days, Tech Takebacks, food cookery workshops and more beside to reduce waste, encourage reuse and repair. - We will also promote national and international campaigns such as Recycle Week, International Week of Waste Reduction, Repair Day etc and run events where resources allow. | ongoing | - This is ongoing – Love Food Hate Waste, Eat Like a Londoner, Real Nappies etc referred to when communicating with residents as a way to reduce food waste and included in leaflets where space allows etc. Also had promotion event on 16 June 2024 for World Refill Day in which we highlighted number of drinking fountains in the Square Mile and gave away reusable bottles / cups. Engaged with 68 people – mix of workers and visitors to Square Mile. In terms of encouraging and supporting residents to reduce / reuse their own waste, the estates in particular tend to have their own organic groups to swap unwanted items e.g. via estate WhatsApp groups / forums etc – as this is not a Recycling Team action, we have no figures for this. - “Do more than just recycle” webpage has evolved into a “circular economy” webpage which continues to be under constant review and a review of our webpages is going on at time of writing – see action COL#35. Give and Take Days (G&T) continue to go from strength to strength with G&T events on 5 October 2024 and in 2025 on 11 January, 12 April, 24 May and 12 July. Next G&T Days booked are 4 October 2025 and 10 January 2026. Other dates for 2026 TBC. Tech Takeback (TTB) events also took place at some G&T Days notably the Barbican G&T Day on 11 January 2025. We also held TTB at a new venue in St Mary Le Bow Church for the first time on 9 and 14 January 2025 where some 85 people donated 346 items equating to 356kg of items collected and a 69% reuse rate achieved. TTB’s also took place in July 2025 where 471 items were collected weighing 0.3tonnes. Additionally on 5 September 2024, we run the first wood workshop with Woodshop of Recycled Delight (WoRD) as part of Zero Waste Week which took wasted wood and turned into window-boxes therefore keeping wood in use for longer, upskilling residents and enabling them to encourage greater biodiversity e.g. by planting their handmade window-boxes. Some 9 people attended this event although 15 had registered. Received excellent feedback from attendees. Also hosted repair event on 19 October 2024 as part of International Repair Day– 98 registered but 40 were in attendance for this event. The event consisted of bike, electrical and textile repair plus worked with Team Repair to give children skills, experience and confidence to take stuff apart. We also participated in London Repair Week in March 2025 where we had 27 people attend various repair sessions. At time of writing, we are planning repair workshops for International Repair Day on 18 October 2025. - Ongoing promo of campaign weeks etc – we supported Recycle Week 2024 online, run the aforementioned wood workshop as part of Zero Waste Week and also run repair workshops as part of International Repair Day and London Repair Week. In January 2025, we also did some comms for Buy Nothing New Month. | - Increased awareness of refill points across the CoL – aside from engaging with 68 people – increased awareness of circular economy - At least 500 guests counted in the queues at the G&T Days on days mentioned queueing to take items. Actual number taking stuff is higher as number relates to in queues only and not those donating items or attended take after opening times had passed. Guesstimate at least 3t of donations over the Give and Take Days on dates mentioned. - At least 67 guests took part in Repair Workshops on dates mentioned - Some 85 people donated 346 items at TTB events in January 2025 equating to 356kg of items collected and a 69% reuse rate achieved. - All of these events raise awareness of keeping items in use for longer and therefore contribute towards recycling rate by reducing general waste. |
| COL#3 | Introduction of a “maker space” to support reuse and repair and CE behaviours | - Artizan Street library will be introducing a maker-space in mid-2023 where reuse and repair workshops will be run to enable residents and workers to repair and reuse their textiles. This will help to reduce waste and encourage CE behaviours. We will work with the library and communicate with residents, workers and visitors to promote repair workshops. - We will continue to work with libraries and other public spaces to ensure that communal areas can be used to support residents to make their belongings last longer. | ongoing | - The CoL opened its first Maker Space in Autumn 2023. The Recycling Team use the Maker Space for the repair events which have taken place on International Repair Day (IRD) ever since which have consisted of bike, textile and electrical repairs on 19 October 2024 where 40 attended workshops despite 90 registering as part of IRD. This was followed by using the same space for London Repair Week events in March 2025 where 27 people attended repair workshops. The Recycling Team will once again be holding IRD events at the Maker Space on 18 October 2025. - Libraries additionally run their own sewing workshops enabling residents to repair their own items, however, as this is not led / hosted by the Recycling Team, we have no data on this. Additionally, the Recycling Team explored the WAMITAB repair training for residents in May / June 2024 however, this was not a viable option at the time of meeting with WAMITAB / Cory owing to not having any suitable trainers. This will be kept under review so that residents may be able to be taught the skills to repair in future. | - Some 67 people attended repair events in 2024-2025 despite higher registration numbers - unknown attendee numbers from sewing workshops at libraries. Artizan Street Library continue to be venue for Give and Take events |
| COL#4 | Support refill opportunities to reduce plastic / packaging | - We promote activities that support refill and reduce plastic / single use plastic packaging such as the Refill app and signpost towards the CoL 15 drinking water refill points. - We will look into options for increasing refill opportunities in the Square Mile e.g.TopUp Truck, refiling dry foods, household detergents etc to support and encourage residents to reduce waste and refill where possible. | ongoing | a) Hosted a promotion event on 16 June for World Refill Day in which we highlighted number of drinking fountains in the CoL and gave away reusable bottles / cups. Engaged with 68 people, a mix of residents, workers and visitors alike. b) To date, have been unable to secure TopUp Truck to attend CoL events and nor are other similar organisations an option for various reasons. We keep options for future refill events under review and we also include places with refill options on our “circular economy” webpage. Additionally, the CoL has also participated in the One World Living Plastic Pledge working group which at time of writing, is still in development. | - Aside from engaging with 68 people, unable to measure impact as a result of these initiatives however raised awareness of reuse / circular economy and reducing plastic - No measurable data however raise awareness of circular economy and waste reduction therefore contribute to targets. |
| COL#5 | Food waste prevention campaigns | - The CoL is a founding fee paying member of the ReLondon food working group which aims to identify the reasons why and how food is wasted. We will continue to input into this process which aims to run food waste reduction campaigns in 2023 – 2024. The campaign is called “Eat Like a Londoner” and will be focussed on behaviour change. We will promote and engage with the campaign throughout the lifetime of the campaign. - Continue to link with Love Food Hate Waste (LFHW) / other food campaign messaging in future to reduce amount of food waste produced at home. This will be promoted via traditional and digital channels. The provision of information stands and cookery demos are subject to funding and resources. - Explore partnership and local promotion of food waste reduction apps eg.Olio, Kitche & the 'Too Good To Go' apps to reduce waste and enable food sharing - Explore options for working with or signposting towards initiatives such as community fridges/surplus to purpose etc to help keep unwanted food from City operations in use for longer. - Review procurement contracts for sites with catering to check for clauses re unwanted / surplus food. - Explore options to partner with the Food Flagship Initiative - for example a project to reduce the environmental impact of school meals, or a food redistribution network by March 2025. | ongoing | - The CoL signed up to the Eat Like a Londoner campaign for 2024-2025 as a silver member. This means that we received out of home (OOH) and online campaign promo (using Meta) during 2024-2025 – data in “impact” column. The campaign has ceased to continue into 2025-2026, however at time of writing, we understand that the campaign may evolve in future to support requirements of Simpler Recycling i.e. encourage food recycling etc. b) No cookery demos taken place since introduction of this RRP, although we will keep this under review as it’s dependent on suppliers, resources and finances. In addition to promoting LFHW, we also promote Eat Like a Londoner. Food waste messaging is promoted at events the Recycling Team attends such as the City of London’s regular Resident Question Time events and other events such as Barbican Summer Party etc. - Food reduction apps such as those listed and additionally, food waste campaigns such as Eat Like a Londoner and Love Food Hate Waste continue to be listed on our food waste / circular economy webpages to raise awareness of these ways to reduce food waste and share food. D, E & F) The Food Pantry which opened at Artizan Street Library in 2023 accepts residents from City of London and Tower Hamlets. Has now increased to two days per week – this enables residents to get cheaper food donated from elsewhere. Whilst there continues to be no community fridges in the Square Mile however, the Guildhall catering supplier works in partnership with a food distribution charity, City Harvest, which offers no-waste “charity canapes” on its menus using surplus items e.g. trimmings etc in its canapes. Each time these canapes are served at an event, a donation is made to City Harvest on behalf of each guest. In 2024, canapes were served to 572 guests at events in the Guildhall, raising funds equivalent to 1,150 meals for vulnerable Londoners.. We also work with our caterers and hold catering focussed supplier meetings. One of our catering suppliers is very focused on measuring food waste and they measure waste from: production, spoilage, hospitality, and plate waste. Data is not available to be shared publicly. Additionally, in 2024-2025, a bio-processor was installed at a CoL school which transforms unavoidable food waste into soil enricher which is used back on the school grounds – this has saved 3.8 tonnes CO2e. | - Unable to measure impact on food waste but greater awareness raising and contribute towards reducing waste and increasing recycling as demonstrated by Eat Like a London campaign results for Meta which were 152,875 impressions; 40,737 unique reach, 2,031 link clicks and 6,163 video views. OOH activity across 7 sites at 3 underground stations had 451,850 impact. - 3.8tonnes CO2e saved at a CoL school by bio-processing food waste (school located outside of the Square Mile) - In 2024, “no-waste” canapes were served to 572 guests at events in the Guildhall, raising funds equivalent to 1,150 meals for vulnerable Londoner |
| COL#6 | Review Resource and Waste (RWS) Strategy requirements to provide food waste service to all residential and commercial properties and increase participation in existing recycling services | - As part of the RWS requirements to provide food waste service to all households, we will review options for rolling this out to the remaining housing stock – approx. 35% - which doesn’t already receive a food recycling service. Non-provision to these sites is due to lack of space within binstore for a food bin or property receives a street collection. The City of London currently provide tri-weekly separate food waste collections for approx. 65% of housing stock. However, the CoL do not believe that it is possible and practical to introduce food waste to all street properties, although we will explore options as to how we may be able to deliver food services to all properties. - As the CoL does not operate a commercial waste service, we will work with our commercial waste collection partner, Veolia, to ensure they are providing separate food waste collections to commercial waste properties as this was part of the City’s specification when the portfolio of commercial waste was included in a wider tender exercise in 2019. - To further support the requirement for commercial properties, we can engage with businesses via the Clean City Awards, Heart of the City, BIDS and other business networks to help ensure compliance. - We will review the existing provision of food waste to all properties currently receiving this recycling service and take action to increase participation. Actions will include updating signage in accordance with ReLondon toolkits, reviewing operations and communications promoting the recycling service. | - On track / part complete | A & D) - We are approaching Simpler Recycling for residents to recycle their food waste in two phases; the first phase is providing food services to properties with space in their binstore or bagstore for communal food bin/s – this roll out will begin November 2025 onwards - some 27 private blocks containing 1034 flats will receive food services by Christmas 2025. The remaining properties – phase 2 - are those with street collections or no space in existing binstores. This is between 200 -250 properties with approx. 600 – 650 flats. We are exploring options for these properties however, at time of writing, it is not confirmed how these properties will be serviced as it’s not an option in the Square Mile to place food bins on street as per ReLondon’s FLASH trials – we will continue to engage with ReLondon for options. However given that we have four residential election wards, we expect uptake of food recycling from street properties (which are located outside of the four residential wards) to be fairly low given that there is a transient population and serviced apartments. When food services are introduced to properties in phase 1 and phase 2, they will receive updated leaflets based on ReLondon’s toolkits plus new stickers on bins and updated posters too. The properties already receiving food services (i.e. not included in phase 1 or phase 2) will receive updated comms / binstores etc in from 2026 onwards unless resources enable this to happen earlier. In terms of non -household municipal properties receiving food waste by March 2025, the educational establishments serviced by the CoL were already compliant and have well established food waste services. Places of worship (PoW) was a big focus in the City of London; 5 churches with kitchens already had established food services and a further 15 now have a food service as a result of Simpler Recycling. More PoW will receive the food service in due course owing to closed PoWs opening up again in Winter 2025 / Spring 2026. Owing to lack of staff / regular services at the PoW’s new to the food service, there is very little, if any, food waste regularly throughout the week, plus teething issues with the food collections there has been no noticeable impact on the recycling rate to date. b). In preparation for Simpler Recycling, we engaged with Reconomy via CBRE to carry out a review of our internal waste processes in Feb and March 2025 which had been delayed from before Christmas 2024. This raised several issues that will be addressed in 2025-2026 through the creation of a new 18-month fixed term role to review these challenges and work with the various teams and waste contractors across the Corporation to not only ensure compliance but to embed best practice, gather data and to improve waste reduction and recycling activities. c). We worked with the BIDS, HoTC and business networks to raise awareness of requirement for businesses to have a food service by April 2025. Legal requirements as part of RWS was introduced at an online Clean City Awards Best Practice Meeting on 9 December 2024 which 21 CCAS members registered for. Through the CCAS we also arranged a site visit to a bin showroom and had Defra as the guest speaker to remind businesses of their legal compliance. This took place on 25 March 2025 – due to the nature and importance and the meeting, given Defra were in attendance, it was an open event, not just for CCAS members. Disappointingly, only 33 registered for the event, however feedback received from those in attendance was excellent. We also promoted Simpler Recycling requirements via CCAS newsletters and emails whereby we also promoted WRAP’s “Business of Recycling” info. | - Expect food waste recycling rate and overall recycling rate to increase when the new food service is rolled out by December 2025 (phase 1) and again in March 2026. - Owing to lack of staff / regular services at the PoW’s new to the food service, there is very little, if any, food waste regularly throughout the week, there has been no noticeable impact on the recycling rate to date. |
| COL#7 | Trial reusable containers to reduce packaging on the go | Explore options to trial reusable containers e.g. takeaway packaging, cups etc at City events e.g. lunch markets. This could be extended to include trials at office canteen e.g. trial caulibox to encourage reuse of packaging, rather than use single use / compostable packaging. | - Delayed / on-hold / no progress to date | The Guildhall Yard Lunch markets haven’t returned post covid and therefore no opportunity to trial reusable containers. The office canteen reopened in June 2024 and in 2025, introduced discounts for not using disposable / single use items. As this is a fairly new initiative led by the caterers with support from the CoL, there is no data on impact to date. As an addition to this and as mentioned in elsewhere in this RRP we will be reviewing the potential to run a reusable cup programme within the Square Mile in 2025-2026 although this is early stages and subject to resourcing, stakeholders and finances. | - As no actions delivered yet, no impacts to report to date however actions will contribute towards targets and greater awareness of circular economy |
| COL#8 | Encourage greater composting of Christmas trees from private blocks | - As less than 1% of dwellings are houses, we are not able to promote home composting as a way to reduce waste as there are very few, if any, private gardens. The four housing estates in the Square Mile have communal outdoor space however installation of compost bins on estates has previously been denied for variety of reasons including lack of ownership / control of compost heap and communal gardens managed by different department. - The CoL continues to provide Christmas Tree recycling service whereby real Christmas Trees will be composted. We will review operations to assess options to capture more Christmas trees from private blocks with would otherwise end as general waste. This would reduce waste and increase recycling. - We will also signpost residents to renting a Christmas tree to keep trees alive and in use for longer and reduce the need for compost, thus further moving towards CE behaviours. | Ongoing | Options for residents in private blocks to compost their Christmas trees remain very limited and general composting options on estates are generally only for estate residents / participants in estate garden clubs. At time of writing, we have been made aware of a church which has a community gardening club being promoted – this is to be explored further in 2025-2026 – at time of writing, we are unaware of what options could be here. The Recycling Team also looked to start promoting reusable Christmas tree options in August 2025, however, the trees weren’t available to book as these won’t be available until October 2025 onwards at which time we will promote this to residents. | - Christmas trees continue to contribute a minimal amount towards the January 2025 recycling rate, with 1.16tonnes of Christmas trees collected in Jan 2025, comparable with the trees collected in Jan 2024 (1.1tonnes) - Promotion of reusable Christmas trees may lead to greater awareness of circular economy by signposting to rented Christmas trees. |
| COL#9 | Bulky reuse opportunities | As there are no charity shops or HWRC in the Square Mile, there are limited opportunities for residents to make unwanted bulky items available for reuse. Previous trials to reuse bulky items have proved challenging, however we will run another bulk reuse trial in 2023/2024 Additionally, as part of our Give and Take Days, we will continue to offer residents on the “host estate” free bulk collections on the day of the event to enable residents to make their bulk items available for reuse at the event to keep these items from being thrown away and support Circular Economy principles. | Ongoing | We continue to promote the British Heart Foundation (BHF) free bulk reuse service. BHF are unable to provide location specific information on items / weights collected from within CoL area. Any bulk items unclaimed at Give and Take Days and unable to be stored for next event are donated to BHF and/or Freecycle. Between April 2024 and March 2025, at least 400kg was collected post events for reuse – these items would have been leftover from Give and Take Days or good quality items set aside by our contractor during the bulk round for reuse. At time of writing, we are in early stages of exploring options with Anglo Recycling whether doorstep collections of reuse could be an option in the future. | - At least 400kg collected for reuse in 2024-2025 in addition to the items donated / claimed at our ever popular Give and Take Days. |
| COL#10 | Review residual waste provisions | Currently, all CoL properties receive a 6pw collection of recycling and general waste. As the majority of our residential population use communal bins, we are unable to restrict size of containers or identify individual properties (flats) producing a lot of waste or not recycling. We will seek to explore to the feasibility of restricting residual waste in some way e.g. shut off /reduce operational chutes. If this is a feasible option, a trial would need to be approved by Committee as would any long-term changes. If it is feasible to shut of chutes, we will undertake consumer behaviour change activities with residents to reduce waste, e.g. promote food waste campaigns such as LFHW, link to mindful shopper and encourage CE behaviours to reduce waste. Support will also be provided to building managers and concierges to ensure they are fully aware of restrictions. We will also strive to help them manage their residents waste appropriately to minimise waste and increase recycling. Promote changes via traditional and digital channels in addition to promoting recycling services. We would seek to use Resource London's communication expertise to convey messages appropriately. We would use Resource London templates, and resources where appropriate. | - Delayed / on-hold / no progress to date – | At time of writing there has been no further discussion about restricting residual waste as the focus is on preparing for Simpler Recycling requirements. We will revisit this as an option after Simpler Recycling requirements have been introduced when we will have a better understanding of the impact the changes have on the production of general waste. As mentioned, unlikely to be able to restrict provision of general waste due to the use of communal bins in the majority of our properties. | - As no actions delivered yet, no impacts to report to date. |
| COL#11 | Identify low performing flats via RFID tags | The CoL have installed bin weighing equipment on all of our refuse and recycling collection vehicles, this will allow us to identify properties deemed to have a high refuse:recycling ratio with a view to encouraging greater recycling in these properties and signpost towards waste reducing behaviours. We will communicate with residents via traditional and digital channels in addition to promoting recycling services. We will seek to use Resource London's communication expertise to convey messages appropriately. We will use Resource London templates, and resources where appropriate and provide targeted communications. | - Delayed / on-hold / no progress to date – | Problems persist with bin weighing resulting in large gaps in data. An improvement plan is in place to identify where / when bins and/or data may indicate issues and what can be done to drive an improvement in data coming through so we receive useable data. This work to improve provision of bin weighing data will continue in 2025-2026, however at time of writing, it has not been possible to identify and therefore work with low performing properties to improve performance. | - As no actions taken to date, there is no measurable impact so far although this would contribute towards recycling targets |
| COL#12 | Circular Economy statements in planning | The CoL strives to incorporate CE principles around the Square Mile and lead by example. To help build a more sustainable Square Mile, we are actively requesting CE statements in planning applications and commenting to ensure that CE principles are incorporated in the design stages of building to reduce waste, increase recycling and maximise potential throughout the design, build and deconstruction part of the process. | Ongoing | We require Circular Economy Statements (CES) to be submitted for all Major (and EIA) applications. Minor applications regularly incorporate CE principles into a sustainability statement, and there will also be occasions when a minor application will submit a CES if relevant to the proposal. We approved 18 major applications between April 2024 – March 2025. The emerging City Plan outlines a “retrofit first” approach to construction in the City and the Sustainability SPD provides detail on best practice in regard to low carbon and energy efficient development, circular construction and operation. In 2024 – 2025, some 47% of applications had more than 50% super structure retained by mass retained and 17 of 18 applications targeted a BREEAM rating of excellent or above. As mentioned, we are also involved in the Romulus trial to increase the amount of material exchange and reuse that happens within the City. See action COL#34 for further info. | - Greater awareness of circular economy and reduction of waste produced in Square Mile. Contributes to achieving the Mayor’s municipal waste recycling target of 65% by 2030 - In 2024 – 2025, 47% of applications had more than 50% super structure retained by mass retained and 17 of 18 applications targeted a BREEAM rating of excellent or above. - Data from Romulus trial to date is in action COL#34 |
| COL#13 | Diverting recyclables away from street bins | Introduce campaign to encourage people to take waste back to office/home where they should be better able to recycle it rather than placing in the street bins. Initiate campaign to divert recyclables away from street general waste bins to reduce LACW waste and increase commercial recycling. Potential for info stands to be located next to designated trial bins to promote messaging, in which items such as reusable bottles could be given away to further reduce waste, encourage behaviour change and promote circular economy behaviours. | - Complete | We launched a “take your litter away with you” campaign in Summer 2024 which featured posters on approx. 30 bins in 20 problematic locations, social media and more besides. Due to resourcing, no info stands next to bins with the signage on. With the opening of the revamped Finsbury Circus in June 2025, it was decided that upon opening, there would be no litter bins available for use therefore, forcing park users to take their litter away with them. Indications are that park users are taking litter / lunch packaging away with them and the gardeners overseeing the space haven’t encountered any big issues. | - Too early to measure. |
| Col#14 | Leading by example – external action; Business engagement activities to reduce waste and improve waste management systems overall | Through the City’s unique Clean City Award Scheme (CCAS) and by working with the Business Improvement Districts (BIDS), we will strive to continue to run business engagement activities through which we will disseminate information and best practice to reduce waste, embrace CE principles, improve air quality and improve waste management systems. We will use existing communication channels (e.g. social media, linked in, CCAS newsletter for members, other business schemes) to educate businesses on the importance of reducing waste, increasing recycling, reducing environmental impact and moving towards CE behaviours. We will also adopt and link with Resource London behaviour change activities, and the CoL has also featured in a ReLondon case study for communicating with businesses thereby demonstrating our keenness to share best practice with others. We are working with our commercial collection partner to engage with businesses and ensure customers are provided with a recycling collection service for at least the six main materials and food waste as a minimum to reduce waste and maximise recycling. The CoL will monitor WRAP’s Business Recycling Support Pilots which are due for completion in mid 2023. We will implement best practice / lessons learnt from the pilots as / when appropriate to do so with a view to increase business recycling and reducing waste. | - Ongoing | The CCAS continues to run Best Practice Meetings with events taking place in 2024 on 26 June, 9 December (legislation update special) and 25 March 2025 focused on Simpler Recycling with Defra as guest speaker. Our next Best Practice Meeting will be 28 November 2025 hosted by the CCAS Circular Economy category winner – we invite the year’s previous winners to host and present at best practice meetings to help share best practice. We continue to work with the BIDS / Heart of the City to engage businesses and also raise awareness of CCAS. The CCAS for 2025 is still in it’s membership drive however, the 2024-2025 CCAS had 46 sites join with approx. 54,000 staff on site. Additionally, we have invited last year’s winners to complete case studies and create vox-pops to help share best practice further amongst the business community and raise awareness of the CCAS. These have also been circulated through other channels e.g. Climate Action newsletter. We continue to try and build our following on social media and at time of writing have approx. 500 followers on GreenSqMile and 300 in CCAS LinkedIn accounts and just under 600 follows on Insta. We’re reducing the use of X as a social media review in 2024-2025 identified that we get the least engagement via that channel. The CCAS Team and HOTC are, at time of writing, in discussions for whether a HOTC award could be a viable option for this year or future years to recognise and reward a HOTC member for the work they are doing – this is TBC. No further info has been received on the outcomes of WRAPs business recycling support pilots. | - No measurable impact on waste reduction however will contribute to maximise recycling from local businesses, which contributes to achieving the Mayor’s municipal waste recycling target of 65% by 2030 - Business engagement levels in 2024-2025, CCAS had 46 sites registered with approx. 54,000 staff on site, 1,400 followers across social media platforms (although not known how many CoL businesses / CCAS are members) |
| COL#15 | Improve communal bin areas in accordance with Flats Recycling Project | Following successfully using the Flats Recycling Project guide to improve an estate’s bin area, we will improve communal bin areas on additional estates in line with best practice identified in Flats Recycling Project subject to funding. Aim is for this project to link in with review of RFID data to identify/ improve low performing area/s on estate/s. We will engage with stakeholders – estate staff, residents, etc to advise about changes to binstores if any are made and encourage participation in recycling service as there may be cost implications e.g. painting binstores, refurbishing bins etc. This will be supported by communication campaign using ReLondon, WRAP best practice and toolkits etc. We will review options to include recycling in tenancy agreements where possible. | On track / part complete | It was originally planned that this project would link with RFID project (COL#11) as we’d hoped to be able to measure impact of better signage on recycling rates / bin weights, however as that project is behind schedule, we will be providing refreshed signage, stickers and leaflets when we roll out phase 1 of the food service. Therefore, we will be using the Flats Recycling Project and ReLondon’s Flat Above Shops toolkits to improve communal recycling areas for phase 1 properties (COL#6) – this should be completed by December 2025. As part of the phase 1 roll out, we are also engaging with managing agents where contact details exist. Additionally, at time of writing, we are exploring potential to include a section on managing agent contact details as part of the contact with a resident via the Contact Centre to help fill in the gaps in our information. The remaining binstores which already receive a food waste service will be refreshed in 2026 onwards unless resources enable this to be done earlier. | - As no actions delivered yet, no impacts to report to date however contribute towards recycling rate target |
| COL#16 | Refresh and audit binstores provisions | We will undertake an audit of binstores, re-stickering bins with stickers produced from Flats Recycling ReLondon toolkits. We will use these binstore audits as an opportunity to identify barriers which may prevent residents from recycling or recycling all that they can, identify solutions where possible and implement best practice identified by Flats Recycling Project where practical and financially viable to do so. We will also review space to identify if additional materials can be captured in binstores e.g. food, batteries, textiles etc, although this has been and will continue to be an ongoing process. Additionally, binstore audit will form part of process for RWS preparations e.g. assessing space for the provision of food to all locations / space for separate containers etc pending confirmation of requirements to comply with the RWS consistency requirements. We will use binstore audits / restickering bins as an opportunity to deliver service leaflets to properties so residents have refreshed communications at the same time. | On track / part complete | As per COL#15, binstores receiving food services in phase 1 (COL#6) of the food roll out will have their binstores refreshed with new stickers, posters, leaflets etc. The remaining properties which already have a food service will be refreshed at a later date. Additionally the binstore audits also showed that a small number of binstores have space for additional services such as textile and WEEE bins – these will be delivered to a small number of properties in 2026-2027 if not before depending on resources, | - As no actions delivered yet, no impacts to report to date although will contribute towards recycling rate |
| COL#17 | RWS requirements to collect core materials separately from households and businesses | Previous TEEP assessment identified that the provision of multiple containers is technically impracticable in CoL binstores. Furthermore, this would also create a hazard when multiple containers placed on street for collection. This would also be financially unsustainable as has previously been identified by the TEEP assessments. This action links with the binstore audit as we will re-assess space within binstores for innovative ways to collect food waste from properties which do not currently receive this service and additionally complete audits / TEEP assessments for collecting core materials separately when the requirements of the RWS are confirmed. Should we be required to provide separate recycling for core materials, we will engage with residents using ReLondon and WRAP guidance and toolkits. As the CoL does not operate a commercial waste service we will work with our commercial waste collection partner, Veolia, to ensure they are complying with the RWS requirement. To further support the requirement for commercial properties, we can engage with businesses via the Clean City Awards, Heart of the City, BIDS and other business networks to help ensure compliance. | - Complete | Simpler Recycling requirements mean that recycling can continue to be collected co-mingled subject to the completion of a TEEP assessment. In the City of London, no changes are required to household or commercial services received by our portfolio. As part of aforementioned household binstore audits (COL#16), space has been assessed with a view to enable residents in larger blocks to be able to recycle more materials in their binstores. Additionally, we also continue to engage with commercial waste collection partner, Veolia to ensure compliance and engage with businesses via CCAS and other networks | - Maximise recycling from local businesses, which contributes to achieving the Mayor’s municipal waste recycling target of 65% by 2030 |
| COL#18 | Keep recycling services under constant review | - The CoL strives to keep recycling services provided to residents under review in all locations e.g. undertaking recycling trials including of garden waste, providing public textile recycling bins in libraries etc. - The CoL is in conversation with Podback to assess viability to trial collection of coffee pods from communal locations. Whilst this would have minimal impact on recycling rates, costs would be borne by Podback as part of an EPR and demonstrates CoL commitment to trial / provide recycling services where possible. - We will also undertake review of space within CoL carparks to ascertain whether additional recycling services can be installed e.g. textile, WEEE recycling etc. | Ongoing | We keep recycling services under constant review and the above mentioned binstore audits (COL#16) have identified some binstores which have space for more services. Libraries have established textile recycling services, however space for WEEE bins will be limited so we will pick this up after Simpler Recycling has rolled out. Additionally, textile and WEEE bins are now available in two CoL car parks (introduced in Spring 2025) therefore providing residents with more locations to recycle more items. Podback is still being promoted on the recycling pages of A-Z In the 2023-2024 update, vape recycling was added. Due to the then impending but now introduced ban of single use vapes, follow up visits by the recycling team did not take place. Sweepers are now collecting vapes separately, however, no vape recycling collections have yet taken place so there is no contribution to the recycling rate. | - Minimal impact to date from new textile and WEEE bins in car parks – 1 location has had 25kg collected. Further promo of the new recycling points will be done in Autumn 2025 - No vape collections have taken place yet therefore no contribution to recycling rate to date. |
| COL#19 | Review RWS requirements to collect garden waste from properties with garden | The CoL has 69 houses and the remaining housing stock is flats. The majority of properties do not have gardens and there are no front gardens. Trials were undertaken in 2018 and 2022 for collecting garden waste from flats; two estates and a private block which have window boxes. The results from the 2022 trial completed in November 2022 identify that incorporating a seasonal garden waste service is not a viable option owing to low tonnages. Instead, options for residents to recycle / compost their green waste will be explored in 2023 e.g. communal composting, rocket composters etc. | - On track / part complete | The Recycling Team has worked with the GIS Team to understand where “gardens” are located according to the national databases. Site visits have been undertaken to the sites on the database and these are mostly communal gardens managed by managing agent or mostly paved gardens with little / no grass. At time of writing, we are exploring a bookable and chargeable garden waste service as Defra have advised that a service should be offered to all properties with a garden. We foresee a low uptake of this service once introduced by April 2026 | As no actions delivered yet, there are no impacts to report. Previous communal bin garden waste trials have returned 5tonnes of garden waste and high contamination levels. We expect minimal uptake of this service and minimal contribution to recycling rate once introduced. |
| COL#20 | Manually collected street sweeping | Review quality of manually sorted recycling as collected by street sweepers. Dry Mixed Recycling is collected in split barrows to ensure adequate separation of recycling. We will undertake audits of sweeper collected recycling to ensure correct items are being recycled and identify additional training requirements to aid understanding of recyclable materials. Additionally, street sweepers also collect coffee cups separately from co-mingled recycling. We will continue to work with our contractor to provide toolbox talks to ensure adequate training is provided to sweepers re correct separation of recycling. | Ongoing | Audits undertaken on manually collected sweeper recycling in April 2025 identified that the quality of manually collected recycling being collected continues to be of good quality. Random audit showed approx. 6% total contamination in all sweeper recycling. Coffee cups continue to be collected separately on sweeper barrows. In 2024 – 2025, 4.42tonnes of cups were recycled from City streets which added 0.1% to the recycling rate and accounted for 0.47% of waste collected for recycling. Recent trials to collect coffee cups in tubes, rather than bags proved successful in making the process more efficient for the sweepers whilst also reducing bag use. At time of writing, new, more sturdy prototypes are being developed to place onto barrows – expect this to be in place by Spring 2026. When these new cup tubes are introduced on all barrows, we will work with contractor / undertake TBTs to remind sweepers of correct separation to prevent contamination reports and ensure maximum recycling. As mentioned in COL#18, street sweepers now also collect vapes for recycling on their barrows, however to date there have been no collections of vapes so no contribution to recycling rate thus far. | - Manually collected street sweeping contributes approx. 0.6% of recycling rate for 2024-2025 and contribute towards the COL LACW target (not 6% as incorrectly stated previously) - In 2024 – 2025, 4.42tonnes of cups were recycled from City streets which added 0.1% to the recycling rate and 0.47% of waste collected for recycling. - As no vape collections have taken place so far, there is no contribution to the recycling rate thus far. |
| COL#21 | Encouraging commercial recycling and compliance with RWS | - CoL commercial waste has been collected in partnership with our domestic waste collection contractors since 2011. This arrangement continued when the new contract was awarded in 2019 to Veolia. Commercial waste is not included as part of the CoL LACW as this disproportionately impacts our residential recycling rate due to the volume of commercial waste. - The contractor is obliged to report on all waste and recycling streams monthly as part of the contract to enable an accurate recycling rate to be calculated. - To further support the requirement for commercial properties, we will engage with businesses via the Clean City Awards, Heart of the City, BIDS and other business networks to help ensure compliance. | Ongoing | Engagement with our commercial waste collection partner is ongoing and there has been much engagement to get the Corporation’s own properties compliant with Simpler Recycling requirements for which we have a TEEP assessment to collect paper and card with mixed recycling. The new previously mentioned Circular Economy post will aim to ensure food waste is being collected from the smaller, difficult to reach locations where there are minimal staff and ensure overall compliance. Veolia continue to provide a dashboard of waste/recycling across CoL sites, however, not all data from all CoL sites is captured (especially those that don’t use Veolia) and therefore the new Circular Economy post will be looking to get a more accurate recycling rate in 2025-2026. As mentioned, we engaged with BIDS / HOTC and CCAS to promote the Simpler Recycling requirements for businesses and hosted a Best Practice Meeting with Defra in attendance in March 2025 to further raise awareness of compulsory food recycling | Working towards internal targets contained in Circular Economy Framework will contribute towards Mayor’s municipal waste recycling target of 65% by 2030 |
| COL#22 | Improve quality of recycling | Given that the majority of our housing stock use communal bins to dispose of waste and recycle, our average MRF contamination rate in 2021-2022, was approx.10% which is below an industry average for this property type. We will encourage better quality recycling and a reduction in recycling contamination by engaging with our contractor and re-introducing contamination stickers and notes through the door for residents on estates. (Estates receive a doorstep collection) | Ongoing | MRF contamination rate continues to good considering the challenges with flatted housing stock / communal bins – the 2024-2025 contamination rate for 2024-2025 was 14.4% Contamination cards on estates where doorstep collection is received will be picked up in 2026-2027. Additionally, improved signage on bins should also help to improve or maintain contamination levels going forward | - MRF contamination has increased 3.8% from 2023-2024 to 14.4%. This is due in most part to the changes in MRF Sampling processes. |
| COL#23 | DRS / EPR preparations in accordance with RWS | - Implications on introduction of EPR and DRS on recycling collections to be investigated in 2023/2024. - At time of writing the CoL is trialling a Reverse Vending Machine to trial effectiveness at capturing bottles and cans for recycling in anticipation of an introduction of a DRS / EPR scheme. In process of gathering data on which to base planning. | - Delayed / on-hold / no progress to date | The implications of EPR and DRS on recycling collections will be picked up in 2026-2027. We received a newer Reverse Vending Machine (RVM) in 2024-2025 however the newer machine also experiences technical issues resulting in no continuous data on which to baseline impact of EPR / DRS. | - The recycling collected by the RVM is being collected by host site therefore no impact on LACW or CoL recycling rate, but contribute to maximise recycling from local businesses, which contributes to achieving the Mayor’s municipal waste recycling target of 65% by 2030 |
| COL#24 | Boost recycling performance in flats by planning waste provisions | As less than 1% of housing stock is houses, we endeavour to boost recycling wherever possible including undertaking doorstepping campaigns, audits and communication campaigns. The CoL Local Plan 2015 includes Development Management Policies which accounts for waste facilities being integrated into the design of buildings which allows for separate storage and collection of recycling and food waste. All bin stores are built to comply with BS5906 specifications. Policy dictates that adequate provision must be made for the volume and types and waste and recyclables expected to be generated, especially paper and packaging waste from offices. Planning conditions relating to waste storage and collection are attached to properties and regulatory powers can also be used. We have dedicated Officers who review waste amenities at planning stage. To further boost recycling performance, we ensure that recycling is captured in the planning stages of the development of new builds to enable suitable recycling provisions to be built into the design of buildings. We will continue to engage with planners and developers to ensure this continues. We will also keep under review the information contained on webpages to ensure planners/developers are kept informed of CoL requirements for planning for residential (and commercial) buildings. | Ongoing | Inclusion of waste provisions at the planning stage is ongoing to ensure recycling, including food waste services is built into the building and therefore adequate space to enable effective recycling. As mentioned in COL#16 audits have been undertaken in binstores to assess space for more services such as textiles and WEEE to help boost recycling in some of our bigger blocks of flats. Additionally, as part of COL#6, we will be doing communication campaign to promote food waste recycling. | - Ongoing action therefore no measurable impacts especially as it can take years for a site to be built once approved by planners. - By ensuring adequate provisions will contribute to maximise recycling from local businesses, which contributes to achieving the Mayor’s municipal waste recycling target of 65% by 2030 and CoL recycling rate by 2025 |
| COL#25 | Low and zero emission fleet | The CoL has already transitioned to zero emission waste fleet for household collections via using eRCVs for household collections, meaning we are helping contribute to Mayor’s net zero carbon target by 2030. We continue to upgrade our non-waste fleet when it is appropriate to do so e.g. the expansion of the ULEZ to North and South Circular meant fleet in North London, Epping Forest etc have and continue to change their fleet, however, market constraints for some vehicles persist preventing vehicles being changed to low / zero emission alternatives. We will keep the vehicle market under review. By the end of 2023 all of the City Gardens vehicles will be fully electric Subject to operational requirements, 100% of vehicles owned or leased by the City Corporation are to be electric or hybrid by 2025 | Ongoing | The CoL continues to reduce the size of its fleet whilst increasing the number of electric vehicles. At time of writing, CoL have 46 fully electric and hybrid vehicles in operation and we continue to trial electric vehicles as they come onto the market. Due to technological constraints, only one vehicle in the City Gardens fleet is not electric as there is currently nothing on the market which meets our requirements. Additionally, household waste collection services continue to be undertaken using five all electric refuse collection vehicles (owned and operated by Veolia). Additionally, we have installed new telematics to help with data for our carbon footprint. At time of writing, we are waiting the data to start coming from the new system to identify improvements. A new CoL Air Quality Strategy was adopted in January 2025 – two of the key areas for the new Air Quality Strategy includes “reducing emissions” and “leading by example” where actions include the ongoing review of the CoL fleet. The following vehicle purchasing hierarchy is implemented: - fully electric - plug in hybrid - petrol hybrid - Euro VI petrol - Euro VI diesel. | - The action is a key area to reduce pollutant concentrations within the square mile to align with the aims of the Air Quality Strategy. - Whilst the impact of action is not measurable, it’ll contribute to the targets as set out in the Air Quality Strategy 2050-2030 which are; - Over 90% of the Square Mile meets an annual mean of 30µg/m3 for nitrogen dioxide by 20305. - To support national and regional action that leads to the Square Mile meeting an annual mean of 15µg/m3 for PM10 by 2030. - To support national and regional action that leads to the Square Mile meeting an annual mean of 10µg/m3 for PM2.5 by 2030. - All except one vehicle in City Gardens fleet is electric. |
| COL#26 | Maintain use of Walbrook Wharf Waste Transfer Station (WWWTS) for refuse disposal | The City of London is fortunate to have its own Waste Transfer Station, Walbrook Wharf Waste Transfer Station (WWWTS) in the Square Mile. This is where refuse, including domestic, commercial and street arising collected in the Square Miles departs the Square Mile via WWWTS on barges where the end destination is the EfW plant at Belvedere. Each barge transports 26 containers, thus avoiding 52 return road journeys. Walbrook Wharf is safeguarded for waterborne freight handling use in accordance with the Mayor's London plan https://www.london.gov.uk/sites/default/files/safeguarding_direction_walbrook_wharf.pdf Walbrook Wharf is also a safeguarded waste site – Walbrook Wharf is protected as a waste site which must be re-provided elsewhere if lost to a non-waste use. | Ongoing | This is ongoing during lifetime of RRP. The WWWTS, whilst owned by the CoL, is operated by Cory. Contract due for tender in 2027. | - Whilst the impact of action is not measurable, taking vehicles off the road will contribute to the targets as set out in the Air Quality Strategy 2050-2030 which are; - Over 90% of the Square Mile meets an annual mean of 30µg/m3 for nitrogen dioxide by 20305. - To support national and regional action that leads to the Square Mile meeting an annual mean of 15µg/m3 for PM10 by 2030. - To support national and regional action that leads to the Square Mile meeting an annual mean of 10µg/m3 for PM2.5 by 2030. It was also contribute to Mayor’s net zero carbon target by 2030 |
| COL#27 | Reduce waste related vehicle movements where possible - river transport | WWWTS is used for the disposal of all household and street arisings collected in the Square Mile and additionally third-party contractors use WWWTS to dispose of refuse thus avoiding even more road journeys. We will continue to use river transport to move LACW and third-party commercial waste disposed of at WWWTS | Ongoing | This is ongoing during lifetime of RRP. The WWWTS, whilst owned by the CoL, is operated by Cory. Contract due for tender in 2027. The tugs which collect the barges from WWWTS, also owned and operated by Cory, are run on hydrotreated vegetable oil (HVO). This is a renewable diesel produced from waste materials such as used cooking oil and waste fats. HVO do not release any new carbon dioxide into the atmosphere and reduces nitrous oxide (NOx) and particulate matter emissions by 19% and 21% respectively (in tests undertaken on a Cory tug in 2021) when compared to marine gas oil. | - Whilst the impact of action is not measurable, taking vehicles off the road will contribute to the targets as set out in the Air Quality Strategy 2050-2030 which are; - Over 90% of the Square Mile meets an annual mean of 30µg/m3 for nitrogen dioxide by 20305. - To support national and regional action that leads to the Square Mile meeting an annual mean of 15µg/m3 for PM10 by 2030. - To support national and regional action that leads to the Square Mile meeting an annual mean of 10µg/m3 for PM2.5 by 2030. - It was also contribute to Mayor’s net zero carbon target by 2030 - Reduction in Nox and particulate matter. |
| COL#28 | Reduce waste related vehicle movements - Waste consolidation in Business Improvement Districts | Pre- covid-19 pandemic, the CoL had been working on identifying whether it would be viable to trial a waste consolidation project in the Cheapside Business Improvement District (BID with the aim to reduce vehicle movements and improve air quality). The project was put on hold due to covid and will be re-considered in the future. The CoL now has 4 BIDS with whom we could run a potential future project. The CoL are also interested in looking at the results of waste zoning trials for commercial waste to see if something similar could be implemented in the Square Mile. | - Delayed / on-hold / no progress to date | As mentioned, a new CoL Air Quality Strategy was adopted in January 2025 – two of the key areas for the new Air Quality Strategy includes “reducing emissions” and “collaborating with partners”. Whilst we continue to consolidate waste movements via the use of Walbrook Wharf, the waste zoning results / potential to consolidate collections from a BID will be picked up in the future. | - As no action has been taken regarding waste zoning or consolidation (other than at WWWTS) reducing the number of waste vehicles on the public highway impacts the contraction of air pollutants within the Square Mile and would help continue towards the targets as set out in the Air Quality Strategy 2050-2030 which are; - Over 90% of the Square Mile meets an annual mean of 30µg/m3 for nitrogen dioxide by 20305. - To support national and regional action that leads to the Square Mile meeting an annual mean of 15µg/m3 for PM10 by 2030. - To support national and regional action that leads to the Square Mile meeting an annual mean of 10µg/m3 for PM2.5 by 2030. - It was also contribute to Mayor’s net zero carbon target by 2030 |
| COL#29 | Climate Action Strategy | The CoL has a Climate Action Strategy which sets out how the CoL will achieve net zero in carbon emissions, build resilience and champion sustainable growth. We aim to achieve net zero carbon emissions in own operations by 2027. Actions include improving energy efficiency by retrofitting buildings, using renewable energy and embedding CE principles into building projects to reduce carbon intensity. We will continue to link in with the Climate Action Strategy actions. We will continue to promote climate action via the Clean City Award Scheme “Air Quality and Climate Action” (AQCA) category. The new Responsible Procurement Strategy, launched in July 2022 links with Climate Action Strategy and minimises environmental impact on procurement / supply chains. We will continue support and contribute towards the delivery of this. | Ongoing | The creation of the Circular Economy Framework has been done in alignment of the Climate Action Strategy with the shared overall aim to be both Net Zero and a Circular City by 2040. There has been a number of specific Climate Action Strategy projects which the Circular Economy plays a large part in, such as the Embodied Carbon Action Plan, the Net Zero Design Standards and the Sustainable Supply Chain Project. We facilitate decarbonisation of Square Mile through the Local Area Energy Plan which sets out the Corporation’s approach to net zero carbon energy system in Square Mile by 2040 – this prioritises building efficiency, heat networks and renewable electricity generation. We also have Heritage Building Retrofit Toolkit and Carbon Options Guidance Planning Advice Note which requires planning applicants to consider development options, including retrofit, to explore and present embodied and operational carbon reduction opportunities throughout the life-cycle of a building. COL#12 also provides information on retrofit and CE planning statements and sustainability SPD which support the Climate Action Strategy. Additionally, the CoL supported climate literacy across the Square Mile and our supply chain by educating 322 small and medium sized businesses in 2023/2024. The Clean City Awards Team also attended the London Climate Action Week event on 25 June 2024 to raise awareness of CCAS and AQCA award. The Clean City Awards Team also received 14 applications for the AQCA award of the CCAS in 2024-2025. Additionally, at time of writing, we are working with the Climate Action Team to ensure that the Circular Economy is built into the planning for the future of the strategy post their current funding cycle which ends in 2027. | - In 2023/24, we achieved a 19% reduction in net carbon emissions since the 2018/19 baseline and in the same timeframe had successfully reduced net emissions in our own operations by 65% and implemented building interventions with energy savings of over 1.5 million kWh per year. Also in 2023/2024, the Corporation full value chain emissions spanning scope 1, 2 and 3 emissions have reduced by 23% since baseline. Note 2023/24 is the most recent year data is publicly available. - Contribute towards Mayor’s net zero carbon target by 2030 |
| COL#30 | Promote greater recycling by promoting Tower Hamlets HWRC | As there are no HWRCs located in Square Mile, residents have permission to use neighbouring Tower Hamlets HWRC. Availability of more recycling streams at Tower Hamlets HWRC promoted through digital channels as appropriate and ditto A-Z recycling page on website to reduce waste and maximise recycling | Ongoing | This is ongoing through the lifetime of this RRP. As no data is provided on CoL residents usage of Tower Hamlets HWRC unable to provide impacts. | - Contribute to recycling rate target by reducing waste disposed of in the City where some streams can’t currently be recycled e.g. wood |
| COL#31 | COL as a waste planning authority | The CoL is a Waste Planning Authority and therefore there is a statutory duty to prepare a waste local plan which is fulfilled through inclusion of waste policies in City of London Local Plan. The City is unique covering just one Square Mile - with a housing stock of approx. 7,000 residential properties and pre-covid over 500,000 workers each day. We have only one designated waste site (WWWTS – above) and no waste management sites. Therefore, the CoL is reliant on cooperation from other Waste Planning Authorities for capacity as it's not feasible to increase or create capacity within the Square Mile to help the CoL manage more waste within our borders. This is achieved through membership of the South East London Waste Planning Group (SELWPG) and specifically a waste apportionment agreement with the LB Bexley. We will continue to liaise with other boroughs to ensure waste is treated accordingly. | Ongoing | This is ongoing through the lifetime of this RRP – no updates or changes to report | - Ongoing action therefore no measurable impacts |
| COL#32 | Waste apportionment targets | The London Plan has set a waste apportionment figure requiring the City to identify sites with capacity to manage 100,000 tonnes of waste annually until 2031. This figure represents the City’s contribution to meeting the Mayor’s target of 100% net self-sufficiency in the management of London’s waste by 2031.The CoL Waste Capacity Study 2009 identified that there were no viable waste management capacity sites within the Square Mile and that the City will not be able to satisfy the London Plan waste apportionment within its boundaries. We will continue working with the London Borough of Bexley, utilising spare waste management capacity in Bexley, and joint partnership working / contribution to the Southeast London Joint Waste Planning Group's Waste technical paper to ensure that the City’s waste apportionment can be met. | Ongoing | This is ongoing through the lifetime of this RRP – no updates or changes to report | - Ongoing action therefore no measurable impacts |
| COL#33 | Resident engagement review | The CoL has a transient population with approx. 3,000 properties on estates, the rest (approx. 5,000) in private blocks. We are reviewing how we engage and communicate with all residents. This has included a review of social media use and how we write letters to residents, as this is currently addressed to resident / occupier. The re-introduction of printed City resident newsletter will help engagement further. | Ongoing | This was a new action added in the 2023-2024 update An external review of our social media usage was undertaken in 2024-2025 and as a result, we have changed how we use social media to incorporate gardens and cleansing messages (to reflect our department) and to give us a “look and feel” on socials. We no longer use X as a main channel, but have now got an Instagram channel which, at time of writing has just under 600 followers. The re-introduction of printed City newsletter every four months has helped bring residents to our events such as Give and Take Days and for Recycle Week 2025, we will be having our first “Recycle Week” special edition resident newsletter to help promote recycling. We have also recently launched a Green Champion network whereby we are looking for engaged residents across the Square Mile to get involved in the City of London, whether this be informing neighbours of events, or recycling services or monitoring biodiversity or more besides. The formation of this group is in its very early days a Terms of Reference is being drawn up at time of writing. | The re-introduced printed newsletter is distributed to approx 6000 residential properties. A twice monthly email newsletter has 450 subscribed (which will also receive the Recycle Week special newsletter). There is also a weekly estate specific newsletter (Barbican) where there over 2000 registered to receive the newsletter. We provide recycling / circular economy content etc into all of these outlets. At time of writing, there are 15 residents who have signed up as Green Champions since April 2025. We expect this number to increase as it develops. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| COL#34 | Romulus | As mentioned in COL#1, we are participating in the Romulus trial which accelerate circular economy in London’s built environment by sharing building audit data and encourage circular economy. We were one of the first members to join the trial having signed up in November 2024 and officially starting in March 2025. Since pilot start in March 2025, key achievements so far - 10 projects involved (2 from the COLC) - 1012 deposits made = 718,082 tonnes - 2086 products tracked for future reuse - 276.82 tonnes of co2 avoided - 66tonnes of waste avoided - £15k residual financial value - Items redistributed to over 45 locations in London area In 2025-2026, we will continue to use Romulus to help redistribute items including from sites which the CoL are redeveloping. | Through the ROMULUS trial we are having a large impact by facilitating the different stakeholders who are usually competitors to come together to co-solution for the challenges of reuse of building materials. We expect the key achievements to continue to return results such as greater waste avoided, items reused etc but the figures will be dependent on future projects (eg demolitions, retrofits etc) | Ongoing. |
| COL#35 | Web page review | In Summer 2025, we started reviewing the CoL recycling web pages with the aim to make the information contained within more user friendly. We are keeping WRAP’s Local Authority Website Good Practice Guide in mind as we make the changes and hope the improvements will be made to coincide with updated information on food services to align with COL#6 We will also be introducing a new “Places of Worship” webpage to account for the sheer number of PoW’s in the City of London and ditto Managing Agent webpage in due course. | Make information on recycling services easier to find and contain succinct information leading to better understanding of recycling services. | Web review to be completed by Winter 2025 to align with food waste roll out to phase 1 properties (CoL#6). |
| COL#36 | Encouraging sharing economy | At time of writing, we are awaiting decision on funding application to introduce a Library of Things at the Barbican Centre. Decision is expected in Winter 2025. If application is successful, we will seek to roll out in compliance with funding timescales and support with communication campaign to promote it. At time of writing, we are also in the beginning stages of trialling an internal “Library of OUR Things within the Guildhall for colleagues to take advantage of eg enabling sharing of little used items eg ceremonial scissors, table to take to events etc. | As not implemented, no impact to date and nor are targets in place as pending decision. | Decision expected on funding for LoT by Winter 2025 Introduction of LoT timescales is TBC pending funding decision. |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| COL#6 | Expand food waste collection service to all remaining households | Please see action COL#6 for further information | Expect food waste to increase after December 2025 which is when food roll out will be completed to phase 1 properties although at time of writing, no estimates as to what increase is expected. Phase 2 roll out – to be completed by April 2026 as required by Simpler Recycling, we do not anticipate a big increase in food recycling as expect uptake to be fairly low. The nature of phase 2 roll out ie provision of food services to those who will need to put food on street for collection is TBC. Provision of food services to the remaining households in the Square Mile will help contribute to recycling rate. | Phase 1 roll out to commence November 2025 and completed by Christmas 2025. Phase 2 roll out options still being considered as on-demand services and bins on street are not an option in the Square Mile. It is anticipated that the way forward for providing food waste to phase 2 properties will be confirmed by Winter 2025 to roll out by Simpler Recycling of April 2026. |
| COL#17 | Simpler Recycling requirements to collect core recyclable materials separately | Please see action COL#17 for further information | Households already able to recycle core materials therefore contribute to recycling rate. Business recycling will help contribute to achieving the Mayor’s municipal waste recycling target of 65% by 2030 and CoL recycling rate by 2025 | completed |
| COL#19 | Introducing garden waste collection service from household properties by April 2026 | Please see action COL#19 for further information Options to collect garden waste are to confirm however, as uptake is expected to be minimal. Further details TBC. | Expect uptake to be minimal due to lack of gardens in the Square Mile. Previous trials to collect garden waste collected 5tonnes, which included contamination (soil, plastic bags etc). Therefore do not expect notable impact on recycling rate. | Garden waste options still being considered. It is anticipated that the way forward for providing garden waste services will be confirmed by Winter 2025 to roll out by Simpler Recycling of April 2026. |
| NEW | Introduction of plastic films into household recycling by April 2027 | We will explore options for introducing plastic film recycling into household recycling by April 2027 in 2026-2027. | To be explored | Begin review in 2026. |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026