- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 343.31 kgs/head | 339.88 kgs/head | 333.6 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 618.70 kgs/hh | 612.51 kgs/hh | 575.55 kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 77 kgs/head | 75 kgs/head | 77 kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56%. If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 32.3% | 34% | 32.71% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 29.7% | 32% | 32% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% collection of 6 main dry recyclable materials 100% collection of mixed food and garden waste 8.5% separate collection of food waste | 100% collection of 6 main dry recyclable materials 100% collection of mixed food and garden waste 8.5% separate collection of food waste | 100% collection of 6 main dry recyclable materials 100% collection of mixed food and garden waste 8.5% separate collection of food waste | 100% collection of 6 main dry recyclable materials 100% separate collection of food waste | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 15% | 90% | 20% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 10% | 0% | 10% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| 1 | Communications and Engagement | - Digital screens on Vehicles - Fully utilising the digital screens on waste/recycling vehicles to reflect current campaigns (seasonal and non-seasonal) by uploading MP4 short clips to capture residents’ attention. Future planned campaigns include: Podback coffee pod recycling, promoting indoor recycling bags, promoting food waste reduction and raising awareness of common contaminants. - Updating livery on fleet vehicles to encourage uptake in recycling participation. - Waste and Recycling Webpages - Review and update webpages to promote key ‘reduce, reuse & recycling’ messages. Links to key webpages such as RRC’s and imbedded NLWA ‘can I recycle it’ look up. Webpages to promote: Home composting, Additional Items, Furniture Recycling and reuse organisations, Bring Banks, Real Nappies. - Waltham Forest News (WFN) – the Council’s magazine which is circulated quarterly to all homes and business in the borough. The Waste Team regularly place advertisements and work with comms colleagues on editorials to educate residents on waste reduction, recycling, and re-use messages. Recent articles/ads have included – coffee pods promotion, contamination messaging, recycling, launch of DIY materials recycling service, increased recycling participation. - Targeted Social Media – The Waste Team working with comms colleagues to target specific messages to specific demographics. Recent targeted campaigns have dealt with contamination (Yes Yes No) and promoting additional items recycling. - Outdoor Advertising i.e. Bus Stops/Bus Backs Billboards and street kiosks – In order to reach a wider segment of residents the Waste Team recognise the importance of adverts in areas of high footfall and to the this end are planning a campaign to disseminate key contamination reduction and recycling participation messages to be delivered in the summer of 2023. | On track | Digital screens continue to be fully utilised on vehicles focussing on the introduction of separate food waste collections in September 2024 to kerbside and communal bin properties and introducing the service change to kerbside properties in Feb/March 2025. Static livery updated with new dry recycling campaign artwork. Different look and feel to previous comms, very colourful, lively and fun to attract a widespread audience through their pictorial nature. We are looking to update vehicles with new signage in the autumn of 2025. Waste and Recycling webpages are continuously being updated. Separate food waste pages redesigned with simple customer journey. A dedicated ‘Frequently Asked Questions’ page created in the build up to the service change to fortnightly collections. The Rethink, Recycle, Repeat campaign continues, focussing on the residents of Waltham Forest and how they could engage with a recycling initiative. The goal was to empower residents to recycle more and reduce contamination, ultimately improving recycling rates across the borough. This strategy led to the creation of a visually striking and memorable visual identity. Playful stickers, inspired by general waste packaging, became the foundation of this identity. The campaign's messaging was designed to be concise, snappy, and memorable, offering a clear call to action. Waltham Forest has recruited over 800 binfluencers which refers to local influencers who promote positive waste management practices and recycling within the community. This term combines "bin," referring to waste bins, and "influencer," indicating individuals who can sway public behaviour and opinions using social media. The initiative is part of a broader effort to encourage residents to adopt more sustainable habits, reduce waste, and increase recycling rates. As part of Waltham Forest Separate Food Waste collection, Waltham Forest hosted a competition and provided information to residents: - Vehicle naming competition – naming the new food waste vehicles to win a prize - E-Newsletters – WF Housing, private landlord, climate news, Binfluencer e-news, voluntary community sector promoting a new collection service - Communication rollout to council housing tenants including: - Information packs provided to Resident Association Leads - Leaflets to every households participating in the food waste collection service Waltham Forest has consistently made efforts to raise awareness throughout the borough and will persist in doing so in the future. Waltham Forest employed a range of communication channels on food waste, including social media platforms, the local Waltham Forest Newspaper (WFN), and various outdoor advertising resources, to effectively reach and engage with the community. These initiatives aim to ensure that important information and messages are widely disseminated, fostering a well-informed and connected borough. | Binfluencers: from initial call-out, Waltham Forest recruited 13 binfluencers. We now have a database of over 1,500 who are regularly contacted via newsletter with important information and materials to disseminate among their networks. While we are unable to track whether this goes into private channels, such as street or family WhatsApp groups, the open rate averages at over 40%, well above the national benchmark. Festive Recycling: Social media: - Facebook – 10 posts, 28,876 reach, 124 clicks, 20 shares - Instagram – 5 posts, 10,422 reach, 10 shares - Twitter - 7 posts, 6,687 reach, 55 clicks, 16 shares Newsletters - Residents’ News: 1,362 unique clicks from three editions (two were highest clicked) - Climate News: 168 unique clicks from one edition (highest clicked) - Binfluencer: 508 unique opens, 93 unique clicks Out of home - Waltham Forest News: https://www.walthamforest.gov.uk/sites/default/files/2024-12/WFN%20Issue%20255%20-%20WINTER%20-%20DIGITAL.pdf - Circulation: 112, 290 Food waste recycling campaign: - Newsletters (Res News, Climate, Binfluencer): 6,000 clicks through newsletter - Website presence strengthened: More FAQs added from resident feedback; two web stories (first trucks on the road and truck naming winner) 20,000 visits to website - Social media: 74 posts across X (Twitter), Facebook, Nextdoor, Instagram – 220,000 reach - 234 new TikTok followers, 225,000 views - 866 Facebook comments - Internal: YourNews, CE blog, Cllr briefings, library staff briefings, contact centre briefings, SLT briefings - Other groups engaged: Faith Leaders, Digitally excluded - Out of home: Mass Media billboards (two locations, combined circa 950k impacts per two week campaign), digital kiosks (five locations), libraries (all), physical briefing pack to Councillors. |
| 2 | Reducing contamination - flats | Crew refresher training to identify common contaminants. Crew refresher training to report contamination on White Space via in-cab technology Crews issued with contamination stickers for bins to inform Managing Agents, Residents and RSL’s that bins are contaminated, and to ensure that contaminated bins are not emptied on future occasions until contamination has been removed. Above training to be mandatory for new crew operatives and for to induct agency/temporary staff to ensure they are aware of practices and policy in this area. Temporary officer recruited to liaise with managing agents and the council’s enforcement team to work collaboratively to reduce contamination in communal bins Contamination communications campaign targeted at estate residents: targeting communal blocks with high contamination with A5 postcards and installation of A3 posters in bin stores. Resources provided to Managing Agents and Residential Social Landlords. | On track | Crew guidance booklet and memos created for both kerbside and communal properties to educate and continually remind crews of established process. Contamination sticker have been refreshed. Contamination stickers have been updated with new branding. Collection crew operatives receive training to ensure compliance is met. Officer with the Council continuing to liaise with managing agents. | Contamination rate for 24/25 was 25.37%. |
| 3 | Improving Quality of Recycling - flats | Recommendations to make improvements to bins and locations of bins e.g. reverse lidded bins & Metrostore Pods to better contain waste/recycling and provide a visual improvement to encourage residents to be diligent with waste and place correct items in correct receptacles. Working with housing to improve service provision - e.g. cleanliness, signage, bin stores. Updating existing literature for communal blocks so it is current, targeted and user friendly. | On track | 5 Recycling Assistants employed on a fixed term basis to initiate the food waste collection service in flats. Associated with this role is a scoping exercise to identify location of bins in communal blocks and to recommend any improvements, report bin misuse & cleanliness to Housing Associations and Managing Agents. For the new food waste collection service, a suite of assets has been designed to include new communal communications and literature which is targeted and user friendly. New food waste units have been procured which are more robust and accessible for communal residents, are visually improved and assist residents to recycle their food waste correctly. Housing Team assessing Waltham Forest refuse areas for cleanliness, access requirements (both for residents and collection crews), suitable surfaces and the discouragement of fly tipping. Reoccurring monthly meetings set up across departments to come together and improve services with our own housing stock, this includes, caretaking, housing officers, housing maintenance, the Neighbourhoods team and the Recycling and Waste teams. | As of the end of March 2025 80% of communal properties currently have separate food waste collections. Pre-January 2024, less than 10% of blocks had access to separate food recycling service. As part of the rollout, guidance leaflets have been distributed to provide residents with information on how to use the service effectively. This will continue to be rolled out until end of September 2025. |
| 4 | Planning Guidance | Working with architects and planners to design effective recycling provision and collections. Waste officers to attend planning meetings at early pre-application stage in order that waste recycling arrangements are given due consideration and designed into original plans. This will enable appropriate capacity and location as well as work-in space for food wate collections and Large Item Collection (reuse). It will further provide an operational perspective to ensure locations and materials are suitable for collection taking into account traffic flow and mitigate Health and Safety issues. Waste able to recommend that a planning application is not approved if appropriate consideration has not been given to the above. Continued engagement with ReLondon and Planning Department to ensure commitment to recycling storage provision is included within all new development applications for flats and estates. Compliance with Mayor of London’s London Plan guidance and policies e.g. London Plan Policy D3 3.3.18 Shared and easily accessible storage space supporting separate collection of dry recyclables, food waste and other waste should be considered in the early design stages to help improve recycling rates, reduce smell, odour and vehicle movements, and improve street scene and community safety’ | On track | Continued engagement with planning officers and developers to ensure that reuse and recycling is designed into developments. Planning guidance updated according to any changes in policy/legislation. New Guidance for Developers released with new Recycling Strategy was released in October 2023. Food waste collections are now mandated, and the guidance has been updated. | Ongoing piece of work. https://www.walthamforest.gov.uk/rubbish-and-recycling/developers-and-managing-agents-bins-your-properties |
| 5 | Kerbside Contamination Project – Part 1 | Leaflets to kerbside properties on worst performing rounds where crew have had the most rejected loads. Analysing data provided by the MRF on gate rejects to identify which rounds/crew have the most full or partial rejections when tipping at the facility. Identifying which roads are serviced by the crews with the most rejected loads. Designing and periodically updating a contamination leaflet with information on the most common contaminants, which receptacles they should go in and why this is a problem. Leaflet is hand-delivered to all street-level properties services by crews with a high MRF rejection rate. Leaflets are delivered quarterly and around 15,000 leaflets are delivered at any one time. Planned door knocking to roads with highest levels of contamination to educate residents. | On track | Officer has been recruited to manage this project, restarted in August 2024. Leaflets delivered to target areas on a quarterly basis. | Ongoing communication is paramount in raising resident awareness and ensuring that the matter remains relevant. |
| 6 | Kerbside Contamination Project – Part 2 | This project is ongoing and aims to tackle the worst offenders through a highly targeted approach to tackle contamination compromising of a four-stage process created to penalise householders that persistently contaminate their dry recycling bins. Householders receive different levels of notifications, warning letters and formal notices for continual abuse of the recycling service, ultimately resulting in Fixed Penalty Notices being issued to the worst contaminating households. The landlords of all properties registered under the Council’s Private Rental Property Licensing scheme are also contacted directly in addition to the warning letter issued to the tenant. As a second strand to this project - Where bins are contaminated the Waste Team will arrange for bins to be emptied as refuse as a one off and at the same time enact interventions. Crew are also instructed to sticker bins that are contaminated so residents are aware. Waste team also liaise with managing agents to disseminate information to residents on contamination. If contamination issues persist then the onus is placed on managing agent to empty contaminated recycling bins and further disseminate literature to residents/organise for recharge. As a third stage, and when cooperation from managing agents is not forthcoming, enforcement action is taken against managing agents. | On track | The process for notifying residents about contamination has been redesigned to ensure a thorough and consistent approach to data collection: - When the collection crew identifies a contaminated recycling bin, they will place a warning sticker on the bin. If only one warning sticker is issued within a 5-week period, no further action is needed. - If a second contamination is found within 5 weeks of the first incident, the Waste Team will issue a Stage 1 letter. - If additional contamination occurs within 12 weeks of the first incident, the Waste Team will issue a Stage 2 letter. - If another contamination is found the following week, the Waste Team will issue a Stage 3 letter. - If contamination continues, a Neighbourhoods Officer will issue a formal Notice of Intent, which remains valid for 12 months. - If further contamination is found within 12 months of the Notice of Intent, a Neighbourhoods Officer will issue a fixed penalty notice. | To date: - Stage 1 letters - 1806 - Stage 2 letters – 1290 - Stage 3 letters – 161 - Stage 4 (properties to monitor for possible CPN) – 48 - Stage 5 (properties that have been issued with a CPN to monitor for possible FPN) – 6 The total number of CPN’s issued to date is 3 The total number of FPN’s issued to date is 1 |
| 7 | Progress the range of expanded materials that can be accepted for Recycling at the kerbside | Waltham Forest is unique amongst North London Boroughs in offering residents of street level properties the ability to recycling small WEEE items (e.g. Kettles, hairdryers etc), household batteries, clothes/shoes and batteries. Residents can place small WEEE, batteries and textiles bagged on top of their recycling bin and the crew will collect the materials and place them in a pod underneath the vehicle to keep them secure and dry. The materials are bulked in the Council’s depot until enough material is amassed so that the off-taker can collect. Since the inception of the scheme in 2020 over 50 tonnes of additional items have been collected. Although some items are recycled this service promotes reuse (for example textile and WEEE) and in the case of coffee pods the coffee goes to AD to produce energy while the pods themselves are recycled. Continuing to promote kerbside recycling for street level properties of small WEEE items (e.g. Kettles, hairdryers etc), household batteries, and textiles. Promoting newly introduced (February 2022) coffee-pod recycling service for plastic and metal coffee pods. Residents leave items in coloured bags on top of their recycling bins to allow for crews to collect from their properties. Over 250,000 pods collected to date. | On track | New additional item added to the collection service, printer cartridge recycling launched end of July 2024. Continued promotion of all the additional items is ongoing. At the end of January 2025, we installed blister pack recycling boxes at 3 of our libraries across the borough. | As of March 2025, 40,800 blister packs recycled with the support from local community donating. Between Apr24-Mar25 Waltham Forest collected: - 3.70 Kg of textiles - 1.61 tonnes of batteries - 2.43 tonnes of coffee pods - 2.46 tonnes of WEEE items - 1.56 Kg of coffee cups |
| 8 | Christmas Tree Recycling | Offering residents in communal and street level properties a collection service for their real Christmas trees. Residents can book a collection using the online form and a dedicated crew will collect on the allotted day and from the agreed location. Promoting the service through seasonal communications. | On track- Recurring | This initiative will run annually. | Approximately 500 bookings for Christmas tree collections per year from flatted who do not usually have a standard garden waste collection. Approximately 1450 tonnes of additional garden waste collected attributed to Christmas trees. |
| 9 | Reducing residual waste capacity | Offering residents a 140 litre refuse bin as standard with a free swap/replacement service if they currently have a 240 litre bin. Currently reviewing residual collection frequency. LBWF have carried out a public consultation to establish residents views on recycling and waste to assist with progressing this review. | Complete | In March 2025 WF commenced the change from weekly to fortnightly residual collections offering residents the opportunity to swap their 140L recycling and garden waste 2-wheeled bins for larger 240L 2-wheeled bins, free of charge during the summer period. | Currently awaiting finalised figures, however early indications show a reduction in refuse collected. |
| 10 | Communal Food Waste | Roll-out of separate food waste collections to all purpose-built flat properties in the borough not currently receiving service, including procurement of food waste caddies and communal containers. Recruitment of Food Waste Officer on a one year contract to escalate the roll out food waste service to all flatted properties that do not currently have the service. Working with Managing Agents and Registered Social Landlords to integrate food waste collection service into existing blocks. | On track | Increase food waste recycled in the borough through diversion from the residual waste stream. Recycling Assistants (RAs) initiating communal food waste bins to all blocks of flats in the borough in June 2024. To enable this, RAs conducting a scoping exercise on properties that have no separate food waste facility and identify how many flats are in the building(s). New communal bins ordered; with updated artwork to align with the new campaign. All residents are delivered internal caddies, a roll of liners and guidance for recycling food waste. Monitoring is carried out to ensure collections are taking places as scheduled and that contamination is reduced. Project paused in September 2024 for two months for Recycling Assistants to assist with monitoring of the roll out of kerbside food waste collections and again in March 2025 for three months to assist with the AWC change. Project to recommence in May 2025 and is expected to be completed end Sept 2025. | As of end March 2025, 80% of communal properties receive a separate food waste collection. |
| 11 | Separation Food Waste Collection at the kerbside | Currently collecting weekly separate food waste from 7,400 kerbside properties on a trial basis The trial shows good service participation and continued use overtime Each resident receives a roll of caddy liners quarterly with a half yearly letter/leaflet to encourage continued participation. | Complete | Separate food waste collections implemented from Sept 2024 to all 80,000 kerbside properties. Each property received a 23ltr outdoor caddy, a 5ltr indoor caddy, a roll of liners (6-month supply) and an information leaflet. Delivery of a further 6-month supply of food waste liners commenced in March 2025 with another planned delivery in September 2025. | By the end of March 2025 over 100 tonnes of food waste being collected per week and diverted from residual waste. |
| 12 | Engaging Schools Projects North London Waste Authority | North London Waste Authority initiative to touring local schools to deliver waste reduction and reuse messages. Linking good recycling with climate change mitigation and reduced contamination. | On track | In 2023, the North London Waste Education Hub was launched, pulling together some of the best existing teaching resources on waste. The Education Hub is regularly promoted through social channels, email marketing, and features a new blog post each half term. Through consultations with borough officers and schools, NLWA have created a brand-new outreach Primary school programme has been developed which launched in 2024. 21 schools applied to take part in the first year of the programme across the 7 NLWA boroughs, and one school per borough has been chosen to participate. Through an initial intensive trial delivery approach, various whole school waste prevention interventions will be tested including: - Waste audits - Waste infrastructure reviews - Pupil engagement - School stakeholder workshops with senior leaders, governors, teachers, premises staff, catering staff, and PTAs - All-staff survey (pre and post intervention) to measure the change of behaviour and culture - Internal communications review | Launched in September 2024, In the Know is NLWA’s innovative outreach programme for primary schools. Over the past year, officers have collaborated with seven schools to elevate the importance of waste prevention and the circular economy. This initiative has included engaging assemblies, interactive staff workshops, thorough waste audits, and insightful senior leadership and subject sessions. In its first year, the programme has successfully engaged over 2,600 pupils and staff. Schools worked with during the 2024/25 year are: - Barnet: Monkfrith Primary School - Camden: Rosary Catholic Primary School - Enfield: Merryhills Primary School - Hackney: Parkwood Primary School - Haringey: Ferry Lane Primary School - Islington: Ambler Primary School - Waltham Forest: Parkside Primary School Building on this initial success, officers are doubling the programme’s capacity, working with 14 primary schools from September 2025. In its second year, the programme will introduce CPD sessions for subject leads, facilitating an exercise to map the national curriculum against waste and the circular economy, and identify opportunities to enhance in-school teaching. In March 2025, officers developed a partnership with the Lightyear Foundation to ensure all NLWA school activities are inclusive. Over the coming year, officers will collaborate with a local Specialist school for students with Special Educational Needs and Disabilities (SEND) to co-design a new workshop. Education Hub NLWA’s Education Hub, an online resource hub for pupils and teachers, has also been revitalised. The Hub now features a wealth of bespoke resources tailored to north London, including ready-to-go lesson plans. Initially developed for primary schools, the Hub now boasts a new secondary area, complete with a series of career profiles that highlight how a background in science can lead to careers in waste management. In the coming year, we will continue to expand the Education Hub, adding more resources and exploring opportunities to signpost students towards work experience, volunteering, and apprenticeship opportunities. Other school activity Additionally, NLWA ran a photography competition for secondary schools across the seven boroughs. The theme, ‘Nature’s Resilience’, invited students to capture moments of nature reclaiming spaces or recovering from human activity as studies have shown that connection to nature can increase engagement in waste prevention behaviours. The competition saw 46 students from 16 schools participate, with a winner and two runners-up selected. Their artwork will be proudly displayed at EcoPark House during the Opening Ceremony. |
| 13 | Championing food waste reduction initiatives | Work in partnership with the NLWA to promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events. Food prevention workshops held at community events and schools; engagement to reduce amount of food waste disposed of per household Explore partnership and local promotion of Olio, Kitchen & the Too Good To Go apps in the borough. Working with local schools to encourage more vegetarian options (to help tackle climate change) and to reduce overall food waste. | Complete | Partnering with local community organisations like the Forest Recycling Project (FRP) and utilising social media during events such as Food Waste Action Week, this approach blends local community involvement with the extensive reach of digital platforms. Imbedded within the Schools and Colleges Climate Charter. Proactive work being carried out by the WF catering team who provide school meals. Planning is underway for this to be further supported at the Big Climate Conversation due to be held in the Autumn of 2025. | Waltham Forest has increased awareness and engagement in the Local Community on a personal level. FRP’s focus on sustainability aligns with food waste reduction goals, helping raise awareness of these issues among their networks. This creates a sense of collective responsibility and encourages community participation. |
| 14 | Food Waste | Offering schools a food waste recycling service. Currently 30% of schools that receive a collection service from the council have a food waste collection service. All schools that currently have a recycling collection (and do not currently have a food waste collection) will be offered this service. | On track | Under the UK’s Simpler Recycling regulations (a part of the Environment Act), non-household premises (including schools) are required to separate food waste from general waste, and also separate dry recyclables (paper, plastic, metal, etc.) by 31 March 2025. Schools must ensure that they have appropriate bins / containers, appropriate services for collection, and that staff and students use them properly. Councils are often required (or voluntarily providing) support in terms of containers, bin liners, caddies, etc. | A school food waste bin in Waltham Forest has a capacity of 500 litres and is collected weekly. Over a school year of 39 weeks, this equates to 19,500 litres of food waste, which could be diverted from the residual waste stream per school. Additional 17 schools with a new food waste recycling service delivered, food waste caddies also supplied and weekly scheduled collections in place. Schools annually offered a food waste unit for those without an existing food waste collection service. |
| 15 | Partnership with social enterprise to develop ‘object lending library’. | Work with partner to stock range of tools and equipment for hire and ensure robust arrangements in place with suppliers. LBWF has recently completed a bid in partnership with the London Legacy Development Corporation to offer a Library of Things in the borough located in Leytonstone., Funding has been awarded. | On track | A Library of Things is a community-based service that lends out useful items, from DIY tools to kitchen appliances, for a small fee The benefits of borrowing items from a Library of Things rather than owning are multiple: - free up space in homes - save money by paying a fraction of the purchase cost - ensure items get a full life of use - reduces over-manufacturing and material usage - reduces waste and carbon emissions. Since the launch in March 2024, Waltham Forest has been on target with subscribers and borrowers. | To date: Total borrows: 1338 Waste prevented: 10.3t Carbon saved 30.7t Webpage visits: 6324 Subscribers: 1935 |
| 16 | Reducing single-use-plastic and promoting waste minimisation | Continue to encourage local businesses in the borough and request they sign up to a charter of commitment to reduce the single-use plastic they produce or use, with the aim of creating single-use plastic free areas/zones. Recycling officers to produce communications materials to encourage small businesses to prevent waste and consume less e.g. avoidable food waste and unnecessary packaging, whilst promoting the use of materials that can be reused and recycled. Recycling officers to provide training to council staff who regularly engage with local businesses and BIDs e.g. environmental health, trading standards etc to raise awareness of Refill London scheme membership, including providing communications materials. Encouraging Council’s facilities management to adopt policies to eliminate SUP from Council buildings (including canteens) and Council supply chains as far as possible, including for Council-run events. Encouraging residents and business to use reusable bags and reduce plastic consumption, through the prompting of council branded tote bags. Promotions also tie in with requirement for local businesses to charge 10p per plastic bag and to encourage behaviour change for customers to claim and tote bag and adopt it for use on local high-street shops. | Complete | Raised awareness of action on single use plastics, re-use and waste reduction. This project has now finished. Refill scheme: Target of 10% increase in number of businesses signed up to Refill London scheme. Leading by example through banning single-use-plastics within its buildings and encouraging staff behaviour change. Promoting South Access Reuse and Recycling Centre’s hard plastic recycling initiative which was introduced in 23/24 | - 57 Stations offering Refill in the borough - 7196 App users (current) - Outreach event promoting the initiative City to Sea – Refill, to the community as well as promoting campaigns such as Plastic Free July and World Refill Day participated in social media comms to raise awareness. |
| 17 | Outreach Activities | Attend community events such as Tour De Waltham Forest, Council Town Hall (Fellowship Square) summer events to disseminate waste reduction/reuse messages and talk about contamination and the importance of recycling correctly. Attend Community/Estates action days organised by Council’s housing team to spread messages outlined above. Recycle Week in October 2023 – focus on delivering community events and promoted targeted comms in including: 1. Engage local businesses and residents to promote Refill and to become part of the scheme. 2. Stalls held in areas of high footfall (e.g. tube stations) to promote Additional Item Recycling. Spring Clean – supporting this annual event by organising litter-picks with community groups. | On track | Organised and hosted daily engagement stalls across the borough to promote National Recycle Week. Supported the annual Spring Clean event, collaborating with over 40 community groups to coordinate local clean-up activities. The Recycling Team has attended at least one community outreach event each month this year, engaging with thousands of residents. To promote engagement, we set up an interactive stall featuring props and games suitable for both adults and children, encouraging conversation and participation. We also bring our electric dustcart to events, giving residents the opportunity to ask questions and view the vehicle up close. | From April 2024-Mar 25, 74 litter pick events have taken place successfully across the borough. All litter picking groups were assisted with tools and clearance bags. Delivered engagement stalls across the borough during Recycle Week 2024, promoting the new food waste recycling service, dry recycling and waste reduction, recycling additional services and information to the community. Promoted WEEE repair vouchers as part of a national campaign, the UK’s first electrical repair voucher scheme offered to local business a free sign-up service, offering 50% off professional repairs to residents. |
| 18 | Reuse and repair activities and events | Working to offer and promote Repair, Reuse and Upcycling events in the borough: A series of events will be delivered across the Authority area to encourage north London residents, reuse household items such as furniture and soft home furnishings, helping to preserve valuable resources and divert a significant volume of reusable items from disposal, whilst also creating opportunities to raise the profile of organisations and individuals operating in this sector in north London. Following our well received Repair Week campaign in March 2023, continuing to develop our Repair Week celebrations in 2024. Again, outreach stalls held to engage the community. Promotion of community partners’ existing events during Repair Week, with encouragement to also create bespoke events for Repair Week. Comms to encourage Covering the repair categories of textiles, bicycles, furniture and electronics. Wide ranging comms with Councillor support to share the message and raise awareness of events. Creation of the borough’s own repair directory, mapping various services and opportunities to upskill, both within the community and with local businesses. | On track | Hosted repair and reuse fairs across the borough working with local community repair organisations and community groups these events showcase local repair initiatives and promote sharing of items to inspire new ways to reuse, repair, recycle, upcycle and repurpose household items including but not limited to electronics, furniture, textiles/clothing, bikes, toys with interactive workshops and demonstrations suitable for different age groups and abilities. Created a repair and reuse map and directory online via our website, showcasing local reliable repair and reuse businesses to encourage residents to shop more ethically and cost effectively, buy reused, reclaimed, second-hand and pre-loved items, have items repaired by local experts or borrow items to repair to reduce their household’s environmental impact and save money. Launched Waste Prevention & Recycling Initiatives Grant funding for local community projects designed to encourage residents to make more mindful choices. This initiative aimed to reduce consumption and motivate residents to embrace the benefits of reusing and using preloved items. The fund sought to enhance and support the efforts of community groups, allowing them to reach more residents than the Council could typically engage, ensuring that as many people as possible could access the benefits of behaviour-changing initiatives. 8 successful applicants were awarded up to £2,000 for their projects which will be carried out from June to December 2024. | Waltham Forest hosted 3 repair & reuse events: - Langthorne Park Leytonstone (partnering with Toy Library) on 14th July 2024 Focus on reuse, repurposing and repair for the outdoors, including tool sharing, play and community gardening.​ Estimated audience of 300, 6 bike maintenance workshops, 15 bike repairs, 22 electronics booked in for repair, Tool Sharing podcast recorded promoting the Library of Things. - Handsworth Primary School, Highams Hill 29th Sept 2024 focus on interiors, including reclaimed paint, upcycling furniture and DIY skill sharing, as well as the usual give & take, electronics repairs and Dr Bike., seeing machine repair workshop. - Big Creative Academy, Blackhorse Road, 30 Nov 2024 (partnering with Reloved Club) seasonal festive fair providing ways to reuse, repair, repurpose and upcycle everyday items just in time for Christmas, in partnership with The Re-Loved Club. Waltham Forest launched the Repair and Reuse Directory in June 2024 and has 115 local businesses listed. https://www.walthamforest.gov.uk/rubbish-and-recycling/reuse-and-recycling/waltham-forest-reuse-and-repair-directoryThe Waste Prevention & Recycling Initiatives Fund was established to support creative and impactful projects that help residents of Waltham Forest reduce waste and increase recycling, ultimately fostering healthier and more vibrant communities. These initiatives aimed to encourage recycling and reuse, educate the public about sustainable practices, and bring innovative ideas to life that make recycling more appealing. Participating projects included providing resources for community litter-picking, organising repair clubs, running workshops on crafting furniture from reclaimed wood, and distributing refurbished laptops to refugees for educational use, just a few examples of the diverse efforts supported by the fund. |
| 19 | Reuse and repair | Continue to promote RRC sites in borough as a means to reuse and recycle items. The average recycling rate across the NLWA RRC network was 72.1% in 2021/22, meaning encouraging visits to the site should help improve overall recycling rates and onward reuse/recycling of material streams. Continue to promote Second Time Around Re-Use shop in located at Kings Road RRC site in Chingford. The shop provides residents with the opportunity to buy ethically by purchasing pre-loved items at affordable prices. Promote NLWA drop off and collection of DIY materials at South Access Road providing an avenue for residents to borrow DIY tools that would otherwise have gone to waste/been recycled. | On track | Activities aim to achieve targets set out in Dashboard, but contributing to waste reduction. DIY materials, polystyrene and hard plastics | In 2024-25, 81.24% of all NLWA RRC material was recycled, reused or composted. |
| 20 | Large Item Collection Re-use | Promoting Reuse service for Large Item Collections. Segregating materials and working with partners for items to have a second life or to be upcycled. | On track | Continuing to partner with charity TCL to supply reusable furniture collected through the Council’s reuse element of the bulky waste service. | 10.52 tonnes of reuse furniture was collected and reused in 23/24. 11.41 tonnes of reuse furniture was collected and reused in 24/25. |
| 21 | Food Waste | Pan-London Food Waste Campaign will be delivered in partnership with ReLondon, London Boroughs and London Waste Disposal Authorities to inform and empower individuals to reduce their personal food footprint. The Eat Like a Londoner campaign is using inspiring messages and practical advice to build on the success of past campaigns such as TRiFOCAL (the ‘Small Change, Big Difference’ campaign), and existing campaigns such as Food Wave. | Complete | NLWA is a delivery partner and steering group member for the Eat Like a Londoner campaign on behalf of the 7 north London boroughs. It is a pan-London communications campaign to encourage and inspire residents to waste less food and eat more sustainably. In 2023/24 the campaign was promoted at events across all boroughs and was complemented by four behaviour change workshops which included a low-waste cooking demonstration. Participants weighed their food waste to monitor their progress and provide crucial data to evaluate the effectiveness of the intervention. The campaign is now ongoing, with plans to build on the campaign in the coming months. | NLWA is a delivery partner and steering group member for Eat Like a Londoner - a pan-London communications campaign to encourage and inspire residents to waste less food and eat more sustainably. The social media campaign in NLWA boroughs alone, generated over 3.1 million impressions, approximately 90,000 video views, a reach of nearly 30,000, resulting in 9254 clicks to the ELAL website. An evaluation of the campaign demonstrated that 3 in 20 of the target audience 21–44-year-olds and 1 in 10 parents of children under 12 recalled seeing the campaign. Of those approximately 60 percent reported to have taken action, by wasting less food, eating more plant-based foods, and eating less meat and dairy. To complement the campaign, NLWA ran behaviour change workshops which assisted residents with tackling their food waste and provided them with the knowledge and skills required. Participants weighed their food waste to monitor their progress. There was a significant positive difference in households' food waste following the workshops, demonstrating that the workshops success. Five workshops were delivered across Barnet, Camden, Enfield and Islington in 2024/25. Participants reported increases in awareness of the impact they can have by reducing household food waste, their understanding of how to reduce their food waste and gained the skills required, making it reportedly easier to reduce their household food waste. 94 percent of participants said they were likely or very likely to implement food waste prevention behaviours following the workshop. |
| 23 | Schools Engagement | Dennis to the Rescue dustcart activity play bus for schools. Retrofitted mobile classroom and workbooks bespoke to the borough. Schools Earth Day. | On track - ongoing | Earth Day 2024 Waltham Forest was invited to participate at Henry Maynard Primary School to Celebrate Earth Day 2024 on the 23 April 2024. The children were entertained with an interactive game on waste and recycling. The children were given reusable straws, reusable water bottles, tote bags and wordsearches. Waltham Forest recycling officers engaged with the parents, offering advice and answering their questions. The Hive Food Waste Lessons The Hive education officers developed and delivered assemblies and hands-on interactive lessons about food waste to 10 schools across the borough from January to April 2025. The aim was to inform pupils about the differences between avoidable & unavoidable food waste, the importance of separating waste & recycling and how energy can be created from food waste through anaerobic digestion. | The Earth Day event raised awareness about waste reduction and engaged the community in recycling practices. The event reached students and parents through interactive games and direct engagement. Earth Day event 2025 at Henry Maynard School, successfully engaged with residents, teachers and children. As like 2024 event, games and recycling goods handed out to children and residents. Supported NLWA ‘In the Know’ Programme to schools in the borough which consisted of carrying out a waste audit and establish a culture of waste prevention. |
| 25 | Reusable Nappies | Reusable nappy scheme: NLWA continues to pay a subsidy, increased as of 1 April 2023 from £54.15 to £70 per baby to parents/carers in north London who use reusable nappies rather than disposable ones. The level of subsidy reflects the saving to NLWA of not having to dispose of the nappies in the waste stream. The voucher scheme is administered by Real Nappies for London (RNfL) and includes all North London boroughs as members. WF to continue to support the scheme on social media and though targeted and paid advertising Work with RNfL to promote nappachino demonstration and second-hand reuse events withing the borough. | On track | Real Nappies for London are a much more environmentally friendly and cost-effective alternative to disposable nappies. Real nappies is a waste prevention campaign to reduce London's single-use nappy waste by promoting reusable, washable nappies. Working in partnership with Waltham Forest to offer a reusable nappy voucher incentive supporting families with the upfront cost of buying reusable nappies, or contribute towards a trial washable nappy laundry service. | In Waltham Forest, 221 vouchers were issued from 1 April 2024 to 31 March 2025, with 127 vouchers redeemed. Throughout 2024/25 financial year (April to March), Real Nappies for London carried out 26 reusable nappy information events in Waltham Forest, consisting of eleven in-person and 15 online sessions reaching 189 people across the borough. Ongoing promotion continues. |
| 26 | RRC’s | All RRCs have reopened after the height of the pandemic and are now operating full time hours. The booking system is under review, looking at the positives and negatives of having/not having this in place, and a decision whether to retain this or not. Textile’s contract has been renewed and we are now looking to increase the scope of textiles and carpets that we accept at our RRCs network. We hope to have this offer up and running in 2023. Waltham Forest South Access RRC, Summers Lane RRC and a third site at Wembley Waste Transfer Station have been part of a trial to recycle expanded EPS since November 2021. The trial is a partnership with British Plastics Federation and Greenbank Recycling Solutions. The recycling of this material will allow it to be used in insulation and similar products, avoiding the need for virgin materials to be used for these purposes. The trial runs till December 2022. A trial to recycle mattresses via RRC sites began in June 2021. By the end of November 2021 almost 26,300 units had been recycled. As of Qtr.1 22/23 Waltham Forest has been attributed 342.5 tonnes of mattresses that have been diverted from EfW. | On track - ongoing | The booking system at the RRC’s has ceased to operate and visiting is on a as and when basis..The NLWA Board accepted a recommendation to withdraw the digital pre-booking system for cars at its authority meeting on 31 October 2022. The booking system was originally introduced as a temporary change in response to the Covid-19 pandemic in March 2020. This change allows residents greater freedom to ‘drop in’ to RRCs and dispose of their items sustainably In 2023/24, NLWA continued to expand the range of material collected at our RRCs. The introduction of legislation in January 2023 requiring Waste Upholstered Domestic Seating (WUDS) to be consigned as POPs, meant that a proportion of bulky waste that would have ordinarily been recycled, is now shredded and sent to energy from waste. This limits our ability to recycle or reuse certain types of bulky waste. Hard plastic recycling at the RRC now offered to residents in the borough. | NLWA saw an increase in the number of mattresses collected compared to 2022/23, with around 9,000 mattresses being processed per month. Recycling of hard plastics increased to 104.89 tonnes in 2023/24. In late 2023, NLWA launched a carpet recycling initiative at our RRCs which captured 26 tonnes of material between November 2023 and the end of March 2024. The Expanded Polystyrene (EPS) scheme grew in 2023/24, collecting 5.34 tonnes up from 0.9 tonnes in 2022/23. NLWA launched a new trial service to encourage reuse at two RRCs in Waltham Forest and Barnet to offer a place for residents to deposit unwanted DIY materials and take free of charge. In 2023/24 between the two sites, 91.79 tonnes of DIY materials were diverted for reuse. NLWA aims to maximise recycling and reuse opportunities across the seven RRCs to make better use of the materials handled by the authority. In 2024/25, NLWA continued to divert difficult-to-recycle materials from the residual waste bin, capturing even more material than in previous years. In 2024/25, NLWA saw a 7% increase in the number of mattresses recycled across the RRCs and waste transfer stations compared to last financial year, collecting an average of 8,512 mattresses for recycling every month. Following a trial period in 2023, north London residents can now recycle hard plastics, such as plastics children’s toys and garden furniture, at four of NLWA’s RRCs. The expansion of this service has seen an increase in the amount of material captured for recycling, with almost 170 tonnes recycled in 2024/25. The carpet recycling service, originally operating as a trial at South Access Road RRC, was introduced at two more RRCs and captured 213 tonnes of material in 2024/25. NLWA saw a 56% increase in the amount of Expanded Polystyrene (EPS) collected for recycling across RRCs in 2024/25 compared to the previous year. NLWA operates a DIY reuse scheme at two RRCs which encourages residents to reuse DIY materials captured across the LEL RRC network, free of charge. The volume of material diverted for reuse increased from 91.8 tonnes in 2023/24 to 104.2 tonnes in 2024/25. 108 tonnes of paint were collected for reuse by residents in 2024/25, up 35 tonnes compared to 2023/24. In 2024/25, NLWA launched a dedicated disposable vape recycling service across RRCs to promote the safe disposal of these products. The scheme captured a total of 830 kilograms of material in its first year of operation. This is equivalent to approximately 39,500 individual disposable vapes diverted from litter, street and kerbside bins. |
| 27 | LEL | In April 2022, NLWA varied their existing contract with LEL to facilitate the use of the Temporary Bulk Waste Facility (TBWF). NLWA are currently developing a new contract to manage the education and visitor centre at the RRF. NLWA are developing (in consultation with the boroughs), a new contract for the management of the state-of-the-art facilities at the Eco Park. The contractor has been instructed to install an additional 370 solar PV panels at the new RRF. There will now a total of 2235 solar panels at the RRF. The Temporary Bulky Waste Facility (TBWF) became operational in April 2022. This facility allows us to transfer organic and recyclable materials for processing and extract some for recovery and reuse. We expect the new RRF facility to come into use in Feb 2023, at which point the TBWF will no longer be required. The R1 rated Energy Recovery Facility (ERF) will be available in 2025. [LBWF officers joining NLWA for a Joint Waste Strategy listening exercise in Walthamstow Market to find out more from the public about some of the key issues and challenges we’ve worked on across North London.] | On track - ongoing | These additional panels will provide a 20% increase in total output for the whole system from 755kWp to 905kWp. In 2023/24, construction of new facilities under the NLHPP continued, including the new Energy Recovery Facility (ERF). The ERF will have the capacity to manage 700,000 tonnes of residual waste from the seven north London boroughs, future-proofing north London’s waste management infrastructure for a growing population. New infrastructure at the EcoPark delivered by the North London Heat and Power Project (NLHPP) will be owned by NLWA and operated by LEL. In 2023/24 the Authority signed a new contract with LEL for the operation and maintenance of the EcoPark’s Resource Recovery Facility (RRF), public Reuse and Recycling Centre (RRC) and EcoPark House, a community and education space. The new LEL contract includes a complete complement of operational, maintenance and asset management requirements - specified to achieve the long-term waste and recycling services required by residents | In 2024/25, construction of new facilities under the NLHPP continued, including the new Energy Recovery Facility (ERF). The ERF will have the capacity to manage 700,000 tonnes of residual waste from the seven north London boroughs, future-proofing north London’s waste management infrastructure for a growing population. As of the end of 2024/25, LondonEnergy Limited (LEL) has completed the internal process to transfer the management of the RRF and RRC from construction to BAU operations, principally governed by the EcoPark South Operational contract. In April 2024, the Resource Recovery Facility (RRF) began welcoming borough vehicles, ramping up to full operations and enabling it to function as a modern waste management facility. In its first year of full operation, around 170,000 tonnes were processed through the facility including residual waste, bulky waste, food waste and garden waste. The expanded capacity of the RRF provides provision for north London to double its food waste collection ability, ahead of the planned compulsory food waste service for all residents across England by April 2026. Space has been allocated to the new RRF to support recycling and reduce waste. In 2024/25, NLWA engaged consultants to conduct a review of existing mixed waste sorting operations in other countries to understand what might be possible in north London. Officers will use the findings of this report, along with knowledge of other innovations in the waste sector, to determine how best this space could be used to increase recycling and reduce the carbon impact of the residual waste stream. The Edmonton EcoPark Reuse and Recycling Centre opened to the public in July 2024. It is the first major public facility delivered as part of the Project and allows north London residents to bring their recycling directly to the EcoPark for the first time. In the first nine months of its opening, more than 16,000 vehicles visited the centre and around 1,700 tonnes of waste have been deposited by residents for reuse, recycling and recovery. As the site enters BAU operation, NLWA are working with LondonEnergy Ltd to review opportunities to expand the reuse and recycling offer at the site. EcoPark House, the Authority’s new education and visitor centre, opened its doors in January 2025. This sustainably built community asset serves as an educational facility and is the new home of the Edmonton Sea Cadets. EcoPark House aims to become one of the best education and visitor centres in the country. In its first month, the education programme at EcoPark House earned a prestigious quality badge from the Council for Learning Outside the Classroom, a Department for Education-backed initiative. Schools are invited to book sessions at EcoPark House to enhance young people’s understanding of waste management and circular economy principles. The programme has been successfully implemented and over 200 students and staff have participated. The programme is receiving outstanding feedback from school staff, notably the impact of students viewing the Resource Recovery Facility and the high-quality, engaging activities. Following their visits, all teaching staff have indicated that they would recommend a visit to a colleague. Since its opening, EcoPark House has become the new hub for visitor tours, featuring an engaging walkaround of the Resource Recovery Facility. The building has also hosted its first community repair day. Looking ahead, officers will continue to expand the range of programmes available, with plans to develop offerings for secondary school students and explore the feasibility of further and higher education programmes. |
| 28 | NLWA Waste Prevention Plan | A new plan is being prepared for 2022-25 and due to be agreed in Autumn 2022. The aims of the plan are to: - Increase residents’ understanding of the journey of waste and the need to shift from a linear to a circular economy - Provide information and advice on how to adopt more sustainable behaviours - Increase residents’ understanding and motivation of how and why it is important to recycle effectively - Promote effective recycling - Provide policy responses and engagement with national and regional strategy development on waste prevention - Campaign for government action to increase support for the circular economy, including reforms which reduce packaging, encourage reuse and repair - Campaign for systemic changes to reduce the manufacture and consumption of single-use and unrecyclable items. | On track | The North London Waste Prevention Plan was published in January 2023. The plan was developed through collaboration with residents, environmental specialists, borough staff, councillors, and campaigners. The development of the plan involved engagement sessions, meetings, and conversations to provide insight into local priorities and identify where NLWA activities can support partners to achieve shared ambitions. The plan is developed to set out the approach to working whilst the next North London Joint Waste Strategy, owned by the constituent boroughs and NLWA, is being developed. Projects delivered or launched in 2023/24 as part of the plan include: - Together We Recycle - Eat like a Londoner - Reusable period products campaign - Education plans - Bring it... - Reusable nappy subsidy | In January 2023 NLWA published Preserving Resources, Driving Change, which sets out our approach to community engagement, communications and policy work. The aim for this ambitious programme is to draw on the collective expert experience of NLWA and constituent boroughs, apply behaviour change methodologies, use existing research and test and evaluate approaches as work is developed and delivered. The priorities are to: - Enable communities to deliver change on the ground by providing residents with prevention, reuse, and repair opportunities - Campaign for change - Work in partnership - Educate and inform residents - Support our boroughs - Work with businesses |
| 29 | NLWA Joint Waste Strategy | NLWA are currently developing a new Joint Waste Strategy with the 7 boroughs for the management of waste from households in North London The strategy planning and design is anticipated to last around 18 months (although this may be extended depending on whether additional requirements, such as a Strategic Environment Assessment, are deemed necessary). All statutory stakeholders will be engaged in this process, an equalities impact assessment will be undertaken together with a full resident consultation. NLWA will carry out modelling, including a detailed composition analysis, into EPR and DRS. The strategy will set out how NLWA and the seven boroughs will work together to minimise the amount of residual waste arising and to increase reuse and recycling rates (amongst other objectives). | On track | The writing of the new North London Joint Waste Strategy began in early 2023, led by NLWA in collaboration with the north London boroughs. A public listening exercise was undertaken in summer 2023 in Walthamstow Market, to understand north London residents’ priorities, which has fed into the drafting of the strategy. NLWA commissioned a waste composition analysis for all boroughs, which was completed across 2022 and 2023 and has been used to inform the strategy. It is currently still in the drafting process, with the draft strategy expected to go to public consultation in summer 2024, and the final strategy expected to be adopted in 2025. As part of the strategy development, a Strategic Environmental Assessment and Equality Impact Assessment are being produced and will go out for consultation alongside the draft strategy. | The new North London Joint Waste Strategy has been developed over the past three years, with writing beginning in early 2023, led by NLWA in collaboration with the north London boroughs. It is a joint Strategy across all eight partners. A public listening exercise was undertaken in summer 2023 to understand north London residents’ priorities, which has fed into the drafting of the strategy. This was followed by a formal public consultation on the draft Strategy undertaken between November 2024 and January 2025. These engagement pieces reflected diverse views across north London’s communities and show robust findings in support of the content of the Strategy. Following the public consultation exercise, NLWA produced a revised version of final draft of the Strategy, taking into account the responses to the consultation surveys, comments from north London environmental groups, feedback from the Greater London Authority (GLA) and from the borough scrutiny committees. The changes made to the Strategy have been shared with the Joint Waste Strategy Evaluation Group and borough officers and members. Their comments and feedback have been further incorporated into the draft document. Once the document is finalised, each of the individual boroughs and NLWA will be asked to take a decision under their own governance arrangements to approve the final draft in summer 2025 (the majority at Cabinet meetings). Assuming each borough and NLWA gives this subsequent approval, this will commit each to the content of the Strategy. Finally, NLWA will adopt the Strategy as NLWA policy (programmed for an NLWA authority meeting in late 2025). NLWA commissioned a third party to conduct a composition analysis of various waste streams across each borough and a summary report was completed in 2024/25. The analysis will provide a useful insight into the makeup of the waste collected by the seven boroughs, enabling officers to identify opportunities to target interventions to increase recycling and reduce waste. It will also inform NLWA’s public affairs and lobbying work, providing local evidence to support asks of the government around key waste issues and policies. |
| 30 | Extracting Recycling | LondonEnergy Ltd leases and operates a sorting facility (at Wembley) which sorts wood, mattresses, metal, cardboard and hardcore material. LondonEnergy report that around 30% of the selection of materials put through this facility are extracted for recycling and reuse. Authority officers are coordinating with LondonEnergy Ltd over the development of a sorting facility within the new Resource Recovery Facility at the EcoPark. NLWA engaged consultants in 2022 to support the development of a facility when the new facility has been successfully commissioned. | Completed | Aim of 10,000 tonnes to be processed at the station per annum This is intended to handle between 30,000 and 65,000 tonnes of residual waste. Construction of the Edmonton EcoPark House (EPH) continued in 2023/24 and is scheduled to open in 2024/25. | EcoPark House opened as scheduled in 2024/25. |
| 31 | Increasing the offer | NLWA are working with Biffa (material recycling provider) to establish a compliant and sustainable UK partner to recycle all types of grades of plastic films. We are evaluating markets options and find a viable solution. The aim is to ensure that Boroughs are able to collect flexible plastics within the timescale set out in the government’s Resources and Waste Strategy. | On track | To find a suitable off-taker by 2024/25 | Conversations are ongoing with Biffa to find a viable solution for this material however; the UK end market is limited. Biffa are submitting a proposal to NLWA in due course which will detail options for managing soft plastics. |
| 32 | Increasing the offer | NLWA’s new state of the art Resource Recovery Facility (RRF) at the Edmonton Eco Park is planned to open in the late summer 2023, with a proposed sorting solution for pre-treatment/separation for certain waste streams within the building. This mechanical and automated application will process between 30,000 and 65,000 tonnes of residual waste. NLWA are continuing to engage with consultants to deliver the best technical solution based on the preliminary findings of a recent waste composition analyses undertaken by the authority in addition to considering the future legislative requirements | Completed | Expect to recover 30% of materials for reuse and recycling. In 2023/24, the construction of the Resource and Recovery Facility (RRF) at the Edmonton EcoPark continued. The site went into operation on 15th March 2024 and will begin accepting borough waste from April 2024. The RRF, which has capacity to manage 374,000 tonnes of waste annually, is designed to bulk recycling and organic waste for onward transport to processors, extract recyclables from residual waste and prepare bulky waste for energy recovery. Space has been allocated to the new RRF to support recycling and reduce waste. In 2023/24, NLWA engaged with consultants to carry out reviews of best practice in the UK which culminated in two reports that explored the feasibility of installing pre-sort technology in the RRF. Following the outcomes of the reports and decisions taken by a working group developed to support this work, NLWA plans to conduct further research into technological innovations for managing waste to understand the best use for this space. | See 29. |
| 33 | LEL Residual transport arrangements | As part of the NLWA’s and LEL’s sustainable strategy, consideration is being given to prioritize a transition to alternative fuels, A collaborative executive committee has been set up with several specific sustainable tangible goals. In addition to operating several fully electric light good vehicles the committee has provided a business case that has been approved to procure a fully electric Heavy Goods Vehicle (HGV) waste bulker to support its operations. LEL currently operate 13 bulker vehicles with leases that expire in late 2024. The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are now all ULEZ compliant. It is a requirement of the main waste contract with LEL to use Euro IV vehicles as a minimum. LEL have initiated a vehicle replacement programme to ensure vehicles comply with ULEZ. All vehicles are now Euro VI, leading to a significant reduction in NOx emissions. | On track | Emission reduction - reference concluded. The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. From 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. The new RRF at the EcoPark features 2,235 solar panels on its saw-tooth rooftop which were switched on in late 2023/24. The EcoPark Array will produce renewable energy, equivalent to powering 300 homes yearly with electricity, and has been added to the site as part of the North London Heat and Power Project (NLHPP). There are also plans for solar panels to be installed on the new ERF once built. NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the decarbonisation of the energy produced. NLWA’s efforts to reduce waste and manage waste in line with the waste hierarchy supports emissions reductions associated with the management of large volumes of waste. In 2023/24, the construction of the Reuse and Recycling Centre (RRC) at the Edmonton EcoPark continued. The site is scheduled to open in the second quarter of 2024/25. | The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. From 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. Solar energy is now being generated by the Edmonton EcoPark solar array located on the roof of the RRF. 2,235 photo voltaic panels cover the size of a football pitch and generates energy that is distributed to the EcoPark for waste operations and construction commissioning activities. Up to and including Sunday 4 May, the power produced by the solar panels totaled 759,123.47 kWh with an average kWh per day of 1668.4. 2 June 2024 saw the highest power producing day in the past 12 months. NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the decarbonisation of the energy produced. The new facility will meet the new requirements for permitting new facilities set out in Defra's residual waste capacity note published in December 2024. NLWA’s efforts to reduce waste and manage waste in line with the waste hierarchy supports emissions reductions associated with the management of large volumes of waste. |
| 34 | Waste Prevention Exchange | This annual event will be delivered to bring together sector experts on a programme of topical waste prevention issues, delivered by NLWA. | Completed | Raise awareness of resource reduction. | The WPE took place 18/05/23 and topics of discussion were challenges and opportunities at the LA level in achieving a circular economy (CE), why are CE principles so important, procurement, planning and design, partnership, behavioural insights, communication and case studies were presented. |
| 35 | Journey of recycling | Production of six videos showing what happens to North London’s waste and recycling. Some videos will follow items of household recycling from the home, through the recycling process, until they are turned into something new. Videos were completed at the end of 2022 and promoted through a paid-for social media campaign. | Completed | To educate about the journey of waste, we commissioned research via YouGov to better understand the existing knowledge of Londoners. Following that, we worked with a video producer to create three distinct videos to show north Londoners what happens to their waste once it’s been disposed of. The three videos focus on general rubbish through the lens of the Energy from Waste facility; recycling, focussing on the Materials Recovery Facility; and lastly large items, focussing on one of our reuse and recycling centres. | The videos received almost 50,000 views and will be used in future work on schools and education. https://www.nlwa.gov.uk/where-your-waste-goes/what-happens-north-londons-rubbish |
| 39 | Reusable period products | Behaviour change project to increase the purchase and use of reusable period products will be delivered in 2023/24, focusing on waste prevention and the benefits of cost savings associated with switching to reusable period products. This initiative will include a digital communications campaign and information webpage on nlwa.gov.uk, discount voucher offers for residents, and in-person and digital outreach and engagement. Procurement of contractor currently in progress. | On track | NLWA committed to promoting reusable period products as an alternative to single-use options. The ‘Reduce, Reuse, Your Cycle’ campaign was designed through the application of behavioural science and seeks to increase the purchase and use of reusable period products in North London. The campaign aims to decrease the purchase and use of single-use period products, leading to a reduction in the generation of single-use plastic waste and the negative environmental consequences associated with their consumption. NLWA has partnered with Women’s Environmental Network (Wen) to offer in-person workshops and sessions with trained facilitators. Free workshops have been hosted in North London schools, universities and workplaces, explaining more about reusable period products and the different kins available. NLWA has also partnered with reusable period product brand Flowette and offer a 25% discount when signing up. | The Reduce, Reuse, Your Cycle campaign launched in January 2024. It was designed through the application of behavioural science, seeking to increase the purchase and use of reusable period products in north London. The project has involved a holistic approach of outreach workshops, school assemblies, discount codes and digital and out-of-home communications to improve the knowledge of, and access to, reusable period products. 42 events have been delivered to date across 7 boroughs, engaging 1,800 members of the public. This included 16 workshops, 4 school visits, 18 engagement stalls, 2 teacher training sessions and 2 ambassador training sessions. 96% of participants said they were likely to recommend RPPs to friends and family, while the most common motivation cited for using RPPs over disposables was the money saved (19% of survey respondents). Two bursts of comms ran across 2024, with channels including a bespoke, branded campaign website, organic and paid social media, outdoor advertising, media outreach, email marketing and google advertising. The most successful channels were the website, (over 41,000 page views to date) and paid Meta advertising (over 5 million impressions). Evaluation showed that digital communications were the most effective way of reaching audiences, so that will be the focus of the campaign from now on. We have also developed a brand toolkit to share the campaign with interested partners, beginning with East London Waste Authority who are expecting to do an RPP campaign with our branding in 2025. |
| 42 | Promoting Reuse Shops and use of RRC’s | Campaign to promote the reuse shop at Kings Road Reuse and Recycling Centre. This will include a promotional event at the shop, social media advertising and a press release. Advertising campaigns to raise awareness of and increase attendance at reuse and recycling centres. | On track | To increase the amount of material donated above existing levels and carry out promotional event, social media and a press release with the overall aim of increasing awareness of the shop and encouraging more residents to visit the shop broadening their understanding of the initiative. Prior to the change to AWC, a new service leaflet was delivered to 80,000 kerbside properties detailing the boroughs RRC’s & Reuse shop offerings. | Footfall to the reuse shop remains consistent and NLWA are continually seeking ways to improve customer experience and donations received. |
| 43 | ‘Bring It’ Campaign | Behaviour change communications campaign tackling recycling on estates. Using personalised messaging from local collection crews. Campaign tactics will include leaflets delivered by crews, PR campaign launch sharing ‘local hero’ stories about recycling collection staff, and outdoor and social media advertising with artwork and video content featuring real crew members sharing stories and anecdotes, as well as recycling tips. | Complete - recurring | The ‘Bring It’ is a campaign that aims to encourage residents to use reusable coffee cups, bottles, bags, and containers to reduce single-use plastic. The campaign initially launched in Barnet and work is now being done to roll out the Bring It campaign to Camden, Enfield, Haringey, Hackney, and Islington – with Waltham Forest receiving it later in 2024/25. | Bring it...which launched in Barnet in January 2024, was successfully rolled out to the remaining six boroughs in 2024/25. The behaviour change campaign aimed to encourage residents to use reusable coffee cups, bottles, bags and containers to reduce single-use plastic. The project focused on social normative messaging, using real residents and businesses to influence peers and included prompts to help residents to remember to bring their reusables with them when they leave home. The social media campaigns generated over 9.3 million impressions, reaching over 4.1 million residents and resulting in over 53,500 landing page views. Out of home advertising targeted residents when visiting the high streets, where 350 local businesses had signed up to the campaign. Residents who saw the campaign were significantly more likely to be concerned about the environmental and health impacts of single-use plastics, believe it is easy to reduce their use, and wanted to see more efforts to facilitate the use of reusables to help protect the planet for future generations. They also reported significantly higher levels of engagement in six out of seven reuse behaviours, including using reusable containers for hot drinks, takeaway breakfasts, lunches, dinners and loose groceries and were more open to borrowing and returning all types of reusable items and using their own containers for takeaway meals. The results are promising, and suggestive of outcomes that contribute to reducing single-use plastic waste across north London. To further facilitate the use of reusable containers additional reuse options must be available to our residents which will require broader systems change. |
| 44 | Waste Prevention Community Fund 2024/25 | Fourteen community groups will receive a share of £250,000 towards waste prevention activity as part of North London Waste Authority’s (NLWA) flagship initiative. The successful recipients, from the seven north London boroughs of Barnet, Camden, Enfield, Hackney, Haringey, Islington, and Waltham Forest, have been allocated small awards of up to £5,000 and medium awards of up to £15,000 each. The projects encompass a range of waste reduction strategies including repair, upcycling and textiles, sustainability, food waste, and recycling and reuse education. Examples of projects include a resident-led household and gardening tool lending library, supporting the establishment of a repair club which builds on the legacy of one of last year’s funded projects, and a youth education programme focused on waste prevention and environmental protection. | On Track | In 2024/25 14 community groups received funding to deliver on various waste prevention activities. A breakdown of this for Waltham Forest is as follows: - Forest Recycling Project Ltd (FRP) – Tool Lending Library - The Mill – Forest Fixers In addition to this, two large awards are being funded: - The Restart Project and ReLondon have launched an electrical repair voucher which offers residents access to 50% discounts on electrical repairs at businesses in Hackney, Haringey and Waltham Forest. Officers are working with Restart and ReLondon to establish effective data collection and evaluation methods and understand how it could be expanded to cover the whole north London area. | - 553 members participated in using the tool library. 96 were low-income members. - 960 loans were undertaken which resulted in 44.3 tonnes of co2 diverted. - 23 repair cafes were delivered where people could have items fixed. - 22 repair clubs were delivered where people could learn repair skills. - 30 appliances were fixed and 7 items passed on for resale at charity shops - 2 volunteers upskilled to safety leads |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| 45 | Extend blister pack recycling offer | Currently in 3 locations in the borough, expand offer to more locations. | Blister pack recycling available in 6 locations in the borough. | 2025/26 |
| 46 | Separate food waste recycling for flats above shops | Following the food waste trial, aim to collect food waste separately from Flats Above Shops. | 49 roads with Flats Above Shops, currently collect from 2. | 2025/26 |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| 47 | Communal Food Waste | Roll-out of separate food waste collections to all purpose-built flat properties in the borough not currently receiving service, including procurement of food waste caddies and communal containers. Recruitment of Food Waste Officer on a one year contract to escalate the roll out food waste service to all flatted properties that do not currently have the service. Working with Managing Agents and Registered Social Landlords to integrate food waste collection service into existing blocks. Increase food waste recycled in the borough through diversion from the residual waste stream. | Please see updates on action 10 above | 2025/26 |
| 48 | Separation Food Waste Collection at the kerbside | Separate food waste collections implemented from Sept 2024 to all 80,000 kerbside properties. Each property received a 23ltr outdoor caddy, a 5ltr indoor caddy, a roll of liners (6-month supply) and an information leaflet. Delivery of a further 6-month supply of food waste liners ongoing | Please see updates on action 11 above | 2025/26 |
| 49 | Food waste in schools | Offering schools a food waste recycling service. All schools that currently have a recycling collection (and do not currently have a food waste collection) will be offered this service. | Please see updates on action 14 above | 2025/26 |
| 50 | Increasing the offer | NLWA are working with Biffa (material recycling provider) to establish a compliant and sustainable UK partner to recycle all types of grades of plastic films. We are evaluating markets options and find a viable solution. The aim is to ensure that Boroughs are able to collect flexible plastics within the timescale set out in the government’s Resources and Waste Strategy. | Please see updates on action 31 above | 2025/26 |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026