London Borough of Waltham Forest RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date. - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action. - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| 1 | Communications and Engagement | Digital screens on Vehicles - Fully utilising the digital screens on waste/recycling vehicles to reflect current campaigns (seasonal and non-seasonal) by uploading MP4 short clips to capture residents’ attention. Future planned campaigns include: Podback coffee pod recycling, promoting indoor recycling bags, promoting food waste reduction and raising awareness of common contaminants. Updating livery on fleet vehicles to encourage uptake in recycling participation. Waste and Recycling Webpages - Review and update webpages to promote key ‘reduce, reuse & recycling’ messages. Links to key webpages such as RRC’s and imbedded NLWA ‘can I recycle it’ look up. Webpages to promote: Home composting, Additional Items, Furniture Recycling and reuse organisations, Bring Banks, Real Nappies. Waltham Forest News (WFN) – the Council’s magazine which is circulated quarterly to all homes and business in the borough. The Waste Team regularly place advertisements and work with comms colleagues on editorials to educate residents on waste reduction, recycling, and re-use messages. Recent articles/ads have included – coffee pods promotion, contamination messaging, recycling, launch of DIY materials recycling service, increased recycling participation. Targeted Social Media – The Waste Team working with comms colleagues to target specific messages to specific demographics. Recent targeted campaigns have dealt with contamination (Yes Yes No) and promoting additional items recycling. Outdoor Advertising i.e. Bus Stops/Bus Backs Billboards and street kiosks – In order to reach a wider segment of residents the Waste Team recognise the importance of adverts in areas of high footfall and to this end are planning a campaign to disseminate key contamination reduction and recycling participation messages to be delivered in the summer of 2023. | On track | Digital screens continue to be fully utilised on vehicles – currently focusing on Rethink Recycle Repeat campaign, advertising Library Of Things and the introduction of separate food waste collections in September 2024 to kerbside and communal bin properties. Static livery updated with new dry recycling campaign artwork. Different look and feel to previous comms, very colourful, lively and fun to attract a widespread audience through their pictorial nature. Waste and Recycling webpage update still underway, completion expected end of August 2024. Separate food waste pages redesigned with simple customer journey. The Rethink, Recycle, Repeat campaign focused on the residents of Waltham Forest and how they could engage with a recycling initiative. The goal was to empower residents to recycle more and reduce contamination, ultimately improving recycling rates across the borough. This strategy led to the creation of a visually striking and memorable visual identity. Playful stickers, inspired by general waste packaging, became the foundation of this identity. The campaign's messaging was designed to be concise, snappy, and memorable, offering a clear call to action. Waltham Forest has recruited over 800 binfluencers which refers to local influencers who promote positive waste management practices and recycling within the community. This term combines "bin," referring to waste bins, and "influencer," indicating individuals who can sway public behaviour and opinions using social media. The initiative is part of a broader effort to encourage residents to adopt more sustainable habits, reduce waste, and increase recycling rates. As part of Waltham Forest Separate Food Waste collection, Waltham Forest hosted a competition and provided information to residents: - Vehicle naming competition – naming the new food waste vehicles to win a prize. - E-Newsletters – WF Housing, private landlord, climate news, Binfluencer e-news, voluntary community sector promoting a new collection service. - Communication rollout to council housing tenants including: - Information packs provided to Resident Association Leads - Leaflets to every household participating in the food waste collection service Waltham Forest has consistently made efforts to raise awareness throughout the borough and will persist in doing so in the future. Waltham Forest employed a range of communication channels on food waste, including social media platforms, the local Waltham Forest Newspaper, and various outdoor advertising resources, to effectively reach and engage with the community. These initiatives aim to ensure that important information and messages are widely disseminated, fostering a well-informed and connected borough. | Binfluencers: from initial call-out, Waltham Forest recruited 13 binfluencers. We now have a database of over 800 who are regularly contacted via newsletter with important information and materials to disseminate among their networks. While we are unable to track whether this goes into private channels, such as street or family WhatsApp groups, the open rate averages at over 40%, well above the national benchmark. Festive recycling campaign success: - 11,702 clicks to webpage from resident e-news- which is over 1000% increase from our average CTR in newsletters​. - Over 23,000 visits to festive recycling page on website – 10,000 visits higher than last year Food waste recycling campaign in August: - Newsletters (Res News, Climate, Binfluencer): 1,748 unique clicks to website - Website presence strengthened: More FAQs added from resident feedback; two web stories (first trucks on the road and truck naming winner) - Social media: 15 posts across Twitter, Facebook, - Instagram, TikTok, Nextdoor and WhatsApp; 21.5k views on videos; 543 comments - Internal: Your News, CE blog, Cllr briefings, library staff briefings, contact centre briefings, SLT briefings - Out of home: Mass Media billboards (two locations, combined circa 950k impacts per two-week campaign), digital kiosks (five locations), libraries (all), physical briefing pack to Councillors. |
| 2 | Reducing contamination - flats | Crew refresher training to identify common contaminants. Crew refresher training to report contamination on White Space via in-cab technology. Crews issued with contamination stickers for bins to inform Managing Agents, Residents and RSL’s that bins are contaminated, and to ensure that contaminated bins are not emptied on future occasions until contamination has been removed. Above training to be mandatory for new crew operatives and for to induct agency/temporary staff to ensure they are aware of practices and policy in this area. Temporary officer recruited to liaise with managing agents and the council’s enforcement team to work collaboratively to reduce contamination in communal bins. Contamination communications campaign targeted at estate residents: targeting communal blocks with high contamination with A5 postcards and installation of A3 posters in bin stores. Resources provided to Managing Agents and Residential Social Landlords. | On track | Crew guidance booklet and memos created for both kerbside and communal properties to educate and continually remind crews of established process. Contamination sticker has been refreshed. Contamination stickers have been updated with new branding. Collection crew operatives receive training to ensure compliance is met. Officer with the Council continuing to liaise with managing agents. | During the course of the communal recycling project a total of 263 Managing Agents have been written to regarding 955 properties on the subject of contamination. Contamination rate for 23/24 was 20.71%. This is an improvement on the last 4 year average of 22.15%. |
| 3 | Improving Quality of Recycling - flats | Recommendations to make improvements to bins and locations of bins e.g. reverse lidded bins & Metrostore Pods to better contain waste/recycling and provide a visual improvement to encourage residents to be diligent with waste and place correct items in correct receptacles. Working with housing to improve service provision - e.g. cleanliness, signage, bin stores. Updating existing literature for communal blocks so it is current, targeted and user friendly. | On track | 5 Recycling Assistants employed on a fixed term basis to initiate the food waste collection service in flats. Associated with this role is a scoping exercise to identify location of bins in communal blocks and to recommend any improvements, report bin misuse & cleanliness to Housing Associations and Managing Agents. For the new food waste collection service, a suite of assets has been designed to include new communal communications and literature which is targeted and user friendly. New food waste units have been procured which are more robust and accessible for communal residents, are visually improved and assist residents to recycle their food waste correctly. Housing Team assessing Waltham Forest refuse areas for cleanliness, access requirements (both for residents and collection crews), suitable surfaces and the discouragement of fly tipping. A reoccurring monthly meeting has been set up across departments to come together and improve services with our own housing stock, this includes, caretaking, housing officers, housing maintenance, the neighbourhoods’ team and the recycling and waste teams. | As of the end of July 2024 29% of communal properties currently have separate food waste collections. Pre-January 2024, less than 10% of blocks has access to separate food recycling service. This will continue to be rolled out until March 2025 |
| 4 | Planning Guidance | Working with architects and planners to design effective recycling provision and collections. Waste officers to attend planning meetings at early pre-application stage in order that waste recycling arrangements are given due consideration and designed into original plans. This will enable appropriate capacity and location as well as work-in space for food wate collections and Large Item Collection (reuse). It will further provide an operational perspective to ensure locations and materials are suitable for collection taking into account traffic flow and mitigate Health and Safety issues. Waste able to recommend that a planning application is not approved if appropriate consideration has not been given to the above. Continued engagement with ReLondon and Planning Department to ensure commitment to recycling storage provision is included within all new development applications for flats and estates. Compliance with Mayor of London’s London Plan guidance and policies e.g. London Plan Policy D3 3.3.18 Shared and easily accessible storage space supporting separate collection of dry recyclables, food waste and other waste should be considered in the early design stages to help improve recycling rates, reduce smell, odour and vehicle movements, and improve street scene and community safety’. | On track | Continued engagement with planning officers and developers to ensure that reuse and recycling is designed into developments. Planning guidance updated according to any changes in policy/legislation. New Guidance for Developers released with new Recycling Strategy was released in October 2023. https://www.walthamforest.gov.uk/rubbish-and-recycling/developers-and-managing-agents-bins-your-properties | Target achieved |
| 5 | Kerbside Contamination Project – Part 1 | Leaflets to kerbside properties on worst performing rounds where crew have had the most rejected loads. Analysing data provided by the MRF on gate rejects to identify which rounds/crew have the most full or partial rejections when tipping at the facility. Identifying which roads are serviced by the crews with the most rejected loads. Designing and periodically updating a contamination leaflet with information on the most common contaminants, which receptacles they should go in and why this is a problem. Leaflet is hand-delivered to all street-level properties services by crews with a high MRF rejection rate. Leaflets are delivered quarterly and around 15,000 leaflets are delivered at any one time. Planned door knocking to roads with highest levels of contamination to educate residents. | On-hold | Paused owing to recruitment of officer to manage this project, restarting August 2024. Once this project is restarted priority will be given to ensuing that we can get leaflets out as soon as possible. Leaflets are delivered a day or two prior to collection to allow residents to ensure that their bin is presented with the correct materials. |  |
| 6 | Kerbside Contamination Project – Part 2 | This project is ongoing and aims to tackle the worst offenders through a highly targeted approach to tackle contamination compromising of a four-stage process created to penalise householders that persistently contaminate their dry recycling bins. Householders receive different levels of notifications, warning letters and formal notices for continual abuse of the recycling service, ultimately resulting in Fixed Penalty Notices being issued to the worst contaminating households. The landlords of all properties registered under the Council’s Private Rental Property Licensing scheme are also contacted directly in addition to the warning letter issued to the tenant. As a second strand to this project - Where bins are contaminated the Waste Team will arrange for bins to be emptied as refuse as a one off and at the same time enact interventions. Crew are also instructed to sticker bins that are contaminated so residents are aware. Waste team also liaise with managing agents to disseminate information to residents on contamination. If contamination issues persist then the onus is placed on managing agent to empty contaminated recycling bins and further disseminate literature to residents/organise for recharge. As a third stage, and when cooperation from managing agents is not forthcoming, enforcement action is taken against managing agents. | Delayed – project restarted September 2024 | The process for notifying residents about contamination has been redesigned to ensure a thorough and consistent approach to data collection: - When the collection crew identifies a contaminated recycling bin, they will place a warning sticker on the bin. If only one warning sticker is issued within a 5-week period, no further action is needed. - If a second contamination is found within 5 weeks of the first incident, the Waste Team will issue a Stage 1 letter. - If additional contamination occurs within 12 weeks of the first incident, the Waste Team will issue a Stage 2 letter. - If another contamination is found the following week, the Waste Team will issue a Stage 3 letter. - If contamination continues, a Neighbourhoods Officer will issue a formal Notice of Intent, which remains valid for 12 months. - If further contamination is found within 12 months of the Notice of Intent, a Neighbourhoods Officer will issue a fixed penalty notice. | In the first five weeks of the project: 6182 kerbside properties were found to have a contaminated dry recycling bin. 670 Stage One letters have been sent. Meaning that residents noted that their bin was contaminated and actively removed this so that it could be collected on the following week. |
| 7 | Progress the range of expanded materials that can be accepted for Recycling at the kerbside. | Waltham Forest is unique amongst North London Boroughs in offering residents of street level properties the ability to recycling small WEEE items (e.g. Kettles, hairdryers etc), household batteries, clothes/shoes and batteries. Residents can place small WEEE, batteries and textiles bagged on top of their recycling bin and the crew will collect the materials and place them in a pod underneath the vehicle to keep them secure and dry. The materials are bulked in the Council’s depot until enough material is amassed so that the off taker can collect. Since the inception of the scheme in 2020 over 50 tonnes of additional items have been collected. Although some items are recycled this service promotes reuse (for example textile and WEEE) and in the case of coffee pods the coffee goes to AD to produce energy while the pods themselves are recycled. Continuing to promote kerbside recycling for street level properties of small WEEE items (e.g. Kettles, hairdryers etc), household batteries, and textiles. Promoting newly introduced (February 2022) coffee-pod recycling service for plastic and metal coffee pods. Residents leave items in coloured bags on top of their recycling bins to allow for crews to collect from their properties. Over 250,000 pods collected to date. [Trialling Podback coffee pod collection in flat buildings with concierge]. | On track | New additional item added to the collection service, printer cartridge recycling launched end of July 2024. Continued promotion of all the additional items is ongoing. Coffee Pod recycling in communal blocks to be launched in late Autumn 2024. | By the end of July 2024, Waltham Forest collected 60.23 tonnes of additional items: - 25.00 tonnes of textiles - 4.55 tonnes of batteries - 9.40 tonnes of coffee pods - 21.28 tonnes of WEEE items |
| 8 | Christmas Tree Recycling | Offering residents in communal and street level properties a collection service for their real Christmas trees. Residents can book a collection using the online form and a dedicated crew will collect on the allotted day and from the agreed location. Promoting the service through seasonal communications, | Complete | This initiative will run yearly. | During Dec 23 - Jan 24 1470t of Christmas Trees were composted from WF residents. 458 bookings for Christmas tree collection from residents in flats were made. |
| 9 | Reducing residual waste capacity | Offering residents a 140-litre refuse bin as standard with a free swap/replacement service if they currently have a 240 litre bin. Currently reviewing collection residual collection frequency. LBWF have carried out a public consultation to establish residents’ views on recycling and waste to assist with progressing this review. | On track | Fortnightly kerbside residual collection will commence in the first quarter of 2025. Introduction of initiative whereby residents can swap their regular dry recycling and garden recycling for a large one free of charge. Residents can already exchange a large refuse bin for a regular one. | WF expects this to have a positive impact on the recycling rate as more material to be recycled will be collected and less residual waste. |
| 10 | Communal Food Waste | Roll-out of separate food waste collections to all purpose-built flat properties in the borough not currently receiving service, including procurement of food waste caddies and communal containers. Recruitment of Food Waste Officer on a one-year contract to escalate the roll out food waste service to all flatted properties that do not currently have the service. Working with Managing Agents and Registered Social Landlords to integrate food waste collection service into existing blocks. | On track | Aim for completion is by March 2025, with a phased roll out. Increase food waste recycled in the borough through diversion from the residual waste stream. Recycling Assistants (RAs) rolling out communal food waste collections to all blocks of flats in the borough. To enable this, RAs conducting a scoping exercise on properties that have no separate food waste facility and identifying how many flats are in the building(s). New communal bins ordered; with updated artwork to align with the new campaign. All residents are delivered kitchen caddies, a roll of liners and guidance for recycling food waste. Monitoring is carried out to ensure collections are taking places as scheduled, and that contamination is reduced. |  |
| 11 | Separation Food Waste Collection at the kerbside | Currently collecting weekly separate food waste from 7,400 kerbside properties on a trial basis The trial shows good service participation and continued use overtime. Each resident receives a roll of caddy liners quarterly with a half yearly letter/leaflet to encourage continued participation | On track | A separate food waste collection service will be implemented from Sept 2024. Each property will receive a 23ltr outdoor caddy, a 5ltr indoor caddy, a roll of liners with a six-month capacity and an information leaflet. | This will be rolled out to approx. 82,000 properties. Roll out of receptacles will take place over a six-week period, with the borough being split into two halves; the north and the south. The south will receive the receptacles first and the week following the three weeks roll out will see collection begin. |
| 12 | Engaging Schools Projects North London Waste Authority | North London Waste Authority initiative to touring local schools to deliver waste reduction and reuse messages. Linking good recycling with climate change mitigation and reduced contamination. | On track | In 2023, the North London Waste Education Hub was launched, pulling together some of the best existing teaching resources on waste. The Education Hub is regularly promoted through social channels, email marketing, and features a new blog post each half term. Through consultations with borough officers and schools, NLWA have created a brand-new outreach Primary school programme has been developed which launched in 2024. 21 schools applied to take part in the first year of the programme across the 7 NLWA boroughs, and one school per borough has been chosen to participate. Through an initial intensive trial delivery approach, various whole school waste prevention interventions will be tested including: - Waste audits - Waste infrastructure reviews - Pupil engagement - School stakeholder workshops with senior leaders, governors, teachers, premises staff, catering staff, and PTAs - All-staff survey (pre and post intervention) to measure the change of behaviour and culture - Internal communications review | 3,479 visits to the Hub since it launched in April 2023 The outreach schools programme is in its infancy and metrics will be updated when the project is more developed. |
| 13 | Championing food waste reduction initiatives | Work in partnership with the NLWA to promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events. Food prevention workshops held at community events and schools; engagement to reduce amount of food waste disposed of per household Explore partnership and local promotion of Olio, Kitche & the Too Good To Go apps in the borough. Working with local schools to encourage more vegetarian options (to help tackle climate change) and to reduce overall food waste. | On track | Partnering with local community organisations like the Forest Recycling Project (FRP) and utilising social media during events such as Food Waste Action Week, this approach blends local community involvement with the extensive reach of digital platforms. Imbedded within the Schools and Colleges Climate Charter. Proactive work being carried out by the WF catering team who provide school meals. Planning is underway for this to be further supported at the Big Climate Conversation due to be held in the Autumn of 2025. | Waltham Forest has increased awareness and engagement in the Local Community on a personal level. FRP’s focus on sustainability aligns with food waste reduction goals, helping raise awareness of these issues among their networks. This creates a sense of collective responsibility and encourages community participation. |
| 14 | Food Waste | Offering schools a food waste recycling service. Currently 30% of schools that receive a collection service from the council have a food waste collection service. All schools that currently have a recycling collection (and do not currently have a food waste collection) will be offered this service. | Achieved | 100% of schools that have a collection from the Council to have a food waste collection | A school food waste bin in Waltham Forest has a capacity of 500 litres and is collected weekly. Over a school year of 39 weeks, this equates to 19,500 litres of food waste, which could be diverted from the residual waste stream per school. |
| 15 | Partnership with social enterprise to develop ‘object lending library’. | Work with partner to stock range of tools and equipment for hire and ensure robust arrangements in place with suppliers. LBWF has recently completed a bid in partnership with the London Legacy Development Corporation to offer a Library of Things in the borough located in Leytonstone., Funding has been awarded. | Achieved | In March 2024, we partnered with the Library of Things to offer a variety of useful and practical items to our community. This collaboration allows members to borrow items such as household goods, electronics, tools, and event supplies, making it easier and more affordable for people to access the things they need without having to purchase them outright. The benefits of borrowing items from a Library of Things rather than owning are multiple: - free up space in homes - save money by paying a fraction of the purchase cost - ensure items get a full life of use - reduces over-manufacturing and material usage - reduces waste and carbon emissions. | Subscribers to date: 1417 Total borrows to date: 632 Our target was for 200 members of the public to borrow items within first two months of opening. Grow reservations by 30 rentals a week by month 1-3 To get to 20 borrows a week: 1500 page visits To get 30 borrows a week: 2500 page visits. Waltham Forest has achieved targets with regards to both borrowers and subscribers. Waltham Forest applied and was granted funding from The London Legacy Development Corporation to host the Library of Things in the borough. A launch was held to introduce the LoT to the area. Prior to this leafleting of local residents, local newspaper adverts and social media were used to spread awareness of the initiative. On-going use of dustcarts screens and social media are used for continued awareness raising. Waltham Forest achieved its aims for the Library of Things through a combination of strategic planning, targeted marketing, community engagement, and securing external funding. |
| 16 | Reducing single-use-plastic and promoting waste minimisation | Continue to encourage local businesses in the borough and request they sign up to a charter of commitment to reduce the single-use plastic they produce or use, with the aim of creating single-use plastic free areas/zones. Recycling officers to produce communications materials to encourage small businesses to prevent waste and consume less e.g. avoidable food waste and unnecessary packaging, whilst promoting the use of materials that can be reused and recycled. Recycling officers to provide training to council staff who regularly engage with local businesses and BIDs e.g. environmental health, trading standards etc to raise awareness of Refill London scheme membership, including providing communications materials. Encouraging Council’s facilities management to adopt policies to eliminate SUP from Council buildings (including canteens) and Council supply chains as far as possible, including for Council-run events. Encouraging residents and business to use reusable bags and reduce plastic consumption, through the prompting of council branded tote bags. Promotions also tie in with requirement for local businesses to charge 10p per plastic bag and to encourage behaviour change for customers to claim and tote bag and adopt it for use on local high-street shops. | Part complete | Raised awareness of action on single use plastics, re-use and waste reduction. This project has now finished. Refill scheme: Target of 10% increase in number of businesses signed up to Refill London scheme. Leading by example through banning single-use-plastics within its buildings and encouraging staff behaviour change. Promoting South Access Reuse and Recycling Centre’s hard plastic recycling initiative which was introduced in 23/24 |  |
| 17 | Outreach Activities | Attend community events such as Tour De Waltham Forest, Council Town Hall (Fellowship Square) summer events to disseminate waste reduction/reuse messages and talk about contamination and the importance of recycling correctly. Attend Community/Estates action days organised by Council’s housing team to spread messages outlined above. Recycle Week in October 2023 – focus on delivering community events and promoted targeted comms in including: 1. Engage local businesses and residents to promote Refill and to become part of the scheme. 2. Stalls held in areas of high footfall (e.g. tube stations) to promote Additional Item Recycling. Spring Clean – supporting this annual event by organising litter-picks with community groups. | On track | Hosted daily engagement stall events across the borough to promote Recycle Week in October 2023. Supported the yearly Spring Clean event, engaging with 40 community groups, to all run events. The Recycling Team have attended one community and outreach event per month this year, speaking with thousands of residents. To promote and encourage engagement we have an interactive stall set up with props to encourage conversations. We have a game that both adults and children can participate in. We take our electric dustcart to events to encourage residents to ask questions and allow them to view the vehicle. |  |
| 18 | Reuse and repair activities and events | Working to offer and promote Repair, Reuse and Upcycling events in the borough: A series of events will be delivered across the Authority area to encourage north London residents, reuse household items such as furniture and soft home furnishings, helping to preserve valuable resources and divert a significant volume of reusable items from disposal, whilst also creating opportunities to raise the profile of organisations and individuals operating in this sector in north London. Following our well received Repair Week campaign in March 2023, continuing to develop our Repair Week celebrations in 2024. Again, outreach stalls held to engage the community. Promotion of community partners’ existing events during Repair Week, with encouragement to also create bespoke events for Repair Week. Comms to encourage Covering the repair categories of textiles, bicycles, furniture and electronics. Wide ranging comms with Councillor support to share the message and raise awareness of events. Creation of the borough’s own repair directory, mapping various services and opportunities to upskill, both within the community and with local businesses. | On track | Hosted repair and reuse fairs across the borough in March & July 2024 with another programmed for September 2024. Working with local community repair organisations and community groups these events showcase local repair initiatives and promote sharing of items to inspire new ways to reuse, repair, recycle, upcycle and repurpose household items including but not limited to electronics, furniture, textiles/clothing, bikes, toys with interactive workshops and demonstrations suitable for different age groups and abilities. Created a repair and reuse map and directory online via our website, https://www.walthamforest.gov.uk/rubbish-and-recycling/waltham-forest-reuse-and-repair-directory showcasing local reliable repair and reuse businesses to encourage residents to shop more ethically and cost effectively, buy reused, reclaimed, second-hand and pre-loved items, have items repaired by local experts or borrow items to repair to reduce their household’s environmental impact and save money. Launched Waste Prevention & Recycling Initiatives Grant funding for local community projects designed to encourage residents to make more mindful choices. This initiative aimed to reduce consumption and motivate residents to embrace the benefits of reusing and using preloved items. The fund sought to enhance and support the efforts of community groups, allowing them to reach more residents than the Council could typically engage, ensuring that as many people as possible could access the benefits of behaviour-changing initiatives. 8 successful applicants were awarded up to £2,000 for their projects which will be carried out from June to December 2024. | Waltham Forest hosted 2 repair & reuse events to date: Fair 1: Stallholders - 50 participants - business owners, staff, volunteers - 400+ conversations by them with the public, enabling and inspiring them to reuse and repair more. Many more conversations between visitors too. - Majority of people working at the event, like the majority of visitors, came by active travel and/or public transport. - Estimated impact: 800-1,000kg of waste diverted by the event. - Exceptionally and almost universally positive and enthusiastic feedback from participants about the event and its organisation. Visitors - Event organiser estimate of around 250+ visitors. - 10% responded to our visitor survey. - People enjoyed the event, which met or exceeded their expectations in attending. Average score was an impressive 4.9 out of 5. - Most visitors were local and most came by active travel or public transport. - Visitors engaged with multiple parts of the event and gave a lot of positive and valuable feedback. Fair 2: - Estimated audience of 300+ - 6 bike maintenance workshop - 15 bikes repairs - 22 Electronics were booked in Feedback from residents: - It was brilliant, very happy with my second hand clothes - unexpected bonus. - It was SO helpful in the electrical repair room - uplifting. - Great resource for re-using and repairing! So useful to speak to knowledgeable people face-to-face! Waltham Forest launched the Repair and Reuse Directory in June 2024 and has 114 local businesses listed. Thus far the directory has been viewed 3,240 online. |
| 19 | Reuse and repair | Continue to promote RRC sites in borough as a means to reuse and recycle items. The average recycling rate across the NLWA RRC network was 72.1% in 2021/22, meaning encouraging visits to the site should help improve overall recycling rates and onward reuse/recycling of material streams. Continue to promote Second Time Around Re-Use shop in located at Kings Road RRC site in Chingford. The shop provides residents with the opportunity to buy ethically by purchasing pre-loved items at affordable prices. Promote NLWA drop off and collection of DIY materials at South Access Road providing an avenue for residents to borrow DIY tools that would otherwise have gone to waste/been recycled. | On track | Activities aim to achieve targets set out in Dashboard, but contributing to waste reduction. | In 2023-24, 72% of all NLWA RRC material was recycled, reused or composted. |
| 20 | Large Item Collection Re-use | Promoting Reuse service for Large Item Collections. Segregating materials and working with partners for items to have a second life or to be upcycled. | On track | Continuing to partner with charity TCL to supply reusable furniture collected through the Council’s reuse element of the bulky waste service. | 10.52 tonnes of reuse furniture was collected and reused in 23/24. |
| 21 | Food Waste | Pan-London Food Waste Campaign will be delivered in partnership with ReLondon, London Boroughs and London Waste Disposal Authorities to inform and empower individuals to reduce their personal food footprint. The Eat Like a Londoner and campaign is using inspiring messages and practical advice to build on the success of past campaigns such as TRiFOCAL (the ‘Small Change, Big Difference’ campaign), and existing campaigns such as Food Wave. | On track | NLWA is a delivery partner and steering group member for the Eat Like a Londoner campaign on behalf of the 7 north London boroughs. It is a pan-London communications campaign to encourage and inspire residents to waste less food and eat more sustainably. In 2023/24 the campaign was promoted at events across all boroughs and was complemented by four behaviour change workshops which included a low-waste cooking demonstration. Participants weighed their food waste to monitor their progress and provide crucial data to evaluate the effectiveness of the intervention. The campaign is now ongoing, with plans to build on the campaign in the coming months. Digital media campaign ongoing. | Using social media, engagement stats as follows: Youtube results 98,560 completed video views Meta results 23,300 three second video views Plug Media results 80.535 viewability |
| 22 | Low Plastic Zone | Resident behaviour change campaign will be delivered in partnership with north London businesses, encouraging customers to bring reusable alternatives for everyday packaging with them when shopping in their local high street. Activity will include business engagement and advertising within participating businesses as well as OOH and social media advertising to target residents directly and drive them to a dedicated webpage. Campaign will be trialled in 1 NLWA borough, Barnet, with roll-out aimed later part of 2023/24 to Waltham Forest. Procurement of contractor recently completed and specific campaign targets being developed. | Complete | The initiative, which aimed to promote the use of reusable packaging among residents, has now concluded. Over thirty businesses were contacted and participated. |  |
| 23 | Schools Engagement | Dennis to the Rescue dustcart activity play bus for schools. Retrofitted mobile classroom and workbooks bespoke to the borough. School Earth Day event attended in April 2023 with waste sorting game for children and outreach stall. Project Earth Rock – supporting a project to deliver live musical assemblies on environmental and sustainability issues to primary school Key Stage 2 and 3 children. Promote teacher training and pupil pack to further explore these issues. | On track and complete | Dennis is to attend schools for one week a year. One school per day and 2-3 classes will be engaged. Next visit is booked for July 2025. Earth Day 2024 Waltham Forest was invited to participate at Henry Maynard Primary School to Celebrate Earth Day 2024 on the 23 April 2024. The children were entertained with an interactive game on waste and recycling. The children were given reusable straws, reusable water bottles, tote bags and wordsearches. Waltham Forest recycling officers engaged with the parents, offering advice and answering their questions | The Earth Day event raised awareness about waste reduction and engaged the community in recycling practices. The event reached students and parents through interactive games and direct engagement. Project Earth Rock has been completed and 30 schools were engaged at Key Stage One and Two. |
| 24 |  | Section removed as it was duplicated. |  |  |  |
| 25 | Reusable Nappies | Reusable nappy scheme: NLWA continues to pay a subsidy, increased as of 1 April 2023 from £54.15 to £70 per baby to parents/carers in north London who use reusable nappies rather than disposable ones. The level of subsidy reflects the saving to NLWA of not having to dispose of the nappies in the waste stream. The voucher scheme is administered by Real Nappies for London (RNfL) and includes all North London boroughs as members. WF to continue to support the scheme on social media and though targeted and paid advertising Work with RNfL to promote nappachino demonstration and second-hand reuse events withing the borough. | On track | In 2023/24, NLWA increased the reusable nappy vouchers available for North London parents/carers to £70 per baby. Ongoing social media campaign will continue as well as demonstrator workshops in the borough. | In Waltham Forest, 270 vouchers were issued in 2023/24 and 168 vouchers were redeemed up to 29th March 2024. This is up from 176 issued and 133 redeemed in 2022/23. Last year 1,131 people signed up to the scheme, which is a 31% increase on the previous year. There is an assumption that whilst a person has redeemed a voucher their baby will continue to use reusable nappies for at least two years, therefore the benefits of disposable nappy waste is experienced for more than one year. It is estimated that in 2023/24, 813 tonnes of disposable nappy waste was avoided |
| 26 | RRC’s | All RRCs have reopened after the height of the pandemic and are now operating full time hours. The booking system is under review, looking at the positives and negatives of having/not having this in place, and a decision whether to retain this or not. Textile’s contract has been renewed and we are now looking to increase the scope of textiles and carpets that we accept at our RRCs network. We hope to have this offer up and running in 2023. Waltham Forest South Access RRC, Summers Lane RRC and a third site at Wembley Waste Transfer Station have been part of a trial to recycle expanded EPS since November 2021. The trial is a partnership with British Plastics Federation and Greenbank Recycling Solutions. The recycling of this material will allow it to be used in insulation and similar products, avoiding the need for virgin materials to be used for these purposes. The trial runs till December 2022. A trial to recycle mattresses via RRC sites began in June 2021. By the end of November 2021 almost 26,300 units had been recycled. As of Qtr.1 22/23 Waltham Forest has been attributed 342.5 tonnes of mattresses that have been diverted from EfW. | On track | The booking system at the RRC’s has ceased to operate and visiting is on a as and when basis. The NLWA Board accepted a recommendation to withdraw the digital pre-booking system for cars at its authority meeting on 31 October 2022. The booking system was originally introduced as a temporary change in response to the Covid-19 pandemic in March 2020. This change allows residents greater freedom to ‘drop in’ to RRCs and dispose of their items sustainably In 2023/24, NLWA continued to expand the range of material collected at our RRCs. The introduction of legislation in January 2023 requiring Waste Upholstered Domestic Seating (WUDS) to be consigned as POPs, meant that a proportion of bulky waste that would have ordinarily been recycled, is now shredded and sent to energy from waste. This limits our ability to recycle or reuse certain types of bulky waste. Hard plastic recycling at the RRC now offered to residents in the borough. | NLWA saw an increase in the number of mattresses collected compared to 2022/23, with around 9,000 mattresses being processed per month. Recycling of hard plastics increased to 104.89 tonnes in 2023/24. In late 2023, NLWA launched a carpet recycling initiative at our RRCs which captured 26 tonnes of material between November 2023 and the end of March 2024. The Expanded Polystyrene (EPS) scheme grew in 2023/24, collecting 5.34 tonnes up from 0.9 tonnes in 2022/23. NLWA launched a new trial service to encourage reuse at two RRCs in Waltham Forest and Barnet to offer a place for residents to deposit unwanted DIY materials and take free of charge. In 2023/24 between the two sites, 91.79 tonnes of DIY materials were diverted for reuse. |
| 27 | LEL | In April 2022, NLWA varied their existing contract with LEL to facilitate the use of the Temporary Bulk Waste Facility (TBWF). NLWA are currently developing a new contract to manage the education and visitor centre at the RRF. NLWA are developing (in consultation with the boroughs), a new contract for the management of the state-of-the-art facilities at the Eco Park. The contractor has been instructed to install an additional 370 solar PV panels at the new RRF. There will now a total of 2235 solar panels at the RRF. The Temporary Bulky Waste Facility (TBWF) became operational in April 2022. This facility allows us to transfer organic and recyclable materials for processing and extract some for recovery and reuse. We expect the new RRF facility to come into use in Feb 2023, at which point the TBWF will no longer be required. The R1 rated Energy Recovery Facility (ERF) will be available in 2025. [LBWF officers joining NLWA for a Joint Waste Strategy listening exercise in Walthamstow Market to find out more from the public about some of the key issues and challenges we’ve worked on across North London.] | On track | These additional panels will provide a 20% increase in total output for the whole system from 755kWp to 905kWp. In 2023/24, construction of new facilities under the NLHPP continued, including the new Energy Recovery Facility (ERF). The ERF will have the capacity to manage 700,000 tonnes of residual waste from the seven north London boroughs, future-proofing north London’s waste management infrastructure for a growing population. New infrastructure at the EcoPark delivered by the North London Heat and Power Project (NLHPP) will be owned by NLWA and operated by LEL. In 2023/24 the Authority signed a new contract with LEL for the operation and maintenance of the EcoPark’s Resource Recovery Facility (RRF), public Reuse and Recycling Centre (RRC) and EcoPark House, a community and education space. The new LEL contract includes a complete complement of operational, maintenance and asset management requirements - specified to achieve the long-term waste and recycling services required by residents The writing of the new North London Joint Waste Strategy began in early 2023, led by NLWA in collaboration with the north London boroughs. A public listening exercise was undertaken in summer 2023 in Walthamstow Market, to understand north London residents’ priorities, which has fed into the drafting of the strategy. NLWA commissioned a waste composition analysis for all boroughs, which was completed across 2022 and 2023 and has been used to inform the strategy. It is currently still in the drafting process, with the draft strategy expected to go to public consultation in summer 2024, and the final strategy expected to be adopted in 2025. As part of the strategy development, a Strategic Environmental Assessment and Equality Impact Assessment are being produced and will go out for consultation alongside the draft strategy. |  |
| 28 | NLWA Waste Prevention Plan | A new plan is being prepared for 2022-25 and due to be agreed in Autumn 2022. The aims of the plan are to: - Increase residents’ understanding of the journey of waste and the need to shift from a linear to a circular economy - Provide information and advice on how to adopt more sustainable behaviours - Increase residents’ understanding and motivation of how and why it is important to recycle effectively - Promote effective recycling - Provide policy responses and engagement with national and regional strategy development on waste prevention - Campaign for government action to increase support for the circular economy, including reforms which reduce packaging, encourage reuse and repair - Campaign for systemic changes to reduce the manufacture and consumption of single-use and unrecyclable items. | On track | The North London Waste Prevention Plan was published in January 2023. The plan was developed through collaboration with residents, environmental specialists, borough staff, councillors, and campaigners. The development of the plan involved engagement sessions, meetings, and conversations to provide insight into local priorities and identify where NLWA activities can support partners to achieve shared ambitions. The plan is developed to set out the approach to working whilst the next North London Joint Waste Strategy, owned by the constituent boroughs and NLWA, is being developed. Projects delivered or launched in 2023/24 as part of the plan include: - Together We Recycle - Eat like a Londoner - Reusable period products campaign - Education plans - Bring it... - Reusable nappy subsidy |  |
| 29 | NLWA Joint Waste Strategy | NLWA are currently developing a new Joint Waste Strategy with the 7 boroughs for the management of waste from households in North London The strategy planning and design is anticipated to last around 18 months (although this may be extended depending on whether additional requirements, such as a Strategic Environment Assessment, are deemed necessary). All statutory stakeholders will be engaged in this process, an equalities impact assessment will be undertaken together with a full resident consultation. NLWA will carry out modelling, including a detailed composition analysis, into EPR and DRS. The strategy will set out how NLWA and the seven boroughs will work together to minimise the amount of residual waste arising and to increase reuse and recycling rates (amongst other objectives). | On track | The writing of the new North London Joint Waste Strategy began in early 2023, led by NLWA in collaboration with the north London boroughs. A public listening exercise was undertaken in summer 2023 to understand north London residents’ priorities, which has fed into the drafting of the strategy. NLWA commissioned a waste composition analysis for all boroughs, which was completed across 2022 and 2023 and has been used to inform the strategy. It is currently still in the drafting process, with the draft strategy expected to go to public consultation in summer 2024, and the final strategy expected to be adopted in 2025. As part of the strategy development, a Strategic Environmental Assessment and Equality Impact Assessment are being produced and will go out for consultation alongside the draft strategy. The drafting included a face to face listening exercise being undertaken to understand residents views, this was conducted jointly between NLWA and WF officers. |  |
| 30 | Extracting Recycling | LondonEnergy Ltd leases and operates a sorting facility (at Wembley) which sorts wood, mattresses, metal, cardboard and hardcore material. LondonEnergy report that around 30% of the selection of materials put through this facility are extracted for recycling and reuse. Authority officers are coordinating with LondonEnergy Ltd over the development of a sorting facility within the within the new Resource Recovery Facility at the EcoPark. NLWA engaged consultants in 2022 to support the development of a facility when the new facility has been successfully commissioned. | On track | Aim of 10,000 tonnes to be processed at the station per annum This is intended to handle between 30,000 and 65,000 tonnes of residual waste. Construction of the Edmonton EcoPark House (EPH) continued in 2023/24 and is scheduled to open in 2024/25. |  |
| 31 | Increasing the offer | NLWA are working with Biffa (material recycling provider) to establish a compliant and sustainable UK partner to recycle all types of grades of plastic films. We are evaluating markets options and find a viable solution. The aim is to ensure that Boroughs are able to collect flexible plastics within the timescale set out in the government’s Resources and Waste Strategy. | On track | To find a suitable off-taker by 2024/25 | Conversations are ongoing with Biffa to find a viable solution for this material however, the UK end market is limited. Biffa are submitting a proposal to NLWA in due course which will detail options for managing soft plastics. |
| 32 | Increasing the offer | NLWA’s new state of the art Resource Recovery Facility (RRF) at the Edmonton Eco Park is planned to open in the late summer 2023, with a proposed sorting solution for pre-treatment/separation for certain waste streams within the building. This mechanical and automated application will process between 30,000 and 65,000 tonnes of residual waste. NLWA are continuing to engage with consultants to deliver the best technical solution based on the preliminary findings of a recent waste composition analyses undertaken by the authority in addition to considering the future legislative requirements. | On track | Expect to recover 30% of materials for reuse and recycling. In 2023/24, the construction of the Resource and Recovery Facility (RRF) at the Edmonton EcoPark continued. The site went into operation on 15th March 2024 and will begin accepting borough waste from April 2024. The RRF, which has capacity to manage 374,000 tonnes of waste annually, is designed to bulk recycling and organic waste for onward transport to processors, extract recyclables from residual waste and prepare bulky waste for energy recovery. Space has been allocated to the new RRF to support recycling and reduce waste. In 2023/24, NLWA engaged with consultants to carry out reviews of best practice in the UK which culminated in two reports that explored the feasibility of installing pre-sort technology in the RRF. Following the outcomes of the reports and decisions taken by a working group developed to support this work, NLWA plans to conduct further research into technological innovations for managing waste to understand the best use for this space. |  |
| 33 | LEL Residual transport arrangements | As part of the NLWA’s and LEL’s sustainable strategy, consideration is being given to prioritize a transition to alternative fuels, A collaborative executive committee has been set up with several specific sustainable tangible goals. In addition to operating several fully electric light good vehicles the committee has provided a business case that has been approved to procure a fully electric Heavy Goods Vehicle (HGV) waste bulker to support its operations. LEL currently operate 13 bulker vehicles with leases that expire in late 2024. The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are now all ULEZ compliant. It is a requirement of the main waste contract with LEL to use Euro IV vehicles as a minimum. LEL have initiated a vehicle replacement programme to ensure vehicles comply with ULEZ. All vehicles are now Euro VI, leading to a significant reduction in NOx emissions. | On track | Emission reduction - reference concluded. The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. From 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. The new RRF at the EcoPark features 2,235 solar panels on its saw-tooth rooftop which were switched on in late 2023/24. The EcoPark Array will produce renewable energy, equivalent to powering 300 homes yearly with electricity, and has been added to the site as part of the North London Heat and Power Project (NLHPP). There are also plans for solar panels to be installed on the new ERF once built. NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the decarbonisation of the energy produced. NLWA’s efforts to reduce waste and manage waste in line with the waste hierarchy supports emissions reductions associated with the management of large volumes of waste. In 2023/24, the construction of the Reuse and Recycling Centre (RRC) at the Edmonton EcoPark continued. The site is scheduled to open in the second quarter of 2024/25. |  |
| 34 | Waste Prevention Exchange | This annual event will be delivered to bring together sector experts on a programme of topical waste prevention issues, delivered by NLWA. | Completed | Raise awareness of resource reduction. | The WPE took place 18/05/23 and topics of discussion were challenges and opportunities at the LA level in achieving a circular economy (CE), why are CE principles so important, procurement, planning and design, partnership, behavioural insights, communication and case studies were presented. |
| 35 | Journey of recycling | Production of six videos showing what happens to North London’s waste and recycling. Some videos will follow items of household recycling from the home, through the recycling process, until they are turned into something new. Videos were completed at the end of 2022 and promoted through a paid-for social media campaign. | On track | To educate about the journey of waste, we commissioned research via YouGov to better understand the existing knowledge of Londoners. Following that, we worked with a video producer to create three distinct videos to show north Londoners what happens to their waste once it’s been disposed of. The three videos focus on general rubbish through the lens of the Energy from Waste facility; recycling, focusing on the Materials Recovery Facility; and lastly large items, focusing on one of our reuse and recycling centers. | The videos received almost 50,000 views and will be used in future work on schools and education. https://www.nlwa.gov.uk/www.nlwa.gov.uk/article/education-hub/journey-waste |
| 36 | Recycling campaign | Behaviour change communications campaign tackling recycling on estates. Using personalised messaging from local collection crews. Campaign tactics will include leaflets delivered by crews, PR campaign launch sharing ‘local hero’ stories about recycling collection staff, and outdoor and social media advertising with artwork and video content featuring real crew members sharing stories and anecdotes, as well as recycling tips. | Completed | Campaign targets are to generate 12,000,000 impressions through outdoor and social media advertising; reach 800,000 people via social media advertising; gain 10 pieces of positive press coverage. For communal recycling rounds receiving personalised leaflets, targets include 10% tonnage increase and 5% reduction of contamination following campaign delivery. The Together We Recycle campaign ran from 28 August to 15 October. The campaign shone a light on what happens to waste after it is collected, aiming to improve the relationship between crews and boroughs, increase recycling tonnage and reduce contamination. The Bring It is a campaign that aims to encourage residents to use reusable coffee cups, bottles, bags, and containers to reduce single-use plastic. The campaign initially launched in Barnet and work is now being done to roll out the Bring It campaign to Camden, Enfield, Haringey, Hackney, and Islington – with Waltham Forest receiving it later in 2024/25. | A dedicated campaign webpage received 13,573 page views and tonnages increased by 13.9% over the campaign period. However, there was little impact on contamination |
| 37 | Pan-London Food Waste Campaign | Objectives of the campaign are to bring together various London stakeholders that can encourage and support residents to reduce their consumption-based emissions by moving to a more sustainable and healthy diet; and wasting less food. The campaign will also support the implementation of London Councils’ One World Living action plan and its ambition to. The campaign is particularly targeting younger Londoners aged 21-44 and those with children under 11 years old at home, as they are amongst the highest food wasters. In-person workshops will be developed in Q2 and delivered throughout Q3 and 4 to support the campaign messaging in 2023/24. | Completed | Deliver in person workshop throughout Q3 and Q4 with ultimate aim of reducing consumption-based emissions by 2/3 by 2030 and support the Mayor of London’s target to reduce food waste by 50% by 2030 |  |
| 38 | Waste Prevention Community Fund | £250,000 committed to fund 17 community-based projects during 2023/24 focused on waste prevention activities at the community level. NLWA will work closely with these organisations to promote their projects and identify opportunities to scale up activity where possible beyond the original target communities. Three projects in Waltham Forest received funding: - Forest Recycling Project running ‘Tackling North London Paint Waste’ - The Mill running Forest Fixers - The Inconvenient Store CIC running the ‘E11 Circular Hub’ | Completed | 85% of targets will be met or exceeded by end of 2023/24 Q4. In 2022/23, 16 community groups received funding to deliver on various waste prevention activities. In Waltham Forest the following projects received funding: - The Inconvenient store, E11 Circular Hub (Food, textiles, various) - Forest Recycling Project, Tackling north London paint waste - The Mill E17, Forest Fixers (WEEE) | Some highlights from these projects in 2022/23 include: - Increased opening hours contributing to 149% increase in paint sales and 215% increase in income. - Diverted over 14,000 litres of paint. - Delivered 23 repair cafés and 19 repair clubs (skill sharing / training sessions) - Engaged with over 220 residents. The projects are ongoing and will continue to be supported by Waltham Forest. |
| 39 | Reusable period products | Behaviour change project to increase the purchase and use of reusable period products will be delivered in 2023/24, focusing on waste prevention and the benefits of cost savings associated with switching to reusable period products. This initiative will include a digital communications campaign and information webpage on nlwa.gov.uk, discount voucher offers for residents, and in-person and digital outreach and engagement. Procurement of contractor currently in progress. | On track | Specific campaign targets to be agreed in Q2 2023/24, once contractor confirmed. NLWA committed to promoting reusable period products as an alternative to single-use options. The ‘Reduce, Reuse, Your Cycle’ campaign was designed through the application of behavioral science and seeks to increase the purchase and use of reusable period products in north London. The campaign aims to decrease the purchase and use of single-use period products, leading to a reduction in the generation of single-use plastic waste and the negative environmental consequences associated with their consumption. | The campaign has achieved the following across north London: - 9000 website visitors - 2.9 million impressions on social media - 7000 click throughs from social media campaign. - 200 locations for outdoor advertising - 145 sign ups discount codes |
| 42 | Promoting Reuse Shops and use of RRC’s | Campaign to promote the reuse shop at Kings Road Reuse and Recycling Centre. This will include a promotional event at the shop, social media advertising and a press release. Advertising campaigns to raise awareness of and increase attendance at reuse and recycling centres. | On track | To increase the amount of material donated above existing levels and carry out promotional event, social media and a press release with the overall aim of increasing awareness of the shop and encouraging more residents to visit the shop broadening their understanding of the initiative. | During 2022-23, we ran an advertising campaign to encourage more people to visit the ReUse Shop. This included local newspaper advertising, digital on-street panels and targeted social media advertising. Outcomes from this promotion include: - 6,443 people visited the ReUse Shop webpage on NLWA’s website. - ReUse Shop Instagram account gained 374 new followers. - Reached 35,000 people through social media advertising. - Outdoor advertising was seen 3,753,250 times. - Newspaper adverts reached 336,258 people. Ongoing campaign on social media and the Waltham Forest website to promote the recycling shop at Kings Road Recycling Centre. - https://www.walthamforest.gov.uk/rubbish-and-recycling/second-time-around-shop |