5. London Borough of Bexley RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| LB Bexley 1.1 | Reduce the quantity of textiles being disposed of in the Borough | - Provide reuse/ repair workshops for textiles so that residents have the opportunity to update and fix clothing, upcycle or turn items into a keepsake rather than put it into the residual waste bins | COMPLETE | - Workshops carried out as planned. Next step is to continue to encourage residents to repair their clothes through mix of workshops and events and continue to run textiles upcycling workshops x 8 per year | - 8 textiles associated activities were provided for the residents. Reaching up to 291 people through events and activities 1 online event to 7 participants. |
| 1.2 | Reduce the quantity of textiles being disposed of in the Borough | - Provide guidance on website relating to how to reduce, reuse and recycle textiles. | No progress to date | - Aim to have a reduce and reuse page which will include information and links related to textiles waste minimisation. | - No impact so far. The aim of this informative page is to provide practical advice on reducing multiple types of waste, including textiles. Our aim is to launch this by spring 2025 – hopefully with the aid of local college students. |
| 1.3 | Reduce the quantity of textiles being disposed of in the Borough | - Hold swishing/clothes swap events and provide 'how to' packs on how to run one for local organisations, housing associations and charities. Encourage reuse of clothing | ON TRACK | - Hold a swishing workshop by end of March 2025. - Clothes swaps have taken place at the Easter and Christmas fairs, clothes provided by TRAID - A Clothes swap will take place at the Bexley Ecofestival 2024, with clothes provided by TRAID, our kerbside collections charity. - To date we have not had any requests from other organisations to run their own clothes swaps. Through related workshops/swaps we will continue to promote others to run their own. | - Promoted the concept of giving away unwanted items by either using their local charity shop/bank or kerbside scheme. - Provided 100’s of items of clothing to residents in the north of the borough. |
| 1.4 | Reduce the quantity of textiles being disposed of in the Borough | - Promote textiles reduction in secondary schools as they are starting to buy more clothing due to fashion trends and ‘fast fashion’. | IN PROGRESS | - In April 2024 an Earth Summit, our eco themed fashion show sponsored by Cory, was planned and due to take place but the schools involved were unable to commit and so the event was cancelled last minute. - Hold an Earth Summit by September 2025. | - In April 2023 Cory and Bexley council held a fashion show with two schools, engaging with over 100 secondary school year 8/9/10 students and local college art students, with 5 disciplines, textiles, food waste, social media, filming and upcycled instruments with original music. |
| 1.5 | Reduce the quantity of textiles being disposed of in the Borough | - Introduce a new ‘on demand’ household textile collection with TRAID. | COMPLETE | - In March 2023 a new kerbside textiles collection was started with TRAID. - The council will continue to promote TRAID in kerbside textiles collections through Social media, JCDecaux boards, | - TRAID recorded collections of 4.95 tonnes of textiles materials collected from 748 collections with an average of 27kg per collection |
| 1.6 | Reduce the quantity of textiles being disposed of in the Borough | - Guidance on website about how to look after your clothes better and reuse when no longer required by April 2023. Ask local charity shops to display posters/leaflets on how to look and upcycle clothes | No progress to date | - Main charities to be sent leaflets after discussions held | - Aim to send this to our four main textiles recycling credit partners. |
| LB Bexley 2.0 | Championing food waste reduction initiatives | - Promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events, workshops, demos and talks held at community events and schools. For most sessions there is a practical part where attendees will cook a simple meal using typical leftovers, such as a stir fry, soup and quesadilla. Attendees to pledge to reduce food waste and recycle any food waste left over. | COMPLETE | - Love food hate waste is promoted at all our community events with a mix of free food, demos, talks, leaflets and useful tools such as spaghetti measures - New collaborations with Schools have been created via Schools Super Zones - Seeking to work in collaboration with our adult education centre to run a set of cookery lessons by end of April 2025 | - LFHW activities were carried out at 17 events, 3 reaching approx. 1026 people through face to face and larger events |
| 2.1 | Championing food waste reduction initiatives | - Update and refresh the council’s food waste page dedicated to food waste reduction tips and advice on the councils website | IN PROGRESS | - The food waste page www.bexley.gov.uk/services/rubbish-and-recycling/food-waste is being updated to make it more informative with ‘what is food waste’, impact of food waste, top tips and FAQs - Worked with influencer Kate Hall from the full freezer to produce expert clips on how to organise your freezer. Permitted to use this for 10 months | - This will be an excellent resource for residents to reduce and recycle their food waste, explaining how and why, with easy practical advice. - To be promoted when live via newsletters, social media and local events - To increase number of view and visits to previous page |
| 2.2 | Championing food waste reduction initiatives | - Promote the Borough’s Community Fridge schemes that currently run at two locations in the borough, Bostall Community Library and Belvedere Community Centre. Food is donated from local shops/supermarkets and any resident may take the food for their own consumption. - Carry out food waste reduction activities with users of community fridge | ON TRACK | - The council has a list of the community fridges on their website - Activities have been held at a community fridge to show residents ways to use up their leftovers. There will be further activities linked to the community fridge scheme in 2024/25 - Promotion of the community fridge is done via the communications team/ There are now 4 fridges in the borough | - Promotion of the community fridge helps more people to benefit from this great initiative - 3 events held over a period of 3 months before Christmas, with 50 people engaging. |
| 2.3 | Championing food waste reduction initiatives | - Promote the 'Too Good To Go' app in the borough to ensure that unsold food from shops and restaurants is saved from going to waste. | Delayed | - This information has been promoted to businesses via our leaflet - Investigate doing this via our contractors or on the website | - Will raise the awareness of this option for more residents. |
| 2.4 | Championing food waste reduction initiatives | - Promote food waste in 3 specific schools food project, working intensively on food topics with whole school in lessons, demos, tasters and offering cookery workshops to families. | COMPLETE | - Carried out food waste projects in 3 schools – completed 2 schools from April 2023-24 and another in April 2024 -25 through council contacts and Schools Superzones project | - Worked in 3 primary schools, in the north of the borough - Carried out 4 activities in 2023/24 reaching 77 parents/carers and their children. - April 2024 to date carried out a further 3 workshops and one school assembly reaching 306 parents/carer or students and 86 of these attending a practical workshop. |
| 2.5 | Championing food waste reduction initiatives | - Continue to promote Olio and Kitche after working in partnership with them as a demonstration project partner for the Food Flagship Initiative | COMPLETE | - Kitche and Olio have been communicated to residents through our food waste page and at events. Information on the Apps will remain on the updated food waste page. | - The A-Z page has had 1,573 views from April – July this year. |
| LB Bexley 3.0 | Encourage home composting to reduce food and garden waste being placed in residual waste | - Direct Bexley residents to home composters at a discounted rate and increase the number that are purchased. | ON TRACK | - Home composters promoted on our website and on the new A toZ of materials page. - Promotion of home composters during September/October 2024 just before Autumn | - Continuing to promote home composters via website. - 55 home composting items were purchased by Bexley residents in 2023 via Get Composting. Only 8 have ben sold in 2024 so more promotion is required. |
| 3.1 | Encourage home composting to reduce food and garden waste being placed in residual waste | - Work with allotments and other garden enthusiasts to set up a home composting champion scheme and increase long term home composting with successful compost being produced. | ON HOLD | - It has been very difficult to recruit any compost champions. Instead, we have visited gardening clubs run at the libraries to share about home composting and carried out composting activities at community events | - Recruiting home composting champions has not been possible – no volunteers at the moment |
| 3.2 | Encourage home composting to reduce food and garden waste being placed in residual waste | - Home Composting Talks/Workshops | COMPLETE | - Talks were successfully carried out across the borough. At least two activities to be carried out between 2024/2025 for adults and families linked to composting awareness weeks - One additional home composting talk currently planned to take place by April 2025. Will also focus on events during Home Composting week in Mary 2025 | - Carried out 4 composting-based activities; two schools reaching one reaching 350 students; 1 roadshows reaching 18 residents and 1 collaborative outdoor event reaching 150 people |
| LB Bexley 4.0 | Waste Reduction Reduce single use plastic bottles | - Increase the number of residents refilling bottles rather than buying new ones especially in key shopping areas of the borough by providing and promoting public water fountains and the National Refill Campaign. | PART COMPLETE | - Divert up to 4,500 of plastic water bottles per annum per refill station. - London Southeast college graphic students have provided some animations one of which is on tap water that we will share via internal and external communications/social media - Reduce the number of plastic bottles purchased at the civic cafe by 10% (1,900 in the last 12 months) | - Encouraging residents to refill their water bottles - Promoting reusing bottles - Engaging with younger audience through college project |
| 4.1 | Reduce single use plastic bottles | - Restart the Bexleyheath water fountain that is still closed since covid and update signage. | Complete | - The fountain is in working order allowing people to refill their water bottles. | - 2359 M3 of water has been used since the water fountain was reopened after covid. This is the equivalent of 10,054 water bottles being refilled. |
| 4.2 | Reduce single use plastic bottles | - No bottled water to be purchased for meetings/events unless under exceptional circumstances at all Council Offices. Single use water bottles to be replaced with glasses and tap water | Complete | - Water is only provided in urns or jugs where possible - London southeast college students amination project with the council has produced an effective animation to encourage people to use tap water | - This has reduced the number of water bottles that were being given out at meetings and therefore the cost of providing them. |
| 4.2 | Reduce single use plastic bottles | - Encourage staff to use reusable water bottles and tap water to reduce the use of raw materials required to produce plastic bottles and the sourcing of spring water (reduction in transport fuels, pollution) | No progress to date | - A new internal comms recycling and reduction plan is due to commence by October 2024 to encourage staff to recycle correctly at work. This will be followed by a series of messages linked to reducing waste and will include using reuseable water bottles | - This will reduce contamination of office bins and allow regular communication with staff about key recycling and waste minimisation messages |
| LB Bexley 5.0 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Provide reuse/ repair workshops for WEEE, Metal, and furniture for residents and local organisations/ housing associations to encourage the continuing use of items and promote the upcycling of items. | Complete | - Ran a pilot Reuse and refurbishment course - Cory and Bexley Council developed a new Reuse and Refurbishment Level 2 CIWM registered qualification. This course was shortlisted for the Awards for Excellence in Recycling & Waste Management 2024. - 2 Recycling engagement officers are training to become assessors so planning to run another course by end of March 2025 | - 13 residents and 3 staff have obtained a level 1 or level 2 qualification in Reuse and refurbishment. - A new reuse club has been started by some members of this group. They are looking to offer their new skills/advice at pop up events. - New qualification shortlisted for 4 national awards in 2024/25 |
| 5.1 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - 1 Electronic repair/ reuse workshop per year, 1 Metal repair/reuse workshop per year and 1 Furniture repair/ reuse workshop per year and 1 Bike workshop per year – run in March 2023. | On Hold | - Still aiming to set this up once experts have been found to run this by March 2025 - Potential to work with local secondary school to provide bikes and possibly fix some too with volunteers - Potential reuse hub is being investigated with a community space at the Exchange in Erith by converting an unused outbuilding | - Will give residents the opportunity to fix their broken items and teach them how to reduce waste - Give students an eco-friendly option to come to school and life skill s |
| 5.2 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Add guidance on website about how to look after your household items better and options for their reuse when no longer required. | Complete | - New A to Z provides key information most common day materials in terms of reducing, reusing and recycling them - Promotion of new A to Z through social media and newsletters | - More information now available for residents and the Contact Centre so that residents know how best to reduce, reuse or recycle a large number of items. |
| 5.3 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Promote the use of the FREEGLE particularly via our links with housing associations to encourage items to be reused and not thrown away. | PART COMPLETE | - Added as a key link with our new A to Z - Looking to engage with larger housing associations to put up information posters/newsletter articles in blocks of flats. Slow response to FREEGLE promotion with housing associations due to lack of communication outlets - Investigating to see if information can be added to phone lines at flats | - To date October 2023 to September 2024 Reused 59.7 tonnes worth £42,460 Saved 30.5 tonnes of CO2 2,186 items gifted With 20,195 members |
| 5.4 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Increase the amount of material that is sent for reuse from the RRC’s. | PART COMPLETE | - Encourage more items to be put aside for reuse at the RRC’s (1-1% of total site volume / 115 tonnes). – Winter 2024 a new contract with Sutton started. Site staff have been selecting suitable items to be sold at the Sutton site. - Promote in autumn 2024 with new signage, info sent residents via newsletters, Social media and updated info on our website | - The tonnage of reuseable material is stable but looking to increase this over time - 20.92 tonnes reused from both sites in 23/24 compared to 18.57 tonnes in 2022/23. This is good progress with our new provider only being in place for part of the year so we are hopeful that with a full year of them being in place in 24/25 even more items will be reused from the two RRC’s. |
| 5.5 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Continue to investigate the possibility of a reuse shop/ workshop managed by a local charity/ partnership to be held within the Borough. | On track | - The creation of a reuse hub will encourage residents to look at reuse options before throwing away or buying new. Progress in this area has been made. The contractors are due to write a business case to provide a shop at one of the reuse and recycling centres in Bexley. This is unlikely to be completed by March 2025 | - Divert reusable items from recycling stream - Promote reuse culture - Helps provide affordable items |
| 5.6 | Reduce the quantity of household items being disposed of in the Borough that could have been repaired/ reused. | - Create a waste minimisation page on the councils website to communicate ways to reduce waste, promote waste reduction campaigns and top tips | NO PROGRESS TO DATE | - This is a new action – currently the councils website does not have a single stop on the website for information on reuse and reduction. - Possibility to work with local college students to create this page – this will also help to promote reuse to a younger audience. | - To give residents ideas and confidence to make simple impactful changes |
| LB Bexley 6 | Waste Reduction Encourage the reduction and reuse of waste items that the London Borough of Bexley produces | - Encourage the reduction and reuse of waste items that the London Borough of Bexley produces - Ensure that the Councils stock of bins includes the washing, repairing, and refurbishing of previously used wheeled bins; Eurobins and recycling banks and their redelivery to residents rather than relying on buying new stock. | On track | - Bins that have been removed from properties are washed out if in good repair and added back into the stock of bins to be delivered to residents or businesses. - Reduced cost of purchasing new waste and recycling containers. | - Reduce the quantity of waste the organisation disposes of. - Demonstrates to residents the importance of reuse. - 2023/24 data: - 372 Euros bins repaired - 7,594 wheelie bins cleaned - 19 Euro bins cleaned |
| 6.1 | Encourage the reduction and reuse of waste items that the London Borough of Bexley produces | - Ensure that staff are informed about how to reduce waste at work via the BeeHive intranet, management and staff briefings. | On Track | - Quick online guide of what goes in each bin via QR code and posters - New regular internal communications to be rolled out Autumn 2024 - All new employees to complete training/guidance on recycling at work | - We have added a slide into the induction presentation for new employees so that as soon as staff start work with LB Bexley they are aware of why and how to recycle. |
| 6.2 | Encourage the reduction and reuse of waste items that the London Borough of Bexley produces | - Ensure that the café at the Civic Offices continues to provide scheme where there is a discount if you use a refillable hot drink cup when purchasing a hot drink and that they will refill water bottles as part of the refill campaign. | COMPLETE | - The café provide a discounted rate for reusing cups – this is ongoing since 2020 | - Increase the number of staff using the refillable hot drink cups and decrease the number of disposable (compostable) coffee cups that are sold in the staff canteen. |
| 6.3 | Encourage the reduction and reuse of waste items that the London Borough of Bexley produces | - Restart the book sharing scheme (closed since COVID) where Bexley Employees can bring already read or unwanted books to swap with one another. | COMPLETE | - This is working well and will be advertised to get more staff using it with the new internal comms project in Autumn/winder 2024/5. We will do some market research to see if staff would like any other materials to be included. | - Reduce waste and encourage reuse concept |
| LB Bexley 7 | Waste Reduction Absorbant Hygiene Products (AHP) | - Provide opportunities for prospective parents to find out about washable nappies and promote the real nappies for London scheme which enables families to apply for a £40 voucher to help them get started with using real nappies. - Link with the libraries, local organisations, housing associations and charities as well as the healthy start campaign. | PART COMPLETE | - 1/4/203 – 31/3/2024 – 87 vouchers given to residents - 1/4/2024 to date – 13 vouchers given - continue to push nappy voucher scheme. RNFL attend monthly baby group and library event. Seek to find new groups to attend to increase uptake. - The council increased voucher to £50 | - Reduction in nappy waste by 100 tonnes in families that participate in the scheme over 3 years. - Continue with an uptake of an extra 2.5% (from the previous year) applying for the nappy voucher scheme every year. |
| LB Bexley 8 | Waste Reduction Waste Reduction Engagement Activities | - Visit schools with SWAC (Schools Waste Action Club) and ensure that whole school assemblies and up to 14 types of additional class activities encourage children to reduce waste and take the message home. - Particularly focus on food waste with the school’s food waste project and food family stickers – targeted food lessons, workshops and demos for the school and parents. - Promote waste reduction activities through public stalls at community events, workshops, demos. - Run an Earth Summit for local secondary schools | COMPLETE | - Carried out food waste project in schools – 7 workshops with 151 attendees. Stickers have been completed and given out as a trial to 2 schools. Feedback was very positive. - Food waste reduction promoted at 17 small and large events, with a reach of over 1,700 residents. - Cory continues to fund a Waste and Recycling Engagement Officer for 3 years from 2022 to increase our level of impact | - In 2023 (March-December) 7,434 children in Bexley schools were taught about Waste, Recycling and Sustainability. - So far in 2024 we have already reached 6,450. - Since the SWAC Officer started in February 2023 they have taught 11,884 children in Bexley schools about Waste, Recycling and Sustainability. |
| LB Bexley 9 | Waste Reduction Encouraging the circular economy in local businesses | - Encourage local businesses to evaluate the waste that they produce and join the circular economy. - Investigate the possibility of using ‘The Library of Things’ where this could be located and funding opportunities | DELAYED | - The action for businesses related to food waste has been very limited as more focus has been on residents. Look to focus on this oct 2024 - onwards - Work with 2 Businesses to evaluate their waste and how they have been able to reduce it and use as case studies. - no business has been selected yet but potential one with tearoom business. - Find out if Library of Things can be installed in undercover area of a shopping centre | - This is delayed due to staff workloads. |
| 9.1 | Encouraging the circular economy in local businesses | - Produce an online business guide for waste to include all waste/recycling disposal costs by material stream and useful waste reduction tips. | NO PROGRESS TO DATE | - Due to start project autumn/winter 2024/25 - Some work was done on this in 2023/24 - Link into talks/events via the BIDS, Business HUB and the Engine House Bexley. | - This is delayed due to staff workloads. |
| 9.2 | Encouraging the circular economy in local businesses | - Send key info via Bexley for business newsletter | PART COMPLETE | - Information was placed in one newsletter, but we would like to be able to do this more regularly going forward. Will work on this for next year. | - Businesses need to receive information on reducing and recycling their waste more often to encourage them to make more impact via their waste management plans. |
| 9.3 | Encouraging the circular economy in local businesses | - The Bexley Food standards team to assist with the education of local business on food waste reduction and recycling when visiting and inspecting premises including information on the Olio or the Too Good To Go APPs which can enable businesses to reduce their food waste by getting it used before its sell by dates instead of throwing it away. | COMPLETE | - Food safety team to hand out leaflets on food waste reduction to the establishments they visit by October 2022. | - This is ongoing. |
| LB Bexley 10.1 | - Maximising Recycling | Introduce a new ‘on demand’ household textile collection with TRAID. | COMPLETE | - TRAID kerbside collection scheme for Textiles started in October 2022. Collections continue and the council promote via JCDecaux boards annually, via our website and through social media platforms. | - Since the scheme started in Oct 2022 TRAID have carried out 1195 collections equating to just under 26 tonnes of textiles being collected for recycling. |
| LB Bexley 10.2 | - Maximising Recycling | Introduce a new ‘on demand’ household WEEE collection with TRAID. | COMPLETE | - TRAID kerbside collection scheme for WEEE started in October 2022 but it can only be collected if the resident has booked textiles to be collected at the same time. Collections continue and the council promote via JCDecaux boards annually, via our website and through social media platforms. | - Collections of nearly a tonne of WEEE since Oct 2022. |
| LB Bexley 10.3 | - Maximising Recycling | Introduce kerbside battery recycling. | DELAYED | - Assessing options for this to decide if bookable collections or adding the material to the kerbside service would be the best solution. Publicising the battery collection locations at the Civic Offices, Council libraries, RRC’s and at retailers until a kerbside option is put in place. | - 0.5 tonnes of batteries collected via the civic offices and Libraries since 2021. |
| LB Bexley 11 | - Maximising Recycling | Box Recycling Collection Service Revamp the recycling service for 2,000 properties that have remained on recycling box collections because they were not suitable for the recycling wheeled bins that we use for the rest of our kerbside properties. Do this by swapping the old colour boxes with the new colour boxes that match the recycling wheeled bins to reduce confusion for both residents and crews. Reinforce this by delivering information regarding the service so that they are fully aware of the changes- particularly that glass can be mixed in with the plastic/ cans now and that they can have more than 1 box for each material if needed. | DELAYED | - This has been delayed due to a digital project that is upgrading the missed bin form. The existing Firmstep missed bin form doesn’t recognise the white and blue boxes, so we have not been able to re-introduce the box recycling service. The new WasteWorks missed bin form will recognise the new boxes. Once this is made live the following will take place: - Update the website to show the new boxes. - Change Whitespace to show two boxes rather than three. - Deliver new boxes to those still using the old ones - Deliver new guides to all residents on the service. | - The old colour boxes and the new colour boxes (that match the recycling wheeled bin colours) are in use at the moment. The inconsistency of this makes it difficult to provide information on the service and publicise it as much as we would like to. We hope to increase recycling through this scheme next year once all the changes have been made to one consistent service. |
| LB Bexley 12 | Reduced Frequency of Residual waste Collections | Investigate the collection of non-recyclable waste less frequently ensuring that an Absorbant Hygiene Product collection scheme is also put in place to ensure that they are still collected at the current frequency. | ON HOLD | - Bexley have been collecting residual waste fortnightly since 2009. Reducing this frequency further is not being considered at this time. |  |
| LB Bexley 13 | - Maximising Recycling | Limit residual waste bin size | PART COMPLETE | - The Council will only collect 1 x residual waste bin per property. The 180L size is the Council’s standard size and a 140L size is offered as well for small households. If a household has extra requirements, they must go through a waste diary process and audit to gain approval for a 240L bin or a double bin collection. - The move to Council provided only bins is not in place yet. | - The replacement container online form will be updated by Autumn 2024 to no longer allow households with 5 or more to automatically order a 240L size bin. This will encourage residents to use the recycling services provided as fully as possible and increase the amount of recycling collected. - To audit how many residents use non-council provided bins to scope out this possible change to our residual waste service |
| LB Bexley 14.1 | - Maximising Recycling | Food Recycling Service | ON TRACK | - The average missed bins per month for food waste in 2022/23 was 587. In 2023/24 the average has reduced to 400. In March 2024 total missed food bins for the month was 306. We have therefore made great progress in improving the service and resident satisfaction in it. Now that the service is more stable, and performance is better we can start focusing on encouraging residents to start using their food boxes again. | - Tonnages collected are similar to 2022/23 at 4,551 tonnes so an increase has not been seen yet partly because of socio-economic factors eg how expensive food is currently. |
| LB Bexley 14.2 | - Maximising Recycling | Food Recycling Service | ON TRACK | - Start a publicity campaign to: 1. Encourage residents that have stopped recycling food waste to start again 2. Enable those that are already recycling - recycle more 3. Encourage residents to remove food from packaging and recycle it - We are already publicising the food recycling service through many types of media and taken part in the regional ‘Eat like a Londoner Campaign’ to increase food recycling rates across the Borough. - The Council’s Communication team are working on a specific food recycling campaign for our residents at the moment. | - Food recycling increased slightly from 4,528 tonnes in 21/22 to 4,628 in 22/23. Unfortunately, we have seen a dip in food waste recycling in 23/24 to 4,551 tonnes so there is still a lot of work to do to get residents to start food recycling again (Pre COVID and the strikes we were recycling over 6,000 tonnes per annum). - There are no results from the Councils specific food waste recycling campaign yet as we have only completed the market research so far. |
| LB Bexley 14.3 | - Maximising Recycling | Food Recycling Service | ON TRACK | - The number of flats with a food waste service has increased from 32% to 48% including 1% of flats above shops. This includes delivering the main collection bin as well as delivering a food waste caddy and leaflet to every flat. | - 9,834 residents are now able to recycle food waste from their flat which is a great improvement. 12,123 still to be provided with the service before 31st March 2026 to meet simpler recycling target. Staff working hard to achieve this. |
| LB Bexley 14.4 | - Maximising Recycling | Food Recycling Service | ON HOLD | - As the packaging will not be recycled, we do not want to look at putting this in place at the moment. It is more important to focus on increasing the participation of the food waste recycling service and ensuring that all property types have access to the food waste recycling service. | - Food waste tonnages have not been increased due to packaged food waste being included in the list of accepted items for the food recycling service. After reviewing this option it was decided that the majority of the weight would be the packaging itself which would not be recycled anyway so we feel it is best to encourage residents to empty packaging of food waste into the food recycling service and recycle the packaging in the correct recycling bin. |
| LB Bexley 15.1 | - Maximising Recycling | Garden Waste Recycling Service Improve the customer satisfaction with the service and reduce the number of garden waste missed collections boroughwide | ON TRACK | - The average missed bins per month for food waste in 2022/23 was 423. In 2023/24 the average has reduced to 166. In March 2024 total missed garden bins for the month was 98. We have therefore made great progress in improving the service and resident satisfaction in it. | - 9,378 tonnes of garden waste were collected in 2023/ 24 which was 1,000 tonnes more than in 2022/ 23. |
| LB Bexley 15.2 | - Maximising Recycling | Garden Waste Recycling Service Communication campaign to increase customer numbers | ON TRACK | - There are now 38,723 garden waste customers so there has been a drop in garden waste customers of over 1,000. This may be due to the rise in service costs over the last few years. | - We have not been able to increase the number of customers but have made the service better for those residents that still subscribe. |
| LB Bexley 15.3 | - Maximising Recycling | Garden Waste Recycling Service Investigate a Christmas tree recycling option for non-garden waste customers | DELAYED | - Non-garden waste customers can take their Christmas trees to the Borough’s RRC’s already; however, we would like to offer a collection option as well to ensure that more garden waste is composted. A booking system is required to make this possible, so we have been exploring options with the digital team. | - We have not been able to increase the amount of Christmas trees composted in the Borough yet although will continue to explore booking system options with the digital team. |
| LB Bexley 16 | - Maximising Recycling | Textile Recycling Increase number of textiles bring banks across the Borough. | NO PROGRESS TO DATE | - The number of textile banks has not increased across the Borough yet. It is hoped that this will happen over the next year. - TRAID kerbside collection scheme for Textiles started in October 2022. | - Tonnage collected in the textile banks has gone up from 396.64 in 22/23 to 460.15 in 23/24 |
| LB Bexley 17.1 | - Maximising Recycling | Flats/HMO Recycling Maximise recycling and reduce contamination in flats and flats above shops recycling services using key findings from the ReLondon Flats Recycling Study including checking bin cleanliness and that signage is adequate. | PART COMPLETE | - We have introduced food waste recycling to 272 blocks – 3094 flats in total. - At each block where food waste is introduced, we have engaged with residents on recycling as well as food. - Where particular issues have been raised, we have worked with MA’s and HA’s to improve facilities at flats. | - 95.48% of all flats have dry recycling collected currently. - 45.17% of all flats have food recycling collected currently. |
| LB Bexley 17.2 | - Maximising Recycling | Flats/HMO Recycling Put in place recycling services at blocks of flats that do not have them already. | PART COMPLETE | - We have introduced food waste recycling to 272 blocks – 3094 flats in total so far. - The number of flats with a food waste service has increased from 32% to 45% including 1% of flats above shops. This includes delivering the main collection bin as well as delivering a food waste caddy and leaflet to every flat. This | - 95.48% of all flats have dry recycling collected currently. - 45.17% of all flats have food recycling collected currently. |
| LB Bexley 17.3 | - Maximising Recycling | Flats/HMO Recycling Work with housing associations/agents/landlords and their tenants to increase recycling. | ON TRACK | - We are having regular meetings with HAs. - Regular site meetings with MAs / HAs where issues occur. - We will be producing a landlord’s guide to recycling which will include posters that they can use to inform their tenants about the recycling services and how to use them. | - We are building good relationships with MA’s and HA’s as this is key to ensuring that we get as much recycling out of our flats as possible. |
| LB Bexley 18.1 | Maximising Recycling Recycling Engagement Activities | Visit schools with SWAC (Schools Waste Action Club) and ensure that whole school assemblies are carried out as well as 50 additional class activities to encourage children to recycle at home. | ON TRACK | - The Cory funded Waste and Recycling Engagement Officer started in February 2023 and has since taught 11,884 children in Bexley schools about Waste, Recycling and Sustainability. | - In 2023 (March-December) 7,434 children in Bexley schools were taught about Waste, Recycling and Sustainability. - So far in 2024 we have already reached 6,450. |
| LB Bexley 18.2 | Maximising Recycling Recycling Engagement Activities | Promote recycling through public stalls at community events, workshops, demos. | COMPLETED | - Over 50 workshops, demos and community events have taken place during April 2023 – April 2024 - Aim to run over 20 workshops April 2024 -April 2025 | - Engagement with over 2,500 residents |
| LB Bexley 18.3 | Maximising Recycling Recycling Engagement Activities | Run an Earth Summit for local secondary schools | DELAYED | - An Earth Summit was booked in May but unfortunately 2 schools pulled out of the event a few weeks before it too place and it was not viable to run with the 1 school that was left. We are therefore hoping to run this in the Autumn term instead. | Over 100 students took part in May 2023 and we hope that the 2024 event that is delayed until Autumn 2024 will reach a similar number of students. |
| LB Bexley 19.1 | - Maximising Recycling | Business recycling services - Increase the number of businesses in the Borough that recycle all materials including food. | ON TRACK | - Mixed Recycling (Plastic/cans/glass) - We have 280 customers. At the start of 22/23 we had 262. - Food Waste – we have 214 customers. At the start of 22/23 we had 213. - Garden Waste - We have 143 customers. At the start of 22/23 we had 140. - With the simpler recycling regulations coming in for businesses by 1st April 2025 we hope that we can increase this even further. | - All Recycling services have had the number of business customers increased. Food waste only by 1 however so this will be focussed on next year. This increase in customers on recycling services has helped to increase the amount of material recycled by businesses in the borough. |
| LB Bexley 19.2 | - Maximising Recycling | Business recycling services - Increase the number of food waste customers from 220 to 300. | DELAYED | - For half of 2023/24 we only had 1 trade waste officer instead of 2 so we have only been able to increase the number of businesses in the Borough with a food waste recycling scheme by 1. We aim to improve on that this year now that we have a 2nd trade waste officer back in post. | - Including schools, we have 214 customers. At the start of 22/23 we had 213. |
| LB Bexley 19.3 | - Maximising Recycling | Business recycling services - Introduce weight related charging for businesses to incentivise them to recycle more. | DELAYED | - The weighing equipment has been added to the dustcarts that collect from the trade waste customers and the fees and charges have been agreed by full Council. - We still need to get every bin tagged at all of our commercial customers premises before we can implement this, however. This should take place in 2025/26. | - We notify customers when their bins are overweight and sometimes cannot complete the collection. Most customers will only reduce the weight of their bins and recycle more if they were charged for the excess materials however, so it is very important that we get this scheme fully into place. |
| LB Bexley 19.4 | - Maximising Recycling | Business recycling services - There are 129 Council trade waste customers that have large bins (Euro's or 360 wheelies) for residual waste and no recycling services. Encourage these customers to reduce the size of their residual waste bins and start a recycling service with us. | NO PROGRESS TO DATE | - We have not had a dedicated member of staff that could progress this for us. Now that we have a 2nd trade waste officer back in position, we hope to progress this action further. | - No impact seen yet. |
| LB Bexley 19.5 | - Maximising Recycling | Business recycling services - Produce an online business guide for waste to include all waste/recycling disposal costs by material stream and useful waste reduction tips. Send key info via Bexley for business newsletter. | DELAYED | - Start new engagement/Link into talks/events via the BIDS, Business HUB and the Engine House Bexley. - Produce business Guide and update website to be done by March 2025 - Add a section in the Bexley Business newsletter - Work with 2 Businesses to evaluate their waste and how they have been able to reduce it and use as case studies. This has proved very difficult, but we still hope to engage with one business if possible | - No impact from these activities yet as they are delayed due to staff workload. |
| LB Bexley 19.6 | - Maximising Recycling | Business recycling services - Start talks with local businesses and BID to install a scheme in Bexleyheath Town Centre for hot drink cups to be collected and recycled. Ensure that all retailers that sell hot drink cups can participate. | NO PROGRESS TO DATE | - Set up meeting with local business, town centre organisers to see if this is possible to put into place. - Help with campaign to encourage people to use the service once it is set up | - Reduce the residual waste and encourage reuse of drinking cups. |
| LB Bexley 20 | - Maximising Recycling | On Street Recycling Ensure that the street recycling bins, and recycling bring site locations in the Borough which give residents flexibility in how they recycle are kept clean and emptied regularly to encourage people to use them. | ON TRACK | - The number of on-street recycling bins in the Borough is being increased from 67 to 130 as part of a litter bin replacement project. So far 28 of the new on street recycling bins have been installed with the rest to be in place by the end of 2024/25. | - 602.19 tonnes were recycled through the recycling bring sites in 23/24 up from 583.64 in 22/23. - No data on street cleansing recycling yet. |
| LB Bexley 21 | - Reducing Environmental Impact | Utilisation of heat produced at Belvedere Riverside Energy from Waste Facility which takes the residual waste from Bexley | ON TRACK | - The Riverside Heat Network aims to provide 21,000 homes with heat as an alternative to gas boilers. In May 2021 Cory received £1.6 million commercialisation grant through the Government’s Heat Networks Investment Project (HNIP) to support the heat networks development. - In March 2024, Cory launched a new project to decarbonise heating by moving waste heat along the River Thames in thermal batteries. The project will take heat from the Belvedere Riverside Resource Recovery Ltd., store it in thermal batteries, and transport it via barge to major heat consumers, such as district heat networks. | - Energy is recovered from the waste disposed of by the London Borough of Bexley but the heat is not currently being used. The operators of the Belvedere Riverside Energy from Waste Facility are working towards this goal however. |
| LB Bexley 22.1 | - Reducing Environmental Impact | Fleet and staff travel greener options Increase the use of biofuels in vehicles used on Street Services Contracts and encourage contractors to trial and use electrical vehicles in their operational activities. | ON TRACK | - Our Contractor Countrystyle Recycling Ltd are installing 2 electrical sockets so that the smaller vehicles in their fleet can be electric eg supervisor vans. They will also be trialling an electric dustcart in the Autumn. | - No impact yet but the use of electric vehicles will result in reduced CO2 being created and help reduce air pollution in the Borough and wider area. |
| LB Bexley 22.2 | - Reducing Environmental Impact | Fleet and staff travel greener options Increase the numbers of staff that use the electric pool car scheme during the workday if they need to make a journey which cannot be done by public transport. | ON TRACK | - Ongoing work with comms to staff regarding the Council’s carpool scheme and the season ticket and cycle loans. | - Usage of pool cars reduced drastically during the COVID pandemic and remains low. The scheme continues to be promoted but there are few incentives for staff to use pool cars rather than their own vehicles. |
| LB Bexley 22.3 | - Reducing Environmental Impact | Fleet and staff travel greener options Implement interest-free season ticket and cycle loans for employees to promote alternative travel to work arrangements | COMPLETE | - Ongoing work with comms to staff regarding season ticket and cycle loans. | - Season ticket loans are rarely taken up because of the location of stations relative to our offices, and the lack of quick and efficient public transport around the borough to undertake duties. |
| LB Bexley 22.4 | - Reducing Environmental Impact | Fleet and staff travel greener options Maintain staff travel plan with the aim of reducing single occupancy car trips to and from the site including those parking remotely. Cycle parking is provided on site. | ON TRACK | - Ongoing work with comms to staff regarding car sharing among staff and promoting the cycling facilities provided at Council Offices. | - Car trips have reduced due to hybrid working but there has been no enthusiasm for car sharing amongst staff. - The Council has a cycle to work scheme but again take up is relatively low. |
| LB Bexley 23 | - Reducing Environmental Impact | Trial the use of advanced/ recycled highways materials | ON TRACK | - Bexley has trialled the use of thermal road treatment to recycle existing asphalt material were possible and are checking on its reliability. | - If the trail is successful, the Council will look to use this technique for road defect repairs to reduce material wastage and production energy. |
| LB Bexley 24 | - Reducing Environmental Impact | Waste and recycling in London Borough of Bexley’s Parks and Open Spaces To work with parks team to ensure there are enough recycling and litter bins in the Borough’s parks and they are kept in a clean state to encourage their use. | PART COMPLETE | - Facilities are in place in the largest of the Councils parks and open spaces, but a review is needed to check that they are in the right locations, that there are enough and that the emptying processes are working. This review will take place over the next 6 months so that we can implement any changes in the spring for Summer 2025. | - Adding recycling bins to the bins that were already in place in the parks and open spaces has given more places for visitors to place their rubbish. Unfortunately, the contamination of the material is very high and often cannot be sent for recycling. The litter in the parks and open spaces has reduced, however it is now concentrated around the extra bins so we are promoting visitors taking their rubbish home with them if the bins are full. |
| LB Bexley 24 | - Reducing Environmental Impact | Waste and recycling in London Borough of Bexley’s Parks and Open Spaces Work with parks and events team to ensure that any main event has adequate waste and recycling facilities provided. | ON TRACK | - The Council provide waste and recycling bins to some events that place in the parks and open spaces. - All event applications have to include a waste management plan. | - Adding waste and recycling bins at events for visitors to use enables the litter in the parks and open spaces to be reduced. Unfortunately, the contamination of the material is very high and often cannot be sent for recycling. The bins are also often overflowing during and after events so we are promoting visitors to take their rubbish home with them if the bins are full. |
| LB Bexley 25 | - Reducing Environmental Impact | Litter Picking Maintain and increase the 400 community litter pickers that are currently signed up to keep Bexley clean and green. | ON TRACK | After a review of all community litter pickers the number of active volunteers has now reduced to 120. There is an event for community litter pickers in August 2024 and we hope to recruit some more volunteers. The Council supply all volunteer community litter pickers with equipment and facilitate removal of the waste for them. | - All of the Councils volunteer community litter pickers make a fantastic difference to how clean and green the Borough is. We have not got any stats on how many sacks are collected by the litter pickers unfortunately but hope to find a way of recording this going forward. |
| LB Bexley 26 | - Reducing Environmental Impact | Recycling Increase recycling to reduce the raw materials required to produce products | DELAYED | - The target of increasing the Council’s recycling rate to 55% by 2025 will be delayed. The Council’s target is 55% because pre-covid it was reaching a 54% recycling rate. Unfortunately Service suspensions due to COVID and 3 strikes from 2020-2022 have negatively impacted the Council’s recycling rate. There has also been a reduction in recycling nationwide as well since COVID and since the downturn in the economy. | - 2021/22 the Borough’s recycling rate reduced to 42.7% which is the lowest that it has been since before 2008/09. In 2022/23 the Borough’s recycling rate increased to 43.8%. The aim is to get over 45% in 2023/24. |
| LB Bexley 27 | - Reducing Environmental Impact | Waste Disposal Energy from waste reducing the electricity produced from non-renewable sources. | ON TRACK | - All of the non-recyclable waste that the Council collects is taken to Belvedere Riverside Energy from Waste Facility. | - Any waste that the Council collects that cannot be reused or recycled goes on to produce electricity instead at an energy from waste facility. Less than 1% of non-recyclable waste in the Borough goes to deep landfill (asbestos). |
| LB Bexley 28.1 | - Promote the circular economy to local business | Link into other environmental talks/events via the Business hub to spread the message wider. | PART COMPLETE | - We have been able to speak at a couple of business talks/events in the last year and will continue to look for opportunities to do this going forward. | - Remind businesses about benefits of considering the circular economy and services we provide to enable them to start making an impact by reducing and recycling the waste that they produce. |
| LB Bexley 28.2 | - Promote the circular economy to local business | Produce an online business guide for waste to include all waste/recycling disposal costs by material stream and useful waste reduction tips. | NO PROGRESS TO DATE | - This is delayed due to staff workload. The aim is to get this completed in 2025/26. | - No impact from these activities yet. |
| LB Bexley 28.3 | - Promote the circular economy to local business | Send key info via Bexley for business newsletter. | PART COMPLETE | - Information was placed in one newsletter, but we would like to be able to do this more regularly going forward. Will work on this for next year. | - Businesses need to receive information on reducing and recycling their waste more often to encourage them to make more impact via their waste management plans. |
| LB Bexley 29 | - Reducing Environmental Impact | On Street Recycling Ensure that recycling options are easily accessible to all via mini recycling sites and on street recycling bins as not all residents can access the Reuse and Recycling Centres. | ON TRACK | - The bring banks will continue in the Borough for another 3 years from October 2024. Over the next 1-2 years we will monitor the impact of the deposit return scheme, extended producer responsibility and simpler recycling legislation to decide a way forward for on street recycling. - The number of on-street recycling bins in the Borough is being increased from 67 to 130 as part of a litter bin replacement project. So far 28 of the new on street recycling bins have been installed with the rest to be in place by the end of 2024/25. - The target of increasing the Council’s recycling rate to 55% by 2025 will be delayed. The Council’s target is 55% because pre-covid it was reaching a 54% recycling rate. Unfortunately Service suspensions due to COVID and 3 strikes from 2020-2022 have negatively impacted the Council’s recycling rate. There has also been a reduction in recycling nationwide as well since COVID and since the downturn in the economy. | - 602.19 tonnes were recycled through the recycling bring sites in 23/24 which is up from 583.64 in 22/23. - No data on street cleansing recycling yet. - 2021/22 the Borough’s recycling rate reduced to 42.7% which is the lowest that it has been since before 2008/09. In 2022/23 the Borough’s recycling rate increased to 43.8%. The aim is to get over 45% in 2023/24. |
| LB Bexley 30 | - Reducing Environmental Impact | Public Transport - Continue to work towards a cross rail extension across the London Borough of Bexley's area to help improved public transport links in the Borough to help residents to change to greener travel options. | ON TRACK | - The Council sent a letter from the Leader to the then Minister for Transport on the 'transport ask' for Bexley (letter sent in Nov 2023). A new letter is to be sent now that there has been a change in government. - The Council sent a submission of a programme of investment to TfL in Nov 23. The TfL programme of investment was subsequently approved by TfL and this is in the process of being implemented. | - The programme of investment covers all projects which aim to improve road safety, public transport facilities and active travel improvements. A positive outcome from these is that they also reduce the number of cars on the roads and therefore the amount of air pollution in the Borough and wider area. |
| LB Bexley 31 | Maximising local waste sites | Change Policies Introduce Fair use Policy | PART COMPLETE | - Proof of address requirements introduced moving away from permit scheme in September 2023. - Usage limits still to be approved pending data analysis. - DIY waste charging has been delayed due to government legislation bringing in limit for charging. Currently looking at how to keep a 4-week rolling record of individual properties to be able to charge. - Reduced vans allowance of waste allowed to be disposed of free of charge from 500kg to 250kg per year. | - A decline in visitor numbers and tonnages at both sites has occurred since the Fair Use Policy was introduced in September 2023. - Residual waste reduced from 3521.4 in 22/23 to 3295.5 in 23/24. |
| LB Bexley 32 | Maximising local waste sites | New provision for pedestrian and cycle access | DELAYED | - This was included in the fair use policy changes but has not progressed. Needs to be re-evaluated. | - Pedestrian and cycle access at Footscray RRC but not at Thames Road RRC currently. |
| LB Bexley 33.1 | Maximising local waste sites | Increase Reuse opportunities on site Improve the reuse areas at both RRC's by better signposting and communications. Encourage as many items as possible to be segregated for reuse at the RRC’s. | ON TRACK | - A new reuse provider was put in place at both RRC’s in September 2023. The aim is to increase the amount accepted for reuse at the sites because previously lots of items had been put aside but the previous provider was only taking a small quantity for reuse and the rest was being recycled/disposed of. | - 20.92 tonnes reused from both sites in 23/24 compared to 18.57 tonnes in 2022/23. - This is good progress with our new provider only being in place for part of the year so we are hopeful that with a full year of them being in place in 24/25 even more items will be reused from the two RRC’s. |
| LB Bexley 33.2 | Maximising local waste sites | Increase Reuse opportunities on site Continue to investigate the possibility of a reuse shop/ workshop managed by a local charity/ partnership to be held within the Borough (preferably at one of the Council’s RRC’s) | ON TRACK | - Our new reuse provider runs 4 reuse shops around the Country and is currently doing a feasibility study to see if one can be opened at one of Bexley’s RRC’s. This will help reduce transport of the items as they are currently being taken to the Sutton Reuse Shop. It will also enable us to reuse more items from the sites and provide a fantastic facility for local residents to buy second hand items at low prices. | - A reuse shop has not opened yet so no impact currently, but we are working towards one being in place by 2025. |
| LB Bexley 34.1 | Maximising local waste sites | Increase Recycling on site Increase the quantity of materials recycled through the Borough's 2 Reuse and Recycling Centres. | ON TRACK | - All site staff are encouraging recycling wherever possible, and we have worked with our contractor to ensure that items such as wood are sent for recycling and not RDF. | - RRC recycling Rate for 2023/24 74.89% slightly up from 74.58% in 2022/23. Fair use policy has caused the recycling rate to drop in final quarters of 2023/24 so need to watch this going forward. |
| LB Bexley 34.2 | Maximising local waste sites | Increase Recycling on site Return (post COVID) to sorting black sacks before they are put into the compactors sacks before they are put into the compactors to pick out any recyclable material. | NO PROGRESS TO DATE | - Still under consideration with the contractor. Unsure if the cost outweighs the benefits. | - None of the extra recycling on site can be attributed to this as it has not been put back in place yet. Still considering whether to do this or not. |
| LB Bexley 35 | Maximising local waste sites | On Street Recycling Ensure that street recycling bins, and recycling bring site locations in the Borough which give residents flexibility in how they recycle are cleaned and emptied regularly, and that the signage is kept fresh and updated to encourage people to use them. | ON TRACK | - The bring banks will continue in the Borough for another 3 years from October 2024. Over the next 1-2 years we will monitor the impact of the deposit return scheme, extended producer responsibility and simpler recycling legislation to decide a way forward for on street recycling. | - 602.19 tonnes were recycled through the recycling bring sites in 23/24 up from 583.64 in 22/23. |
| LB Bexley 36 | Maximising local waste sites | Strategic Waste Sites in London Borough of Bexley Local Plan | ON TRACK | - LB Bexley continues to ensure that the 6 strategic waste sites in the Borough are safeguarded for waste management use. | - The Borough is continuing to meet its apportionment targets. |