- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 422.9 | 390 | 365.11 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 891.2 | 805.6 | 684.48 kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 77 | 35 | 60 kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70% Unavoidable food waste in residual: 30% Avoidable food waste recycled: 44% Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 25.20% | 32.20% | 32.6% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 25.80% | 33% | 31.86% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 0% | 0% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 0% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 0% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 0% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 0% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 0% | 20% | 20% | 20% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| LBBD - 1 | Waste and Recycling communication and education campaign | - Intensify communication and education campaigns to raise awareness on environmental impacts of waste and to encourage greater levels of household waste reduction and increased material reuse and recycling. This will further inform residents and reinforce the recent service change that has seen LBBD meet the Mayor’s minimum level of service for recyclable materials. - Increase use of council’s communication channels (social media and electronic newsletter) to promote council’s waste minimisation programmes, increase waste awareness and encourage increased recycling. - LBBD is developing comms and engagement plan with the underpinning message on managing waste and wider impact on climate change and community involvement. | - On track | - Delivered 77 events in 2024-25, including roadshows, recycling assemblies, workshops with community groups and schools, engaging with approximately 8,200 residents. - Boroughwide mailout highlighting LBBD recycling services and encouraging residents to segregate their waste and recycle correctly. Information on current improved recycling rate and waste produced per household were shared with residents to further motivate them. - Public Realm communications and engagement plan was developed and approved at member level. As part of this plan, a strong programme of activities was organised for Great Big Green Week to encourage resident participation. However, financial constraints limited the implementation of some projects and activities. - First edition of Waste Minimisation Newsletter was published. - Waste and Recycling communication and education campaigns are planned for 2025-26. | - Recycling rate increased to 30.7% in 2024/25 from 30.5% in 2021/22. - Waste per household per year reduced from 772.36 Kg in 2021/22 to 711.91 Kg in 2024/25. However, it is higher than 683.18 Kg in 2022/23. - The quality of recycling has improved due to the consistent messaging and resident engagement. - We leveraged on 7 national and 5 international environmental awareness events to promote our waste minimisation agenda. - The Waste Minimisation newsletter reached out to 1675 subscribers. |
| LBBD - 2 | School and Community engagement | - Work with schools and community groups from across the borough to promote waste minimisation activities and projects with core message around waste reduction. - Promote Eco-Schools to raise waste awareness among pupils and to encourage schools to reduce their waste and increase recycling. Support environmental initiatives by school environmental groups e.g., Eco Councils. | - On track | - Delivered 32 events across 16 schools, including workshops, recycling assemblies, and roadshows for students and parents, engaging a total of 1,647 participants. - Supported 2 schools in setting up in-situ composting facilities by providing free composters and delivering training sessions. - Assisted 3 schools—Henry Green Primary School, Barking Abbey Secondary School, and Grafton Primary School—in achieving Eco-Schools Green Flag Awards. - Established community composting at 5 schools: Henry Green Primary, Grafton Primary, Barking Riverside Primary, and Eastbury Community School, helping them manage organic waste and reduce residual waste tonnages. - Further school and community engagement activities are planned for 2025–26. | - Received positive feedback from several schools, with many requesting more meaningful engagement events in the future. - One school shared the Waste Minimisation workshop content on their website and social media, helping to amplify the message. - Community composting was established at 2 schools to support organic waste management and reduce residual waste tonnages. - Supporting schools through their Eco school journey has helped raise environmental awareness and contributed to reducing their environmental impact. |
| LBBD - 3 | Restriction on the volume of residual wheelie bin provided to households | - Engage with residents on the reasons for restriction of residual wheelie bin capacity to 140L and limit on one bin provision per household. | - On track | - Since the introduction of the restricted bin size (140L) and one-bin policy, there have been 6,500 resident engagements, focused on waste minimisation education, promoting recycling, and encouraging composting to reduce residual waste and maximise bin space. - In 2024/25, this increased to 8,350 engagements, continuing efforts to educate residents on sustainable waste practices under the same policy. - The restriction on residual wheelie bin volume will remain in place for 2025–26, supporting ongoing waste reduction and recycling initiatives. | - The number of residents requesting larger bins has declined, as these are no longer offered. Residents are increasingly able to manage their waste within the standard residual bin capacity, demonstrating improved waste minimisation practices. - Waste per household per year has reduced from 772.36 Kg in 2021/22 to 711.91 Kg in 2024/25. However, it is higher than previous year which was 683.18 Kg in 2022/23. |
| LBBD - 4 | Charge for providing residual wheelie bin | - Charge for new and replacement residual wheelie bins. | - On track | - The charge for residual wheelie bin has been reflected on the council’s annual fees and charges. | - The number of requests for new and replacement bins has declined from 1236 requests in 2022/23 to 1082 refuse bins request in 2023/24 and further declined to 776 requests in 2024/25. As the bins are now chargeable, this has encouraged a sense of accountability and ownership. |
| LBBD - 5 | Handling excessive residual household waste | - Implement the household waste and recycling guidance to provide impetus for enforcement action on extra black bag waste presentation by residents. There is provision for residents to dispose of their excess residual waste and restricted household waste at Frizlands Lane Reuse and Recycling Centre (RRC). | - On track | - Residents continue to be encouraged to present their waste correctly in line with council policy, with a focus on avoiding the presentation of side waste. - Residents are regularly signposted to appropriate disposal options, including the chargeable bulky waste collection service and the Recycling and Reuse Centres (RRC), which are free to use. - While enforcement action is not currently taken for side waste presentation (except in cases of fly-tipping), the team carries out targeted engagement with residents who persistently present side waste or when complaints are received. | - The waste produced per household has declined from 772.36 Kg in 2021/22 to 711.91 Kg in 2024/25. However, it is higher than previous year which was 683.18 Kg in 2022/23. |
| LBBD - 6 | Support for composting initiatives | - Promote composting at home and community levels. Deliver composting workshops to educate residents on composting practices. - Provide free compost bins as an incentive to residents, schools or community groups who are passionate to undertake long term composting. | - On track | - In 2024/25, 8350 residents were encouraged to try composting and were provided with information and resources on best composting practices. In 2024/25, a total of 8,350 residents were encouraged to adopt composting practices and were provided with information and resources on best composting practices. - Two schools were supported in setting up their own composting facilities, receiving free composters and training sessions to help manage organic waste. - Virtual composting training was delivered through the ELWA Waste Prevention Programme, attended by 119 East London residents, compared to 220 attendees in 2023/24. - A total of 7 composting workshops were delivered in 2024/25 to further promote composting across the community. - Continued support for composting initiatives is planned for 2025/26, building on the progress made. | - The 9 new home composting sign-ups and 2 school composting setups is estimated to divert 1,650 kg of waste from domestic waste bins annually. - 7 composting workshops delivered in 2024/25 attended by 425 participants help to promote composting and share best practices. - Feedback from residents who signed-up for the composters were that it helped in keeping a lot of waste out of refuse bins, helped to manage food waste, and avoided trips to the RRC or paying for the Green Garden Waste subscription service. |
| LBBD - 7 | Green garden waste collection service | - Promote green garden waste collection service through local newspaper, council newsletters, social media outlets and door knocking exercise. This service is currently a non-statutory service paid for by residents who wish to use the service. | - On track | - Conducted targeted door knocking at 624 properties in areas with low subscription rate to promote garden waste service. - Actively promoted green garden waste service at all Waste Minimisation engagement events and activities, ensuring consistent messaging across community interactions. - The service was widely advertised in Barking & Dagenham Post (local newspaper), One Borough Newsletter, leaflet, digital screens, social media handles, on railing banners and on side of bin collection truck. | - A total of 6,805 households subscribed to the green garden waste collection service in 2024-25. And for 2025-26 6523 residents have subscribed to the service so far. |
| LBBD - 8 | Waste services property survey Best recycling practices in flats | - To capture accurate data on bin assets, number of flats, state and usage of bins at properties across the borough, a property survey is being carried out across the borough. - To work with residents and managing agents/estate managers to enable waste reduction and correct recycling practices especially around recycling contamination. LBBD will work with managing agents and residents through organising roadshows, door knocking, having managing agent to include LBBD’s household waste and recycling guide as part of information pack handed to new residents and putting up recycling posters on noticeboards within block of flats. | - On track | - Completed waste services property survey as a part of data acquisition for the introduction of Bartec Waste Management System. - Waste facility audit was carried out at 50 flatted developments to enable managing agents make adequate preparation for managing waste in the development including recycling provision. - Displayed recycling posters on noticeboards 1,150 blocks of council buildings, reinforcing best recycling practices among residents. - Delivered a letter drop to 920 flat holders at Gascoigne Estate, providing guidance on the correct use of the Underground Refuse System (URS). - Planned consultation with managing agents to display recycling posters on noticeboards and include recycling leaflets in new resident information packs has been delayed due to time constraints. | - Recycling rate has increased to 30.7% in 2024/25 from 30.5% in 2021/22. - Increased recycling participation in flatted developments. - The quality of recycling has improved due to the consistent messaging and resident engagement. - Engagement with managing agents enable determining the adequate bin capacity provisions. |
| LBBD - 9 | Provision of food waste service | Work on implementing proposal for food waste collection with the view of having a functioning service by the time food waste collection becomes a statutory service. However, this will depend on ELWA agreeing food waste disposal route for boroughs and also LBBD confirming funding commitment. While we do not currently collect separate food waste, our waste minimisation programme encourages residents to adopt the philosophy of minimising food waste and finding ways to utilise left over food. LBBD’s food waste reduction/prevention initiatives include the Food Waste game and Let’s cook and save initiative. In principle, LBBD will now be implementing separate food waste collection prior to the end of the current PFI IWM contract and in line with new statutory requirements as soon as reasonably practicable, following the Government providing legislative clarity on the requirements and the funding available in support introduction of this new service. | - On track | - There has been initial modelling for food waste collection provision which is currently under review. Discussions on collection arrangement is still ongoing with ELWA in respect of obligations within the IWMS contract. - Food waste disposal arrangement through a third party has been agreed with East London Waste Authority. - Food waste collection project plan developed (see LBBD-14 and section 4 for further details) - In 2024/25, 13 Food Waste Prevention workshops were delivered and one school trip to food waste processing unit organised with 340 participants attending. |  |
| LBBD - 10 | Reusable nappy scheme | Reusable (real nappy) scheme was launched in May 2021 as part of East London Waste Authority (ELWA) waste prevention programme, offering free trial nappy packs worth £35. Continue to promote reusable nappy launched in May 2021 as part of the ELWA waste prevention programme to point residents to reusable nappy option. | - On track | - In 2023/24, a total of 156 free reusable nappy trial packs were issued to residents, exceeding the target of 100 packs set for the RRP period. - In 2024/25, 15 reusable nappies were delivered to residents as part of continued support for sustainable parenting practices. - Promotional activities for reusable nappies were carried out at Dagenham Registry Office and during various Waste Minimisation engagement events. - The Reusable Nappy Scheme will continue in 2024/25, supporting waste reduction and offering alternatives to disposable nappies. | - The 156 reusable nappies issued to residents diverts estimated 21,975 kg of disposable nappies from the waste stream and potentially saves 17,525.04 kgCO2eq. In 2024/25, 15 reusable nappy trial packs were offered to residents. By this, an estimated 7.752 kg of disposable nappies are diverted from waste stream and a potential 1685.10 kgCO2eq. |
| LBBD - 11 | Repair Café and other reuse events. | - Organise repair cafes in partnership with ELWA to encourage repair for e.g., electronic equipment and textile and to promote sustainable consumption and upskilling on simple household repair tasks. - Organise “Give and Take” events to promote reuse | - On track | - In 2024/25, a total of 5 repair cafe and clothes swaps were delivered in collaboration with ELWA. - Delivered 4 Give and Take / Swap events organised with local community groups such as Tots N Tunes, Baby Bank HQ, Early years cocoon. - Skill Share events were organised to teach technical skills to children to perform simple electronics fixes. - Repair cafes and other reuse events will continue to be promoted in 2025-26. | - Promoted reuse initiatives and waste diversion. - The repair cafes and clothes swaps received 183 attendees, 115 items were repaired, 21 electricals were recycled, 193 kg of waste was prevented leading to 1558 kgCO2eq. - Encourage reuse culture amongst young people. |
| LBBD - 12 | Library of Things | The Barking Library of Things was launched in September 2022 to provide tools and equipment borrowing service to residents in the borough. | - On track | - Delivered 6 Library of Things promotion events and directly engaged with 500 residents. - Distributed 15,000 Library of Things leaflets through Frizlands RRC, Community Hubs and Waste Minimisation events. Leaflets were produced as part of ELWA intervention strategy to encourage use of the Library of Things scheme. - Offered 50% off first borrows from the Library of Things - Promoted Barking Library of Things through council newsletters and social media. | - Impact statement provided by Library of Things organisation indicated that over £70k has been saved by the 335 people who have used Barking Library of Things since its launch, which translates to 4 tonnes of electricals reused and 10 tonnes of CO2e saved. |
| LBBD - 13 | East London Waste Prevention Programme (ELWA) | - The Waste Prevention Programme (WPP) is delivered in partnership with the four Constituent Councils (including Barking and Dagenham Council), working alongside community partners and third sector organisations. - The East London WPP has been approved to continue from April 2023 to March 2025. The programme includes a number of projects and initiatives across a range of waste streams, which will be delivered in collaboration between: ELWA; the four Constituent Councils; the IWMS contract Operator and its communications partner; and other stakeholders. - The action plan for 2023-24 is available on the ELWA website. An action plan for 2024-25 will be developed later in 2023. - ELWA is contributing to the pan-London food campaign, both through funding on behalf of the four Constituent Councils as well as participation in both the steering group and project board for the campaign. | - On track | - The East London Waste Prevention Programme (WPP) has been approved to March 2025 and includes a range of projects and services focusing on key material streams. - ELWA is part-funding the regional Eat Like A Londoner campaign as part of the WPP, working with ReLondon and other London local authorities - In 2024/25, 7 Food Waste Prevention workshops were supported by ELWA’s Waste Prevention Programme. - In 2024/25, 15 reusable nappy trial packs were offered to residents. - In 2024/25 virtual composting training was provided through the ELWA waste prevention program. - 7 School Uniform Banks - 5 repair cafe and clothes swaps delivered in collaboration with ELWA in 2024/25 - LBBD will continue supporting East London Waste Prevention Programme (ELWA) in 2024/25 | - Food Waste Workshops for the year 2024/25 had 152 participants compared to 30 in 2023/24. - In 2024/25, 15 reusable nappy trial packs were offered to residents. By this, an estimated 7.752 kg of disposable nappies are diverted from waste stream and a potential 1685.10 kgCO2eq. - In 2024/25 virtual composting training was provided through the ELWA waste prevention program, attended by over 119 residents of East London compared to 220 in 2023/24. - 7 School Uniform Banks - The repair cafes and clothes swaps received 183 attendees, 115 items were repaired, 21 electricals were recycled, 193 kg of waste was prevented leading to 1558 kgCO2eq. |
| LBBD - 14 | Preparing for introduction of separate food waste collections | - The establishment of separate food waste collections across East London is a commitment within the Joint Strategy for East London’s Resources and Waste. - These collections are also a new legal requirement arising from the Environment Act 2021. The implementation of this requirement is subject to further regulations and guidance from the Government, the publishing of which has been delayed until at least May 2023. - It is anticipated that the requirement will come into effect from March 2025, although there are now significant concerns across the waste and resources sector about the ability of supply chains for vehicles and containers to meet the national demand this requirement will create. - ELWA and the Constituent Councils are awaiting further information from DEFRA on the requirements and support available for introducing separate food waste collections, before detailed planning for the services can begin. Some of the steps that have been identified for these services to begin across the sub-region are (in no particular order): - Determination of procurement options for vehicles and containers, including appraisal of options for using existing fleet through operational changes, and evaluation of any joint or framework routes - Identification of public consultation requirements and options - Development of options appraisal for service introduction, as part of developing business case for review by Members - Stakeholder engagement plans developed, to include housing associations and managing agents for properties served by communal waste collections. - Formal governance processes for approval of proposed collection services - Procurement process and lead-in times for delivery of equipment and resources - Development and implementation of communications plan(s) for service introduction Securing of treatment capacity by ELWA’s IWMS contract Operator once further information about rollout of collections is known. - Given the commitment of the East London JRWS to food waste collections, LBBD are also committed to introducing comprehensive food waste collections in line with new statutory requirements as soon as reasonably practicable, following the Government providing legislative clarity on the requirements and the funding available in support. | - On track | - The modelling work for waste collection options including food waste has been completed and under review. Further discussions with ELWA regarding disposal arrangements under existing IWMS contract is ongoing. - Food waste disposal arrangement through a third party has been agreed with East London Waste Authority. - LBBD food waste service rollout will be phased starting with street level properties from October 2026 followed by communal properties and flats above shops. - Procurement of food waste caddies and outdoor bins, and collection vehicles is in process. - Communication strategy for implementation of food waste service will be developed which will likely include printing of leaflets, circulation through council newsletters and social media handles. |  |
| LBBD - 15 | Introduce additional Recycling banks | LBBD currently has a network of 33 public recycling bringsites across the Borough operated by Renewi (ELWA’s waste contractor). We are looking to increase the number of sites as we identify viable locations across the borough. | - Complete | - One new bring bank site has been installed at Barking Park. - Issues of fly-tipping and noise during emptying are limiting factors to introducing more bring banks. - No further update for 2024/25 | - Bring bank at Barking Park is well used recovering good recycling tonnage. No fly-tipping incidence is reported for this site. |
| LBBD - 16 | Reducing contamination | Contaminated recycling bin presented for collection will not be emptied and will be tagged with contamination tag to inform residents of what contaminants are contained in their recycling bin. | - On track | - Recycling contamination tagging system is still work in progress. However, letters are issued to the residents about the right way of recycling in certain persistent contamination incidents identified by the collection crew. - Newly procured Bartec Waste Management System is helping to generate contamination report. | - The quality of recycling has improved due to the consistent messaging and resident engagement. - The contamination report is used for designing resident engagement activities. |
| LBBD - 17 | Education and awareness outreach events | LBBD actively participate in national recycling and repair events such as Recycle Week and Repair week with community groups, schools and educational institutions. In addition to waste minimisation roadshows, school recycling assembly and recycling and reuse workshops, future education and awareness events will focus on delivering residents’ engagement activities at sites of medium to high density estate developments. | - On track | - A total of 77 events were delivered in 2024/25 including roadshows, workshops with community groups, schools, recycling assemblies etc. and engaged with around 8,200 residents compared to 64 events in 2023/24. | - Recycling rate has increased to 30.7% in 2024/25 from 30.5% in 2021/22. - Waste per household per year has reduced from 772.36 Kg in 2021/22 to 711.91 Kg in 2024/25. However, it is higher than previous year which was 683.18 Kg in 2022/23. - Residents are increasingly aware of what items to recycle as waste minimisation message is reinforced through education and awareness events and activities. |
| LBBD - 18 | Door knocking exercise | LBBD has an ongoing door knocking programme and since January 2022 has directly engaged with about 2700 households. | - On track | - In 2024/25, a total of 2,656 door knocking activities were carried out to engage with residents and provided information on waste and recycling. | - Increasing recycling rates is evidence of impact of sustained education and engagement activities. |
| LBBD - 19 | Library of Things Facility | LBBD has opened the Barking Library of Things for residents to be able to borrow equipment/tools without need to buy items that they do not use often or may never use again. It is our ambition to replicate the scheme at other parts of the borough pending the successful operation of the Barking Library of Things. | - Cancelled | - While Barking Library of Things remain operational, the scheme will not be replicated to other parts of the borough due to operational and financial constraints. | - Impact statement provided for Barking Library of Things indicated that over £70k has been saved by the 335 people who have used Barking Library of Things since its launch, which translates to 4 tonnes of electricals reused and 10 tonnes of CO2e saved. |
| LBBD - 20 | Recycling provision in new housing developments | - LBBD will continue to strengthen recycling in new developments and particularly in flatted accommodations through engagement with residents, Tenant Resident Associations (TRA) and housing management with a focus to reduce contamination. - LBBD is embarking on a bin store improvement project for 130 sites in estates across the borough. - The caretaking team is also running a bin provision competition to upgrade bin facilities for council housing. Comms and engagement plan is being developed focused on managing waste in the borough. - Free reusable recycling bags are provided for residents in flatted developments to encourage segregation of recycling at home. - LBBD’s planning Advice Note (PAN3) - Waste and Recycling Provisions in New and Refurbished Residential Developments provide guidance for planners, developers, architects, and facility managers on the provision of waste and recycling facilities in new and refurbished residential developments. Planning applications are assessed for adequate provision of recycling facilities. | - On track | - In 2023/24, door-knocking, leafletting, and letter drops were carried out at Gascoigne Estate to improve resident awareness and participation in recycling. - The pilot stage of the bin store improvement project has been successfully completed and is now progressing to the next phase. - Free reusable recycling bags continue to be offered to residents during engagement events to support better recycling habits. - Recycling posters have been displayed on noticeboards across council estates to reinforce best recycling practices. - In 2024/25, planning advice on waste management provision has been provided for 15 new major flatted developments. | - The free reusable recycling bags offered to residents during engagement events encourages segregation and storing of their recycling which adds to the recycling rate. - Recycling posters were provided to approximately 1,150 blocks of council owned buildings across the borough. - The planning application advice provides adequate recycling provisions are in place which will encourage residents to recycle correctly. |
| LBBD - 21 | School uniform bank project | Establish school uniform bank at schools for donation of school uniforms which will be administered by the participating schools. | - On track | - A total of 7 schools textile reuse opportunities through ELWA WPP School Uniform Bank initiative remain in place. | - Currently, no tonnages data have been provided by the schools through ELWA WPP to determine impact. |
| LBBD - 22 | Recycling quiz competition | Recycling quiz competition will be launched in the borough similar to one launched in September 2020 in which 20 winners were each awarded £25 worth of shopping vouchers. | - Complete | - The recycling competition was launched during the Great Big Green Week 2023 to help inspire residents to recycle more, raise environmental awareness and ultimately help increase our recycling. 20 winners were awarded £25 worth of shopping vouchers. - No further update for 2024/25 | - 354 residents participated in the quiz competition. |
| LBBD - 23 | Commercial recycling | LBBD offer commercial recycling service for businesses within the borough, collecting the same range of materials consistent with the household stream. The trade waste team will seek to increase uptake of recycling collection agreement with existing and new customers through intensive marketing drive. | - On track | - Due to waste collection capacity constraints, there has not been much drive for intensive marketing of the commercial recycling service. However, customers are provided information on Simpler recycling requirement during marketing and engagement. | - There are currently 713 commercial waste customers with 105 signed up to recycling service. Majority of commercial waste customers are micro-firms who have until 31 March 2027 to comply with Simpler recycling legislation. |
| LBBD - 24 | Food and drink carton bring bank | LBBD provides carton bring banks which accepts Tetra Pak and paper containers with metal ends (such as Pringles tubes). | Cancelled | - The carton bring banks will not be extended to other locations in the borough due to financial constraints. Residents are signposted to existing facilities, particularly Frizlands Land RRC. - ACE UK who provides collection for cartons including Tetra Paks will be withdrawing the service as it is expected to be collected within household recycling stream from 2026, but ELWA will continue to provide dedicated bins at RRC’s. |  |
| LBBD - 25 | Reverse side recycling bins trial | Trial of reverse side recycling euro bins at selected estates. The reverse side bins have aperture of the bin positioned in a way that users are not able to lift open the bin lid to drop large materials or bin bags. | - Cancelled | - Trial of recycling reverse-side bins at 10 locations across the borough has been completed. However, the reverse side recycling bins will not be extended to other locations in the borough due to financial constraints. | - The key findings from the trial were that residents in flatted developments with existing bin stores were encouraged to participate in recycling and the level of contamination were lower for these bins. |
| LBBD - 26 | Improving reuse and recycling across the IWMS Contract (ELWA) | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five Year Service Delivery Plan (2020-25), which includes a number of focus areas for improving reuse and recycling performance on the contract. - This includes actions to improve the recovery of recyclable items from residual waste through the mechanical-biological treatment (MBT) process. Significant improvements have already been made, in line with the targets for the second and third year of the service delivery plan, and ELWA will work with the Operator to continue to identify any further opportunities to improve recovery. - Other focus areas include the performance of the Reuse and Recycling Centres (see dedicated RRC line below), improved performance of dry mixed recycling services and recovery, and increased recovery of recyclable materials from bulky waste and street cleansing (the latter having contributed to recent performance improvements significantly). - ELWA notes that that a number of proposed Government policies and regulatory changes may impact on the ability of the Operator to achieve its targets, including the potential need to discontinue recycling activities for materials identified as containing persistent organic pollutants, the diversion of recyclable materials away to deposit return schemes, and the possible removal of compost like output from inclusion in recycling performance calculations. | - On track | - Improvements have been made to recovery processes for recyclable materials from residual waste, both within the MBT processes and at RRC sheds. - POPs requirements have removed some recycling opportunities. | - Recycling rates are improving across the ELWA constituent councils. - Reuse and recycling rate for the IWMS contract hit 32.8% for 2023-24. |
| LBBD - 27 | Reducing waste sent to landfill (ELWA) | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five Year Service Delivery Plan (2020-25) which includes an ongoing target to achieve a minimum of 67% diversion from landfill for the waste it handles. Actual performance is considerably higher than this target and has exceeded 99% since 2019-20. - Landfill diversion is achieved in a number of ways: - Separation of waste for recycling by householders and businesses using the collection services provided by the Constituent Councils. - Increasing the amount of reusable and recyclable waste segregated from residual waste by visitors to the Reuse and Recycling Centres. - Recovering recyclable items from residual waste, through a combination of manual separation at transfer stations, and mechanical separation at Renewi’s mechanical-biological treatment (MBT) plants and other third-party material recovery facilities. - Bio-drying of residual waste at the MBT plants, which reduces the overall mass by about 30%. Conversion of non-recovered materials from the MBT facilities into fuels, for use in energy-from-waste facilities. | - On track | - Landfill diversion remains just below 100%, with the only materials going to landfill being asbestos (which is the only viable option). | - Diversion of waste from landfill |
| LBBD - 28 | Textile banks/Collection | - Textiles is identified as a high carbon material and diversion from residual waste stream through reuse and recycling will reduce carbon impact. To encourage textile recycling at the RRC, new recycling banks have been provided allowing for more recycling capacity and the convenient use of facility. This is in addition to the textile recycling banks provided across the borough. We continue to encourage residents to donate textiles to charity shop through providing visibility for these organisations on our website to encourage residents to use them as first option before considering booking for bulky waste collection. LBBD will be partnering with a third sector organisation (Traid) to offer bookable textile collection service directly from households. | - On track | - In 2024/25, a total of 5 repair cafe and clothes swaps were delivered in collaboration with ELWA. - Delivered 4 Give and Take / Swap events organised with local community groups such as Tots N Tunes, Baby Bank HQ, Early years cocoon. - 7 School Uniform Banks established at schools in the borough. - Proposed bookable and door-to-door household textile collection service arrangement with Traid and Pink Elephant are still in progress. | - Promoted reuse initiatives and waste diversion. - The repair cafes and clothes swaps received 183 attendees, 115 items were repaired, 21 electricals were recycled, 193 kg of waste was prevented leading to 1558 kgCO2eq. |
| LBBD - 29 | Optimization of collection rounds | The waste collections rounds have been reduced from 10 to 8 rounds for refuse and from 5 to 4 rounds for recycling. Procurement of a new waste management solution will among other functions further optimise collection route. LBBD is procuring a waste management solution (digitisation and data management) - Bartec system - to track and manage waste collection operation. | - Part complete | - The Bartec System is now operational for the domestic waste collection rounds but there is ongoing work on the trade waste element. | - Helps to reduce our carbon footprint by virtue of reduced vehicular movement and for managing waste and operational data. - The Bartec system is helping to generate contamination report used for designing resident engagement activities. |
| LBBD - 30 | Innovative waste collection system | - Introduction of ENVAC waste collection system (e.g., Barking Riverside development) which compacts waste and allows for bulk collection. We continue to encourage developers to consider integrating such new technologies in their waste strategy for new developments. Introduction of Underground Refuse System (URS) at the Gascoigne Estate in Barking. The new system will be accessed via fobs by residents so allows for greater accountability in waste disposal and monitoring of resident behaviour. | - On track | - The ENVAC waste collection system is working well. - Underground Refuse System (URS) at the Gascoigne Estate in Barking is in operation but have significant operational challenges including lack of LBBD owned specialised collection vehicles and fly tipping issues. | - Reduced collection rounds and vehicular movement with positive impact for carbon emission for the specialised collection vehicles. |
| LBBD – 31 | Improving reuse and recycling performance of RRCs (ELWA) | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five Year Service Delivery Plan (2020-25), which includes targets to increase reuse and recycling performance at the four Reuse and Recycling Centres (RRCs) that cover the London Boroughs of Barking and Dagenham, Havering, Newham and Redbridge. - The uplift in reuse and recycling performance will be delivered through a combination of general site improvements and greater separation of recyclable materials from residual waste. Site improvements will include layout changes where possible to encourage visitors to separate more items from the residual stream, an increased range of materials accepted for recycling where the market allows, and improved performance of on-site reuse schemes. - ELWA notes that a number of proposed Government policies and regulatory changes may impact on the ability of the Operator to achieve its targets, including the potential need to discontinue recycling activities for materials identified as containing persistent organic pollutants and the diversion of recyclable materials away to deposit return schemes. | - On track | - RRC performance remains a focus for ELWA’s contractor, with staff continuing to encourage visitors to segregate recyclable material. - Segregation of recyclable material from residual waste sheds/skips continues, with bagged waste being diverted to the MBT facilities to enable recovery of more recyclable waste. | - Frizlands Lane RRC recycling rate for 2024/25 was 54.4% compared to 59.4% in 2023/24. There is no single clear reason for the decline, but this was similar across all ELWA sites. |
| LBBD -32 | The Book Exchange | - Established The Book Exchange kiosks at Community Hubs in the Borough for residents to donate and borrow books that otherwise. | - On track | - The Book Exchange reuse initiative has been successfully established at four Community Hubs and the Eastbrookend Discovery Centre, providing residents with accessible opportunities to share and reuse books. | - The five Book Exchange Facilities are well utilised by residents helping to divert reusable material from the recycling collection stream. |
| LBBD -33 | Small Electricals Collection Project | - This is a pilot study. - Small electricals recycling bins will be installed at 10 Community Hubs and other public locations across the borough to encourage recycling of small electrical items. | - On track | - The Small Waste Electrical and Electronic Equipment (WEEE) recycling pilot project was officially launched on 27th July 2024 during the One Borough Festival. - A total of 9 Small WEEE recycling bins have been installed at various community hubs and public locations, providing residents with convenient options to responsibly dispose of small electrical items. | - In 2024/25 over 1,120 electrical items were recycled during this pilot period, recovering around 620kg of recyclable electricals. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
|  | No new actions proposed for 2025-26 |  |  |  |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| LBBD - 35 | Commercial Recycling Service | LBBD offer commercial recycling service for businesses within the borough, collecting the same range of materials consistent with the household stream. The trade waste team will seek to increase uptake of recycling collection agreement with existing and new customers through intensive marketing drive. | To offer Commercial Recycling Service to 650 existing commercial waste customers. | March 2027 |
| LBBD - 36 | Food Waste Collection Vehicles | Procurement of Food Waste Collection Vehicles to enable food waste collection from households in the borough. Procurement of vehicles in process. | Project planning in progress. Phased roll out service to 58,000 kerb side properties during the first phase. | October 2026 - March 2027 |
| LBBD - 37 | Household Food Waste Containers | Procurement and distribution of Food Waste containers to households. Procurement of household food waste containers in process. Communication strategy for implementation of food waste service will be developed which will likely include printing of leaflets, circulation through council newsletters and social media handles. | Procurement and distribution of Food Waste containers to households prior to launch of service in October 2026. Potential delay to service launch could result in extended lead time for product delivery from suppliers due to existing demands. | October 2026 - March 2027 |
| LBBD - 38 | Food Waste Disposal | Disposal arrangement will be under the current ELWA contract with BIFFA subcontracted to ReFood. | Disposal arrangement will be under the current ELWA contract with BIFFA subcontracted to ReFood. | October/November 2026 |
| LBBD - 39 | Household recycling service provision | Align the number of materials collected to reflect simpler recycling requirements. LBBD already collects most of the items. Collection of further material streams such as flexible plastics will depend on processing capability of the waste disposal authority and MRFs, but this is most likely to be accommodated. | Aims to make recycling easier and effective thereby increasing amount of waste that is recycled and to support circular economy by reducing contamination and promote recycling rate. | October 2026 - March 2027 |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026