## Q1 2014-15
1) Number of jobs created through GLA Group investment and associated spend (ie. levered or match funded)
2013/14* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
50000 |  | 50785 |  |  | Our target is to create and support 200,000 jobs over the Mayoral term. By the end of 2013/14, we had created 95,131 jobs. Our prospects for achieving the target are GREEN.
JOBS |  | GREEN
Commentary
• From the information received to date, 95,131 jobs are estimated to have been created and supported across 2012/13 and 2013/14. It is estimated a further 105,000 jobs will be created over the remainder of the Mayoral term. That estimate is at this stage based on incomplete information. For instance, no information on jobs created has been received from MOPAC to date. There are other reporting gaps at present; for example, jobs within the Royal Docks Enterprise Zone and on GLA land that has been released. Taking this into account, the Mayor is on target to achieve his target of 200,000 jobs created. * Reported figures are estimates, as described in detail in the biannual reports to the Investment and Performance Board. The overall measure of jobs is consistent with that used in previous reports. However, a stricter methodology has been adopted in compiling jobs figures for some programme areas and accordingly there have been revisions to the data, including the 2012/13 outturn.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 7500 | 7500 | 17500 | 17500 |  | 50000 | 50000 | N/A | 200000
Actual
Forecast | 10265 | 10264 | 15743 | 15743 |  | 52015 | 52976 | N/A | 200122
Cumulative*
* Over the Mayoral term.
2) Number of new apprenticeships started
2013/14* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
56204 |  | 40710 |  |  | Our target is to see that 250,000 apprenticeship opportunities are created over the Mayoral term. So far, 84,590 have been created. Our prospects for achieving the target are AMBER.
APPRENTICESHIPS |  | AMBER
Commentary
• The most recent data for this KPI, from the Department for Business, Innovation and Skills, relates to quarter 4, 2013/14. Following the underachievement against the 2013/14 target, the forecast of future outputs is being reviewed and will be reported next time. • Activity to boost apprenticeships in London includes an imminent new marketing and awareness raising campaign and a direct mail / telemarketing campaign to increase the number of SME employers who create apprenticeships opportunities. • Discussion are taking place to determine the best use of additional resource for this area that were identified through the 2014/15 budget process. * The 2013/14 figures covers May 2013 to April 2014 and quarterly reporting is aligned accordingly. The outturn for that year is provisional as data will only be confirmed by BIS in January. Similarly, when reported 2014/15 figures will be provisional until confirmed.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 16720 | 16721 | 16722 | 16723 |  | 66882 | 79684 | N/A | 250000
Actual
Forecast | TBC | TBC | TBC | TBC |  | TBC | TBC | N/A | TBC
Cumulative*
* Over the Mayoral term.
3) Square metres of public realm improved or created through GLA investment and associated spend (ie. levered or match funded)
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
20031 |  | 32010 |  |  | Our target is to improve or create 80,124 sqm of public realm this year; in addition to 32,114 sqm in 2013/14. Our prospects for achieving the target are GREEN.
SQUARE METRES |  | GREEN
Commentary
• Together the OLF and MRF are investing £120m in London's high streets and their environs. Creating and improving public spaces is an important component of the Mayor's regeneration programmes. • Performance for quarter 1 is higher than projected as some projects that were expected to be completed in quarter 2 were in fact completed earlier. The quarter 2 forecast is, as a result, lower than the original target. • The quarter 1 actual includes improvements to the public realm in Bromley town centre and in Nunhead. Completed works on Tottenham High Road are also included in the data. * As a matter of course, the quarterly actual should be treated as provisional until the following quarter. This is because data may change somewhat if late returns from boroughs are received and following verification.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 20031 | 20031 | 20031 | 20031 |  | 80124 | 49887 | TBC | N/A
Actual | 32010
Forecast |  | 8052 | 20031 | 20031 |  | 80124 | 49887 | TBC | N/A
Cumulative* | 64124
* From the start of 2013/14.
4) The number of employers signed up to the London Living Wage (LLW)
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
10 |  | 85 |  |  | Our target was to see that 250 employers were signed up to the LLW over this Mayoral Term. Already, 378 employers have signed up. So we have MET THE TARGET well ahead of schedule.
ACCREDITED EMPLOYERS |  | GREEN
Commentary
• The Mayor's manifesto target was exceeded in 2013/14, well ahead of schedule. Strong performance has continued in the early part of this year and reflects in part that businesses have responded to the Mayor's letters encourage them to seek accreditation. However, the first is the busier half of the year, so performance is unlikely to remain at this level. * This count includes only those employers with London offices who are fully accredited with the Living Wage Foundation. It covers all sectors (including public sector/third sector). The count does not include businesses who pay the living wage but are not accredited.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 10 | 5 | 5 | 5 |  | 25 | 25 | N/A | 250
Actual | 85
Forecast |  | 30 | 30 | 10 |  | 155 | 50 | N/A | 498
Cumulative* | 378
* From the start of 2012/13.
5a) The number of young Londoners who are actively supported
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
839 |  | 2217 |  |  | Our target is to support 4,446 young Londoners this year - having supported 13,133 in 2013/14. Our prospects for achieving this target are GREEN.
YOUNG LONDONERS |  | GREEN
Commentary
• This KPI counts the number of young people supported by: the GLA's European Social Fund (ESF) Youth Programme; Mayor's Mentoring; Leadership Clubs; Championing Careers Guidance in Schools Pilot; Peer Outreach Team; Lynk Up Crew; and Earn Your Travel Back (EYTB) (the same projects contribute to part (b) of this indicator, except EYTB). • Performance exceeded the target in quarter 1. This is in main due to early reporting of young people who have benefited from the school-based careers guidance in London Academies Enterprise Trust (LAET) schools. In addition, recruitment to 'excluded from schools' ESF projects was almost double that expected. In both cases, outputs have been brought forward from future quarters. Forecast have been amended accordingly. * As flagged in the quarter 4 report, there have been changes to the KPI for 2014/15. Peer Outreach and Lynk Up Crew projects had not previously been counted towards this KPI. In addition, rather than reporting on the number of pupils attending LAET Academies, the KPI now reports those benefiting from the Championing Careers Guidance in Schools project in the Academies. The 2014/15 target has been amended since quarter 4. This is to reflect higher than expected performance in 2013/14.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 839 | 1528 | 1380 | 699 |  | 4446 | 122 | N/A | N/A
Actual | 2217
Forecast |  | 528 | 1007 | 694 |  | 4446 | 122 | N/A | N/A
Cumulative* | 15350
* From the start of 2013/14.
5b) The number of young Londoners supported into and achieving an improved and sustained outcome
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
763 |  | 733 |  |  | Our target is to support 2,972 young Londoners to achieve an improved and sustained outcome this year - having supported 7,846 in 2013/14. Our prospects for achieving this target are GREEN.
YOUNG LONDONERS |  | AMBER
Commentary
• 96% of the target was met, being short by just 30 young people. More young people were supported by the Mayor's Mentoring Programme than forecast and through the GLA's youth engagement work (Peer Outreach Team and Lynk Up Crew). However, not as many young people supported by the ESF programme sustained their employment or education for 6 months as anticipated. This is due in part to a delay in evidencing outcomes for young people on the excluded from schools projects. In addition, fewer than anticipated young ex-offenders and young people with learning difficulties sustained their employment or education. The GLA is working closely with delivery partners to meet challenging targets in respect of both these projects. * As highlighted in the quarter 4 report, there have been changes to the definition of this KPI for 2014/15 to improve consistency of reporting. In 2013/14 some sustained outcomes were counted at 6 months, others at 12 months. All are now counted at 6 months - as per the definition. The scope of the KPI has also been extended to include the Peer Outreach and Lynk Up Crew projects.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 763 | 339 | 438 | 1432 |  | 2972 | 743 | N/A | N/A
Actual | 733
Forecast |  | 339 | 438 | 1462 |  | 2972 | 743 | N/A | N/A
Cumulative* | 15350
* From the start of 2013/14.
5c) The number of schools supported to improve their practice
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1168 |  | 2451 |  |  | Our target is to support 3,700 schools to improve their practice this year, thereby boosting standards in the capital's schools. So far, we have supported 2,451 schools. Our prospects for achieving the target are GREEN.
SCHOOLS |  | GREEN
Commentary
• This is a new KPI counting the number of schools supported through: the 100 projects funded by the London Schools Excellence Fund (LSEF) to support teaching excellence; the London Curriculum, which draws on London itself and its heritage to support teaching under the new National Curriculum; and the Gold Club, which identifies and shares lessons from those schools 'bucking the trend'. All 3 initiatives flow from the Mayor's Education Inquiry and collectively aim to boost standards in the capital's schools. • The number of schools supported through the LSEF exceeded the quarter 1 target. The quarter 4 forecast is now lower than the target, as it is likely that outputs have been brought forward. * Note that a school may be counted more than once if it participates in more than one of the 100 LSEF projects and/or the Gold Club and London Curriculum.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 20014-16
Target | 1168 | 17 | 47 | 2468 |  | 3700 | 67 | N/A | 3767
Actual | 2451
Forecast |  | 17 | 47 | 1185 |  | 3700 | 67 | N/A | 3767
Cumulative* | 2451
* From the start of 2014/15.
6) GLA Group sites identified for new schools
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target was to identify 10 GLA Group sites for new schools over this Mayoral Term. By the end of 2013/14, 11 sites had already been identified. So we have MET THE TARGET ahead of schedule.
GLA SITES |  | GREEN
Commentary
• In 2011, the Mayor launched the Education Inquiry: an independent investigation into the successes of and challenges for London schools. Support for free schools was one of the Inquiry's twelve recommendations. The Inquiry also highlighted the increasing pressure on school places in the capital. In addition, the Mayor made a Manifesto commitment in 2012 to use GLA Group assets to secure sites for ten free schools. • So far, the Mayor has freed up public land and property to enable the delivery of 11 schools in the capital, providing places for around 7,300 pupils. The new schools will be developed in former police stations, on GLA land and in Queen Elizabeth Olympic Park. They include 7 primaries; one secondary; one 16-19 school; one 14-19 school; and one all-through school. Nine will be free schools, one a new University Technical College and one a new Academy. Seven sites are located in boroughs ranked in the top 10 most deprived in England. * Ten of 11 announced sites have been completed on. Since one is yet to be completed, the 2013/14 data is unconfirmed at this stage. Note also the 2013/14 outturn has been updated from 10 to 11.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 0 | 1 | 0 | 1 |  | 2 | 1 | N/A | 10
Actual | 0
Forecast |  | 1 | 0 | 1 |  | 2 | 1 | N/A | 13
Cumulative* | 11
* From the start of 2012/13.
7) Number of volunteering opportunities taken up by volunteers through Team London
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
8750 |  | 13622 |  |  | Our target is for 100,000 volunteering opportunities to be taken up over 2013-16. So far, 32,313 opportunities have been taken up. Our prospects for achieving the target are GREEN.
VOLUNTEERS |  | GREEN
Commentary
• Performance is ahead of target. This is partly due to the number of events that have been held that required volunteers and who have been recruited through Team London, such as the London stage of the Tour De France. Also contributing strongly to performance were the number of adult and young volunteers active in the Team London School Ambassadors programme (4,103) and through projects supported by the final tranche of last year's Small Grants initiative (3,148). In addition, Metropolitan Police Service volunteering figures are now being consistently incorporated into this KPI, in the form of Special Constables and Met Volunteers. * There is an element of estimation involved in calculating these figures. Figures for volunteering through the Team London brokerage website are derived by applying a conversion ratio to the number of applications. The conversation rate is calculated by a sample study of activity with charities registered with the website. Note also that quarterly figures are provisional when first reported, pending in some cases final confirmation of numbers from GLA teams and external organisations.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 8750 | 8750 | 8750 | 8750 |  | 35000 | 48000 | N/A | 100000
Actual | 13622
Forecast |  | 8750 | 8750 | 8750 |  | 39872 | 48000 | N/A | 106563
Cumulative* | 32313
* From the start of 2013/14.
8) Number of Londoners participating in sport or physical activity through the Mayor's Sports Legacy Programme: Phase 2
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
6276 |  | 7378 |  |  | Our target is for 62,263 Londoners to participate in sport or physical activity between 2013 and 2016. So far, there have been 12,878 participants. Our prospects for achieving the target are GREEN.
PARTICIPANTS |  | GREEN
Commentary
• Performance exceeded the quarter 1 target. Two projects are currently short of their individual targets; but these shortfalls have been offset at programme level by the over-performance of other projects. * This KPI measures outputs through the Make a Splash and the Mayor's FreeSport projects, as well participation projects funding through phase 2 of the Mayor's Sports Legacy Programme. Since the quarter 4 report, final targets have been set for this KPI, based on signed funding agreements, and are shown below.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 6276 | 7916 | 14941 | 3415 |  | 32548 | 23850 | N/A | 62263
Actual | 7378
Forecast |  | 7916 | 14941 | 3415 |  | 33650 | 23850 | N/A | 63000
Cumulative* | 12878
* Since 2013/14.
9) The number of street trees planted through the Mayor's street trees initiative
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to plant 10,000 street trees over 2012-15. At the end of 2013/14, we had planted 6,314 against an interim target of 7,850. Our prospects for meeting the overall target, however, are GREEN.
STREET TREES |  | AMBER
Commentary
• Overall, 6,314 street trees were planted in rounds 1 and 2. The window for applications for round 3 funding closed in August and bids for funding for 6,000 street trees have been received. This round will see at least 3,700 trees planted, meeting the Mayor's target. The planting season is in the winter. Therefore the remaining trees will all be planted in quarter 4. • Over and above the street tree planting being reported on by this KPI, 10,221 street trees were planted in 2008-12. * The 2014/15 target has been amended from that previously reported to reflect that fewer trees were planted in 2013/14 than initially expected - the deficit will be made up this financial year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 3700 |  | 3700 | N/A | N/A | 10000
Actual | 0
Forecast |  | 0 | 0 | 4000 |  | 4000 | N/A | N/A | 10314
Cumulative* | 6314
* From the start of 2012/13.
10a) The number of pocket parks established
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5 |  | 9 |  |  | Our target is to create or improve 100 pocket parks over 2012-15. To quarter 1 2014/15, we had established 12 - somewhat short of interim targets. Our prospects for meeting the overall target, however, are GREEN.
POCKET PARKS |  | GREEN
Commentary
• Eighteen pocket parks have now been completed (including 8 so far in quarter 2) and funding agreements are in place to ensure the target of 100 pocket parks will be delivered by March 2015 - hence the green traffic light despite falling short of the 2013/14 target. * The 2014/15 target has been amended since the quarter 4 report to reflect that some parks will be completed this financial year rather than in 2013/14 as previously envisaged.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 5 | 20 | 50 | 23 |  | 98 | N/A | N/A | 100
Actual | 9
Forecast |  | 9 | 18 | 61 |  | 97 | N/A | N/A | 100
Cumulative* | 12
* From the start of 2013/14.
10b) The area of green space created or restored in acres through the Big Green Fund
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to create or restore 300 acres of green space by March 2015. Delivery has begun this year and our prospects for meeting the overall target are GREEN.
ACRES |  | GREEN
Commentary
• Six projects funded through the Big Green Fund will meet the target of improving 300 acres of green space. The projects are not due to be completed until March 2015 - hence the profiling of targets. • Four of the 6 projects are currently in delivery. The other 2 are at final design stage and agreements to define the scope of works were, at the time of writing, expected to be in place shortly.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Actual | 0
Forecast |  | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Cumulative* | 0
* From the start of 2013/14.
11a) Tonnes of CO2 saved as a direct result of Mayoral homes efficiency programmes
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to save 141,217 tonnes of CO2 over 2009-17. So far, we have saved 25,821 - short of interim targets. However, we rate our prospects of meeting the overall target as GREEN.
TONNES CO2 |  | AMBER
Commentary
• RE:NEW is a pan-London home energy retrofit scheme aimed at reducing CO2 emissions in the domestic sector, cutting fuel bills and alleviating fuel poverty. RE:NEW Phase III takes a new strategic approach, through which technical assistance to support retrofit is provided by a RE:NEW Support Team. • RE:NEW has been awarded funding of ¤3,016,440 from the European Investment Bank (EIB) European Local Energy Assistance (ELENA) facility under a 3-year contract that came into force in July. The GLA has provided a match of 10%. The GLA entered into a contract with Capita in July and services under the contract have commenced. * This KPI is an estimates based on the expected average savings per home. Figures are reported at the time a contract that has received support from the RE:NEW Suppor Team is let. However, figures remain unconfirmed until the contract has been implemented. The 2013/14 outturn is at this stage unconfirmed. Note that targets have been revised. Changes reflect delays in entering into contracts with the EiB and Capita and take account of the 2013/14 provisional outturn. The result is a delayed start in 2014/15 with over-delivery in the following 2-years compared with previous targets. There will also now be 4 months of delivery in 2017/18.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-18
Target | 0 | 666 | 3667 | 5333 |  | 9666 | 36834 | 36500 | 118821
Actual | 0
Forecast |  | 666 | 3667 | 5333 |  | 9666 | 36834 | 36500 | 118821
Cumulative* | 25821
* Since 2009/10.
11b) Tonnes of CO2 saved as a direct result of Mayoral workplace energy efficiency programmes
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
4219 |  | 9181 |  |  | Our target is to save 45,427 tonnes of CO2 over 2009-16. So far, we have saved 37,809 - ahead of interim targets. We rate our prospects of meeting the overall target as GREEN.
TONNES CO2 |  | GREEN
Commentary
• RE:FIT is a ready-to-use, cost neutral procurement initiative that allows public sector organisations to retrofit existing buildings with energy efficiency measures, reduce carbon emissions and achieve substantial guaranteed annual cost savings. • In quarter 1, 9,181 tonnes of carbon were saved across 39 projects. The over-achievement against the target is mainly the result of signing a large contract with LB Croydon. Options to secure the future of RE:FIT beyond March 2015 have been finalised and are being reviewed. * Estimated carbon savings are recorded once the building contract has been signed and include all contracted carbon through RE:FIT, schools and GLA buildings. The suppliers of the RE:FIT framework have an obligation to report on actual installed measures on a yearly basis. Figures for 2013/14 and this year are therefore subject to change at this stage. Note also since the previous report, the 2014/15 target has been updated to reflect the pipeline of projects. The lifetime target has been amended to align with the Climate Change Mitigation and Energy Strategy.
| This Year | [5 empty] | Future Years |  | Lifetime**
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-16
Target | 4219 | 4219 | 4219 | 4220 |  | 16887 | 13023 | N/A | 45427
Actual | 9181
Forecast |  | 6578 | 6578 | 6578 |  | 28915 | 13023 | N/A | 70566
Cumulative* | 37809
* Since 2009/10. ** To June 2015.
11c) Tonnes of CO2 saved as a direct result of Mayoral energy supply programmes
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1212.25 |  | 1212.25 |  |  | Our target is to save 156,000 tonnes of CO2 over 2010-21. To date, we have met interim targets and we rate our prospects of meeting the overall target as AMBER.
TONNES CO2 |  | GREEN
Commentary
• Reported carbon savings flow from: a) The Gospel Oak combined heat and power (CHP) project, operating since quarter 1 2013/14 and saving 2,890 tonnes of CO2 per year (723 per quarter); b) The Crystal Palace CHP project, operating since quarter four 2010/11 and saving an estimated 1,850 tCO2/year (463 per quarter); c) The Olympic Fringe project, operating since quarter one 2014/15 and contributing the remaining (estimated) savings. • All future CO2 savings will be indirect and achieved if/when each of the decentralised energy projects taken to market by the GLA is implemented (by others). It is assumed indirect CO2 savings will start to be achieved from 2015/16; though they are not yet factored into targets. The GLA is not accountable for the construction and operation of the projects. * As described, savings from (b) and (c) above are estimated at this stage.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2010-21
Target | 1212.25 | 1212.25 | 1212.25 | 1212.25 |  | 4849 | 4893 | 4903 | 156000
Actual | 1212.25
Forecast |  | 1212.25 | 1212.25 | 1212.25 |  | 4849 | 4892 | 4903 | 156000
Cumulative* | 37809
* Since 2009/10.
12) The number of affordable homes delivered
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
300 |  | 463 |  |  | Our target is to deliver 100,000 affordable homes over two Mayoral Terms. So far, we have delivered 77,058 and we are meeting interim targets. We rate our prospects of meeting the overall target as GREEN.
AFFORDABLE HOMES |  | GREEN
Commentary
• The outturn for quarter 1 is historically low due to the volume of outputs that are delivered at the end of the previous financial year. Performance is, however, above target and officers are working closely with providers to ensure as many completions as possible are delivered. • Performance is also on track to meet the 100,000 homes target. However, the profile of delivery over 2014/15 is heavily backloaded to the final quarter. This presents a risk. The GLA is carefully managing project delivery to mitigate this risk. Slippage within year will be managed through substitutions. • New programme allocations for the 2015-18 programme were announced in July and will contribute towards delivery of the Mayor's housing targets. * Note that the 2013/14 outturn has been updated since reported at quarter 4 (from 8,792); the figure is unconfirmed as it includes an estimate of those outputs monitored by DCLG (a figure of 700 has been assumed). Note also that the 2015/16 target has been amended from that published in the Business Plan, which was set prior to the 2013/14 outturn being available.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2008-16
Target | 300 | 300 | 2000 | 15290 |  | 17890 | 4815 | N/A | 100000
Actual | 463
Forecast |  | 300 | 2000 | 15827 |  | 18590 | 4815 | N/A | 100000
Cumulative* | 77058
* Since May 2008.
13) The number of council homes made decent
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
336 |  | 336 |  |  | We aim to bring 45,000 homes up to the decent homes standard over 2011-15. We are meeting interim targets and so far have made 38,176 homes decent. We rate our prospects for meeting the overall target as GREEN.
HOMES |  | GREEN
Commentary
• The 2011-15 programme is rated green as there are no issues with boroughs being able to meet their allocations: the programme is on track to bring 45,000 homes to decent standard. * Annual outturns have been confirmed by boroughs and reported to DCLG. Past data has been amended to ensure consistent report of decent homes figures, with figures no longer reported a quarter in arrears. However, the effect is that reported quarterly data will be subject to change and confirmation in the subsequent quarter's report. In addition, the 2014/15 target has been reduced; again to bring consistency to GLA reporting, but also due to funding being brought forward from 2014/15 into 2013/14 which accelerated delivery last year. The lifetime target is unchanged.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2011-15
Target | 336 | 600 | 1179 | 5045 |  | 7160 | N/A | N/A | 45000
Actual | 336
Forecast |  | 600 | 1179 | 5045 |  | 7160 | N/A | N/A | 45000
Cumulative* | 38176
* For the 2011-15 programme, to date.
14) Percentage of rough sleepers who did not spend a second night out as a result of the GLA-funded NSNO service
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 91% |  |  | Our target is that 90% of rough sleepers seen by NSNO do not spend a second night out in the same quarter. We met the target this quarter. Our prospects of continuing to meet the target are AMBER.
OF ROUGH SLEEPERS |  | GREEN
Commentary
• Quarter 1 performance has been rated as green as the target of 90 per cent has been met - 481 rough sleepers were seen by the service and 440 did not spend a second night out. This is an improvement on quarter 4 last year, when performance was 88 per cent. • No Second Night Out and No Living on the Street will in future be co-located and co-staffed. This will result in efficiency savings that can be ploughed back in to the service to help ensure that targets continue to be met. * Quarterly figures relate to rough sleepers seen by the service during the quarter in question and the proportion of those who did not spend a second night out during that same quarter. Annual figures relate to rough sleepers seen by the service in the year and the proportion those who did not spend a second night out during the same year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Actual | 91%
Forecast |  | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Cumulative*
* Since 2009/10.
15) Release of GLA land in hectares
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0.33223 |  | 0.3 |  |  | Our target is to release 198 hectares of GLA land over 2012-15. So far, we have released 148 hectares - somewhat behind interim targets. Our prospects for meeting the overall target are AMBER.
HECTARES |  | AMBER
Commentary
• The target in 2013/14 was not met because some sites did not enter contract within the expected timeframe. The most significant (circa 8 hectares) relates to White Hart Triangle, where there have been protracted negotiations with TfL/Crossrail. • The rating is amber because there is always a risk of delays to completion of sales or signing of development agreements. Meeting forecasts is also reliant on Housing Investment Group approval for the disposal of sites. • Project managers are working to ensure development agreements are being progressed and new sites are being marketed effectively. * Based on the above risks, and due to slippage from 2013/14, contract dates have been reviewed and amended and the 2014/15 target has increased - in line with the overall business plan target.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0.33223 | 5.7 | 16.3 | 28.5 |  | 50.8322 | N/A | N/A | 198
Actual | 0.3
Forecast |  | 10.7151 | 11.291 | 28.506 |  | 50.512 | N/A | N/A | 198
Cumulative* | 147.5
* From the start of 2012/13.
16) Value of match funding from partner bodies as a result of GLA investment through the MRF and OLF
2013/14* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
4799170 |  | 15592054 |  |  | Our target is £61.3m of match funding over 2012-17. To the end of 13/14, match funding had totalled £24.3m - somewhat behind our interim target. Our prospects of meeting the overall target are GREEN.
£ MATCH FUNDING |  | AMBER
Commentary
• Performance data for quarter 1 is delayed due to the process of re-profiling grant agreements. It is expected that both quarters 1 and 2 performance will be available for the next report. • As the remainder of MRF projects enter grant agreement this financial year, the aggregate level of match funding commitments will increase, contributing to achievement of the overall target. * 2013/14 performance has been amended following final verification. The lifetime match funding target has been reprofiled across financial years following changes to approvals and slippage from 2013/14 into future years. The target has also reduced slightly, from that reported in the Business Plan, due to a change in match funding arrangements for the Croydon programme.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-17
Target | 2058500 | 2058500 | 4117000 | 8234000 |  | 16468000 | 10741579 | 9775000 | 61298411
Actual
Forecast | 2058500 | 2058500 | 4117000 | 8234000 |  | 16468000 | 10741579 | 9775000 | 61298411
Cumulative*
* Since 2012/13.
17) The return on investment made to secure outside sponsorship
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
N/A |  | 5.9904 |  |  | Our target is that there is a return on the investment to secure sponsorship over 2012-15 of a factor of 7. We are meeting interim targets and our prospects for meeting the overall target are AMBER.
RETURN AS RATIO |  | GREEN
Commentary
• At end of quarter 1, the value of sponsorship agreed for the year was £1.3m. The majority was generated from multi-year and prospective deals agreed in the preceding financial year. The value is expected to rise to £1.8m by the end of quarter 2, giving an income to cost ratio of 8.25:1. The majority of the additional income will be generated from two multi-year deals for Team London Young Ambassadors and HeadStart. • The key risk to achieving the target is securing corporate partners to sponsorship opportunities that add value to both parties. The Commercial Partnerships Team (CPT) will work with Jack Morton to identify a headline sponsor for New Year’s Eve and will identify partners to support other Mayoral programmes. * It is not possible to profile this KPI across the year so there are no quarterly targets. In-year figures may include sponsorship income from contracts not yet signed / not yet paid. The cost element of the KPI - the annual spend of the CPT - is the budgeted figure. Data will not be confirmed until after year-end, based on actual income received and the actual spend on the CPT.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | N/A | N/A | N/A | 10 |  | 10 | N/A | N/A | 7
Actual | 5.9904
Forecast |  | 8.3 | TBC | TBC |  | 10 | N/A | N/A | 7
Cumulative* | 147.5
* From the start of 2012/13.
18) The percentage of invoices from small and medium sized enterprises (SMEs) paid within ten days
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 92% |  |  | Our target is to pay 90% of all invoices from SMEs within 10 days. In the past quarter, we paid 92% of SME invoices within the set time. We rate our prospects of meeting the target over the medium-term as GREEN.
% OF INVOICES |  | GREEN
Commentary
• Performance is consistent with that achieved in the previous financial year. * This KPI is measured according to SAP periods, so does not precisely follow a quarterly timetable.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 92%
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Cumulative*
* Over this financial year.
19) Average number of working days per GLA employee lost to sickness absence
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5.9 |  | 2.75 |  |  | Our target is keep staff sickness absence at less than 5.9 days per year. Over the past 12 months the average number of days was 2.8. We rate our prospects of meeting the target over the medium-term as GREEN.
DAYS |  | AMBER
Commentary
• Performance remains better than target and that of comparator groups. However, we continue to have concerns about the data reported from the sickness absence system. Procurement of a new, more robust system will take longer than originally envisioned, but is otherwise progressing well. It will go live for the start of 2015/16. • In the meantime, manual consistency checks are being undertaken and suggest the reported figure is broadly in line with expectations. • The new system will support self-reporting of absence. It is unclear at this stage what impact this will have on the completeness of the data. However, this will be monitored closely. * This KPI is measured over a rolling year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 5.9 | 5.9 | 5.9 | 5.9 |  | 5.9 | 5.9 | 5.9 | N/A
Actual | 2.75
Forecast |  | 3.4 | 3.4 | 3.4 |  | 3.4 | 5.9 | 0.9 | N/A
Cumulative*
* Over this financial year.
20) The percentage of correspondence responded to in full in 20 working days
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 88% |  |  | Our target is to respond to 90% of correspondence within 20 days. In the past quarter, we responded to 88% of correspondence within 20 days. Our prospects of meeting the target over the medium-term as AMBER.
% CORRESPONDENCE |  | AMBER
Commentary
• Performance is consistent with that achieved in the previous financial year. * This KPI is measured according to SAP periods, so does not precisely follow a quarterly timetable.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 88%
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Cumulative*
* Over this financial year.

## Q2 2014-15
1) Number of jobs created through GLA Group investment and associated spend (ie. levered or match funded)
2013/14* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
50000 |  | 50785 |  |  | Our target is to create and support 200,000 jobs over the Mayoral term. By the end of 2013/14, we had created 95,100 jobs. Our prospects for achieving the target are GREEN.
JOBS |  | GREEN
Commentary
• From the information received to date, 95,100 jobs are estimated to have been created and supported across 2012/13 and 2013/14. It is estimated a further 105,000 jobs will be created over the remainder of the Mayoral term. That estimate is at this stage based on incomplete information. For instance, no information on jobs created has been received from MOPAC to date. There are other reporting gaps at present; for example, jobs within the Royal Docks Enterprise Zone and on GLA land that has been released. Taking this into account, the Mayor is on target to achieve his target of 200,000 jobs created. • This KPI is reported biannually. Data will next be collated in December. * Reported figures are estimates, as described in detail in the biannual reports to the Investment and Performance Board.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 7500 | 7500 | 17500 | 17500 |  | 50000 | 50000 | N/A | 200000
Actual
Forecast | 10265 | 10264 | 15743 | 15743 |  | 52015 | 52976 | N/A | 200121
Cumulative*
* Over the Mayoral term.
2) Number of new apprenticeships started
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
16720 |  | 10720 |  |  | Our target is to see that 250,000 apprenticeship opportunities are created over the Mayoral term. So far, 95,310 have been created. Our prospects for achieving the target are AMBER.
APPRENTICESHIPS |  | AMBER
Commentary
• Activity to boost apprenticeships in London includes the new marketing and awareness raising campaign, launched in September, and a direct mail/ telemarketing campaign to increase the number of SME employers who create apprenticeships opportunities. • A £2 million budget for an Employer-led Apprenticeship Programme has been approved and is expected to create an additional 4,000 apprenticeships in London. • An enhanced Apprenticeship Grant for Employers incentive will be made available to SMEs from January 2015. * The 2013/14 figures covers May 2013 to April 2014 and quarterly reporting is aligned accordingly. The outturn for that year is provisional subject to confirmation from the Department for Business, Innovation and Skills. Similarly, when reported, 2014/15 figures will be provisional until they are confirmed after year-end. This is because learning providers do not always submit data in time for it to be included in quarterly figures - despite data being reported 3 months in arrears.
| This Year (May to April) | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 16720 | 16720 | 16721 | 16721 |  | 66882 | 79684 | N/A | 250000
Actual | 10720
Forecast | 14950 | 14950 | 15996 | 18887 |  | 60553 | TBC | N/A | TBC
Cumulative* | 95310
* Over the Mayoral term.
3) Square metres of public realm improved or created through GLA investment and associated spend (ie. levered or match funded)
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
41110 |  | 40062 |  |  | Our target is to improve or create 80,124 sqm of public realm this year; in addition to 32,114 sqm in 2013/14. Our prospects for achieving the target are GREEN.
SQUARE METRES |  | GREEN
Commentary
• Together the Outer London Fund (OLF) and Mayor's Regeneration Fund are investing £120m in London's high streets and their environs. Creating and improving public spaces is an important component of the Mayor's regeneration programmes. • Projects completed in quarter 2 include improvements to the public realm in Northwood Hills and Hounslow High Street. • As the target was profiled evenly across the year, it will be the case that in some quarters performance exceeds the target and in others it falls short. Performance in quarter 2 was, however, higher than forecast and we are on track to meet the annual target. * As a matter of course, the quarterly actual should be treated as provisional until the following quarter. This is because data may change somewhat if late returns from boroughs are received and following verification.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 20031 | 20031 | 20031 | 20031 |  | 80124 | 49887 | TBC | N/A
Actual | 32010 | 9100
Forecast |  | 8052 | 20031 | 20031 |  | 80124 | 49887 | TBC | N/A
Cumulative* | 64124 | 73224
* From the start of 2013/14.
4) The number of employers signed up to the London Living Wage (LLW)
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
15 |  | 136 |  |  | Our target was to see that 250 employers were signed up to the LLW over this Mayoral Term. Already, 429 employers have signed up. So we have MET THE TARGET well ahead of schedule.
ACCREDITED EMPLOYERS |  | GREEN
Commentary
• The Mayor's manifesto target was exceeded in 2013/14, well ahead of schedule. Strong performance has continued in the first half of this year and reflects in part that businesses have responded to the Mayor's letters encourage them to seek accreditation. However, the first is the busier half of the year, so performance is unlikely to remain at this level. * This count includes only those employers with London offices who are fully accredited with the Living Wage Foundation. It covers all sectors (including public sector/third sector).
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 10 | 5 | 5 | 5 |  | 25 | 25 | N/A | 250
Actual | 85 | 51
Forecast |  | 30 | 30 | 10 |  | 176 | 50 | N/A | 498
Cumulative* | 378 | 429
* From the start of 2012/13.
5a) The number of young Londoners who are actively supported
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
2367 |  | 5253 |  |  | Our target is to support 4,446 young Londoners this year - having supported 13,133 in 2013/14. At the mid-year point, we have already MET THE TARGET for 2014/15.
YOUNG LONDONERS |  | GREEN
Commentary
• Projects are performing well and the annual target has already been exceeded. The European Social Fund (ESF) Youth programme has supported over 1,000 young people this year against an annual target of 694. The Championing Careers Guidance programme has also exceeded its annual target and is not forecast to support any more young people. Future forecasts have been reduced accordingly. * This KPI counts the number of young people supported by: the GLA's ESF Youth Programme; Mayor's Mentoring; Leadership Clubs; Championing Careers Guidance in Schools Pilot; Peer Outreach Team; Lynk Up Crew; and Earn Your Travel Back (EYTB). Note that the quarter 1 actual includes some mentoring outputs which were delivered but not counted in 2013/14. This is to ensure the KPI is representative of actual, overall performance.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 839 | 1528 | 1380 | 699 |  | 4446 | 122 | N/A | N/A
Actual | 2217 | 3036
Forecast |  | 528 | 167 | 10 |  | 5430 | 122 | N/A | N/A
Cumulative* | 15350 | 18386
* From the start of 2013/14.
5b) The number of young Londoners supported into and achieving an improved and sustained outcome
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1102 |  | 2736 |  |  | Our target is to support 2,972 young Londoners to achieve an improved and sustained outcome this year - having supported 7,846 in 2013/14. Our prospects for achieving this target are GREEN.
YOUNG LONDONERS |  | GREEN
Commentary
• The Championing Careers Guidance programme reported sustained outcomes earlier than anticipated - and with nearly 50% more young people continuing in education or employment than expected. The Leadership Clubs project also reported outcomes earlier than forecast and exceeded its target. • The number of young people sustaining employment or education after being supported through ESF programmes is improving and the project is forecast to meet its annual target. • Future forecasts have been updated to reflect the above. We expect to exceed the annual target. * The scope of this KPI is the same as KPI 5a, except that EYTB is not relevant.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 763 | 339 | 438 | 1432 |  | 2972 | 743 | N/A | N/A
Actual | 733 | 2003
Forecast |  | 339 | 339 | 512 |  | 3587 | 743 | N/A | N/A
Cumulative* | 8579 | 10582
* From the start of 2013/14.
5c) The number of schools supported to improve their practice
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1185 |  | 2543 |  |  | Our target is to support 3,700 schools to improve their practice this year, thereby boosting standards in the capital's schools. So far, we have supported 2,543 schools. Our prospects for achieving the target are GREEN.
SCHOOLS |  | GREEN
Commentary
• This KPI was introduced for 2014/15 to count the number of schools supported through: the 100 projects funded by the London Schools Excellence Fund (LSEF) to support teaching excellence; the London Curriculum, which draws on London itself and its heritage to support teaching under the new National Curriculum; and the Gold Club, which identifies and shares lessons from those schools 'bucking the trend'. All 3 initiatives flow from the Mayor's Education Inquiry and collectively aim to boost standards in the capital's schools. • The number of schools supported through the LSEF has to date exceeded targets. The forecast have been amended as some outputs have been brought forward from future quarters. * Note that a school may be counted more than once if it participates in more than one of the 100 LSEF projects and/or the Gold Club and London Curriculum. The quarter one actual includes outputs carried over from 2013/14. This is to ensure reported performance is representative of the total number of schools supported (and given the KPI did not exist in 2013/14).
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 20014-16
Target | 1168 | 17 | 47 | 2468 |  | 3700 | 67 | N/A | 3767
Actual | 2451 | 92
Forecast |  | 17 | 47 | 1185 |  | 3700 | 67 | N/A | 3767
Cumulative* | 2451
* From the start of 2014/15.
6) GLA Group sites identified for new schools
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target was to identify 10 GLA Group sites for new schools over this Mayoral Term. By the end of 2013/14, 11 sites had already been identified. So we have MET THE TARGET ahead of schedule.
GLA SITES |  | GREEN
Commentary
• In 2011, the Mayor launched the Education Inquiry: an independent investigation into the successes of and challenges for London schools. Support for free schools was one of the Inquiry's twelve recommendations. The Inquiry also highlighted the increasing pressure on school places in the capital. In addition, the Mayor made a Manifesto commitment in 2012 to use GLA Group assets to secure sites for ten free schools. • So far, the Mayor has freed up public land and property to enable the delivery of 11 schools in the capital, providing places for around 7,300 pupils. The new schools will be developed in former police stations, on GLA land and in Queen Elizabeth Olympic Park. They include 7 primaries; one secondary; one 16-19 school; one 14-19 school; and one all-through school. Nine will be free schools, one a new University Technical College and one a new Academy. Seven sites are located in boroughs ranked in the top 10 most deprived in England. * Ten of 11 announced sites have been completed on. Since one is yet to be completed, the 2013/14 data is unconfirmed at this stage. Note also the 2013/14 outturn has been updated from 10 to 11.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 0 | 1 | 0 | 1 |  | 2 | 1 | N/A | 10
Actual | 0 | 0
Forecast |  | 1 | 0 | 1 |  | 2 | 1 | N/A | 13
Cumulative* | 11
* From the start of 2012/13.
7) Number of volunteering opportunities taken up by volunteers through Team London
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
17500 |  | 22307 |  |  | Our target is for 100,000 volunteering opportunities to be taken up over 2013-16. So far, 41,000 opportunities have been taken up. Our prospects for achieving the target are GREEN.
VOLUNTEERS |  | GREEN
Commentary
• The Small Grants programme finished in July. A total of 4,500 volunteers were engaged and together volunteered for 57,731 hours. 82% rated their experience as 7 or above out of 10. The total funding for the project through Team London totalled £100,000 to 10 organisations. • Team London is on track to meet the annual target. The launch of the 'speed-volunteering' initiative in quarter 3 is expected to boost volunteering numbers considerably. * There is an element of estimation involved in calculating these figures. Figures for volunteering through the Team London brokerage website are derived by applying a conversion ratio to the number of applications. The conversation rate is calculated by a sample study of activity with charities registered with the website. Note also that quarterly figures are provisional when first reported, pending in some cases final confirmation of numbers from GLA teams and external organisations. On this basis, quarters 1 and 2 data are still unconfirmed. 2013/14 data are, however, final.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 8750 | 8750 | 8750 | 8750 |  | 35000 | 48000 | N/A | 100000
Actual | 13622 | 8685
Forecast |  | 8750 | 8750 | 8750 |  | 39807 | 48000 | N/A | 106498
Cumulative* | 32313 | 40998
* From the start of 2013/14.
8) Number of Londoners participating in sport or physical activity through the Mayor's Sports Legacy Programme: Phase 2
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
14192 |  | 15722 |  |  | Our target is for 62,263 Londoners to participate in sport or physical activity between 2013 and 2016. So far, there have been 21,222 participants. Our prospects for achieving the target are GREEN.
PARTICIPANTS |  | GREEN
Commentary
• While performance varies from project to project, with some picking up the slack of others, performance across the programme is exceeding targets. * This KPI measures outputs through the Make a Splash and the Mayor's FreeSport projects, as well participation projects funding through phase 2 of the Mayor's Sports Legacy Programme. Since the quarter 4 report, final targets have been set for this KPI, based on signed funding agreements, and are shown below.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 6276 | 7916 | 14941 | 3415 |  | 32548 | 23850 | N/A | 62263
Actual | 7378 | 8344
Forecast |  | 7916 | 14941 | 3415 |  | 34078 | 23850 | N/A | 63428
Cumulative* | 12878 | 21222
* Since 2013/14.
9) The number of street trees planted through the Mayor's street trees initiative
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to plant 10,000 street trees over 2012-15. At the end of 2013/14, we had planted 6,314 against an interim target of 7,850. Our prospects for meeting the overall target, however, are GREEN.
STREET TREES |  | AMBER
Commentary
• Overall, 6,314 street trees were planted in rounds 1 and 2. The grant assessment panel for round 3 met on 30 September. Funding for 4,278 street trees was allocated, subject to funding agreements being signed. This means the programme is on track to meet the Mayor's target of planting an additional 10,000 street trees. • The planting season is in the winter. Therefore the remaining trees will all be planted in quarter 4. • Over and above the street tree planting being reported on by this KPI, 10,221 street trees were planted in 2008-12.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 3700 |  | 3700 | N/A | N/A | 10000
Actual | 0 | 0
Forecast |  | 0 | 0 | 4278 |  | 4278 | N/A | N/A | 10592
Cumulative* | 6314 | 6314
* From the start of 2012/13.
10a) The number of pocket parks established
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5 |  | 9 |  |  | Our target is to create or improve 100 pocket parks over 2012-15. To quarter 2 2014/15, we had established 29. Our prospects for meeting the overall target are GREEN.
POCKET PARKS |  | GREEN
Commentary
• Twenty-nine pocket parks have now been completed and funding agreements are in place to ensure the target of 100 pocket parks will be delivered by March 2015.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 5 | 20 | 50 | 23 |  | 98 | N/A | N/A | 100
Actual | 9 | 17
Forecast |  | 9 | 18 | 61 |  | 97 | N/A | N/A | 100
Cumulative* | 12 | 29
* From the start of 2013/14.
10b) The area of green space created or restored in acres through the Big Green Fund
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to create or restore 300 acres of green space by March 2015. Delivery has begun this year and our prospects for meeting the overall target are GREEN.
ACRES |  | GREEN
Commentary
• Six projects funded through the Big Green Fund will meet the target of improving 300 acres of green space. The projects are not due to be completed until March 2015 - hence the profiling of targets. • Four of the 6 projects are currently in delivery. The other 2 are at final design stage and agreements to define the scope of works were, at the time of writing, expected to be in place shortly.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Actual | 0 | 0
Forecast |  | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Cumulative* | 0 | 0
* From the start of 2013/14.
11a) Tonnes of CO2 saved as a direct result of Mayoral homes efficiency programmes
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
666 |  | 2827 |  |  | Our target is to save 141,217 tonnes of CO2 over 2009-17. So far, we have saved 28,648 tonnes. We rate our prospects of meeting the overall target as GREEN.
TONNES CO2 |  | GREEN
Commentary
• The RE:NEW Support Team is now engaging with organisations. To date, contact had been made with 58 organisations and scoping meetings have been held with 24. Nine support plans were ready for issue / had been issued. The Support Team's weighted pipeline of projects stands at £166m of capital investment, 42,476 tCO2 and 79,794 homes. • OJEU procurement preparation is being finalised and the new RE:NEW Framework OJEU notice and the pre-qualifying questionnaire were due to be launched early in quarter 3. • Following support from the Support Team, LB Newham has entered into a contract through the original RE:NEW Framework to obtain ECO funding to install a range of measures in over 2,700 social homes. * This KPI is an estimates based on the expected average savings per home. Figures are reported at the time a contract that has received support from the RE:NEW Support Team is let. However, figures remain unconfirmed until the contract has been implemented. On this basis, 2013/14 and later data is still unconfirmed.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-18
Target | 0 | 666 | 3667 | 5333 |  | 9666 | 36834 | 36500 | 118821
Actual | 0 | 2827
Forecast |  | 666 | 3667 | 5333 |  | 11827 | 36834 | 36500 | 120982
Cumulative* | 25821 | 28648
* Since 2009/10.
11b) Tonnes of CO2 saved as a direct result of Mayoral workplace energy efficiency programmes
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
8438 |  | 17347 |  |  | Our target is to save 45,427 tonnes of CO2 over 2009-16. So far, we have saved 32,856 - ahead of interim targets. We rate our prospects of meeting the overall target as GREEN.
TONNES CO2 |  | GREEN
Commentary
• RE:FIT is a ready-to-use, cost neutral procurement initiative that allows public sector organisations to retrofit existing buildings with energy efficiency measures, reduce carbon emissions and achieve substantial guaranteed annual cost savings. • RE:FIT is currently exceeding it quarterly targets and this is set to continue for the reminder of the year. * Estimated carbon savings are recorded once the building contract has been signed and include all contracted carbon through RE:FIT, schools and GLA buildings. The suppliers of the RE:FIT framework have an obligation to report on actual installed measures on a yearly basis. Figures for 2013/14 and this year are therefore subject to change at this stage. Note also since the previous report, the 2014/15 target has been updated to reflect the pipeline of projects. The lifetime target has been amended to align with the Climate Change Mitigation and Energy Strategy. NOTE: CURRENTLY DISCUSSING MEASUREMENT METHODOLOGY TO ENSURE PERFORMANCE IS REFLECTED HERE ACCURATELY AND CONSISTENTLY.
| This Year | [5 empty] | Future Years |  | Lifetime**
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-16
Target | 4219 | 4219 | 4219 | 4220 |  | 16887 | 13023 | N/A | 45427
Actual | 9181 | 8166
Forecast |  | 6578 | 6578 | 6578 |  | 28915 | 13023 | N/A | 70566
Cumulative* | 37809
* Since 2009/10. ** To June 2015.
11c) Tonnes of CO2 saved as a direct result of Mayoral energy supply programmes
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
2580 |  | 2406 |  |  | Our target is to save 214,835 tonnes of CO2 over 2010-21. To date, we have met interim targets and we rate our prospects of meeting the overall target as AMBER.
TONNES CO2 |  | AMBER
Commentary
• Reported carbon savings flow from: a) The Gospel Oak combined heat and power (CHP) project saving a minimum of 2,890 tonnes of CO2 per year; b) The Crystal Palace CHP project which saved 2,002 tCO2 in 2013/14; and c) The Olympic Fringe project which saved 420 tCO2 in 2013/14. • Additional CO2 savings, from 2015/16, will come from projects constructed and operated by others but which are supported to procurement by the GLA. * Past data and targets for 2014/15 have been amended, reflecting that the GLA has worked to increase the accuracy of this KPI, replacing estimated data with actual energy generation readings (from which CO2 savings are derived by comparing emissions from CHP to conventional energy generation). Data from 2013/14 and prior years are therefore confirmed. In-year data will be confirmed after year-end. Future targets have also been amended, with the project pipeline now factored in; these targets are subject to change depending on project delivery timescales.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2010-21
Target | 1290 | 1290 | 1290 | 1290 |  | 5160 | 6169 | 30398 | 214835
Actual | 1203 | 1203
Forecast |  | 1290 | 1290 | 1290 |  | 4985 | 6169 | 30398 | 214835
Cumulative* | 10681 | 11884
* Since 2009/10.
12) The number of affordable homes delivered
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
600 |  | 2153 |  |  | Our target is to deliver 100,000 affordable homes over 2 Mayoral Terms. So far, we have delivered 77,058 and we are meeting interim targets. We rate our prospects of meeting the overall target as GREEN.
AFFORDABLE HOMES |  | GREEN
Commentary
• Performance to the end of quarter 2 is above target and officers working closely with providers to ensure as many completions as possible are delivered. • Performance is also on track to meet the 100,000 homes target. However, the profile of delivery over 2014/15 is heavily backloaded to the final quarter. This presents a risk. The GLA is carefully managing project delivery to mitigate risks. Slippage within year will be managed through substitutions. • New programme allocations for the 2015-18 programme were announced in July and will contribute towards delivery of the Mayor's housing targets and the GLA will shortly launch continuous bidding which will further contribute towards the Mayor's targets * The 2013/14 outturn includes an estimate of those outputs monitored by DCLG (a figure of 700 has been assumed). The figure will be confirmed in November 2014.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2008-16
Target | 300 | 300 | 2000 | 15290 |  | 17890 | 4815 | N/A | 100000
Actual | 463 | 1690
Forecast |  | 300 | 15000 | 14937 |  | 18590 | 4815 | N/A | 100000
Cumulative* | 77058 | 78748
* Since May 2008.
13) The number of council homes made decent
Quarter One 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
336 |  | 831 |  |  | We aim to bring 45,000 homes up to the decent homes standard over 2011-15. We are meeting interim targets and so far have made 38,176 homes decent. We rate our prospects of meeting the overall target as GREEN.
HOMES |  | GREEN
Commentary
• The 2011-15 programme is rated green as there are no issues with boroughs being able to meet their allocations: the programme is on track to bring 45,000 homes to decent standard. * When figures are first reported they will in most cases be partial and therefore provisional. This reflects the time lag between the end of the quarter and boroughs sending in their claim forms. On this basis, the quarter 1 figure has been updated from that previously reported (336). The quarter 2 outtuns is not yet available as borough have until December to return their claim forms.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2011-15
Target | 336 | 600 | 1179 | 5045 |  | 7160 | N/A | N/A | 45000
Actual | 831
Forecast |  | 105 | 1179 | 5045 |  | 7160 | N/A | N/A | 45000
Cumulative* | 38671
* For the 2011-15 programme, to date.
14) Percentage of rough sleepers who did not spend a second night out as a result of the GLA-funded NSNO service
Quarter Two 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 91% |  |  | Our target is that 90% of rough sleepers seen by NSNO do not spend a second night out in the same quarter. We met the target this quarter. Our prospects of continuing to meet the target are AMBER.
OF ROUGH SLEEPERS |  | GREEN
Commentary
• Quarter 1 performance has been rated as green as the target of 90 per cent has been met - 507 rough sleepers were seen by the service and 464 did not spend a second night out. • It is possible that staff at the service provider St Mungo's Broadway will strike for seven days during quarter 3, which could impact on performance. * Quarterly figures relate to rough sleepers seen by the service during the quarter in question and the proportion of those who did not spend a second night out during that same quarter. Annual figures relate to rough sleepers seen by the service in the year and the proportion those who did not spend a second night out during the same year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Actual | 91% | 92%
Forecast |  | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Cumulative*
* Since 2009/10.
15) Release of GLA land in hectares
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
6.0322 |  | 8.2 |  |  | Our target is to release 198 hectares of GLA land over 2012-15. So far, we have released 148 hectares - somewhat behind interim targets. Our prospects for meeting the overall target within this timescale are RED.
HECTARES |  | AMBER
Commentary
• Over the year to date, more land has been released than previously forecast. However, the overall target will not be met by the end of this year, as previously envisioned, as the release of some significant sites have slipped into 2015/16. This includes the Stephenson Street site (10 hectares) and, separately, other industrial sites (totalling 8 hectares) that will be included in a single joint venture to be agreed in quarter 1 next year. • Housing and Land will continue to ensure that the release of GLA sites continues to support Mayoral priorities for jobs, growth and regeneration.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0.33223 | 5.7 | 16.3 | 28.5 |  | 50.8322 | N/A | N/A | 198
Actual | 0.3 | 7.9
Forecast |  | 10.7151 | 17.3 | 3.8 |  | 29.3 | N/A | N/A | 176.5
Cumulative* | 147.5 | 155.4
* From the start of 2012/13.
16) Value of match funding from partner bodies as a result of GLA investment through the MRF and OLF
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
4117000 |  | 1244793 |  |  | Our target is £61.3m of match funding over 2012-17. So far, match funding had totalled £25.6m - somewhat behind our interim target. Our prospects of meeting the overall target are, however, GREEN.
£ MATCH FUNDING |  | AMBER
Commentary
• Performance data for quarters 1 and 2 is only partial data. In part, this reflects that a significant number of claims have been submitted without a signed declaration sheet, which is required to validate the spending of match funding. Figures for the first half of the year are expected to rise considerably once these signed forms are received. • As the remainder of MRF projects enter grant agreement this financial year, the aggregate level of match funding commitments will increase, contributing to achievement of the overall target.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-17
Target | 2058500 | 2058500 | 4117000 | 8234000 |  | 16468000 | 10741579 | 9775000 | 61298411
Actual | 278788 | 966005
Forecast | 2058500 | 2058500 | 4117000 | 8234000 |  | 13595793 | 10741579 | 9775000 | 58426204
Cumulative*
* Since 2012/13.
17) The return on investment made to secure outside sponsorship
April to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
N/A |  | 8.0749 |  |  | Our target is that there is a return on the investment to secure sponsorship over 2012-15 of a factor of 7. We are meeting interim targets and our prospects for meeting the overall target are AMBER.
RETURN AS RATIO |  | GREEN
Commentary
• At end of quarter 2, the value of sponsorship agreed for the year was £1.8m, an income to cost (the cost of the Commercial Partnerships Team (CPT)) of 8:1. The majority was generated from multi-year and prospective deals agreed in the preceding financial year. The value of sponsorship is expected to rise to £1.9m by the end of quarter 3, an income to cost ratio of 9:1. The majority of the additional income will be generated from a multi-year deal for Team London HeadStart and from sponsorship deals for GLA events. • The key risk to achieving the target is securing corporate partners to sponsorship opportunities that add value to both parties. The CPT is working GLA teams to identify partners to support other Mayoral programmes. It is also working with policy teams to review delivery within each of its active partnerships and to identify new partnership opportunities ahead of each financial year. * It is not possible to profile this KPI across the year so there are no quarterly targets. In-year figures may include sponsorship income from contracts not yet signed / not yet paid. The cost element of the KPI is the budgeted figure for the CPT. Data will not be confirmed until after year-end, based on actual income received and the actual spend on the CPT.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | N/A | N/A | N/A | 10 |  | 10 | N/A | N/A | 7
Actual | 5.9904 | 8.0749
Forecast |  | 8.3 | 8.8265 | TBC |  | 10 | N/A | N/A | 7
Cumulative* | 147.5
* From the start of 2012/13.
18) The percentage of invoices from small and medium sized enterprises (SMEs) paid within 10 days
Quarter Two 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 91.71% |  |  | Our target is to pay 90% of all invoices from SMEs within 10 days. In the past quarter, we paid 92% of SME invoices within the set time. We rate our prospects of meeting the target over the medium-term as GREEN.
% OF INVOICES |  | GREEN
Commentary
• Performance is consistent with that achieved in the previous financial year and ahead of target. In quarter 2 we paid 1,328 of 1,448 SME invoices within 10 days. * This KPI is measured according to SAP periods, so does not precisely follow a quarterly timetable.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 92% | 91.71%
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Cumulative* |  | 92.05%
* Over this financial year.
19) Average number of working days per GLA employee lost to sickness absence
12 Months to September 2014/15* |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5.9 |  | 2.75 |  |  | Our target is keep staff sickness absence at less than 5.9 days per year. Over the past 12 months the average number of days was 2.8. We rate our prospects of meeting the target over the medium-term as GREEN.
DAYS |  | AMBER
Commentary
• Performance remains better than target and that of comparator groups. However, we continue to have concerns about the data reported from the sickness absence system. Procurement of a new, more robust system will take longer than originally envisioned, but is otherwise progressing well. It will go live for the start of 2015/16. • In the meantime, manual consistency checks are being undertaken and suggest the reported figure is broadly in line with expectations. • The new system will support self-reporting of absence. It is unclear at this stage what impact this will have on the completeness of the data. However, this will be monitored closely. * This KPI is measured over a rolling year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 5.9 | 5.9 | 5.9 | 5.9 |  | 5.9 | 5.9 | 5.9 | N/A
Actual | 2.75 | 2.62
Forecast |  | 3.4 | 3.4 | 3.4 |  | 3.4 | 5.9 | 0.9 | N/A
Cumulative*
* Over this financial year.
20) The percentage of correspondence responded to in full in 20 working days
Quarter Two 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 80.56% |  |  | Our target is to respond to 90% of correspondence within 20 days. In the past 6 months, we responded to 85% of correspondence within 20 days. Our prospects of meeting the target over the medium-term are AMBER.
% CORRESPONDENCE |  | AMBER
Commentary
• We missed our target this quarter due to a number of complex enquiries that required significant time and resource to respond to. Many of these did not directly relate to GLA activity or areas of responsibility. The Public Liaison Unit has suggested changes in process to relevant teams to improve performance.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 88% | 80.56%
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Cumulative* |  | 84.79%
* Over this financial year.

## Q3 2014-15
1) Number of jobs created through GLA Group investment and associated spend (ie. levered or match funded)
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
9589 |  | 19177 |  |  | The target is to create and support 200,000 jobs over the Mayoral term. To end Q2, we had created 115,429 jobs. The prospects for achieving the target are GREEN.
JOBS |  | GREEN
Commentary
• From the information received to date, 115,429 jobs are estimated to have been created and supported across 2012-13, 2013-14 and the first 2 quarters of 2014-15, now confimed. The final 2013-14 data has increased slightly from the previous estimate. It is estimated that 202,344 jobs will be created over the Mayoral term. That estimate is at this stage based on incomplete information. For instance, no information on jobs created has yet been received from MOPAC. There are other reporting gaps at present; for example, jobs within the Royal Docks Enterprise Zone and on GLA land that has been released. Without such data, the Mayor is nevertheless on target to achieve his target of 200,000 jobs created. * This KPI is reported biannually. This data is in line with the Q2 data to be reported in Feb 2015. Q3 is a forecast projection. Reported figures are estimates, as described in detail in the biannual reports to IPB.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 7500 | 7500 | 17500 | 17500 |  | 50000 | 50000 | N/A | 200000
Forecast | 9588 | 9589 | 14411 | 14411 |  | 47999 | 58093 | N/A | 202344
Actual | 9588 | 9589
Cumulative* | 105840 | 115429
* Progress to date over Mayoral Term.
2) Number of new apprenticeships started
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
33440 |  | 22100 |  |  | Our target is to see that 250,000 apprenticeship opportunities are created over the Mayoral term. By Q2 2014-15 106,690 had been created. The prospects for achieving the target are AMBER.
APPRENTICESHIPS |  | AMBER
Commentary
•Q2 performance data continues to be substantially below target (albeit showing a small increase from Q1) hence the Amber RAG status. Q3 data is expected to be available at the end of March 2015. •Impact evaluations for the GPF funded Apprenticeship Marketing activity (Awareness creation campaign and Direct Marketing/Telemarketing activity) are due mid February. GLA Policy Leads will work with GLA Economics to analyse the results to establish whether further marketing investment is worthwhile. * There is a minimum three-month lag between quarter end results and BIS publishing the data. Figures are initially provided as unconfirmed. This is because learning providers may not submit data in time for the quarterly figures. These outputs will be added into Q4 data when end-of-year figures are confirmed. It should be noted that the forecast is heavily caveated. Seasonal trends are not identified in this approach. It is assumed the change occurs equally throughout the year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 16720 | 16720 | 16721 | 16721 |  | 66882 | 79684 | N/A | 250000
Forecast | 14950 | 14950 | 15996 | 18887 |  | 56983 | TBC | N/A | TBC
Actual | 10720 | 11380
Cumulative* | 95310 | 106690
* Progress to date over Mayoral Term.
3) Square metres of public realm improved or created through GLA investment and associated spend (ie. levered or match funded)
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
60093 |  | 47415 |  |  | Our target is to improve or create 80,124 sqm of public realm this year, in addition to 32,114 sqm in 2013-14. The prospects for achieving the target are GREEN.
SQUARE METRES |  | GREEN
Commentary
• Performance for Q3 has been quite low, as whilst a number of projects have now completed public realm improvement, the performance remains to be verified as part of the evaluation process and so figures for this period will be reported in Q4 once verified. We remain confident that the overall figures will be met. • As the target was profiled evenly across quarters, it will be the case that in some quarters performance exceeds the target and in others it falls short. * Data to inform KPI performance is provided by delivery partners upon completion of public realm schemes. GLA project leads are working closely with delivery partners to ensure quality of data reporting and verification.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 20031 | 20031 | 20031 | 20031 |  | 80124 | 49887 | TBC | N/A
Forecast |  | 8052 | 20031 | 20031 |  | 67446 | 49887 | TBC | TBC
Actual | 32010 | 9100 | 6305
Cumulative* | 64124 | 73224 | 79529
* Progress since 2013/14
4) The number of employers signed up to the London Living Wage (LLW)
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
20 |  | 200 |  |  | Our target that 250 employers were signed up to the LLW over this Mayoral Term. Already, 493 employers have signed up. So we have MET THE TARGET well ahead of schedule.
ACCREDITED EMPLOYERS |  | GREEN
Commentary
• There has been strong growth in this quarter due to extra publicity afforded to the the initiative during Living Wage Week in November. • Of the 493 accredited employers 232 are in the private sector, 77 are in the public sector and 184 are in the third sector. * This count includes only those employers with London offices who are fully accredited with the Living Wage Foundation. It covers all sectors (including public sector/third sector).
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 10 | 5 | 5 | 5 |  | 25 | 25 | N/A | 250
Forecast |  | 30 | 30 | 10 |  | 210 | 50 | N/A | 553
Actual | 85 | 51 | 64
Cumulative* | 378 | 429 | 493
* Progress to date over Mayoral Term.
5a) The number of young Londoners who are actively supported
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
3747 |  | 5485 |  |  | Our target is to support 4,446 young Londoners this year - having supported 13,133 in 2013-14. At the mid-year point, we had already MET THE TARGET for 2014-15.
YOUNG LONDONERS |  | GREEN
Commentary
• The majority of projects have now exceeded their profiled number of young people to be supported, and the annual target has now been exceeded. The past performance traffic light has been rated as green as the annual performance target has already been met. Returns for the supplementary programme for schools have not yet been received so their Q3 starters have not been included in these figures. * This KPI counts the number of young people supported by: the GLA's ESF Youth Programme; Mayor's Mentoring; Leadership Clubs; Championing Careers Guidance in Schools Pilot; Peer Outreach Team; Lynk Up Crew; and Earn Your Travel Back (EYTB). Note that Q1 actual includes some mentoring outputs which were delivered but not counted in 2013/14. This is to ensure the KPI is representative of actual, overall performance.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 839 | 1528 | 1380 | 699 |  | 4446 | 122 | N/A | N/A
Forecast |  | 528 | 167 | 50 |  | 5535 | 122 | N/A | N/A
Actual | 2217 | 3036 | 232
Cumulative* | 15350 | 18386 | 18618
* Progress since 2013/14
5b) The number of young Londoners supported into and achieving an improved and sustained outcome
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1540 |  | 2939 |  |  | Our target is to support 2,972 young Londoners to achieve an improved and sustained outcome this year - having supported 7,846 in 2013-14. The prospects for achieving this target are GREEN.
YOUNG LONDONERS |  | GREEN
Commentary
• The Championing Careers Guidance, and the Leadership Clubs projects reported sustained outcomes earlier than anticipated - and with nearly 50% more young people continuing in education or employment than expected. • The ESF youth programme's sustained figures remain below profile, partly due to the delay that delivery partners have experienced in securing appropriate evidence prior to claims being made. • There are sufficient volumes of young people who have entered either education or employment during the period that would realise a 26-week outcome in this financial year (almost 1,100 in total) and it is therefore anticipated that the ESF project target will be met. * The scope of this KPI is the same as KPI 5a (minus Earn your Travel Back). The outcome has to be sustained for 26 weeks.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 763 | 339 | 438 | 1432 |  | 2972 | 743 | N/A | N/A
Forecast |  | 339 | 339 | 512 |  | 3451 | 743 | N/A | N/A
Actual | 733 | 2003 | 203
Cumulative* | 8579 | 10582 | 10785
* Progress since 2013/14
5c) The number of schools supported to improve their practice
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1232 |  | 2846 |  |  | Our target is to support 3,767 schools to improve their practice, thereby boosting standards in the capital's schools. So far, we reached 2,846 schools. Prospects for achieving the target are GREEN.
SCHOOLS |  | GREEN
Commentary
• The number of schools supported is on track. Q4 forecast has been decreased due to overachievement in Q3. In addition to figures reported here, approximately 200 schools have registered to use the London Curriculum material, during Q4 we will confirm whether these schools have started using the resources and report those that have done so. • The number of schools supported through the LSEF has to date exceeded targets. The forecast have been amended as some outputs have been brought forward from future quarters. * Note that a school may be counted more than once if it participates in more than one of the 100 LSEF projects and/or the Gold Club and London Curriculum. Note that Q1 actual includes outputs carried over from 2013-14. This is to ensure reported performance is representative of the total number of schools supported (given the KPI did not exist in 2013-14).
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2014-16
Target | 1168 | 17 | 47 | 2468 |  | 3700 | 67 | N/A | 3767
Forecast |  | 17 | 200 | 854 |  | 3700 | 67 | N/A | 3767
Actual | 2451 | 92 | 303
Cumulative* | 2451 | 2543 | 2846
* Progress to date over 2014-16.
6) GLA Group sites identified for new schools
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
1 |  | 0 |  |  | Our target was to identify 10 GLA Group sites for new schools over this Mayoral Term. By the end of 2013-14, 11 sites had already been identified. So we have MET THE TARGET ahead of schedule.
GLA SITES |  | GREEN
Commentary
• Support for free schools was one of the Mayor's Education Inquiry's 12 recommendations. In addition, the Mayor made a Manifesto commitment in 2012 to use GLA Group assets to secure sites for 10 free schools. So far, the Mayor has freed up public land and property to enable the delivery of 11 schools in the capital, providing places for about 7,300 pupils (developed in former police stations, on GLA land and in Queen Elizabeth Olympic Park): 7 primaries; one secondary; one 16-19 school; one 14-19 school; and one all-through school. Nine will be free schools, one a new University Technical College and one a new Academy. Although no additional site was found so far this year, rating remains green as the overall target has been met. An announcement against this target is scheduled for Q1 2015/16.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | Mayoral Term
Target | 0 | 1 | 0 | 1 |  | 2 | 1 | N/A | 10
Forecast |  | 1 | 0 | 1 |  | 1 | 1 | N/A | 13
Actual | 0 | 0 | 0
Cumulative* | 11 | 11 | 11
* Progress to date over Mayoral Term.
7) Number of volunteering opportunities taken up by volunteers through Team London
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
26250 |  | 33624 |  |  | Our target is for 100,000 volunteering opportunities to be taken up over 2013-16. So far, 52,315 opportunities have been taken up. Prospects for achieving the target are GREEN.
VOLUNTEERS |  | GREEN
Commentary
• Q3 Performance includes 2,682 volunteers for Pocket Parks; 1,210 estimated active volunteers through Team London website (using a 17.3% conversion rate of all enquiries made); 92 for the Christmas Visitor Welcome; 9 for NYE fireworks; 500 for Re:Leaf; an estimated 6,250 as part of the Team London Young Ambassadors programme; 369 from the Tottenham volunteering programmes; 58 for the Royal Parks Half Marathon and 65 as part of the HeadStart Programme. Schools programme figures are estimated at the moment, and Free The Children will provide a comprehensive end of year report (to be available at the end of the Academic year) detaling all activites for the year. * There is an element of estimation involved in calculating these figures. Figures for volunteering through the Team London brokerage website are derived by applying a conversion ratio to the number of applications. The conversation rate is calculated by a sample study of activity with charities registered with the website. Quarterly figures are provisional when first reported, pending in some cases final confirmation of numbers from GLA teams and external organisations. Q1, 2 and 3 are unconfirmed yet but 2013-14 is final.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 8750 | 8750 | 8750 | 8750 |  | 35000 | 48000 | N/A | 100000
Forecast |  | 8750 | 8750 | 8750 |  | 42374 | 48000 | N/A | 109065
Actual | 13622 | 8685 | 11317
Cumulative* | 32313 | 40998 | 52315
* Progress to date over 2013-16.
8) Number of Londoners participating in sport or physical activity through the Mayor's Sports Legacy Programme: Phase 2
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
29133 |  | 29320 |  |  | Our target is for 62,263 Londoners to participate in sport or physical activity between 2013 and 2016. So far, there have been 34,820 participants. Prospects for achieving the target are GREEN.
PARTICIPANTS |  | GREEN
Commentary
• Performance across the portfolio is good and slightly above the cumulative target for the year. • The quarterly performance (and cumulative lifetime programme performance) is marginally below expectations, due to the absence of participation figures for the Make a Splash mobile swimming pools latest pool deployment in Hounslow. We are expecting a report on the project by the end of January (the latest funding instalment has not been released and will not be until the report is submitted with satisfactory participation figures). * This KPI measures outputs through the Make a Splash and the Mayor's FreeSport projects as well participation projects funding through phase 2 of the Mayor's Sports Legacy Programme. Since Q4 13-14, final targets have been set for this KPI, based on signed funding agreements.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2013-16
Target | 6276 | 7916 | 14941 | 3415 |  | 32548 | 23850 | N/A | 62263
Forecast |  | 7916 | 14941 | 3415 |  | 32735 | 23850 | N/A | 62085
Actual | 7378 | 8344 | 13598
Cumulative* | 12878 | 21222 | 34820
* Progress to date over 2013-16.
9) The number of street trees planted through the Mayor's street trees initiative
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to plant 10,000 street trees over 2012-15. At the end of 2013-14, we had planted 6,314 against an interim target of 7,850. Prospects for meeting the overall target, however, are GREEN.
STREET TREES |  | AMBER
Commentary
• Overall, 6,314 street trees were planted in rounds 1 and 2. The grant assessment panel for round 3 met 30 September. Funding for a further 4,278 street trees was allocated, subject to funding agreements being signed. This means the programme is on track to meet the Mayor's target of planting an additional 10,000 street trees. • The planting season is in the winter. Therefore the remaining trees will all be planted in Q4. • Over and above the street tree planting being reported on by this KPI, 10,221 street trees were planted in 2008-12.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 3700 |  | 3700 | N/A | N/A | 10000
Forecast |  | 0 | 0 | 4278 |  | 4278 | N/A | N/A | 10592
Actual | 0 | 0 | 0
Cumulative* | 6314 | 6314 | 6314
* Progress to date over 2012-15.
10a) The number of pocket parks established
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
75 |  | 43 |  |  | Our target is to create or improve 100 pocket parks over 2012-15. As at Q3, we had established 46. Prospects for meeting the overall target are GREEN.
POCKET PARKS |  | AMBER
Commentary
• 46 pocket parks have now been completed and funding agreements are in place to ensure the target of 100 pocket parks will be delivered by March 2015. Q3 performance is rated as Amber to reflect the delays, although the remainder of the 100 Pocket Parks is expected to be delivered fully in Q4.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 5 | 20 | 50 | 23 |  | 98 | N/A | N/A | 100
Forecast |  | 9 | 18 | 64 |  | 99 | N/A | N/A | 102
Actual | 9 | 17 | 17
Cumulative* | 12 | 29 | 46
* Progress to date over 2012-15.
10b) The area of green space created or restored in acres through the Big Green Fund
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
0 |  | 0 |  |  | Our target is to create or restore 300 acres of green space by March 2015. Delivery has begun this year and prospects for meeting the overall target are GREEN.
ACRES |  | GREEN
Commentary
• Six projects funded through the Big Green Fund will meet the target of improving 300 acres of green space. As forecast, the projects are not due to be completed until March 2015 - hence the profiling of targets. This creates however a risk of slippage.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0 | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Forecast |  | 0 | 0 | 300 |  | 300 | N/A | N/A | 300
Actual | 0 | 0 | 0
Cumulative*
* Progress to date over 2012-15.
11a) Tonnes of CO2 saved as a direct result of Mayoral homes efficiency programmes
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
4333 |  | 3078 |  |  | Our target is to save 118,821 tonnes of CO2 over 2009-18. So far, we have saved 28,899 tonnes. We rate our prospects of meeting the overall target as GREEN.
TONNES CO2 |  | RED
Commentary
• The tonnes of CO2 saved as a direct result of Mayoral homes efficiency programmes KPI fell short of target due to 1) delays in contracting for an number projects supported by the RE:NEW Support Team and 2) delays in receiving contractual evidence from clients for projects supported by the RE:NEW Support Team. • It is anticipated that these projects will still go ahead in the coming months, however delays are anticipated to be beyond this financial year (2014-15) in some cases. * Savings are reported at the time a contract that has received support from the RE:NEW Support Team is let and are the savings due to be achieved over the contract period (ie. figures do not refer to the actual amount of carbon saved in a given quarter/year). Savings are estimates based on the expected (average) savings from the measures to be installed as set out in the contract.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-18
Target | 0 | 666 | 3667 | 5333 |  | 9666 | 36834 | 36500 | 118821
Forecast |  | 666 | 3667 | 5333 |  | 8411 | 36834 | 36500 | 117566
Actual | 0 | 2827 | 251
Cumulative* | 25821 | 28648 | 28899
* Progress to date over 2009-18.
11b) Tonnes of CO2 saved as a direct result of Mayoral workplace energy efficiency programmes
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
7626 |  | 22499 |  |  | Our target is to save 45,427 tonnes of CO2 over 2009-16. Already, RE:FIT has saved 83,400 tonnes. So we have MET THE TARGET well ahead of schedule.
TONNES CO2 |  | GREEN
Commentary
• Although no new carbon savings have been added within this quarter, the programme continues to exceed its targets for this financial year up to Q3 taking into account the contracted baseline performance (performance for period - existing and new). * Carbon savings are recorded once the contract has been signed. Although the savings reported are contracted rather than actual, the savings are guaranteed and extremely robust. Note that quarterly and annual figures are now being reported as the total of new and ongoing savings in the period. Past figures have therefore been amended to ensure reported figure are consistent. Note also that KPI 11 a, b and c are reported differently and cannot therefore be directly compared.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2009-16
Target | 4219 | 4219 | 4219 | 4220 |  | 16877 | 13023 | N/A | 45247
Forecast |  | 6578 | 7626 | 7626 |  | 30125 | 13023 | N/A | 104011
Actual | 7247 | 7626 | 7626
Cumulative* | 68110 | 75736 | 83362
* Progress to date over 2009-16.
11c) Tonnes of CO2 saved as a direct result of Mayoral energy supply programmes
2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5160 |  | 4810 |  |  | Our target is to save 214,835 tonnes of CO2 over 2010-21. To date, we have met most interim targets and we rate the prospects of meeting the overall target as AMBER.
TONNES CO2 |  | AMBER
Commentary
• The reported carbon savings flow from: a) the Gospel Oak combined heat and power (CHP) project saving at least 2,890 tonnes of CO2 per year; b) the Crystal Palace CHP project which saved 2,002 tCO2 in 2013/14 and an estimated 750 tCO2 in the first half of 2014/15; and c) the Olympic Fringe project, saving 420 tCO2 per year. • Additional CO2 savings, from 2015-16, will come from projects constructed and operated by others but which are supported to procurement by the GLA. * Data from 2013-14 and prior years are confirmed. At present, annual contracted (and therefore provisional) data are shown. Data will be updated and confirmed after year-end, after actual energy generation has been checked (from which CO2 savings are derived by comparing emissions from CHP to conventional energy generation). Future targets are based on the current project pipeline; these targets are subject to change depending on project delivery timescales.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2010-21
Target | 1290 | 1290 | 1290 | 1290 |  | 5160 | 6169 | 35784.2161 | 251313.7936
Forecast | 1290 | 1290 | 1290 | 1290 |  | 4810 | 6169 | 35784.2161 | 251313.7936
Actual | 1202.5 | 1202.5 | 1202.5 | 1202.5 |  | 4810
Cumulative* | 10681 | 11883.5 | 13086 | 14288.5 |  | 14288.5
* Progress to date over 2010-21.
12) The number of affordable homes delivered
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
2600 |  | 5208 |  |  | Our target is to deliver 100,000 affordable homes over 2 Mayoral Terms. So far, we have delivered 81,803 and are meeting interim targets. We rate prospects of meeting the overall target as GREEN.
AFFORDABLE HOMES |  | GREEN
Commentary
• Strong delivery performance reported in quarter 3 with the highest number of completions in December reported since 2008. This reflects the programme management approach undertaken by H&L Area Teams to maximise delivery and manage the high volume programme for 2014-15. • As reported previously, the programme remains significantly back loaded to Q4 with 71% of the programme to be delivered during this period. Whilst all efforts are being made to bring forward programme (as reflected in the December figures) the risk to delivery in Q4 remains high. To note, the outturn for Q3 is reported as unconfirmed as this excludes any completions expected from DCLG. As noted previously, DCLG report additional completions in their affordable housing statistics in November of each year. The next report is due in November 2015.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2008-16
Target | 300 | 300 | 2000 | 15290 |  | 17890 | 4815 | N/A | 100000
Forecast |  | 300 | 1500 | 13382 |  | 18590 | 4815 | N/A | 100000
Actual | 463 | 1690 | 3055
Cumulative* | 77058 | 78748 | 81803
* Progress to date over 2008-16.
13) The number of council homes made decent
April to September 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
936 |  | 4313 |  |  | We aim to bring 45,000 homes up to the decent homes standard over 2011-15. We are meeting interim targets and made 38,671 homes decent. Prospects of meeting the overall target are GREEN.
HOMES |  | GREEN
Commentary
• Boroughs have until March to send in the Q3 claims for works carried out between September and December, so Q3 data will be reported at the Q4 update. This is in line with data reported at the GLA budget sub committee. • It is rated green as we are on track to deliver and exceed the target. The 2011-15 programme is rated green as there are no issues with boroughs being able to meet their allocations: the programme is on track to bring 45,000 homes to decent standard. * When figures are first reported they will in most cases be partial and therefore provisional. This reflects the time lag between the end of the quarter and boroughs sending in their claim forms.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2011-15
Target | 336 | 600 | 1179 | 5045 |  | 7160 | N/A | N/A | 45000
Forecast |  | 105 | 1179 | 5045 |  | 10537 | N/A | N/A | 48377
Actual | 831 | 3482
Cumulative* | 38671 | 42153
* Progress to date over 2011-15.
14) Percentage of rough sleepers who did not spend a second night out as a result of the GLA-funded NSNO service
Quarter Three 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 91% |  |  | Our target is that 90% of rough sleepers seen by NSNO do not spend a second night out in the same quarter. We have consistently met targets. Prospects of continuing to meet the target are GREEN
OF ROUGH SLEEPERS |  | GREEN
Commentary
• The service is continuing to achieve its performance targets. Performance was expected to have reduced slightly due to 7-day industrial action. This impacted on the numerator for the period, but did not affect the success rate of the project. The GLA continues to closely monitor this flagship project. * Quarterly figures relate to rough sleepers seen by the service during the quarter in question and the proportion of those who did not spend a second night out during that same quarter. Annual figures relate to rough sleepers seen by the service in the year and the proportion those who did not spend a second night out during the same year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Forecast |  | 90% | 90% | 90% |  | 80% | 80% | 80% | N/A
Actual | 91.48% | 92% | 91%
Cumulative*
* Progress to date over N/A.
15) Release of GLA land in hectares
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
22.3322 |  | 11.6297 |  |  | Our target is to release 198 hectares of GLA land over 2012-15. So far, we have released 158.8 hectares - behind interim targets. Prospects for meeting the overall target are AMBER.
HECTARES |  | AMBER
Commentary
• Some sites forecasted to be signed in Q3 slipped into Q4, including Branch Road, Lymington Fields, Floating Village, Pontoon Dock and LSIP Plot 5 (total 9.48 hectares). 4.42 ha of land at White Hart Triangle also slipped into Q4 (contracting with Crossrail). • 0.31 ha at Lion Green Road relating to Cane Hill in Croydon has slipped into Q1 15-16. Forecast/projection has been amended to reflect this position. • The lifetime target is still expected to be met, however some significant sites have slipped into 2015-16, which may require some reprofiling. Significant procurement work is underway to have c.26 ha of land under one single Industrial sites portfolio, which would have been included within the the original 14-15 target, aim to be in contract with a JV partner by Q2 15-16. Feasibility work is currently being completed for major large sites including Beam Park, Stephenson Street, and Albert Island so disposal strategies are in place by Q2 15-16.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-15
Target | 0.33223 | 5.7 | 16.3 | 28.5 |  | 50.8322 | N/A | N/A | 198
Forecast |  | 7.869 | 3.4307 | 17.4179 |  | 29.0476 | N/A | N/A | 176.2176
Actual | 0.33 | 7.869 | 3.4307
Cumulative* | 147.5 | 155.369 | 158.7997
* Progress to date over 2012-15.
16) Value of match funding from partner bodies as a result of GLA investment through the MRF and OLF
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
8234000 |  | 7610866.83 |  |  | Our target is £61.3m of match funding over 2012-17. So far, match funding had totalled £31.9m - behind our interim target. Prospects of meeting the overall target are, however, GREEN.
£ MATCH FUNDING |  | AMBER
Commentary
• Q3 figures for match funding are slightly low against targets, this is because some boroughs are deferring the validation of match expenditure to Q4 as this coincides with the project closure and allows them to declare the figures more accurately. We remain confident of reaching our 14/15 target overall. • To note that the Q1 and Q2 performance have also improved following later confirmations of match were received from the boroughs. Q2 in particular is now above target. Data to inform KPI performance is provided by delivery partners as part of the quarterly grant claim process. Match expenditure is certified as having been defrayed by Borough's Section 151 officer. Reported figures relate to the quarter in which the funding was spent. Data when first reported is provisional and confirmed the following quarters.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-2017
Target | 2058500 | 2058500 | 4117000 | 8234000 |  | 16468000 | 10741579 | 9775000 | 61298411
Forecast | 2058500 | 2058500 | 4117000 | 8234000 |  | 15844866.83 | 10741579 | 9775000 | 60675277.83
Actual | 1869779.44 | 2925129.18 | 2815958.21
Cumulative* | 26183611.44 | 29108740.62 | 31924698.83
* Progress to date over 2012-2017.
17) The return on investment made to secure outside sponsorship
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
N/A |  | 9.3112 |  |  | Our target is a return on the investment to secure sponsorship over 2012-15 of a factor of 7. We are meeting interim targets and prospects for meeting the overall target are GREEN.
RETURN AS RATIO |  | GREEN
Commentary
• At Q3 the value of sponsorship agreed for the year in contract documentation was £1.955m, an income to cost ratio of 9.3:1. Income received in Q3 has been for Team London HeadStart, St Patrick’s Day festival sponsorship and an additional partner for the London Rental Standard. We are expecting to meet our target of £2.1m by the end of Q4. We expect that the majority of this income will be raised to support Team London HeadStart, we are targeting £50k p.a. for three years from three partners to achieve target. • The key risk to achieving the target is securing corporate partners for HeadStart before the end of the quarter. The Commercial Partnerships team is also working closely with teams within the GLA to identify further partnership opportunities. These include New Year’s Eve for 2015, Skills and Education and Health and Community programmes. * It is not possible to profile this KPI across the year so there are no quarterly targets. In-year figures may include sponsorship income from contracts not yet signed / not yet paid. The cost element of the KPI is the budgeted figure for the CPT. Data will not be confirmed until after year-end, based on actual income received and the actual spend on the CPT.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | 2012-2015
Target | N/A | N/A | N/A | N/A |  | 10 | N/A | N/A | 7
Forecast |  | 8.25 | 8.8265 | TBC |  | TBC | N/A | N/A | TBC
Actual | 5.9904 | 8.0749 | 9.3112
Cumulative*
* Progress to date over 2012-2015.
18) The percentage of invoices from small and medium sized enterprises (SMEs) paid within 10 days
April to December 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 92.56% |  |  | Our target is to pay 90% of all invoices from SMEs within 10 days. In the past quarter, we paid 94% of SME invoices within the set time. Prospects of meeting the target over the medium-term as GREEN.
% OF INVOICES |  | GREEN
Commentary
• Performance is consistent with that achieved in the previous financial year and ahead of target. In quarter 2 we paid 1,328 of 1,448 SME invoices within 10 days. * This KPI is measured according to SAP periods (13 periods in a year), so does not precisely follow a quarterly timetable.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 92.35% | 91.71% | 93.53%
Cumulative* | 92.35% | 92.05% | 92.56%
* Progress to date over the financial year.
19) Average number of working days per GLA employee lost to sickness absence
12 Months To December 2014 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
5.9 |  | 2.19 |  |  | Our target is keep staff sickness absence at less than 5.9 days per year. Over the past 12 months the average number of days was 2.2. Prospects of meeting the target over the medium-term are GREEN.
DAYS |  | GREEN
Commentary
• Performance remains better than target and that of comparator groups. However, we continue to have concerns about the data reported from the sickness absence system. Procurement of a new, more robust system will take longer than originally envisioned, but is otherwise progressing well. It will go live for the start of 2015-16. The new system will be accompanied by process changes to the recording of sickness absence. It is unclear at this stage what impact this will have on the completeness of the data. However, this will be monitored closely • In the meantime, manual consistency checks are being undertaken and suggest the reported figure is in line with actual performance. * This KPI is measured over a rolling year.
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 5.9 | 5.9 | 5.9 | 5.9 |  | 5.9 | 5.9 | 5.9 | N/A
Forecast |  | 3.4 | 3.4 | 3.4 |  | 3.4 | 3.4 | 3.4 | N/A
Actual | 2.75 | 2.62 | 2.19
Cumulative* | N/A | N/A | N/A
* Progress to date over N/A.
20) The percentage of correspondence responded to in full in 20 working days
Quarter Three 2014/15 |  |  |  |  | The Bigger Picture
Target |  | Actual |  |  | What's our aim and where are we?
90% |  | 81% |  |  | In the quarters 1,2 and 3 in 2014/15, we responded to 84% of correspondence within 20 days. To date our performance is AMBER, however it is expected that significant improvement will be made in Q4.
% CORRESPONDENCE |  | AMBER
Commentary
• Even though the authority didn't meet the set target in Q3 there are reasons to expect significant improvement in Q4: the escalation process introduced a couple of months ago is beginning to pay dividend and a fully staffed Public Liaison Unit should also boost performance. • There are several reasons for the set target not being met in Q3. These are: complex enquires requiring a longer clearance period, staff being away for Christmas and the New Year and the Public Liaison Unit not being fully staffed during this period (historically there is always a drop in performance in Q3).
| This Year | [5 empty] | Future Years |  | Lifetime
| Q1 | Q2 | Q3 | Q4 |  | 2014/15 | 2015/16 | 2016/17 | [Annual KPI]
Target | 90% | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Forecast |  | 90% | 90% | 90% |  | 90% | 90% | 90% | N/A
Actual | 88% | 81% | 81%
Cumulative* | 88% | 85% | 84%
* Progress to date over the financial year.