London Borough of Harrow RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date. - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action. - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| HAR1 | Waste Reduction Implement the Environment Act at a local level (applies to all themes) | Work with other boroughs, the West London Waste Authority (WLWA) and across the service to ensure successful delivery of the Environment Act at a local level. | On track | - The council continues to work with other boroughs, the West London Waste Authority (WLWA) and across the service to ensure successful delivery of the Environment Act at a local level. - Simpler Recycling to be in place for most households - current timescale is 31 March 2026 (subject to change by Defra). - Defra has awarded the council a Capital Transitional Grant to support the delivery of weekly food waste collections, subject to grant conditions. Work in this area will continue over the forthcoming year including scoping of activity and procurement for example of caddies. - The service is also exploring options for two new dedicated food waste vehicles that will assist in rolling out food waste services to residents in flats and flats above shops. | - Requirements of the Environment Act implemented effectively at a local level. |
| HAR2 | Champion food waste reduction | - Undertake enhanced communications and engagement over the next 6 months focused on reducing the amount of food waste disposed of per household building on #Recycleforharrow. This will include a focus on flats. This will be via social media, newsletters and on our website - #FeedYourCaddy and #RecycleForHarrow campaigns. With a focus on awareness raising as well as behavioural change. - Promote waste reduction activities such as Love Food, Hate Waste. - Explore local promotion of Olio, Kitche & the Too Good To Go apps in the borough to reduce food waste and to promote food sharing. | On track | - Improving recycling is a flagship action for the council for 2024/25 as outlined in the corporate plan. - New recycling team established, and their work includes a focus on increasing food waste recycling. - Enhanced communications and engagement have taken place. This has included door knocking where take-up is a particular challenge, engagement events and drop-in sessions at local schools and libraries. In 23/24 door knocking at over 550 properties, 10 school events, 9 engagement events, (including 2 library drop-in sessions and 1 Town Centre stall, outreach as part of Weeks of Action and community visits). - Recycling week 16-20 October 2023 included a focus on increasing food waste and seasonal campaigns also undertaken e.g., recycle your pumpkin at Halloween. - This is alongside internal comms on food recycling across the council with advice on how to recycle better. - Work will continue in this area over the forthcoming year. | - Increased awareness across the borough of the options to reduce food waste because of engagements and communications from the council. - Recycling team recruited with a focus on improving recycling. - Better signposting of services. |
| HAR3 | Use waste composition information to reduce contamination, shape services and tailor communications. | - Work with the WLWA to undertake waste composition analysis at least once every 15 months. - Use the results of the waste composition to tailor services and communications. | On track | - Waste composition analysis undertaken by the WLWA for all west London boroughs. Findings have been used to tailor activity including comms and engagement with a particular focus on promoting textile and food recycling. - To encourage textile recycling – repair cafes have taken place across the year with the most recent in April and June 2024. This is a flagship action in the corporate plan. - Door knocking and engagement undertaken by the recycling team using the findings from the waste composition analysis to encourage better quality recycling. - Bin stickers rolled out where contamination is a particular challenge. | - Composition data on contamination levels, and avoidable waste that can be used to support services and to target activity where it is most needed. - Tailored communications e.g., food waste recycling and textile recycling. - Better signposting of services. - Well attended Repair cafes (with 24- 45 signups for each) and increased take up of kerbside textile recycling service. |
| HAR4 | Promote and support home composting | - Continue to promote and support home composting via the Council website and signposting to https://getcomposting.com | On track | - Home composting is promoted via the council website and through borough engagement including the Conversation café as well as via social media. - Promoted as part of recycling week in October 2023. - Compost bins are available to order via the website. | - Better information available for those who wish to compost. |
| HAR5 | Reduce single-use-plastic and promote waste minimisation. | - Engagement and communications to encourage businesses to prevent waste e.g., unnecessary packaging, whilst promoting the use of materials that can be reused and recycled. - Engagement and briefings for council staff who regularly engage with local businesses and BID e.g., environmental health, trading standards to raise awareness of Refill London scheme membership. - Continue to work with West London boroughs and the WLWA in the delivery of the West London Low Carbon Procurement policy. | On track | - Refill London promoted in business newsletter and on council website. Reuse and recycling – London Borough of Harrow - Environmental Health team briefed on scheme for sharing with businesses across the borough as part of their day-to-day work. - Tailored internal engagement events for staff e.g., Planet vs Plastics World Earth Day – 22 April 2024. - Continue to work with West London boroughs and the WLWA in the delivery of the West London Low Carbon Procurement policy. | - Positive communications and raised awareness of action on single use plastics, re-use, and waste reduction. - Increased awareness across local businesses of the Refill London scheme and how they can get involved. - Leading by example, by encouraging innovative, sustainable solutions from our supply chain. |
| HAR6 | Collection of 6 main recyclables of glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) Increase the number of flats that receive a dry mixed recycling service. Improve recycling quality and reduce contamination | - Ongoing communications and engagement – focused on increased participation, reduced contamination across types and tenures of housing. Including use of ReLondon cost of contamination toolkit and contamination resources and communications supported by ‘London Recycles’ templates and resources. - Review the ReLondon’s Flats Recycling Package and consider how this could be implemented in the borough. - Review current welcome service information for all new residents in the borough, ensuring it sets out clearly the waste and recycling services available, how to use them and the benefits of doing so. - Increase the number of flats that receive a dry mixed recycling service. - Explore partnerships with the WLWA and other boroughs to trial collections of hard to capture materials, for example, flexible plastics (work already underway in this area in West London e.g., Ealing working with Terracycle). - Use IT solutions and data to support waste reduction and recycling. | On track | - The service has used IT solutions and data to support waste reduction and recycling. This has been a particular focus over the past months and has enabled customer services, back-office functions and operational teams’ activity to be streamlined and better connected. - Recycling team has improved recycling information available for residents. Increased engagement has included: - Using existing forums to increase reach e.g., warm hubs, conversation café, libraries including Stanmore library on 12 May and Wealdstone library on 16 May. - Recycling week a tailored and well received engagement event led by the recycling team in Harrow town centre working with the Business Improvement District. - Cross- service working on bespoke weeks of action. Tailored work on reducing contamination rates including: - Recycle as much as you can message promoted. - Use of social media such as Twitter. - Waste vehicles have been used to advertise what goes in what bin. - ReLondon’s resources used to help tailor activity. The recycling team has reviewed the ReLondon Flats Recycling package with considerations on how this could be implemented in the borough. This work will continue in the forthcoming year. Including identification of opportunities for implementation at local level. The service is also looking to expand food waste collections in flats and flats above shops. The service is an active member of the WLWA partnership meetings, and this includes ongoing discussions on collections of hard to capture materials. | - Positive impact on local recycling rates. Residual waste has decreased from 172.62kg per household in Q3 2022/23 to 154kg per household 2023/24. Recycling rates improved during that same period– from 29.67% Q3 2022/23 to 32% Q3 2023/24. Work has also been undertaken to improve the quality of recycling (see references throughout the document). - Positive contribution to the circular economy. - IT solutions that enable better scheduling and identification of challenges so that these can be addressed. - Improved engagement with those who live, work, study or visit the borough. - Improved information for those who move into the borough. - Focused activity where contamination is a particular issue. - Tailored engagement and activity using learning from ReLondon’s publications. |
| HAR7 | Extend food waste recycling to flats above shops and communal flats. Increase food waste recycling across the borough. | - Pilot underway (funded by the WLWA) for food waste recycling for flats above shops (FAS) and communal flats. - Use learning from this pilot to identify barriers to participation and to further extend recycling to flats (including flats above shops). - Build on the current communications campaign (including a focus on the reduction of plastic contamination) to encourage greater usage of the food recycling service for unavoidable food waste. - Continue to work with services internally such as housing to make food waste recycling accessible and tailored to meet specific needs. | On track | - The food waste pilot continues to progress as detailed in the WLWA published report of March 2024 “Harrow have installed bin units at communal properties to expand the food recycling service available for flats and flats above shops. Harrow are also expanding the food recycling service to more schools and businesses. Harrow have made steady progress on the rollout and are expected to exceed the targets by the end of 2024/25”. WEST LONDON WASTE AUTHORITY (harrow.gov.uk) - Defra funding – capital transitional grant awarded for weekly food waste collections. - The recycling team continues to work with housing colleagues in improving recycling facilities. - The service is also looking to expand food waste collections in flats and flats above shops. | - Decrease residual waste. - Increase recycling. - Contribute to the circular economy. - Food waste pilot (see WLWA published report – March 2024) – detailing 124 new businesses are receiving the service, 5,048 flats in communal properties have been added to service,588 flats above shops have been provided with a service. |
| HAR8 | Pan-London Food Campaign (Harrow Council is contributing to the campaign as part of the food workstream of the One World Living Programme (OWL). The pan-London food campaign is an awareness-raising campaign to inform and empower Londoners to reduce their personal food footprint | - Continue to participate in the pan-London food campaign. Harrow was one of the sites for phase 1 of this project – customer insights on food and sustainable diets (one of 23 London boroughs) - Will link into the “Eat like a Londoner” campaign and use associated assets to encourage behaviour change and reduce food waste | On track | - Part of wider pan-London project – participation is ongoing. - Review of findings underway by ReLondon. The pan-London project will use these findings to shape future activity. | - Increased awareness pan-London on how to reduce the personal food footprint. |
| HAR9 | Commercial waste recycling | - Continue to promote the in-house chargeable commercial waste recycling services. - Increase number of customers. - Undertake focused engagement with local businesses (existing and new) including use. of ReLondon’s commercial waste service communications assets toolkit. - Undertake waste audits for businesses as requested to help them understand the waste they produce and the options available to them. | On track | - Service promoted on the council website. - ReLondon’s commercial waste service assets toolkit used by the team. - Engagement with businesses and via the recycling team continues. - Work in this area will continue in 2024/25.This will include review of current service and future options. | - Promotion of service on website and via engagement with businesses. - Using IT effectively enabling customer services, back-office functions, and operational teams’ activity to be streamlined and better connected. - Continued engagement with businesses. |
| HAR10 | Expand the range of materials that can be accepted for recycling at the kerbside. | - Promote the doorstep collection of textiles using the existing TRAID collection services https://traid.org.uk/collect/ - Work with the WLWA and other boroughs to explore the options for kerbside collected materials in addition to the current service offered. | On track | - Regular and frequent promotion of the free TRAID home collection service on the council website. Small WEE also collected. - Flagship action in corporate plan. - TRAID collections of textiles (and small WEEE) will continue in 2024/25.Work is ongoing across west London to explore service options. | - Free textile (and small WEE) home collection service available to residents. In 23/24 there were 553 TRAID collections weighing a total of 12930.8kg. - Increased accessibility of recycling options. - Increase to household recycling rate. - Positive contribution to the circular economy. - Strengthened partnerships. |
| HAR11 | Increase participation in garden waste service | - Targeted communications to encourage participation in the garden waste scheme | On track | - Moved to annual collection. - Targeted communication. | - Garden waste scheme is available across the borough. |
| HAR12 | Promote Reuse and Repair | - Extend our information to residents to encourage diversion of reusable items directly to organisations/people that can keep them in use including e-waste e.g., Harrow Sustain IT. - Identify local businesses and charities that support a circular economy and encourage their addition to a virtual circular economy hub run with the WLWA. - Explore the introduction or sharing of reuse hubs where repairs, reuse and prevention of waste will occur. - Promote the WLWA washable nappy trial packs https://westlondonnappies.com/ when made available by the WLWA. - Work with the WLWA to explore options for a community event where participants will learn how to mend clothes with TRAID and electrical items with the Restart Project – a Repair Café in Harrow. | On track | - As part of Repair week – set up laptop drop off point at the HRRC. Regularly promote Sustain Harrow Sustain IT for laptop repairs. - TRAID events have included Dr Bike to repair bicycles ready for use. This work will continue in 2024/25 linked to our flagship action for this area. c/ref - HAR3. | - Reduction in residual waste to landfill and consumption-based carbon emissions. |
| HAR13 | Waste storage provision (linked to planning) | - Specification in place with the planning department regarding requirements for waste that align with Borough provision. | On track | - Local Plan development underway with input from the waste service on waste policy element including storage requirements | - Continued engagement with planning officers to ensure that reuse and recycling is designed into developments. - Contributes to ensuring access to recycling across the Borough and increasing recycling rate. |
| HAR14 | Use of reduced emission vehicles in our fleet. | - Work will continue to ensure the use of reduced emission vehicles. - Where electric vehicles are not yet feasible, the use of ‘transition’ fuels such as hydrotreated vegetable oil (HVO) blends will be explored. - The council’s ongoing procurement programme for fleet includes a focus on greening the fleet. | On track | - EV strategy developed. - Increasing the availability of EV charging points in the borough is a key flagship action in our corporate plan. - Transport strategy developed. - Engagement has taken place with the Energy Saving Trust to explore options for further electrification of the fleet. - Work in this area will continue.- focused on fleet renewal and decarbonisation. - Visits to other boroughs have already taken place to share learning and this is being used to scope future activity. | - Contribute to the London's zero carbon emissions target. - Contribute to the Climate Strategy. - Contribute to the WLA Low Carbon Procurement Strategy. - Learning from others e.g., engagement with the Energy Saving Trust. |
| HAR15 | HWRC and transfer station (LBH operates one Household Waste and Recycling Centre at Forward Derive) | - Booking system in place. Work will continue with the WLWA and other boroughs with a focus on ensuring an enhanced booking system and services that are easy to use including the effective separation of materials. - Communications will be further developed about using the HRRC sites so residents can maximise their separation for recycling and reuse. - Review of the layout of the site to maximise diversion from residual waste e.g., battery collection next to the small WEEE containers. - Gatekeeping at residual waste containers to encourage maximum sorting of materials. | On track | - Well used HRRC. - Facility in place for residents to book two slots per day in place. - Social media coverage of the site and facilities. - HRRC Improvement project – successful bid to WLWA and being implemented. A review of the site layout has been completed, new CCTV installed, improved signage installed and increased comms. - HRRC has been shortlisted for a LARAC award 2024 HRRC of the year. - Support to residents for separation of materials. - Gatekeeping at residual waste containers to encourage maximum sorting of materials. - Regular meetings with WLWA and other west London boroughs to share learning. - Going forward further improvements will be made in line with the improvement project. | - Accessible HRRC for residents to use. - Improved signage and layout. - Improved CCTV. - Improved separation of materials. - Diversion rates from HRRC increase. |
| HAR16 | DMR collection | - Utilising local waste sites where possible. - Keeping contamination low and maximising recycling. | On track | - Through the HRRC improvement project better promotion of the site and its facilities for residents. (see above). - Residents are supported to put the right items in the right bays. - Increased focus on recycling over the past year. - This work will continue in 2024/25. | - Increase in recycling rates (see above). - Decrease in rates of contamination (see above). |