Part 1 –Reduction and Recycling Plan (RRP) April 2023 to March 2025

- Context:

Sutton’s Environment Strategy prioritises waste minimisation, a move towards the circular economy and the decarbonisation of services, and our waste management priorities reflect this. Having undertaken a significant service change in 2017/18 with the introduction of a weekly food waste collection service; a separate fortnightly paper/card and plastic;cans and glass collections service, and a fortnightly general waste collection. Sutton does not plan to undertake any service changes between now and 2025.

Sutton will continue to focus on waste minimisation and maximising recycling by tackling contamination working with our partner boroughs in the South London Waste Partnership and contractors. Sutton will focus on the upcoming commissioning of its services post 2025 to support the needs of over 200,000 residents and 83,000 properties within the borough.

- Key strategic documents linked to this plan:

In December 2019 the London Borough of Sutton adopted a Waste Minimisation Strategy. The vision of the strategy is to create an environment in which we can reduce waste, maximise recycling, reduce the environmental impact of waste, maximise the use of local waste sites, be innovative and lead by example with our own waste. The Reduction and Recycling Plan acts as an implementation plan for the Waste Minimisation Strategy.

The council also has an ambitious Sutton Environment Strategy and Climate Emergency Response Plan. Published in 2020, the accompanying Climate Emergency Response Plan is reviewed and updated annually. The latest update was published online as the Climate Emergency Response Plan 2022. The Environment Strategy is split into five themes, one of which is Creating a Circular Economy. Actions in this section include those related to reducing waste, increasing recycling and keeping goods and services in use at their highest value to create a circular economy.

- RRP Dashboard:

| Common Performance Targets | Baseline Performance (2019/20) | Performance Target 2024/25 | Metric Guidance / Data source | Target Guidance |
| --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 355.84 | 325.35 | Defra stats (Ex BVPI84a) | Borough sets own targets, informed by ReLondon /WRAP good practice. |
| Total annual household residual waste collected per household (kgs/household) | 450.93 | 434.18 | Defra stats (Ex NI191) | Borough sets own targets, informed by ReLondon/WRAP good practice. |
| Total annual household avoidable (edible) food waste (kgs/head) | 34.38 | 29.92 | Borough to estimate based on own or WRAP food waste composition data. Estimates should be based on avoidable food waste produced (i.e. not just food waste collected). | Based on estimated avoidable food waste produced. Borough to set own targets, informed by ReLondon/WRAP good practice and support programmes (e.g. Trifocal). |
| Annual household waste recycling rate (% by weight) | 46.1% | 50% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP Route Map modelling and other good practice. The GLA will use the borough recycling benchmarking table in the Route Map modelling as a reference point when assessing local authority targets set in the RRP process (See Appendix 2 of the London Environment Strategy, page 111: https://www.london.gov.uk/sites/default/files/les_appendix_2_-_evidence_base_0_0.pdf) |
| Annual LACW recycling rate (% by weight) | 47.97% | 50% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP good practice. Targets should at least match household recycling targets, going beyond the Mayor's 50 per cent LACW recycling target by 2025 where possible. |
| Proportion (%) of properties receiving the Mayor's minimum level of service for household recycling: |  |  |  |  |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) and separate food waste | 100% | 100% | Borough to take from own info. Separate food waste does not include co-mingled with garden waste | Borough sets own target, informed by ReLondon/WRAP good practice. Separate food waste does not include co-mingled with garden waste |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) | 100% | 100% | Borough to take from own info (Nb included for boroughs that are unable to provide food waste collections due to long term contractual issues). | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 100% | 100% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays). | 100% | 100% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)) and separate food waste | 0% | 0% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice and FAS data. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)). | 100% | 100% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice and FAS data. |
| Proportion (%) of waste fleet heavy vehicles that are ULEZ compliant | 90% | 100% | See www.tfl.gov.uk/modes/driving/ultra-low-emission-zone | Borough should aim to operate a fully ULEZ compliant waste fleet as a minimum; with aspirations to introduce zero emission vehicles where practicable. Please include baseline and target % of waste vehicles that are zero emission capable where applicable |
| Performance of LACW activities against the Mayor's EPS (tonnes of CO2eq per tonne of waste managed). | -0.067 | -0.085 | Use tool found here Boroughs to set by uploading WDF data into the GLA tool. | Borough to run their own scenarios using GLA tool to determine planned service changes (DSO borough) or new contract options against the EPS for target years (2024/5). See London Environment Strategy Proposal 7.3.2.b |

- RRP Actions:

| Ref | Theme - Waste Reduction - Maximising Recycling - Reducing Environmental Impact - Maximising local waste sites | Action title | Action Description | Expected Target / Impact | Timescale for action | WCA/ WDA |
| --- | --- | --- | --- | --- | --- | --- |
| LBS1-A | Waste Reduction | Sutton Waste Minimisation Strategy - Promote ways to produce less waste and reuse instead. | Continue to offer a kerbside battery and textile recycling collection. Borough wide campaign to promote the service. - Promote awareness of textiles reuse and recycling in the borough using data from waste composition analysis. | Increase in battery tonnages collected, small reduction in general waste tonnages. - Expected increase in participation of service. - Minimal increase in recycling rate. | Ongoing |  |
| LBS1-B |  |  | Continue to promote the reuse shop at the Household Reuse and Recycling Centre. | Maximise reuse and recycling, increase in reuse items/tonnes diverted, with a total tonnage decrease of disposed waste at HRRC. - Expected increase in HRRC recycling rate by 0.1% | Ongoing |  |
| LBS1-C |  |  | Promote repair cafe and library of things - Promote repair cafes and look to work with resident groups who want to introduce new locations - Leaflets, website, social media, email comms/campaigns - Information at events, fairs etc. - Raise awareness at community groups - Promote the library of things and review items available for hire - Leaflets, website, social media, email comms/campaigns - Information at events, fairs etc. - Raise awareness at community groups - Monitor and baseline hire items | Minimise waste. - Increase in sessions and reuse topics covered - Decrease in waste disposed of. - Behaviour change towards repair and reuse, where this is possible. - Increase in items hired at LoT and longer term decline in electricals disposed of (decline not expected to be seen for a number of years) | - From 2023 - From 2023 to 2024 - From Q3 2023 to 2025 |  |
| LBS2-A | Waste Reduction | Sutton Environment Strategy - develop Sutton as a testbed for the circular economy | Maintain and promote the Sutton reuse network by mapping and promoting reuse schemes and identifying support they require (if any). | Unlikely to have a significant impact on residual tonnages but enables positive waste minimisation behaviour. | Ongoing |  |
| LBS2-B |  |  | Promote Water Refill - Promote Sutton Refill (London) with drinking water available at Council sites and continue to promote local businesses to sign up. - Support the Successful Sutton BID in its 'Free water refill' campaign and extend to more BID areas and other high streets in the borough. Promote free water refill through social media. - Increase business participation | - This will support efforts to reduce the number of single use plastic bottles thrown away, but measuring the impact through waste tonnage data will be impossible. - Maintain and then increase business sign up - This will support efforts to reduce the number of single use plastic bottles thrown away, but measuring the impact through waste tonnage data will be impossible. | - Ongoing - Ongoing |  |
| LBS2-C |  |  | Continue to offer the nappy cashback scheme; explore opportunities to work with children and families teams, midwives and health visitors to increase awareness and take-up. - Information on disposable nappies, wet wipes and contaminating recycling will be produced to run alongside information about reusable nappies. | The nappy cashback scheme on its own is unlikely to have a significant impact on residual tonnages but it enables us to incentivise positive waste minimisation behaviour and provide residents with a more sustainable option to disposable nappies. | Ongoing |  |
| LBS3 | Waste Reduction | Sutton Environment Strategy - reduce food waste by 20% by 2025. | Continue to offer a food waste service. - Bid for funding for food waste campaigns to complement service offered. - Food waste communications campaign to increase participation in the service. - Encourage low participation areas to dispose of food waste separately to general waste, to target and minimise recyclable material entering the general waste stream - Promotion of home composting. - Promotional activities, hints and tips. - Flats contamination campaign - Targeted communication campaign informed by waste composition analysis. | - Reduction in household waste tonnages. - Improve Sutton's overall recycling rate by up to 1.9% by 2025. - Reduce k/g of waste per household to 74.2 kilograms per year - Minimal reduction in food waste tonnages and residual tonnages. - Increase in food waste collected from flats. | - Ongoing - Ongoing - From 2023/24 |  |
| LBS5 | Maximising Recycling | SLWP waste collections contract | Continue to encourage participation in the recycling collection service, and promoting ways of minimising waste to all residents in the borough, via: - Annual service leaflets; - Collection crew contamination process awareness, Contamination tags, and follow up engagement with residents; - Garden waste promotion; and - Christmas waste communications. | - Increased participation in recycling schemes and services - Reduction in contamination of recycling and reduction in residual waste tonnes. | - Annual service leaflets - Annually in November - Contamination tags, and follow up engagement with residents - Ongoing - Garden waste promotion - Monthly, with targeted campaigns in May and September - Christmas waste communications - November and December |  |
| LBS6-A | Maximising Recycling | Sutton Environment Strategy - achieve a recycling rate of 50% or above | - Continue to offer a comprehensive recycling service, including food waste where feasible, to all kerbside properties and flats. - Communications will continue to remind people what the service is and how to use it correctly. This will be tailored based on waste contamination analysis. - Use the latest waste composition analysis data to inform evidence on contamination, communications activity and waste minimisation efforts. - Specific communications will then be developed based on the waste composition analysis. | - Recycling rate at 50% or higher. - Reduction in contamination of specific material types. | - Ongoing - From 2023/24 to 2024/25 |  |
| LBS6-B |  |  | - Make it easy for people to recycle correctly, by undertaking audits (particularly of flatted estates that make up 38% of properties in Sutton) to make sure people have the right bin provision. Work with managing agents, housing associations and Sutton Housing Partnership. Use the results of the ReLondon and Peabody flats contamination project to propose interventions and changes. - Work with managing agents, residents associations, local charities, voluntary, community and self-help groups that live or work in flats within Sutton to promote recycling in communal areas. - Set up a grant fund allowing bids for promoting recycling initiatives - Promote grant fund - Award grants - Baseline data gathering - Interventions data gathering - Review findings | - Recycling rate at 50% or higher. - For each project the improvement is expected to vary and focus on: - Increase in recycling collected (between 5% to 8%) - Reduction in contamination (between 3% to 6%) - Reduction in general waste | - from 2023/24 to 2024/25 |  |
| LBS6-C |  |  | Subject to funding, explore opportunities to expand on-the-go recycling to the street cleansing rounds. | - Recycling rate at 50% or higher. - Increase in recycling collected - Minimal increase to recycling rate | - from 2023/24 |  |
| LBS6-D |  |  | Promote planning guidance document on waste provision - work with developers, architects and managing agents to ensure adequate service provision. - Waste provision planning guidance for developers, architects, and managing agents will be provided and planning staff made aware of guidance. | This will not improve recycling on its own - residents have to use the service correctly - but should prevent poor design that hinders correct use. | - April 2021 - complete - Ongoing working with planning team |  |
| LBS7 | Maximising Recycling | Promote recycling more widely at council sites. | - Following implementation at the central office location, improve recycling and reduce contamination at council satellite sites / offices through review and improvements (where necessary) to bins. - Update posters / labelling and internal communications about the new bins. - Explore whether additional waste streams (e.g. crisp packets) can be added at council sites and satellite offices. - If possible to introduce this, we will need to promote it. - Implemented at Civic offices. | - Increase in council recycling rate; this will contribute to the municipal recycling rate. - Increase in council recycling rate; this will contribute to the municipal recycling rate. | - Completed main sites in 2019/20. Ongoing reviews of satellite offices. - From 2023/24 |  |
| LBS8 | Reducing Environmental Impact | Waste Minimisation Strategy - Improve the contribution waste and litter makes to the street environment. | - For bulky items, continue to promote options such as reuse, and use of charity shops etc. first, before booking a bulky waste collection. - Continue to provide 'report it' functions on the council website for dog fouling, fly tipping, overflowing street bins etc. - Promote this function, including to councillors, to improve efficiency of responses. - Following a one year review of the recently commissioned Environmental enforcement contract, 2024 will seek to increase our focus on littering offences through widespread enforcement activity and a heavier emphasis on education and awareness seeking to drive improved behaviour and culture change. Work already conducted in 2023 against fly tipping offences will continue in a similar vein and seek to reduce the number of resident reports of fly tipping improving on the 15% reduction in 2022. - Annual communication education and awareness campaigns continue to be delivered and expanded as the service enters into new areas and begins to focus on more environmental crimes; this should see a reduction in the instances when enforcement action is required. - Continued review of litter bin numbers and placement throughout the borough as the service continues to look to increase the provision of smart litter bins including solar powered compactor bins and sensor technology, to have a continued positive impact on street cleanliness while reducing vehicle movements reducing our carbon footprint, reduce street clutter and waste minimisation - Litter bin strategy | - Decrease in bulky waste tonnages. - Better data means more targeted interventions are possible. - The number of reported flytipping instances is recorded; so is the number of FPNs issued for environmental offences and the number of prosecutions. A more robust approach would expect to see an increase in FPNs issues, followed by a decline as people change their behaviour. - Targeted approach to the placement of litter bins where need is. Reduction in litter bin waste collected; no overall negative impact on street cleanliness | - Ongoing - Ongoing - Annual review current environmental enforcement arrangements from Apr 2023 to be in place for 2024 - April 2023 - ongoing with the annual provision of smart bin technology |  |
| LBS9 | Reducing Environmental Impact | Waste Minimisation Strategy - encourage civic pride and local ownership of spaces by making it easy for people to get involved. | - Promoting and supporting community clean ups and waste minimisation initiatives by encouraging residents to take ownership. - Programme of community litter picks, particularly focusing on areas the council is not responsible for or does not clean on a regular basis. Continue to offer litter pickers, gloves, sacks etc. Demonstrate the impact it has through social media and other communications activity. - Promote the Great British Spring Clean. - organise events and promote awareness in the borough - Supporting community led waste minimisation initiatives. | - Reduction in complaints about specific areas. Greater civic pride and ownership of areas; this will not be possible to measure. - Increase civic pride and reduce street litter - Increase the voluntary sector involvement in community led environmental campaigns and activities embracing civic pride values | - N/A - From 2023/24 - From 2023/24 |  |
| LBS10 | Reducing Environmental Impact | Switch to environmentally preferable treatment methods | Continue to minimise general waste being sent for landfill by diverting this waste to the energy recovery facility. - Communications about what should not be put into the residual bin based on issues flagged by the contractor - particularly relating to metal and gas canisters. | - The ERF will cut carbon emissions tonnes per year, compared to landfill operations. | - Ongoing communication campaign. |  |
| LBS11 | Reducing Environmental Impact | Shift towards a decarbonised fleet | - Review fleet decarbonisation options for waste and street cleansing services. Subject to results, depot charging/fueling capacity and Member approval, propose decarbonisation of the fleet in the next waste and street cleansing contract period (beyond 2025). - Explore alternative power/fuel solutions for fleets such as electric or hydrogen vehicles, and the use of ‘transition’ fuels such as hydrotreated vegetable oil (HVO) blends. | - Contribute towards the councils ‘pathway to net zero’ carbon ambitions. - Reduction in carbon emissions associated with the fleet compared to full diesel. | - 2025 - 2025 |  |
| LBS12 | Reducing Environmental Impact | Investigate ways to introduce food waste collection at flats above shops | Through the commissioning of the future waste collections contract (post 2025) investigate options for introducing food waste collections from flats above shops. - Discuss potential food waste collections for the circa 1,200 flats above shops in the borough, this includes: - the need for storage coupled with limited options where to put waste out for collection, and; - the impact on the cleanliness of the local street scene when bags are placed out. | - Increase in recycling. - Reduction in general waste collected from flats above shops. - No impact to street scene and cleanliness | - Discussions to be held Q4 2023/24 - 2024/25 decision to be made |  |
| LBS13 | Maximising Local Waste Sites | Minimise waste and work towards a circular economy | - Promote recycling and reuse at Kimpton Household Recycling and Reuse Centre and continue to support the contractor to achieve a 65% recycling rate from the HRRC. - Promote the site as for recycling and reuse. Build a communications campaign and target visitors to maximise reuse and recycling and reduce general waste - Complete a WCA/bag splitting exercise of general waste and use findings to promote items that can be recycled at the HRRC. - Monitor HRRC recycling rates. - Offer residents a bookable service to help dispose of items on site. | - 65% HRRC recycling rate and borough recycling rate at 50% or higher. - Improve recycling rate by 1.5% - Increase recycling rate - Support for residents to increase visitor satisfaction levels | - From 2023 - Ongoing - From 2023/24 |  |
| LBS14 | Maximising Local Waste Sites | Mayor's London Plan - treat London's waste within its boundaries | Analysis in the South London Waste Plan has determined no further waste sites are required in the borough. Sutton's residual waste is already handled within the borough - at Beddington. Promote community composting, the reuse shop at the HRRC, textile banks and books banks as local ways to reuse or recycle. | - Promoting community composting - Sites owned or commissioned by the council contribute towards the household or municipal recycling rates. | - Promote community composting - Ongoing |  |

5. RRP Action update:

- To be completed annually

- Action table to be updated with new dates/targets etc at same time

| Ref | Action title | Action update | Status Completed On track Not on track On hold Awaiting data Cancelled | Date of Update |
| --- | --- | --- | --- | --- |