Royal Borough of Kensington & Chelsea RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| 1 | Household kerbside residual waste and recycling method and frequency | - A previous study carried out by Resource Futures, and supported by LWARB found that "Whilst there are properties in RBKC that have suitable frontages for containerised collections, our analysis shows there is not the critical mass of such properties to warrant a dedicated round". - We will revisit the work carried out by Resource Futures and assess the scope for introducing a wheelie bin round to 5000 properties. - In the absence of containerisation, we will continue to incentivise recycling by offering an equal number of residual and recycling collections. - We will continue to offer collections twice a week, as the majority of our households do not have space to store waste and recycling for one week. - Residents have fed back via various surveys that the twice weekly collections allow them to use their limited storage space to store the two streams separately. | - CANCELLED | - The decision was taken to not introduce a wheelie bin round as it was deemed the potential increase in the recycling rate of 0.3%, was outweighed by the negatives of the additional street clutter, and the costs and embedded carbon of purchasing new vehicles and bins. There is scope to revisit this once Simpler Recycling, EPR and DRS are rolled out, and the impact on the composition of household waste and recycling can be assessed. | - No increase delivered against expected 0.3% on the household recycling rate |
| 2 | Expand food waste recycling coverage | - We previously committed to modelling how a food waste collection service would impact carbon emissions overall, and if it reduced them, then we would progress with a borough wide food waste roll out. The modelling showed that due to the extra vehicles required, it would lead to an overall increase in carbon equivalent emissions. - Separately, since the RRP was first commissioned, the government has stated, via the Resources and Waste Strategy and DEFRA's consistency consultation, that it will fund the start up and ongoing costs, of introducing food waste collections. - However, we kept our commitment to purchase a new vehicle. There were some slight delays, internally, due to the impact of Covid but the main setback has been due to supply chain issues. The new vehicle took 12 months to arrive, and we have had to push the roll out of the new rounds back due to our caddy supplier increasing their lead time from 5 weeks to 5 months. - We’ve also continued to plan for the boroughwide roll out. We currently have surveyed over 60% of the borough’s households, recording which properties have space for caddies and this work will be complete by September. We will be proposing trials for on-street bins as well as single use sacks, for houses with no storage space, later in the year. We do intend to expand to a full borough roll-out in line with national government requirements, and with the use of the (TBC) funding from DEFRA. - More than quadruple food waste recycling service coverage to 20,000 households, including more estates. - Map and survey the whole borough to assess suitability and locations for storing caddies and communal bins. - Produce a proposal for an evening and weekend food recycling service for commercial customers. We currently have one vehicle, operating collection rounds on Mon, Tues, Thurs and Fri. We have been trying to sign up commercial customers with limited success, as they often need collections later in the day/ night and on the weekend. They also don’t have space for food caddies or bins. We are speaking with bag suppliers to trial a single-use sack for collecting food waste. If this is successful, we will survey businesses with the option for a 6 day a week day and night collection option. To bulk out the weekend day rounds we will add estates and on-street bins. - Have visited Westminster Council to see their on-street food bins, which allow kerbside properties with limited storage space to use food waste. We will put forward our proposal to trial these in RBKC. | - ON TRACK / PART COMPLETE | - Surveying complete. Every household has been visited and their potential for storing caddies recorded. - New food waste vehicle rolled out in June 2023. - 33 estates now can recycle food waste, covering 2,923 households. - 14,373 kerbside households have been offered food waste recycling. - 10 on-street communal food waste recycling bins in housing units have been introduced. - New food waste vehicle will be rolled out in October 2024. - Proposal being drafted to introduce more on-street communal food waste bins, and for the purchase of two more food waste vehicles. - Evening and weekend commercial food waste crew has been put on hold. If this is to work it will be via bag collections (as our bin food waste customers can receive collections during normal domestic hours). In the next month we are trialling food waste bag collections in the day and will pay close attention to spillages, pavement staining and reports of animals ripping open the bags. We have also been working with a bin supplier to design specialised small food bins for commercial premises to store on-street (these will, not be ready for 12 months). | - Food waste from new vehicle increased household recycling rate by 0.5% against an expected target of 0.46%. - No increase from commercial food waste against expected increase in LACW rate by 0.08% - By April 2025, 25,000 households will have been offered food waste recycling (against a target of 20,000) |
| 3 | Increasing recycling capture from estates and flats | - Previous work has involved making sure almost every estate we collect from (covering 25,000 households) has sufficient recycling infrastructure (there are a few where it is just not possible). This includes converting rubbish chutes to recycling chutes, increasing frequency of collections and swapping frequently contaminated bins for reverse bins (with locked lids and a cage at the bottom, for crews to see inside). We also work closely with caretakers, resident associations and housing providers to identify areas for improvement. We've delivered reusable bags and leaflets to every estate, installed recycling signage, and carried out estate action days to promote waste minimisation and recycling. At appropriate sites that are managed, we now deliver disposable recycling bags instead of reusables. Small new builds are offered free recycling bins. - Improve recycling quality and reducing contamination at flats and estates through implementing Flats Recycling Package (FRP) interventions. - Commitment to audit and refurbish bin store areas up to the standards of the 'Flats Recycling Package' at 10 estates in the borough, e.g. carrying out improvements to signage, communications, bins, bin stores and establishing regular servicing & cleaning frequencies. - Further expansion of the FRP to more communal bin store areas across the borough. - Recycling and contamination communications campaign targeted at estate residents; use of own Hubbub campaign toolkit as well as ReLondon cost of contamination toolkit & contamination resources and communications supported by ‘London Recycles’ templates and resources. - Pilot project to close old rubbish chutes on 1 estate, using funding from the Council’s green fund. - Establish partnership with local charity such as REWORK, Emmaus or Bright Sparks to provide good quality items collected via clear outs and too big for the bin collections for onward reuse. - Continue to provide estates with information regarding reuse and community sharing networks, including putting posters in bulky waste stores and notice boards. | - ON TRACK AND ONGOING | - Continued to visit all estates reported on crew’s daily contamination report sheets, as well as proactive site visits. - Closed rubbish chutes on one estate and introduced a new external waste and recycling bin storage area. Further roll out delayed due to difficulty in securing resident support. Work in this area continues. - In the last 12 months, interventions have been delivered to 73 estates, including relocating recycling bins, adding more bins, increasing the frequency of collection, adding and updating signage and stickers, doorknocking and reusable bag drops. - 39 of the estates worked on received the full flat recycling package intervention (signs, stickers, bags delivered and doorknocked). - New leaflets for estates and bin area signage have been designed and delivered. | While it’s not practical to measure the impact of these smaller interventions, we did see our overall contamination rate reduce from around 15% to 10% following the work of the Recycling Monitoring Officers. |
| 4 | Increase recycling capture from kerbside properties | - Previous work has included working closely with crews to identify frequent contaminators then educating residents via doorstepping and comms. If their behaviour doesn't' change, we stop delivering recycling bags to the address. - Will carry out doorstepping on targeted rounds covering 15,000 households a year. - Gather data from residents who struggle to receive their recycling bags and find better ways of distributing to them. - New recycling bag contract to ensure residents have the quality and quantity of recycling bags to help them recycle. - Recycling leaflet in every pack of recycling bags and posters for bin cupboards and shared hallways - Monitor food waste recycling participation rates and follow up with caddy hangers and doorknocking. | ON TRACK AND ONGOING | - In the 2023/2024 financial year, four kerbside rounds were worked closely with. This included route riding, crew training, targeting households not recycling or contaminating with comms and doorknocking and stopping the delivery of recycling bags for households repeatedly contaminating. - 14,000 households were doorknocked (slightly under the 15000 target, due to staff shortages and additional pressures from the food waste roll out) | While it’s not practical to measure the impact of these smaller interventions, we did see our overall contamination rate reduce from around 15% to 10% following the work of the Recycling Monitoring Officers |
| 5 | Crew training and reporting | - Continue annual training of our contractor to improve their operations to maximise recycling capture and minimise contamination. This includes tailored training for container and kerbside crews. - Introduce new in cab technology reporting system CORE, to give officers live key data, e.g. missed collections, contamination, rubbish dumping | - ON TRACK / PART COMPLETE | - As part of the route-riding above, bespoke training was delivered for each crew. - Changes have been made to the overall training delivered to all crews, including the content and frequency. New training encourages maximising recycling capture while also being mindful of contamination. - The implementation of CORE is ongoing. This has been set back due to ongoing IT and data issues. | While it’s not practical to measure the impact of these smaller interventions, we did see our overall contamination rate reduce from around 15% to 10% following the work of the Recycling Monitoring Officers |
| 6 | Commercial waste and recycling | - Continue to offer a discounted rate for recycling to our commercial customers. - Continue to follow up-on commercial reports of contamination swiftly, educating customers in the first instance and taking away recycling bags or bins after repeated misuse. - The domestic recycling team and commercial waste team are now under one manager (as of Jan 22), which will allow more alignment in communications, and processes to incentivise waste reduction and recycling. - New waste reduction and recycling training for sales staff - New incentives and targets to be introduced to sales staff to encourage recycling over waste contracts. - New environmental business charter for all businesses to sign up to. Pledges and guidance given around plastic waste reduction, maximising recycling capture, consolidating collection contracts with local businesses and making use of sharing platforms and encouraging businesses to adopt circular economy practices. | - ON TRACK / PART COMPLETE | - CW sales staff trained in recycling, including how to encourage customers to recycle correctly. - New recycling comms materials designed and delivered for CW customers. - A Business Environmental Charter has been drafted and submitted for internal approval. The Business Environmental Charter is voluntary and allows any size or type of business from all sectors to join and to make an official public pledge to do their bit in tackling the climate and ecological emergency and reduce their environmental impact across a wide range of environmental themes. Signatories will be supported every single step of the way with technical guidance and toolkits, bespoke resources, a series of events and trainings, knowledge-sharing, promotion and grants/funding where possible. The Charter outlines a set of environmentally impactful actions separated into 10 themes that relate to a business, organisation or institute’s operations and management, one of them being related to waste and circular economy: Reduce waste across buildings and operations, embedding a reduce, reuse, recycle culture. A soft engagement with several businesses and SMEs across the borough was carried out in 2023 to assess what type of support is needed, which key environmental areas are more important for them, their challenges and their appetite for signing up. All the feedback has been analysed and has informed the environmental charter. The charter and sustainability support for businesses will include advice and guidance on waste reduction, phasing out single use plastic pledges to encourage businesses and SMEs to adopt circular economy practices and initiatives. Currently reviewing the lessons learned from other boroughs who have adopted similar charters. | Not practical to measure the impact of these smaller interventions. |
| 7 | Garden waste | - Continue to offer a separate (subscription), garden waste collection service. This will be promoted on our website and intermittently through social media and local communication channels, as well as directly to garden squares. - Continue to educate and target properties that contaminate, based on data from live crew reporting. - Have increased garden waste tonnage from 288 tonnes in 16/17 to 430 tonnes in 21/22. Also increase subscribers from 1385 to 1839. - Continue to offer a free separate Christmas tree recycling service every year, both from kerbside and at collection sites. Continue to seek to increase the number of collection points. | ON TRACK AND ONGOING | - In 23/24 the garden waste service had 1870 subscribers. - 74 tonnes of Christmas trees were collected and recycled. | Not practical to measure the impact of these smaller interventions. |
| 8 | On-street recycling bins | - Previously installed bin housing around our recycling banks, with bespoke artwork - some of which was chosen by the local community. We will maintain these and the charity banks located throughout the borough. This has been made possible by working with our enforcement team and charities (responsible for the charity banks), to minimise rubbish dumping and resident complaints. - Look for one new location for an on-street recycling bin unit | ON TRACK AND ONGOING | - 10 on-street recycling bins now have food waste recycling as well. - Clothes bank added to one on-street recycling bin. | Not practical to measure the impact of these smaller interventions |
| 9 | Waste reduction and recycling events | - Hold at least 10 events a year, including clothes swaps, refill, reusable nappy demos, electrical and clothes repair workshops and recycling demonstrations. - Organise 3 tours of the MRF a year. - Locate vacant spaces accessible to the council e.g. within local shopping centres or high streets and deliver a programme of ‘pop-up’ repair café sessions. | - ON TRACK / PART COMPLETE | - Five events were held (instead of ten), due to staff shortages- priority was given to expanding food waste and the kerbside and estates recycling interventions (e.g. doorknocking). - Two sustainability events delivered on the Portobello Market, in June 2023 and September 2023. - Two reusable Nappy Events delivered in collaboration with The Washable Nappy Company. - MRF tours now covered under action 14. | Not practical to measure the impact of these smaller interventions |
| 10 | Communications | - Deliver annual communication campaigns making use of a wide variety of channels and resources, including digital and social media. - Create updated materials for estates, kerbside and commercial customers - Create new materials promoting waste reduction - Create materials linking the benefits of waste reduction and recycling in term so savings carbon emissions - Review and update domestic and commercial waste and recycling websites | ON TRACK AND ONGOING | - Some new comms materials have been produced, such as a new kerbside recycling leaflet, new signage for estates, new food waste leaflets and a new recycling leaflet for estates. - A range of new comms materials for CW due to be delivered in the next few months. - Waste reduction information has been added to our website www.rbkc.gov.uk/recycling - New carbon savings report designed for CW customers to encourage recycling and waste reduction. - Commercial waste website simplified and moved off old microsite: www.rbkc.gov.uk/commercialwaste | Not practical to measure the impact of these smaller interventions |
| 11 | Notting Hill Carnival | - Continue to send all waste collected from Notting Hill Carnival to a dirty MRF. - Continue to offer stallholders a separate food waste collection (introduced in 2018) - Continue to work with Thames Water to offer water refill points to reduce single-use plastic bottles. - Explore the viability of introducing reusable cups | PART ONGOING / PART CANCELLED | - The carnival food waste recycling collection service has been removed due to heavy contamination. Different methods were trialled with comms and training delivered but the level of contamination was always unacceptable. - The introduction of reusable cups has been parked, due to logistical difficulties | Not practical to measure the impact of these smaller interventions |
| 12 | Additional materials | - We collect all of the main dry recyclables including drinks cartons (Tetrapaks). We collect batteries from a number of community spaces, such as libraries, across the borough. We work closely with Traid and promote their free home clothes and electronic collection service. - We put ourselves forward for the flexible packaging collection trial, FlexCollect, led by Suez in partnership with Ecosurety, RECOUP and WRAP. Unfortunately, after several meetings with Suez, they were unable to find a solution that could work with our collection systems and MRF. We will continue to seek opportunities to expand the range of materials we can collect. | ON TRACK AND ONGOING | - No new developments | Not practical to measure the impact of these smaller interventions |
| 13 | Internal Recycling | - Clearly marked, separate waste and recycling bins are located throughout all our main offices, libraries and satellite offices for many years. - New recycling posters recently were distributed to all offices. - Internal green champions to promote waste reduction and recycling comms to wider staff to raise awareness. | ON TRACK AND ONGOING | - Food waste recycling introduced to Council buildings. | Not practical to measure the impact of these smaller interventions |
| 14 | Schools and education | - WRWA run daily class trips (across the 4 boroughs), to the Smugglers Way Education Centre, a programme of assemblies and workshops in schools and online tours and workshops, promoting the 3Rs. These are hands-on, fun activities which engage children with the topic of waste and their responsibilities for looking after our environment. They include stories, songs, craft activities, recycling races, papermaking and getting hands dirty by literally sorting through the bins to get to the bottom of how well schools are recycling. - In the 2021/22 academic year, 17 RBKC primary schools have either visited the Smugglers Way Education Centre or received an online workshop (8 on-site tours and 21 online workshops). - We will continue to maximise the use of the Smugglers Way education centre over the next couple of years. As we anticipate the Education Programme being fully booked again next year, we will also be producing more resources for schools to use themselves and spread good practice across schools as much as possible. We will also be continuing to encourage schools to sign up to the Surfers Against Sewage Plastic Free Schools scheme. - Continue to offer free recycling collections to schools, as well as discounted food waste collections. - Publish regular communications about recycling into the schools’ newsletter. | ON TRACK AND ONGOING | - In the 2023/24 academic year, 13 RBKC primary schools have either visited the Smugglers Way Education Centre or received an online workshop (11 on-site tours and 2 in school workshops). - One MRF tour for an adult group in Feb 2024. Should hold more in 24/25, as we are recruiting a second Education Officer. | Not practical to measure the impact of these smaller interventions |
| 15 | Food waste reduction | - Promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events. Food prevention workshops held at community events and WRWA to deliver engagement to reduce amount of food waste disposed of per household - Explore partnership and local promotion of food sharing apps in the borough - Distribute fresh pods at community events - Complete application to become a demonstration project partner for the Food Flagship Initiative - for example a project to reduce the environmental impact of school meals, or a food redistribution network (to be confirmed) in the borough by March 2025. Support three local businesses with application to Food Flagship Initiative. - Potential to pilot a programme for 5 schools to use Olio to distribute surplus food within the nearby community. | PART ONGOING / PART CANCELLED | - All five events in the last financial year, included food waste reduction information such as that from Love Food Hate Waste, Hubbub and OLIO. - Fresh pods distributed at all recycling events. - A Schools Environmental Charter has been produced and submitted internally for review and approval. This allows schools to make an official public pledge to do their bit in tackling the climate and ecological emergency and reduce their environmental impact. Throughout the process, the Council will support the schools with training, resources and grants to help them achieve this. Some of the topics included are related to Waste and Circular Economy Initiatives, Biodiversity, Food etc. In addition, the Children’s Parliament on the Environment is being organised every year and every year at least one school has researched a project related to food waste, food growing and/or reducing plastics and waste. - Under the Future Neighbourhoods 2030 programme Phase 3, a Holistic Environmental Programme for schools is being developed and implemented which will include measures such as: energy efficiency retrofitting, food growing initiatives in schools, climate adaptation measures for schools affected by overheating and flooding, air quality and greening initiatives, education and climate change assemblies etc. | Not practical to measure the impact of these smaller interventions. Outputs and impact will be reported once the initiatives are fully implemented. |
| 16 | Incentivise residents to reduce their waste | - Continue to offer residents a range of 40% subsidised composters. These will be promoted on our website and intermittently through social media and local communication channels, including those that are subscribed to our garden waste collection service. - Continue to offer residents free reusable nappy vouchers. These will be promoted on our website, at reusable nappy events and intermittently through social media and local communication channels. - Joined the Restart Project Repair Directory Continue to provide Electrical Repair events with WCL Fixer. | ON TRACK AND ONGOING | - 71 Nappy vouchers issued in 23/24. - Subsidised composters still offered | Not practical to measure the impact of these smaller interventions |
| 17 | REWORK Workshop | - Continue to promote Rework, a reuse workshop, run by Groundwork and established as part of the London Resource funding programme. RBKC residents can donate to the project by leaving their items at the Smugglers Way Household Waste and Recycling Centre, where the Project is based. This is promoted on our website and intermittently through social media and local communication channels, including promoting to residents and businesses requesting 'Too Big for The Bin' (bulky waste collections). - Trial REWORK collection of bulky waste items from Housing management, following the clearing out of vacant properties. | PART ONGOING / PART CANCELLED | - Housing management bulky waste collections parked due to logistical difficulties. - 16.55t tonnes of RBKC waste diverted by reuse, in 23 24. | Not practical to measure the impact of these smaller interventions |
| 18 | Community kitchen gardens | - Community Garden Team continue to work with residents and support them in growing their own food through community kitchen gardens across the borough. This reduces food packaging and facilitates wider conversations around reducing food waste and food waste packaging in general. | ON TRACK AND ONGOING | - The Ecology Service currently maintains 55 community kitchen garden sites and about 650 plot holders across the programme. - All the community kitchen gardens have composting facilities, and the Community Gardeners deliver training in composting to residents throughout the year. - Larger 400l composters installed at Olympia community kitchen garden to cope with high usage. Compost created is used by plot holders across the gardens. | Not practical to measure the impact of these smaller interventions |
| 19 | Single use plastic | - The RBKC green champions network will continue to work with the canteen / cafeteria at Kensington Town Hall to reduce single use plastics. - The Events Team will work to reduce the single-use plastics used in the event Halls. - Committee Rooms at Kensington Town Hall will introduce porcelain cups instead of plastic cups. | ON TRACK AND ONGOING | - A new all-service single use plastic audit due to commence shortly to follow up on previous initiatives. This will cover operations and contracts. - Taking part on the One World Living working group to develop a new plastics pledge and targets for councils. - New public drinking fountains will be ready for use soon. | Not practical to measure the impact of these smaller interventions |
| 20 | Notting Hill Dale Future Neighbourhood | - Delivering new green jobs and skills in a circular economy - New Library of Things and associated Re-Use Workshops - Holistic Sustainability support to local businesses - Pop-up repairs shops at different community spaces in Notting Dale - Supporting a local organisation SPACE to scale up their offer including providing a school uniform swapping service - Green skills academy, focussing on training opportunities for staff, residents and contractors (e.g. Retrofit Coordinator, Passivhaus trainings etc.) - Energy advisor certified and circular economy training opportunities for residents and contractors - Youth Training Programme (40 hours paid AQA training course for 16-19 year olds) Support trainees and unemployed adults (19+ year old) to gain qualifications / certifications in green skills and manage work placements with partner organisations through the delivery programme. This would act as a steppingstone for local residents to gain employment in green jobs. - Notting Dale 2030 Project Manager role - targeted recruitment within North Kensington |  | - Green Skills Academy: 84 People have been trained under the green skills academy. The project did result in the creation of one job, a Project Support Officer for the Green Skills Academy. One sharing initiative was established by setting up an equipment library for measuring energy efficiency, available for use by trainees. Four local businesses received decarbonisation training. Three jobs paying at least the London Living Wage were created, including two through the academy and one to support its operations. The project conducted 10 workshops on the circular economy and climate change/energy. - Youth training programme: AQA 40 hours paid training for young people – 16 to 19 years old. 26 young people participated, with 22 work placement experiences completed, 10 core modules related to sustainability, renewables, community energy etc. 723 hours of paid training at London Living Wage. - Pop-up repair workshops: Pop-up Repair Shop Delivery project under Future Neighbourhoods 2030 has been completed. It achieved a reduction of 1879 kg of CO2 and prevented 136 kg of waste, corresponding to the same amount of CO2 reduction. The project implemented one sharing initiative and conducted 15 repair workshops, as well as 15 workshops focused on the circular economy and climate change/energy. Existing sustainable businesses and grassroots community groups, including WCL Fixes and The Restart Project, were involved. Six volunteer opportunities were created, and volunteers contributed a total of 386 hours. - Bike repairs: Bikeworks delivered 7 bike repair sessions (in phase 2) in various points in Notting Dale. The bike repairs were delivered to 79 residents in total. - Any upcycling initiatives: 15 upcycling clothes workshops/sessions delivered as part of Phase 1 Future Neighbourhoods. - As part of the household furniture upcycling initiative in Phase 2, furniture has been distributed to residents and more donations received. 31 households have been served so far and 29 items re-distributed. - The Library of Things (LOT) have been installed at North Kensington Leisure Centre in September 2023. We have been monitoring the borrows monthly and carried out promotion to boost uptake. There were 85 borrow in March, 66 in April and 86 in May. - The local organisation Space is one of the local partners in the Notting Dale Future Neighbourhoods 2030 programme, supporting hundreds of families with uniforms, clothes, food etc. Space also set up a local parents forum to help tackle the cost of living crisis. To respond to the needs of the community and residents and the cost of living crisis, Space had to extend the service to clothing for children of all age and parents including warm clothes. SPACE have also engaged with their service users plus with their 82 active parents included in the Space Cost of Living Crisis Parents Forum set up to tackle the cost-of-living crisis. They have over 500 responses from local users of the service. A main theme of this consultation has shown a desire to branch out from just doing food and clothes (which they currently service) to do a wider array of goods including bulkier items such as furniture. More information on the project here on the story map https://storymaps.arcgis.com/stories/807cd8fa79934f67a14cda4d18b4454c and FN website - https://www.rbkc.gov.uk/environment/climate-change/notting-dale-future-neighbourhood-2030 | We are reporting the impact of these initiatives and the outputs and outcomes as part of the Future Neighbourhoods 2030 programme. |
| 21 | Planning | - New Greening SPD now includes detailed information on the circular economy: https://www.rbkc.gov.uk/committees/Meetings/tabid/73/ctl/ViewMeetingPublic/mid/669/Meeting/8372/Committee/1593/Default.aspx - The waste team will continue to comment on new developments ensuring they have sufficient capacity for dry recycling and food recycling and are designed to incentivise waste reduction and recycling. - The Draft New Local Plan Review includes policies on Circular Economy and Waste Management which intend to reduce waste and ensure that new developments provide waste and recycling storage facilities. | ON TRACK AND ONGOING | - We have updated the RBKC Waste Storage Guidelines document with an up-to-date recommendation on space required for waste, recycling and food waste storage for the new developments. - Greening SPD was adopted in June 2021 and includes detailed information on the circular economy and how to meet Local Plan policy requirements: - https://www.rbkc.gov.uk/planning-and-building-control/planning-policy/greening-spd - The New Local Plan Review includes policies on Circular Economy and Waste Management which intend to reduce waste and ensure that new developments provide waste and recycling storage facilities. The Local Plan was adopted at Full Council on the 24 July 2024. | Not practical to measure the impact of these smaller interventions |
| 22 | Procurement | - July 2021 - Circular economy principles have been submitted to be included in the new social value element of procurement. - Circular economy training delivered to procurement staff | ON TRACK AND ONGOING | - No new developments | Not practical to measure the impact of these smaller interventions |
| 23 | Vehicles | - Trials of electrical waste collection vehicles were ongoing throughout 2022 to help plan our transition to fully EV waste fleet. - The small vehicle fleet will continue to be replaced by EVs over the next couple of years as the existing lease contracts expire - We currently have 21 charging points installed across our sites, with more to come shortly. - Eco driving training has been rolled out for staff and we will continue to offer this - Enforcement and bag delivery vans can go electric once the new fleet lease contract has been procured this year - We currently have approximately 120 small vehicles on our fleet. Our Green Fleet Strategy stresses the need to reduce mileage where possible so this number will reduce over time. - We currently have 80 vehicles related to our heavy waste fleet We are working closely with UKPN to have additional electrical capacity hooked up to our Pembroke Road depot, as current capacity is insufficient. The supply has to be laid from approximately one mile away and is a large undertaking. | ON TRACK AND ONGOING | - New small fleet provider contract now procured and live, this includes a variety of EV lease options for fleet users - Small fleet will continue to transition to EV as charging infrastructure allows - We currently have 33 charging points across a variety of operational sites, with more to come - Eco driving training has been rolled out for staff and we will continue to offer this if required and funding identified. - Trials of various electrical waste collection vehicles ongoing to help plan our transition to fully EV waste fleet. - We are currently developing charging infrastructure arrangements for our heavy waste fleet. We have already deployed a variety of small EVs for waste collection and cleansing activities. - Our Grounds Maintenance contract is now fully EV. | Not practical to measure the impact of these smaller interventions |
| 24 | Waste disposal | - Current waste disposal emissions https://wrwa.gov.uk/wp-content/uploads/2021/06/WRWA-21-14-Carbon-Metric-report2.pdf - WRWA is about to start the process of developing a new Joint Waste Strategy with the collection authorities, which will consider:- - the future requirements for improving recycling rates and managing waste streams to minimise environmental impacts; - the future services for recycling collections, including separate collections of food waste and adding on more dry recycling materials to existing services; - waste prevention and reuse activity to tackle resource efficiency and reduce waste from entering the system in the first place; - the carbon impacts of WRWA’s current and future activities, measured in a transparent way; - WRWA monitors its’ contractor, Cory’s plans to reduce emissions to achieve the UK Govt’s Net Zero target, which are set out in their sustainability report: https://www.corygroup.co.uk/application/files/7216/6066/0318/Cory_Sustainability_Report_2021.pdf - In addition, Cory are signed up to the Environmental Services Association’s Net Zero strategy which has a target to reduce emissions from waste management activity and achieve Net Zero by 2040 – 10 years before the UK Govt target. Cory’s Sustainability Report has an ambition to bring this forward to 2030. | ON TRACK AND ONGOING | - The plan is for the new Joint Waste Strategy to be formally adopted at it’s February 2025 Committee Meeting. RBKC, along with other constituent collection authorities, will be asked to formally endorse and adopt the final JMWMS at their own Council meetings prior to this. | Not practical to measure the impact of these smaller interventions |
| 25 | Household Waste and Recycling Centre | - The Smugglers Way HWRC accepts a wide range of materials for reuse and recycling, including garden waste, scrap metal, hardcore, small appliances, wood, timber, mixed paper, card, TVs and monitors, batteries, books, CDs, DVDs, cooking oil, engine oil, fridges and freezers, gas bottles, large appliances, microwaves, mixed lightbulbs and fluorescent tubes, mixed textiles and shoes, printer cartridges, water and oil-based paint and spectacles. - We have been trialling Rigid Plastics on the HWRC for a few months now. Cory has a reliable outlet for rigid plastics and a container has been made available at the Smugglers Way Household Waste and Recycling Centre which will accept many types of rigid plastic items. - We will continue to publicise the HWRC through various communication channels, including making the information available on our website. WRWA continue to seek to expand the range of materials received at the Centre, providing there are outlets available that are sustainable and make it financially viable to do so. Currently, the Smugglers Way site copes well. | ON TRACK AND ONGOING | - Rigid plastics now accepted at the HWRC, and over 2.5 years, 437 tonnes have been collected. | Not practical to measure the impact of these smaller interventions |
| 26 | Planning - apportionment targets | - The Council has prepared a Waste Data Study. The available waste management capacity in the borough is 90,600 tpa. The adopted London Plan sets a waste apportionment target of 123,000 tonnes in 2041 for the borough. https://planningconsult.rbkc.gov.uk/gf2.ti/f/1364450/124977509.1/PDF/-/04%20Blue-Green%20Future%20Waste%20Data%20Study%20Feb%202022.pdf We will continue to pay to license Cremorne Wharf as a waste transfer station, and work with other boroughs to identify where we can combine capacity. | ON TRACK AND ONGOING | - The Council’s Waste Data Study (2022) identifies a waste management capacity gap of 32,400 tonnes of LACW. The Council has worked with the London Borough of Hammersmith and Fulham, and the Old Oak Park Royal Development Corporation who have agreed to share 32,400 of surplus waste management capacity within their area to meet this Borough’s waste management needs. This has been agreed through a Statement of Common Ground that support the New Local Plan Review. | Not practical to measure the impact of these smaller interventions |
| 27 | Markets | - Develop Portobello Market as a Green Market – including waste reduction initiatives, food waste, removing single use plastics and promoting the circular economy. See Market Plan 2022-25 - Food waste collection - Action C 11, - Clothing diversion from waste to recycle and Traid scheme Action C 11. TRAID clothing bank has been installed in Tavistock Depot for traders/ local community use. Collection scheme with Suez - Bulk buying opportunities for food containers etc Action C 14 - Already have a shopper bag that has been running over 10 years - Streetrunner delivery service for shoppers who order online from traders and retailers in the area - Sustainable education market (first held last December, more to follow) Action C 12. - Review plastic bag alternatives with traders Action C 14, - Waste audit to establish what else can be diverted from waste streams e.g. furniture, books, etc Action C 10, Completed in 2022 - Minimise collecting recycling cardboard in plastic sacks Action C 13, - Plan to bring in fountains to minimise water bottle need Action C 15, | ON TRACK AND ONGOING | - Several sustainability market series at Portobello Market have been organised, featuring eco-friendly sessions, info points on recycling, climate change, air quality and biodiversity initiatives, bike repair stations and fun activities around Re-Use, Repair and Recycle. - First Community sustainable and affordable market in Notting Dale: Following the successful sustainability fairs organised at Portobello Market and the requests received from residents during the FN2030 consultation, a smaller scale community affordable and sustainable market will be organised in Notting Dale as part of the Phase 3 Future Neighbourhoods 2030 programme (see Action 20). - Targeted enforcement education along the market streets has been ongoing throughout the year, which has seen improved presentation of waste especially recycling and uptake of recycling waste contracts. - Clothes bank is still operating with no complaints so far. Regularly used by whole community. - Shopping bag still widely successful with shoppers. - Streetrunner still in operation - Building on the success of last year’s markets, currently looking at a location that will hold up to 20 stalls. - Planning to add an additional event at the Worlds End Market as well as an event at Tavistock Square - Small Business Saturday on 30 November 2024. - Working with LoT to promote the service. | Not practical to measure the impact of these smaller interventions |