- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 344.2 | 300 | 328.2 | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 743 | 640 | 668.2 | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 59.33 | 55 | 79 | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70% Unavoidable food waste in residual: 30% Avoidable food waste recycled: 44% Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 25.4% | 35% | 30.2% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 24.7% | 35% | 29.1% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 0% | 0% | 0% | 10.5% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 99% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 0% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 99% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 0% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 0% | 100% | 0% | 0% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| LBR1 | East London Waste Authority Waste Prevention Programme (WPP) | - In September 2024, ELWA Members agreed to make the Waste Prevention Programme an ongoing part of ELWA’s budget and programme meaning that annual approval to continue the funding will no longer need to be sought. - The programme includes several projects and initiatives across a range of waste streams, which will be delivered in collaboration between: ELWA; the four Constituent Councils; the IWMS contract Operator and its communications partner; and other stakeholders. - The action plan for 2023-24 is available on the ELWA website. An action plan for 2024-25 will be developed later in 2023. - ELWA is contributing to the pan-London food waste reduction campaign, both through funding on behalf of the four Constituent Councils as well as participation in both the steering group and project board for the campaign. - Actions LBR2 to LBR11 link to the ELWA Waste Prevention Plan and include additional actions that the Redbridge is conducting to enhance the impact within the borough. | On track | - The East London WPP has been approved as a permanent part of the ELWA provision to include a range of projects and services focusing on key material streams. - ELWA was part-funding the regional Eat Like A Londoner campaign as part of the WPP, working with ReLondon and other London local authorities over a 3-phase programme until March 2025. - The WPP is delivered in partnership with the four Constituent Councils, working alongside community partners and third sector organisations to enhance reach and impact of the interventions. | - Community Composting - WEEE collection points - Repair cafés - School recycling workshops - Clothes swaps - Reusable nappies scheme - Food waste workshops - eastlondonwaste.gov.uk/campaigns |
| LBR2 | Support home composting initiatives | - Promote community composting schemes through facilitating community ‘cascade learning’ about composting - Promote composting as a focus in Great Big Green Week with a promotional discount on compost bins during this period. - Provide advice on composting at all events, roadshows and across all comms platforms throughout the year and at key festivals/events like Halloween/Compost Awareness Week | On track | - 31 ESOL (English for Speakers of Other Languages) classes were delivered, focusing on waste management and the principles of home composting, helping learners understand both the "why" and "how" of composting. - 15 in-person composting workshops provided hands-on learning opportunities for residents. - Composting advice was consistently shared at all public-facing events, including roadshows and doorstep interactions. - Composting was featured in four editions of the Our Streets council e-newsletter (reaching approximately 17,000 subscribers), aligned with key awareness campaigns such as International Compost Awareness Week and Food Waste Action Week. - Free online composting training remained available to residents, delivered by Garden Organic and funded by ELWA. - Subsidised compost bins continued to be offered to residents through GetComposting, funded by ELWA. - The original community composting site expanded from one 330L bin to four, reflecting increased demand and participation. - Four new community composting sites were established across private estates, parks, and community venues such as youth centres. These sites were equipped with free compost bins funded by ELWA. | - 678 residents participated in face-to-face composting sessions, 429 through ESOL classes and 249 via community workshops, helping to increase awareness and understanding of composting. - 21 subsidised compost bins were purchased by residents through the GetComposting scheme. - In 2024/25, a total of 119 residents across the four ELWA boroughs successfully completed the online Garden Organic composting course. - There are now 10 community composting sites available across the borough, offering composting options for residents who lack space to compost at home. |
| LBR3 | Encourage parents to use reusable nappies. | - Continue to provide £5 trial packs of reusable nappies to families with children under 18 months. - Work with ELWA to promote the use of reusable nappies through social media, face-to-face engagement, local press adverts, Redbridge Life, and other communication channels. | On track | - £5 reusable nappy trial pack continued to be offered to families/carers with children under 18 months. - Two in-person reusable nappy promotional stalls held. - Two articles dedicated to Reusable nappies in the Our Streets council e-newsletter (reaching approximately 17,000 subscribers), aligned with key awareness campaigns such as Reusable Nappy Week - In 2025 we’re revising our policy on requests for larger bins due to nappy waste. The updated approach will include a time-limited provision for extra capacity, allowing us to re-engage with households around 18 months with potty training advice to help reduce waste. This change also provides an opportunity to promote our cloth nappy trial pack scheme through targeted communications. | - 46 reusable nappy packs distributed in 2024/25. - This equates to carbon savings of 6,976.54 kg CO₂e. - Indicative figures suggest a reduction in residual waste in 2024/25 – though this cannot be directly linked to reduced nappy waste. - Waste composition analysis shows that nappies make up 61% of the sanitary waste category, accounting for approximately 6.7% of Redbridge’s total residual waste stream. |
| LBR4 | Encourage residents to shop more sustainably | - Promote and practically embed sustainable shopping within Redbridge. | On track | - Reusable nappy packs distributed via local refill shop to support shop and collectively promote waste minimisation activities. - Keep Britain Tidy’s ‘Waste Hierarchy’ graphics used across comms platforms. - ‘I Love Redbridge’ cloth tote bags distributed at events where waste minimisation education has taken place. | - Six articles about sustainable shopping published in the Our Streets council e-newsletter, reaching 17,000 residents. - Two articles promoting local refill shop published in the Our Streets council e-newsletter. |
| LBR5 | Reduce avoidable food waste in Redbridge | - Explore partnership and local promotion of Olio, Kitche & the ‘Too Good To Go’ apps in the borough. - Work in partnership with internal (i.e., Climate, Anti-Poverty, Public Health, Child Friendly Borough) and external stakeholders (ELWA) to promote waste reduction activities such as Love Food, Hate Waste through public stalls, community events and partnership settings. Engagement and community learning to enable reduction in amount of food waste disposed of per household. | Part complete | - Though no formal partnership agreements are currently in place, food waste apps are promoted at events and through corporate communications. - On steering groups for, or working closely with Climate, Anti-Poverty, Public Health and Child Friendly Borough colleagues to ensure food waste messaging is shared widely. - 31 ESOL classes were delivered, focusing on waste management and the principles of Love Food Hate Waste. - Four ELWA funded live cookery workshops were held with a professional chef to showcase cooking with a Love Food Hate Waste mindset. - Phase 1 of the separate food waste collection service will launch in November 2025. The rollout is expected to encourage behavioural change through increased awareness and engagement, as residents begin to see and reflect on the volume of food waste they generate. | - 470 residents attended in-person sessions about composting (429 via ESOL and 41 via workshops) – helping to reduce food waste and save money. - From the latest analysis, 24.83% of the residual waste bin was edible food. |
| LBR6 | Side Waste Policy | - Continue to implement the no side waste policy that was introduced in 2020 to restrict the amount of residual waste resident place out for collection - Implement face-to-face engagement is areas where crews are consistently reporting side waste to assist residents in reducing the amount of waste that they put out for collection and increase their use of recycling | On track | - The side waste policy was upheld, with ongoing encouragement for collection crews to continue reporting instances of side waste. - Outcomes from the side waste project were shared with crews to demonstrate how their reports have directly contributed to service improvements - The structured four-stage approach to addressing properties that repeatedly present side waste remains in place: - Stage 1: Properties identified as presenting side waste five or more times within a three-month period receive a Stage 1 letter, outlining their responsibilities regarding waste disposal. - Stage 2: If side waste continues to be presented two or more times over the following three months, a Stage 2 letter is issued. This reiterates waste responsibilities and advises that an in-person visit may follow if issues persist. - Stage 3: Properties that continue to present side waste two or more times over the next three-month period are visited by Neighbourhood Engagement and Education Officers (NEEOs) to provide direct support and guidance. - Stage 4: If behaviour does not improve following NEEO intervention, particularly in cases involving suspected HMOs or clear environmental enforcement concerns, the property is referred to relevant teams for further action. This may include issuing Community Protection Warnings (CPWs) or investigating property licensing issues. | In 2024/25: - 357 Stage 1 letters were issued to households. - 171 Stage 2 letters were subsequently sent following non-compliance. - 99 doorstep visits were carried out by the NEEO team to engage directly with residents. - 10 cases (approximately 2% of total households contacted) were referred to Environmental Enforcement. - 19 cases (approximately 4%) were referred to Property Licensing for investigation. - Following either Stage 1 or Stage 2 letters, 72% of households successfully reduced side waste to below the threshold, eliminating the need for an in-person visit. - Indicative figures suggest a reduction in residual waste in 2024/25 – though this cannot be directly linked to the side waste project. |
| LBR7 | Encourage sustainable fashion | - Continue partnership with TRAID to collect textiles for reuse. - Explore the option to close the resource loop and set up a TRAID charity shop in Ilford Town Centre - Promote bookable textiles collections through Redbridge Life, the Councils website, social media and at roadshows and events. - Create and promote a sustainable clothing webpage to encourage residents to buy second-hand and make what they already own last longer. | On track | - The partnership with TRAID to collect textiles for reuse is continuing. This has been promoted through Council e-newsletters, social media channels, at events and roadshows, and whilst doorstepping. - A permanent TRAID charity shop in Redbridge is not currently feasible for TRAID. The possibility of pop-ups continues to be explored. - Two clothes swap events took place in 2024/25 in partnership with ELWA. - ‘Love your clothes’ webpage promoted via Our Streets e-newsletter, social media channels and in-person | - 446 bookable textiles collections took place in 2024/25, totalling 12 tonnes of collected textiles. - There were 1,996 views on the Love Your Clothes webpage in 24/25 |
| LBR8 | Appraise the setup of an initiative to encourage the lending of things within Redbridge | - Partner with a social enterprise such as ‘Library of Things’ as part of LBR Waste Reduction Strategy and ELWA Waste Prevention Plan. Locate space for object lending library such as a library or town centre retail space. - Promote the facility in a broad and targeted way - Encourage residents to share through existing sharing platforms including Freecycle, Freegle, etc | Part complete | - Partnership with ‘Library of Things’ was not feasible in 2022/23 but is being revisited in 2025/26 with further data insights from LoT and LBR. - Re-use and lending are promoted through ESOL classes, face-to-face engagement and roadshows that are held across the borough | - 429 ESOL students received in-person advice about re-use and lending. |
| LBR9 | Increase the reuse of unwanted bulky items | - Continue to encourage residents contacting the council for a bulky item collection to use a third sector organisation if their items are good quality. - Explore partnership with local reuse organisation for the reuse of bulky waste items collected at the kerbside and at Chigwell Reuse and Recycling Centre | On track | - The Council’s website continues to signpost residents to use third sector organisations where items are of good quality. - A potential incentive arrangement between ELWA and TCL Reuse was explored but not progressed. TCL Reuse remains the primary option promoted on the council website for bulky waste collections. |  |
| LBR10 | Conduct reuse and repair activities | - Promote upcycling and private sales of unwanted furniture/home appliances. - Promote the concept and activity of repair through Repair Cafes in partnership with ELWA. - Support start-up community Repair cafes with networking, advice and where possible, funding. - Provide ‘how to’ simple repair resources/tutorials on Neighbourhood Engagement and Education team’s social media platform. - Map and share the professional/not for profit/voluntary repair providers in and near the borough | On track | - Upcycling and private sales of unwanted furniture/home appliances promoted via Council website. - Continued to support 2 existing resident-led repairs cafes with ELWA funding, resources, promotions, collection of electricals and attendance by NEEO and ELWA officers. - Supported the set-up of a new Repair Café in Wanstead. - A standalone ELWA funded repair café was held in Fullwell Cross Library in March 2025. - London recycles 'repair directory' promoted in Our Streets e-newsletter, to map repair providers in the Borough. The repair directory is signposted on the Council webpage. | - A total of 31 repair cafés were held during the 2024/25 period. - 12 social media posts promoting repair initiatives were published via the Neighbourhood Engagement and Education team’s channels. - One in-person workshop was delivered, focusing on practical skills such as how to sew on a button. |
| LBR11 | Reducing single-use-plastic and promoting waste minimisation in partnership with businesses | - Approach and encourage local businesses in the borough (starting with local high streets in identified areas where there is willing to partner from local community groups) and request they sign up to charter of commitment to reduce the single-use plastic they produce or use, with the aim of creating single-use plastic free areas/zones as per Our Streets strategy objective. - Promote refill scheme to internal officers who liaise with businesses and BIDs to raise awareness of Refill London scheme membership, including providing communications material. - Encourage internal colleagues to move away from single use plastic. Campaign during Plastic Free July 2023 and 2024. | On track | - Joint working approaches are being developed with Environmental Enforcement colleagues to support business compliance with Simpler Recycling Reforms. The LBR Environmental Enforcement team recently received training from ReLondon, and collaboration is in early planning stages. To date, businesses have been informed of their responsibilities through the Business and Enterprise Team in Regeneration. - In 2024, the Council sold its commercial waste service to First Mile. All transferred customers now have access to recycling alongside refuse collection—an option previously unavailable through LBR. | - LB Redbridge Forum attendees have awareness of reuse and refill initiatives. - Plastic Free July has been promoted across Our Streets and Corporate comms channels. |
| LBR12 | Continually improve communication with householders and businesses regarding waste and recycling collection services and RRC (LB Redbridge Waste Reduction Strategy 2019) | - Continue to improve communication with householders and businesses regarding waste and recycling collection services so that the services are clearly understood by everyone: - Place recycling service instructional graphic in every edition of quarterly Redbridge Life - Ensure recycling service graphic supplied to LBR Enforcement officers and collection crews to issue to non-conforming properties - Undertake EQIA of waste management communication and work with specific community groups to increase understanding and participation - Promote information about the range of materials that can be taken to Chigwell Road RRC - Feature a focus material per month on the Our Streets FB page (i.e., a range of materials to increase capture and decrease contamination) - Include the recycling service graphic in the Our Streets E News four times a year - Attend or initiate community events and roadshows to communicate waste management best practise - Undertake internal recycling and waste management education to upskill all LBR colleagues, increasing knowledge base - Deliver a school program focussing on waste and recycling once per academic year - Run departmental and corporate communications campaigns at key points in the calendar year; Big Green Week, Recycle Week, key festivals notably where collection dates also change. | On track | - Myth-busting articles on single-use plastics, Tetra Paks, and composting were published via the Our Streets e-newsletter and shared across Neighbourhood Engagement and Education team social media channels. - A recycling service infographic was featured in Redbridge Life to raise awareness and improve understanding. - Picture-based messaging continues to be used, in line with recommendations from the Equality Impact Assessment (EQIA). - The Chigwell Road Reuse and Recycling Centre (RRC) was promoted through the Our Streets e-newsletter. - Waste management advice was provided at all in-person engagement events. - Articles addressing common recycling contaminants - such as Tetra Paks, soft plastics, nappies, and food waste - have been shared on the Our Streets Facebook page. These posts aim to raise awareness and guide residents on the correct disposal methods for these materials. - A dedicated schools webpage is in development, which will include tailored waste management guidance and signposting to relevant resources. - The Schools Essay Competition on “How to reduce carbon emissions in Redbridge” received 59 entries. 12 winning students were invited to City Hall, where they shared their ideas with Mete Coban, Deputy Mayor of London for Environment and Energy. - ‘The Future of Waste and Recycling in Redbridge’ consultation received 341 responses and provides insights for future comms and engagement. | - 12 workshops and school assemblies were delivered during 2024/25, reaching a total of 878 students. - 26 community events and roadshows were held throughout the year, engaging with over 1,700 attendees. - The indicative recycling rate for the period stands at 30%. - The latest report shows a 30.4% contamination rate, representing a 6% increase since 2021. Targeted communications are being developed to address this issue. |
| LBR13 | Introduction of 180l wheeled bins for recycling services | - Following successful introduction of 180l wheeled bins for residual waste in 2021, explore options to containerise recycling and garden waste service in line with residual to improve services and increase material capture. - Review waste and recycling provision at flats and flats above shops. | On track | - In 2025, Cabinet approved a proposal to modernise waste services by introducing wheeled bins for recycling, aimed at improving crew safety and increasing household capacity and convenience. - Due to ELWA contract constraints, implementation will begin after December 2027. A trial is planned in a Redbridge location with limited recycling access, where current collections require a cushion vehicle due to busy road conditions. - Recycling provision for flats and flats above shops are being reviewed as part of the wider Simpler Recycling reforms. | - An internal growth bid for capital funding for wheeled bins for recycling was submitted and approved in 24/25. - A monthly project board has been established to oversee the implementation of the wheeled bin recycling programme. |
| LBR14 | Introduce a separate food waste collection service | - The establishment of separate food waste collections across East London is a commitment within the Joint Strategy for East London’s Resources and Waste. - These collections are also a new legal requirement arising from the Environment Act 2021. The implementation of this requirement is subject to further regulations and guidance from the Government, the publishing of which has been delayed until at least May 2023. - It is anticipated that the requirement will come into effect from March 2025, although there are now significant concerns across the waste and resources sector about the ability of supply chains for vehicles and containers to meet the national demand this requirement will create. - ELWA and the Constituent Councils are awaiting further information from DEFRA on the requirements and support available for introducing separate food waste collections, before detailed planning for the services can begin. Some of the steps that have been identified for these services to begin across the sub-region are (in no order): - Determination of procurement options for vehicles and containers, including appraisal of options for using existing fleet through operational changes, and evaluation of any joint or framework routes - Identification of public consultation requirements and options - Development of options appraisal for service introduction, as part of developing business case for review by Members - Stakeholder engagement plans developed, to include housing associations and managing agents for properties served by communal waste collections - Formal governance processes for approval of proposed collection services - Procurement process and lead-in times for delivery of equipment and resources - Development and implementation of communications plan(s) for service introduction - Securing of treatment capacity by ELWA’s IWMS contract Operator once further information about rollout of collections is known Continue to work with ELWA and other Constituent Boroughs on identifying and securing food waste treatment before to the end of the PFI IWMS contract | On track | - The procurement of containers and introductory liners for approximately 10,000 kerbside properties in Redbridge has been successfully completed via the YPO framework. A hire vehicle has also been secured to support collections during phase 1 of the rollout. - Storage arrangements for the pilot phase container quantities have been confirmed. - The procurement process for permanent collection vehicles is at award stage. Estimated lead times are anticipated to be under nine months at this stage. - Planning is underway to secure permanent storage for the nine additional vehicles required to support the food waste collection service. - Procurement for containers and liners for the full borough-wide rollout is on track. - Storage arrangements for containers required for the full rollout will be confirmed based on the phased delivery capabilities of the selected supplier. Final details will be available upon contract award. - We are currently awaiting the next announcement regarding new burdens funding to determine the level of ongoing revenue available to support the continued operation of the scheme. This announcement, originally expected in June 2025, has now been delayed until October 2025. - The projected timeline for the boroughwide roll-out is: - Phase 1 (November 2025) - 10,000 kerbside properties - Phase 2 (Spring 2026) – remainder of kerbside properties - Phase 3 (Autumn 2026) – Communal blocks and flats above shops - A monthly project board has been running since August 2023 for the delivery of a separate food waste scheme with representation from all teams that need to be involved/ informed (e.g. finance, housing, communications, fleet) - ‘The Future of Waste and Recycling in Redbridge’ consultation received 341 responses and provided insights into specific comms and engagement planning for the roll out of the food waste service. - Our waste disposal authority, ELWA, are progressing arrangements with local facility ‘ReFood’, an anaerobic digestion plant in East London, for the disposal of food waste collected in LBR. | - Significant progress has been made (see Action Progress Update) but a service has not been implemented to date. - We’ve worked with our collection authority to estimate food waste tonnages expected once the rollout begins. For 2025/26, projections are between 100 and 200 tonnes, rising to between 5,000 and 6,000 tonnes in 2026/27. - These figures haven’t been modelled to assess their impact on overall recycling performance. Once the rollout begins, we’ll start tracking real data to inform that modelling. - Local benchmarking suggests a potential increase of between 4 - 8 percentage points in recycling rate. |
| LBR15 | Ensure all new-build applications to have suitable storage provisions for recycling | - Update Design SPD with planning guidance that includes requirements for new and redeveloped properties to ensure that there is sufficient indoor and outdoor storage for all properties that is compliant with the Mayor of London’s London Plan and policies. - Engage with Redbridge Planning Department to ensure commitment to recycling storage provision. - Review the process for handling planning applications so that sufficient recycling facility provisions are included for all developments coming forward. | On track | - A draft proposal has been developed, and discussions are now underway with Planning colleagues to progress it further. | - The waste team continue to engage with Redbridge Planning Department to ensure commitment to recycling storage provision. |
| LBR16 | Increase recycling by schools and council buildings | - Continue to provide recycling collection service for schools in Redbridge. - Consider options to expand the recycling collection service offered to schools to include food waste. - Work with colleagues in property to provide a comprehensive recycling scheme for all Redbridge council offices | On track | - All schools are offered a free recycling collection for mixed recycling (plastic, glass, metal). - Schools are supported to start composting on site. This includes the provision of a 330L compost bin, a 5L internal compost caddy, and a student workshop delivered by the Neighbourhood Engagement and Education Team. - Schools are supported to implement uniform reuse/recycling schemes. This involves the provision of a 180L wheeled bin for uniform donations from Redbridge, along with promotional materials supplied by ELWA. - New signage has been installed in all Council offices, in line with Simpler Recycling reforms. | - The Council will not be providing a food waste recycling service to schools, as private providers are currently better positioned to deliver this service effectively. |
| LBR17 | Improving reuse and recycling across the IWMS Contract (ELWA) | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five Year Service Delivery Plan (2020-25), which includes a number of focus areas for improving reuse and recycling performance on the contract. - This includes actions to improve the recovery of recyclable items from residual waste through the mechanical-biological treatment (MBT) process. Significant improvements have already been made, in line with the targets for the second and third year of the service delivery plan, and ELWA will work with the Operator to continue to identify any further opportunities to improve recovery. - Other focus areas include the performance of the Reuse and Recycling Centres (see dedicated RRP line below), improved performance of dry mixed recycling services and recovery, and increased recovery of recyclable materials from street cleansing. - ELWA notes that that several proposed Government policies and regulatory changes may impact on the ability of the Operator to achieve its targets, including the potential need to discontinue recycling activities for materials identified as containing persistent organic pollutants, the diversion of recyclable materials away to deposit return schemes, and the possible removal of compost like output from inclusion in recycling performance calculations. | On track | - Improvements have been made to recovery processes for recyclable materials from residual waste, both within the MBT processes and at RRC sheds, although there have been issues with the latter (eg staffing disruptions) which have reduced its anticipated impacts. - POPs requirements have removed some recycling opportunities. | - Reuse and recycling rate for the IWMS contract hit 32.68% for 2024-25 (now operated by Biffa rather than Renewi) |
| LBR18 | Improving recycling and reducing contamination at flats and estates through implementing various intervention | - Deliver a flats recycling specific recycling campaign - Make use interventions guided by the ReLondon Flats Recycling Package to drive up recycling and reduce contamination in a pilot area. This will include carrying out improvements to signage and working with managing agents on communications. - Following the pilot, review the campaign and identify the next steps to further expanding the recycling campaign to other blocks of flats | Part complete | - A positive working relationship has been established with Housing Engagement colleagues, with further opportunities for collaboration to be explored. The "Do It For Your Dog" campaign has provided a strong foundation for joint working. This area of work will also fall within the responsibilities of the newly created 'Assistant Waste Collections Officer' role. - Private blocks of flats can apply to establish a community composting site on their premises. This includes the provision of a 330L compost bin, 5L internal compost caddies, and a composting workshop delivered by the Neighbourhood Engagement and Education Team. - Use of the ReLondon flats recycling package is currently on hold. It will be revisited as part of a broader review of flats, which will also incorporate food waste recycling. | - Two community compost sites established on private flats premises in 24/25. - Design and implementation of the flats’ recycling campaign is currently on hold until food waste collections are introduced. Recycling performance and contamination levels will be reviewed following implementation. |
| LBR19 | Make recycling easier for flats above shops properties and blocks of flats with limited provision. | - Review options around the provision of recycling flats above shop properties and any blocks of flats that do not have sufficient capacity for recycling - Implement solutions where this is viable financially and environmentally to support residents in flats above shops properties and blocks of flats to recycle. - Engage with managing agents, housing associations, residents’ associations and residents living in blocks of flats about any expansion of recycling facilities on a block-by-block basis. | On-hold | - A targeted campaign is currently underway to improve the correct presentation of waste from flats above shops. This includes updated leaflets, a revised webpage, and active involvement from ward councillors to support engagement and compliance. - Recycling services for flats above shops and blocks of flats will be fully reviewed in conjunction with the development of a food waste collection solution, scheduled for implementation in the 2025/26 period. |  |
| LBR20 | Provide recycling collections to 1,000 narrow access properties | - Review options around the provision of recycling to narrow access properties that do not currently have access to a recycling service. This will involve working closely with parking colleague to reduce parking issues. - Rerouting of the service and consideration of additional resource to deliver a narrow access recycling collection service. | On track | - Worked with Redbridge Civic Services (RCS) and parking colleagues to review collections methodology. - Restricted access is now a standing item in monthly RCS contract meetings. - A narrow access service has been implemented by RCS. - 6 locations were identified for Highways parking interventions in 2024/25, and these are at final approval and implementation stage. | - 100% of kerbside properties have access to a kerbside collection in the borough. The narrow access service has vastly improved the consistency of these collections. |
| LBR21 | Maintain network of recycling banks | - Work with ELWA to ensure that the collections of recycling at on street recycling banks are regular and sufficient to enable residents to easily recycle any excess recyclable materials - Review locations of bring sites and number of recycling banks as part of the ELWA procurement of the bring site management contract. | On track | - Continued working with ELWA to ensure that the collections of recycling at on street recycling banks are regular and sufficient to enable residents to easily recycle any excess recyclable materials. - There are no changes to report regarding number of bring banks. | - The indicative recycling rate for the 2024/25 stands at 30%. |
| LBR22 | Improving reuse and recycling performance of RRCs (ELWA) | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five Year Service Delivery Plan (2020-25), which includes targets to increase reuse and recycling performance at the four Reuse and Recycling Centres (RRCs) that cover the London Boroughs of Barking and Dagenham, Havering, Newham and Redbridge. - The uplift in reuse and recycling performance will be delivered through a combination of general site improvements and greater separation of recyclable materials from residual waste. Site improvements will include layout changes where possible to encourage visitors to separate more items from the residual stream, an increased range of materials accepted for recycling where the market allows, and improved performance of on-site reuse schemes. - ELWA notes that several proposed Government policies and regulatory changes may impact on the ability of the Operator to achieve its targets, including the potential need to discontinue recycling activities for materials identified as containing persistent organic pollutants and the diversion of recyclable materials away to deposit return schemes. | On track | - RRC performance remains a focus for ELWA’s contractor, with staff continuing to encourage visitors to segregate recyclable material. - Segregation of recyclable material from residual waste sheds/skips continues, with bagged waste being diverted to the MBT facilities to enable recovery of more recyclable waste. - Black bag splitting area introduced on all sites | - See action update |
| LBR23 | Diverting waste from landfill | - Renewi, the Operator of ELWA’s Integrated Waste Management Services contract (2002-27), has in place a Five-Year Service Delivery Plan (2020-25) which includes an ongoing target to achieve a minimum of 67% diversion from landfill for the waste it handles. - Actual performance is considerably higher than this target and has exceeded 99% since 2019-20. - Landfill diversion is achieved in several ways: - Separation of waste for recycling by householders and businesses using the collection services provided by the Constituent Councils. - Increasing the amount of reusable and recyclable waste segregated from residual waste by visitors to the Reuse and Recycling Centres. - Recovering recyclable items from residual waste, through a combination of manual separation at transfer stations, and mechanical separation at Renewi’s mechanical-biological treatment (MBT) plants and other third-party material recovery facilities. - Bio-drying of residual waste at the MBT plants, which reduces the overall mass by about 30%. - Conversion of non-recovered materials from the MBT facilities into fuels, for use in energy-from-waste facilities. | On track | - Landfill diversion remains just below 100%, with the only materials going to landfill being asbestos to deep-landfill (which is the only viable option) or waste contaminated by events such as fires. | - See action update |
| LBR24 | Greening the fleet | - Continue to operate a Euro VI compliant fleet. - Following the completion of the baseline report on existing fleet and potential future vehicle and infrastructure requirements, create a detailed project plan that delivers a greener fleet based on the report recommendations. | On track | - Continuing to operate a Euro VI compliant fleet. - There is a detailed plan in place in terms of future vehicle design. - Procurement is ongoing for food waste and bulk bin vehicles. - Large RCVs are being specified with roof mounted solar panels to reduce fuel usage. - Telematics have been fitted to vehicles to reduce fuel usage. - A proposal to transition the fleet to HVO was considered in 2023. Following review, concerns were raised regarding sustainability, fuel sourcing, and cost implications, and the proposal was not progressed. - The Council has trialled various electric RCVs in recent years. While performance was encouraging, current financial constraints mean procurement of these vehicles is not being pursued at this time. | - Fuel usage reduced by c.5%. |
| LBR25 | Encourage Redbridge businesses to recycle | - Introduce a sustainable/ climate friendly pledge scheme to encourage businesses to recycle as much of their waste as possible. - Signpost businesses to waste providers that provide recycling schemes in Redbridge. - Explore options available to LBR for the provision of a recycling collection service | On track | - The Neighbourhood Engagement Team regularly attend the Business Forum, where a wide range of businesses are represented, to talk about waste management and provide tips on waste minimisation and recycling. | - The Council transferred its commercial waste service to a private waste company on 1 August 2024. Part of the reason for doing this is because the private sector is in a stronger position to be able to offer expansive recycling services to their customers. |
| LBR26 | Contribute to the delivery of Redbridge’s Climate Action Plan | - Work with Strategy colleagues to plan and implement measures in the waste and street services that will enable the Council to become carbon neutral by 2030 - Join the Circular Economy Matchmaker to connect to innovative circular businesses | On track | - Collaborated with Strategy colleagues to assess progress on the Council’s Action Plan. - Supported the development of the Draft Climate Change Strategy (2025–2030) in partnership with Strategy colleagues. - The Neighbourhood Engagement Team plays an active role in delivering the quarterly Climate Forum and engaging the community in borough-wide climate action initiatives. - Circular economy matchmaker is signposted on the LBR website. | - Baseline data is being gathered on CO2 emissions. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| LBR27 | Reducing contamination | - We are currently planning a four-step approach to tackle recycling contamination at properties that are regularly flagged by collection crews for presenting contaminated waste. This initiative will follow a similar structure to our existing side waste process. - Development is underway for contamination awareness training aimed at collection crews, with the first iteration planned for delivery in Q4 2025/26. - There is scope for possible interventions to tackle contamination, jointly with other ELWA boroughs. Details of the exact approach for this is currently yet to be determined. | - Reduce contamination. - Specific figure to be determined – baseline data being gathered. | - To be determined. |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| N/A | Food Waste Collections - Kerbside | - See detail in LBR14 |  |  |
| N/A | Food Waste Collections – Communal properties and flats above shops | - See detail in LBR14 & LBR19 |  |  |
| N/A | Flats Above Shops Recycling | - See detail in LBR13 & LBR19 |  |  |
| LBR28 | Carton recycling | - Introduce a kerbside recycling collection service for cartons, not currently available to ELWA boroughs. - Implement in 2026, in line with Simpler Recycling requirements. - Liaising with ELWA. |  |  |
| LBR29 | Flexible Plastic Recycling | - Introduce a kerbside recycling collection service for flexible plastics, not currently available to ELWA boroughs. - Implement in 2027, in line with Simpler Recycling requirements. |  |  |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026