Part 1 –Reduction and Recycling Plan (RRP) April 2023 to March 2025

- Context:

Our vision at the London Borough of Enfield is that by 2040 people who live or work in Enfield will have reduced the amount of waste they produce; no waste will end up in landfill and waste will be used as a resource. Enfield already collects all six main dry recycling materials and offers a weekly food recycling service to over 87,000 kerbside properties. Waste minimisation, education and behaviour change programmes are delivered in partnership with the North London Waste Authority (NLWA).

Enfield’s waste is made up of 47% from kerbside properties, 22% communal properties and 31% other waste such as street litter, fly tipping and non-household waste.

In 2019/20 Enfield introduced weekly food recycling to all kerbside properties and an alternate weekly collection service for rubbish and recycling collections. Soon after implementation the Country went into a national lock down due to the Covid 19 pandemic, which consequently resulted in changes to waste behaviours and relaxation to our collection policies.

Enfield’s focus is to continue to realise the benefits of our service change, through reducing contamination of recycling at the kerbside, capturing more recyclable material and gain an understanding on how waste behaviours have changed.

Enfield aims to continue the work on improving recycling in communal situations, exploring how more recycling can be extracted from many other services as well as continue to prioritise waste minimisation and circular economy projects.

Enfield has set an ambitious target of achieving 49% recycling from household waste; alongside this document, Enfield has a commitment to the creation of a five-year action plan which will focus on ways to achieve this target.

- Key strategic documents linked to this plan:

Climate action | Enfield Council

Sustainable and Ethical Procurement Policy

https://www.enfield.gov.uk/consultations/draft-sustainable-and-ethical-procurement-policy2

- RRP Dashboard:

| Common Performance Targets | Baseline Performance (2019/20) | Performance Target 2024/25 | Metric Guidance / Data source | Target Guidance |
| --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 353.45 kg/head | 322kg/head | Defra stats (Ex BVPI84a) | Borough sets own targets, informed by ReLondon /WRAP good practice. |
| Total annual household residual waste collected per household (kgs/household) | 631.62kg/household | 412kg/household | Defra stats (Ex NI191) | Borough sets own targets, informed by ReLondon/WRAP good practice. |
| Total annual household avoidable (edible) food waste (kgs/head) | 72.63 kg/head | 69.03kg/head | Borough to estimate based on own or WRAP food waste composition data. Estimates should be based on avoidable food waste produced (i.e. not just food waste collected). | Based on estimated avoidable food waste produced. Borough to set own targets, informed by ReLondon/WRAP good practice and support programmes (e.g. Trifocal). |
| Annual household waste recycling rate (% by weight) | 33.1% | 49.55% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP Route Map modelling and other good practice. The GLA will use the borough recycling benchmarking table in the Route Map modelling as a reference point when assessing local authority targets set in the RRP process (See Appendix 2 of the London Environment Strategy, page 111: https://www.london.gov.uk/sites/default/files/les_appendix_2_-_evidence_base_0_0.pdf) |
| Annual LACW recycling rate (% by weight) | 29.9% | 44.03% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP good practice. Targets should at least match household recycling targets, going beyond the Mayor's 50 per cent LACW recycling target by 2025 where possible. |
| Proportion (%) of properties receiving the Mayor's minimum level of service for household recycling: |  |  |  |  |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) and separate food waste | Rolled out to all wheeled bin properties 100% in 19/20 Kerbside Sack properties 0% | 100% Wheeled Bin 100% kerbside sack properties | Borough to take from own info. Separate food waste does not include co-mingled with garden waste | Borough sets own target, informed by ReLondon/WRAP good practice. Separate food waste does not include co-mingled with garden waste |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) | 100% wheeled bins Opt In kerbside Sack Recycling | 100% wheeled bins 100% Kerbside sack recycling | Borough to take from own info (Nb included for boroughs that are unable to provide food waste collections due to long term contractual issues). | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 1% | 25% Enfield Housing properties | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays). | 78% | 85% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)) and separate food waste | 0% | <5% FAS sack properties <5% FAS communal bins | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice and FAS data. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)). | Unknown | <5% FAS sack properties <5% FAS communal bins | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice and FAS data. |
| Proportion (%) of waste fleet heavy vehicles that are ULEZ compliant | 100% | 100% | See www.tfl.gov.uk/modes/driving/ultra-low-emission-zone | Borough should aim to operate a fully ULEZ compliant waste fleet as a minimum; with aspirations to introduce zero emission vehicles where practicable. Please include baseline and target % of waste vehicles that are zero emission capable where applicable |
| Performance of LACW activities against the Mayor's EPS (tonnes of CO2eq per tonne of waste managed). | -0.024 | -0.001 | Use tool found here Boroughs to set by uploading WDF data into the GLA tool. | Borough to run their own scenarios using GLA tool to determine planned service changes (DSO borough) or new contract options against the EPS for target years (2024/5). See London Environment Strategy Proposal 7.3.2.b |

- RRP Actions:

| Ref | Theme - Waste Reduction - Maximising Recycling - Reducing Environmental Impact - Maximising local waste sites | Action title | Action Description | Expected Target / Impact | Timescale for action | WCA/WDA |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | - Waste Reduction | The North London Waste Authority Waste Prevention Plan | - A new plan is being prepared for 2022-25 and due to be agreed in Autumn 2022, which will continue to support the waste prevention activity of the constituent boroughs through digital and outreach activities, whilst also enabling community-based organisations to develop and deliver waste reduction projects through the Waste Prevention Community Fund. Stakeholders, including residents are being engaged to inform this plan, for example, through a behaviour change research project to gain insight to the most effective routes to resident engagement and messaging that will motivate actions to prevent waste, based on the approaches delivered by NLWA. Monitoring and evaluation of the plan will be carried out against project-based targets. - UPDATE MARCH 23 - Project planning for delivery on the WPP commenced. Each area of work will have specific deliverables and targets. Stakeholder engagement strategy being developed and will be implemented throughout the year, will include targeted communications, inviting opportunities for stakeholders to help shape activity in the plan, information sharing on the progress of project delivery, and continued contribution to and campaigning on policy and legislation. | - Monitoring and evaluation of the plan will be carried out against project-based targets. | - 2022 - 2025 | WDA |
| 1.1 | - Waste Reduction | Barrowell Green Reuse and Recycling Centre | - Enfield continues to work with the operator of the centre, Suez, to explore maximising the Revive Reuse Shop situated within the Centre. Enfield aspires to ensuring that the shop is open 6 days per week. Enfield continues to work with Suez to explore further reuse opportunities such as paint and small electricials. - Enfield is looking to increase communications via email to users of the centre that have pre booked an appointment on recycling more and reducing waste | To increase sales by 16% will increase the amount of household items that will be reused in 23/24 | - 2023 - 2025 | WCA |
| 1.2 | - Waste Reduction | Home Composting | - Enfield continues to offer free home compost bins to residents through getcomposting.com | To maintain current compost bin sale levels to residents for 23/24 | - 2023 - 2025 | WCA |
| 1.3 | - Waste Reduction | Circular Economy | - Enfield is taking steps to adopt more circular economy approaches within its business and changing behaviours of its residents. - Enfield underwent a Circular Economy workshop, facilitated by ReLondon to assess how Enfield can move to more circular economy thinking - The outcome of this training aims to influence to revised climate action plan commitments - Circular economy resident initiatives being investigated include library of things and bulky waste reuse | To explore the potential of diverting 5% Of bulky waste to reuse by 2025 To explore the potential of rolling out library of things that will help to contribute towards improving recycling. | - 2023-2025 | WCA |
| 1.4 | - Waste Reduction | Textile reuse | - Enfield is exploring further opportunities to expand reuse of textiles within the borough; Enfield is working with TRAID, contributing to the One World Living, pan London, campaign. TRAID offer a kerbside collection service within Enfield, however, take up could be much improved. | To explore the potential of increasing use of the service by a minimal of 5% through improved resident communications by 2025. | - 2023 - 2025 | WCA |
| 1.5 | - Waste Reduction | Bulky waste reuse | - Enfield currently refer residents to the British Heart Foundation for bulky waste reuse; however, Enfield is committed to exploring a more formal approach to bulky waste reuse, through procuring a reuse contract with a third sector organisation. | To explore the potential of diverting 5% to bulky waste to reuse by 2025 | - 2023 - 2025 | WCA |
| 1.6 | - Waste Reduction | North London Waste Authority Initiatives | - Pan-London Food Waste Campaign – The objectives of the campaign are to bring together various London stakeholders that can encourage and support residents to reduce their consumption-based emissions by moving to a more sustainable and healthy diet; and wasting less food. The campaign will also support the implementation of London Councils’ One World Living action plan and its ambition to reduce consumption-based emissions by 2/3 by 2030 and support the Mayor of London’s target to reduce food waste by 50% by 2030. The campaign is particularly targeting younger Londoners aged 21-44 and those with children under 11 years old at home, as they are amongst the highest food wasters. - Low Plastic Zones – Resident behaviour change campaign will be delivered in partnership with north London businesses, encouraging customers to bring reusable alternatives for everyday packaging with them when shopping in their local high street. Activity will include business engagement and advertising within participating businesses as well as OOH and social media advertising to target residents directly and drive them to a dedicated webpage. Campaign will be trialled in 1 borough, Barnet, with roll-out aimed later part of 2023/24 to other 6 boroughs. Procurement of contractor currently in progress, to develop and deliver campaign. Specific campaign targets to be agreed by start of Q1 2023/24, once contractor confirmed. - Education – Continue development of an online Education Hub on nlwa.gov.uk, promote and provide central point for teachers to access a wide range of educational resources and case studies. Engage 15 schools to collate feedback on the effectiveness of existing waste prevention education resources and identify what NLWA could develop and deliver to fill identified gaps. Work with boroughs to gain an understanding of the waste and recycling services on offer and promote to schools. - Reusable nappy scheme – Voucher value will be increased from Q1 2023/24. Uptake of scheme will be monitored and evaluated. A project focused on the use of reusable nappies in nurseries will be funded in 2023/24 through the North London Community Fund, dues to be completed and reported by December 2023. - Waste Prevention Community Fund – £250,000 committed to fund 17 community-based projects during 2023/24 focused on waste prevention activities at the community level, 5 of which will continue into 2024/25. 85% of targets will be met or exceeded by end of 2023/24 Q4. - Repair and upcycling events – At least 9 organisations planning to deliver repair/reuse-related projects in 2023-24, funded through NLWA’s North London Community Fund. Activity will include direct support through advice/practical sessions/training for north London residents. NLWA will work closely with these organisations to identify opportunities to scale up activity where possible beyond the original target communities of the projects. - Waste Prevention Exchange conference: this annual event will be delivered to bring together sector experts on a programme of topical waste prevention issues. | To be implemented for 2022-24 | - 2022 - 23 | WDA |
| 2.0 | - Maximising Recycling | Adoption of a new collection service 2019/20 | - Kerbside services: Enfield's new waste and recycling collection service launched in 2019 provided the minimum level of service to all properties, including separate food waste collections to kerbside properties. The six main dry recyclable items are already captured through the existing service. The introduction of alternate weekly residual waste and recycling in March 2020 aimed to maximise recyclable materials collected at the kerbside and increase the recycling rate. - The outcomes and recycling rate potential for the service changes were extensively modelled by an external consultancy. These outcomes were used to set our 49% recycling rate target. - Due to the Covid 19 pandemic and a national lockdown two weeks following the launch of our alternate weekly collection service, the results were not realised in the timescales originally set out. - This RRP details the steps we are taking in the next two years to make steps to achieving our original target. | To increase Enfield’s recycling rate in line with the service change modelling of 49% by 2025. | - 2023 - 2025 | WCA |
| 2.1 | - Maximising Recycling | Diverting/Recycling bulky waste from EfW | - NLWA operates a sorting facility (at Wembley) which sorts wood, mattresses, metal, cardboard and hardcore material. It is envisaged that 10,000 tonnes will be processed at the station per annum. We are recovering around 30% of materials for recycling and reuse. - We are investing in a residual pre-treatment facility (sorting facility) within the new RRF. This will process between 30,000 and 65,000 tonnes of residual waste, and we expect to recover 30% of materials for reuse and recycling. We have engaged consultants this year (2022) to carry out a best practice review across Europe, with a view to installing a facility which will provide maximum value. We expect the materials processed to be like those at Wembley, with additional waste streams such as plastics, but this is dependent on the best available technology. | New RRF to be in operation 2023 To recover 30% of materials for reuse and recycling from bulky waste through sorting and pre-treatment by 2024. | - 2023-2025 | WDA |
| 2.2 | - Maximising Recycling | Contamination of recycling in kerbside properties | - Enfield is committed to reducing contamination from wheeled bins. - A recent project aims to revert to Enfield’s existing contamination policy; rubbish-and-recycling-information-recycling-contamination-policy.pdf (enfield.gov.uk) - A significant increase has been seen since the Covid 19 pandemic of recycling loads delivered to the materials recycling facility being rejected, due to over 20% contamination within the material. - The ongoing project aims to reduce the number of rejected loads to pre covid 19 levels - The exercise looks to educate on the importance of clean, correct recycling | To increase recycling by 4.8% by increasing the amount of kerbside recycling collected and reducing rejected loads at the MRF by a total of 5312t in 2024. | - 2023-2025 | WCA |
| 2.3 | - Maximising Recycling | Improving recycling at communal properties | - Enfield has piloted the ReLondon flats recycling package in Enfield Housing communal properties; https://relondon.gov.uk/resources/toolkit-flats-recycling-package - The best practice detailed within the flats recycling package has been applied to several Enfield Housing sites to improve on recycling infrastructure, education residents and improve signage - Enfield is looking to improve and introduce food recycling in communal properties - Enfield is committed to continuing to improve recycling in communal properties and is seeking approval and adequate funding and resource to continue this project - Enfield is looking to establish a strategy for recycling in privately managed communal properties - Enfield is committed to reviewing and adopting a strategy to achieve 50% recycling in the Meridian Water Development and any future communal developments; Meridian Water ¦ A major 20 year regeneration programme led by Enfield Council. Bringing 10,000 homes & 6,000 jobs to Enfield, next to the beautiful Lee Valley Regional Park - Funding for the above projects is yet to be secured | To achieve 30% recycling in 85% of communal properties, and 50% recycling in any new developments; through adopting the flats recycling package good practice and replacing our guidance documents for developers; resulting in an overall recycling rate increase of 2-3% by 2025. | - 2023-2025 | WCA |
| 2.4 | - Maximising Recycling | Flats above shops (FAS) | - Enfield operates a sack service, this is mixture of kerbside properties with limited space for bins and flats above shops - The current recycling offering to these properties is an opt in recycling sack service - Enfield is looking to improve on this opt in service, and investigate options - Ascertain data on flats above shops on sacks collections - In addition to looking at ensuring that all flats above shops that have communal bins are offered recycling where possible | To ensure that 100% of sack properties including FAS have access to recycling facilities, by delivering blue recycling sacks twice yearly, by 2025. | - 2022 - 2025 | WCA |
| 2.5 | - Maximising Recycling | Increasing recycling from kerbside properties | - Enfield is awaiting the completion of a waste composition analysis, being carried out by the North London Waste Authority - To ascertain how waste behaviours have changed post covid. - The latest waste composition analysis was carried out in 2017 - Enfield plans to establish, alongside a suite of communications material including new videos, a communications and outreach plan to increase recycling material captured from wheeled bins | To use 2023 waste composition data to create a bespoke waste behaviour campaign, resulting in a minimum 1% increase in household recycling by 2025. | - 2023 - 2025 | WDA&WCA |
| 2.6 | - Maximising Recycling | Barrowell Green Reuse and Recycling Centre | - Enfield is committed to working in partnership with our existing contractor Suez, to increasing recycling at the Barrowell Green Reuse and Recycling Centre - Hard to recycle materials such as mattresses, carpets, paint and hard plastics are being diverted for recycling when markets allow, and Enfield is committed to establishing stable outlets for these items. - The team are operating ‘black bag splitting’ at the centre to maximise recycling material capture - Communications will be key to educating centre users on maximising what can be recycled at the centre | To work with our current contractor Suez, to achieve an annual minimum of 65% recycling at the centre each year. | - 2023 - 2025 | WCA |
| 2.7 | - Maximising Recycling | Small WEEE and textile recycling | - Enfield is exploring options on offer kerbside small WEEE and textile recycling | To explore implementing a kerbside collection of small WEEE and textiles in Enfield, with the aim of diverting 50% of small WEEE and textiles currently in our household refuse bins, by 2025. | - 2023 - 2025 | WCA |
| 2.8 | - Maximising Recycling | Non household recycling collections | - Enfield is carrying out a trial for commercial recycling - If successful, will roll commercial recycling out more widely - Will look at food collections in the future | To continue trialling commercial recycling, with the aim of offering recycling services to 2300 commercial waste contract with Enfield Council by 2025. | - 2022 - 2025 | WCA |
| 2.9 | - Maximising Recycling | Recycling of street cleansing material | - Enfield will explore options to extract recycling from the street cleansing service - Areas of focus are litter, hand barrows and street sweepings | To explore the potential of extracting 100% of recyclable material from litter, hand barrows and street sweepings, to assist in increasing overall recycling, by 2025. | - 2023 - 2025 | WCA |
| 2.10 | - Maximising Recycling | Parks recycling | - Enfield are trialling split litter and recycling bins in four parks and open spaces - If successful, Enfield will look to expand on this service | To continue to pilot split litter bins in four parks, through extracting 100% of recyclable material from these bins, by 2024. | - 2023 - 2025 |  |
| 3.0 | - Reducing Environmental Impact | Commitment to electric fleet | - Enfield is committed to replacing 60% of the Council fleet with electric vehicles. | To reduce Enfield’s emissions in line with the commitments detailed within the Climate Action Plan. | - To be achieved by 2025/2026 | WCA |
| 3.1 | - Reducing Environmental Impact | NLWA commitment | - We are currently carrying out a review looking at alternative fuels for vehicles with London Energy Ltd (LEL). The ambition ultimately is to have a zero-carbon emissions fleet. This will be dependent on having the appropriate technology to provide a sustainable service. - The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are now all ULEZ compliant. - It is a requirement of the main waste contract with LEL to use Euro IV vehicles as a minimum. LEL have initiated a vehicle replacement programme to ensure vehicles comply with ULEZ. All vehicles are now Euro VI, leading to a significant reduction in NOx emissions. - NLWA are currently reviewing the environmental impact of the fleet with LEL and potential improvements which can be made. NLWA have transitioned its vehicles from diesel to an electric. We have an electric Volkswagen golf and a Peugeot, and Volkswagen van (petrol). The aim is to replace the petrol van in 2022. - The contractor has been instructed to install an additional 370(no) solar PV panels at the new RRF. These additional panels will provide a 20% increase in total output for the whole system from 755kWp to 905kWp. There will now a total of 2235 solar panels at the RRF. | Impact unknown/not provided | - 2023-2025 | WDA |
| 3.2 | - Reducing Environmental Impact | Climate Action Plan | - Our Climate Action Plan 2020 (PDF) explains how we will become a carbon neutral organisation by 2030, and a carbon neutral borough by 2040. It sets out our current carbon emissions (our baseline) and the action we need to take to achieve our net zero targets. - This new plan follows the previous successes we achieved through the delivery of our Sustainable Enfield Plan. | The plan details our targets from 2020 – 2025 Targets from 2025 – 2030 And targets from 2030 – 2040 | - 2020 - 2040 | WCA |
| 3.3 | - Reducing Environmental Impact | Sustainable Procurement | - Enfield launched our new Sustainable and Ethical Procurement Policy earlier this year. This is underpinned by 4 core principles – Social Value, Ethical Practices, Supporting the local economy and local employment, and Climate Action. The Policy is mandatory for all procurement activity above Threshold and should also be considered for below Threshold contract opportunities (such as smaller construction projects that fall under the Works Threshold) or where there is a long-term contract agreement being put in place. | This policy is valid from 2022 – 2026 | - This policy is valid from 2022 - 2026 | WCA |
| 4.0 | - Maximising Local Waste Sites | To maximise the local waste sites within Enfield | - Enfield as part of the North London Waste Authority, deliver all residual waste to London Energy situated within the Borough. Our recyclables contractor, Biffa, again is situated within the borough. This contract is in place until 2023. Any future procurements will be undertaken in line with Enfield's responsible procurement guidelines (2022-2026) which aims to meet the Council's guiding principles, as detailed in the corporate plan; These guidelines reference building on the local economy. | This policy is valid from 2022 – 2026 | - This policy is valid from 2022 - 2026 | WCA |
| 4.1 | - Maximising Local Waste Sites | Barrowell Green Reuse and Recycling Centre | - Barrowell Green RRC is the only RRC within Enfield. This site is operated by Suez, and together planning will commence with regards to expanding the acceptance of some hazardous waste items, such as gas bottles, fire extinguishers and paint. The City of London hazardous waste collection arrangement is already in place for Enfield residents to use. This allows collection of hazardous items from the kerbside. Waste electrical and electronic equipment, automotive and non-automotive batteries, cooking oil and mineral oil are already accepted on site. | On the expiration of the Suez contract in 2022, any new contract will focus on maximisation of the site; within the confines of the local infrastructure. Enfield are looking to extend the contract with Suez for 1 year. | - 2022 - 2025 | WCA |

5. RRP Action update:

- To be completed annually

- Action table to be updated with new dates/targets etc at same time

| Ref | Action title | Action update | Status - Completed - On track - Not on track - On hold - Awaiting data - Cancelled | Date of Update |
| --- | --- | --- | --- | --- |