- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 353.45 kg/head | 322kg/head | 317 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 631.62kg/household | 412kg/household | 547kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 72.63 kg/head | 69.03kg/head | 51kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56%. If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 33.1% | 49.55% | 33% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 29.9% | 44.03% | 28% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | Rolled out to all wheeled bin properties 100% in 19/20 Kerbside Sack properties 0% | 100% Wheeled Bin 100% kerbside sack properties | 100% Wheeled Bin 100% kerbside sack properties | 100% Wheeled Bin 100% kerbside sack properties | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% wheeled bins Opt In kerbside Sack Recycling | 100% wheeled bins 100% Kerbside sack recycling | 100% wheeled bins 100% Kerbside sack recycling | 100% wheeled bins 100% Kerbside sack recycling | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 1% | 25% of flat properties | 25% of flat properties | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 78% | 85% | 85% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | <5% FAS sack properties <5% FAS communal bins | <5% FAS sack properties <5% FAS communal bins % | 20% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | Unknown | <5% FAS sack properties <5% FAS communal bins | <5% FAS sack properties <5% FAS communal bins | 20% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| 1.0 | The North London Waste Authority Waste Prevention Plan | - A new plan is being prepared for 2022-25 and due to be agreed in Autumn 2022, which will continue to support the waste prevention activity of the constituent boroughs through digital and outreach activities, whilst also enabling community-based organisations to develop and deliver waste reduction projects through the Waste Prevention Community Fund. Stakeholders, including residents are being engaged to inform this plan, for example, through a behaviour change research project to gain insight to the most effective routes to resident engagement and messaging that will motivate actions to prevent waste, based on the approaches delivered by NLWA. Monitoring and evaluation of the plan will be carried out against project-based targets. - UPDATE MARCH 23 - Project planning for delivery on the WPP commenced. Each area of work will have specific deliverables and targets. Stakeholder engagement strategy being developed and will be implemented throughout the year, will include targeted communications, inviting opportunities for stakeholders to help shape activity in the plan, information sharing on the progress of project delivery, and continued contribution to and campaigning on policy and legislation. | On track / part complete | The North London Waste Prevention Plan was published in January 2023. The plan was developed through collaboration with residents, environmental specialists, borough staff, councillors, and campaigners. The development of the plan involved engagement sessions, meetings, and conversations to provide insight into local priorities and identify where NLWA activities can support partners to achieve shared ambitions. The plan is developed to set out the approach to working whilst the next North London Joint Waste Strategy, owned by the constituent boroughs and NLWA, is being developed. Projects delivered or launched in 2023/24 as part of the plan include: • Together We Recycle • Eat like a Londoner • Reusable period products campaign • Education plans • Bring it The council is working with the NLWA, who are reviewing resources and approaches to waste education for schools. Meetings with the first primary school taking part is due to start in October 2024, but was sadly delayed. Much of this work has been delayed due to staffing issues, NLWA are now helping with this work. During 2023/24 the Real Nappies for London (RNFL) subsidy was increased to £70 to encourage uptake and more waste reduction through the avoidance of disposable nappies. The North London Community Fund, administered by NLWA and funded via its constituent boroughs, has supported a number of community-led waste prevention projects. | - All activities help to contribute to increase our overall recycling rate and reduce our waste tonnages - In Enfield 96 vouchers were issued in 2023/24 compared with 91 in the previous year which is a 5% increase. - During Reusable Nappy week Enfield had 7,882 impressions and 125 link clicks compared with 70 in 2022/23 74 (meta-advertising). - Our comms team have been working closely with NLWA to promote the other schemes (Together We Recycle, Eat like a Londoner, Reusable period products campaign and Bring it) |
| 1.1 | Barrowell Green Reuse and Recycling Centre | - Enfield continues to work with the operator of the centre, Suez, to explore maximising the Revive Reuse Shop situated within the Centre. - Enfield aspires to ensuring that the shop is open 6 days per week. - Enfield continues to work with Suez to explore further reuse opportunities such as paint and small electricals. - Enfield is looking to increase communications via email to users of the centre that have pre booked an appointment on recycling more and reducing waste | On track / part complete | - More advertisement of site shop on our social media. Shop also has own Facebook page - Shop is open 6 days a week - Continuing to work with Suez to explore further reuse opportunities such as paint and small electricals. Vapes collections now introduced - Adding a link to booking email for feedback | - Barrowell Green Recycling Centre is a well used recycling centre. - Even though the Edmonton Eco Park recycling centre is now fully open, it has not significantly affected the number of visitors at Barrowell Green - Barrowell Green is achieving a 66% diversion rate of waste to recycling In 2024-25. |
| 1.2 | Home Composting | - Enfield continues to offer free home compost bins to residents through getcomposting.com | On track / part complete | - Available on our website here | - Number of compost bin sales is steady, but pushing communications on this could increase sales further. |
| 1.3 | Circular Economy | - Enfield is taking steps to adopt more circular economy approaches within its business and changing behaviours of its residents. - Enfield underwent a Circular Economy workshop, facilitated by ReLondon to assess how Enfield can move to more circular economy thinking - The outcome of this training aims to influence to revised climate action plan commitments - Circular economy resident initiatives being investigated include library of things and bulky waste reuse | On track / part complete | - Working closely with Climate Action Team and collaborating on events in the borough - Give and Take events for Residents regularly taking place in Libraries. Attended by over 180 people - Enfield Tool Library has now been set up | - Activities helping to contribute to increase our overall recycling rate and reduce our waste tonnages - Give and Take events are continuing to be a success. - Although slow to begin with the Enfield Tool Library is starting to build pace in usage. |
| 1.4 | Textile reuse | - Enfield is exploring further opportunities to expand reuse of textiles within the borough; Enfield is working with TRAID, contributing to the One World Living, pan London, campaign. TRAID offer a kerbside collection service within Enfield, however, take up could be much improved. | On track / part complete | - Enfield is still working with TRAID. - TRAID is now well advertised on the Enfield Council website (www.enfield.gov.uk/textiles) and regularly on social media. | - With textiles being a large/weighty contaminate in recycling bins but also found heavily in waste bins, this service will help to increase our overall recycling rate and reduce our waste tonnages - Tonnage is slowly increasing with the increase in communication. |
| 1.5 | Bulky waste reuse | - Enfield currently refer residents to the British Heart Foundation for bulky waste reuse; however, Enfield is committed to exploring a more formal approach to bulky waste reuse, through procuring a reuse contract with a third sector organisation. | Delayed / on-hold / no progress to date | - All work on reuse of Bulky Waste has been put on hold as other work has taken priority. |  |
| 1.6 | North London Waste Authority Initiatives | - Pan-London Food Waste Campaign – The objectives of the campaign are to bring together various London stakeholders that can encourage and support residents to reduce their consumption-based emissions by moving to a more sustainable and healthy diet; and wasting less food. The campaign will also support the implementation of London Councils’ One World Living action plan and its ambition to reduce consumption-based emissions by 2/3 by 2030 and support the Mayor of London’s target to reduce food waste by 50% by 2030. The campaign is particularly targeting younger Londoners aged 21-44 and those with children under 11 years old at home, as they are amongst the highest food wasters. - Low Plastic Zones – Resident behaviour change campaign will be delivered in partnership with north London businesses, encouraging customers to bring reusable alternatives for everyday packaging with them when shopping in their local high street. Activity will include business engagement and advertising within participating businesses as well as OOH and social media advertising to target residents directly and drive them to a dedicated webpage. Campaign will be trialled in 1 borough, Barnet, with roll-out aimed later part of 2023/24 to other 6 boroughs. Procurement of contractor currently in progress, to develop and deliver campaign. Specific campaign targets to be agreed by start of Q1 2023/24, once contractor confirmed. - Education – Continue development of an online Education Hub on nlwa.gov.uk, promote and provide central point for teachers to access a wide range of educational resources and case studies. Engage 15 schools to collate feedback on the effectiveness of existing waste prevention education resources and identify what NLWA could develop and deliver to fill identified gaps. Work with boroughs to gain an understanding of the waste and recycling services on offer and promote to schools. - Reusable nappy scheme – Voucher value will be increased from Q1 2023/24. Uptake of scheme will be monitored and evaluated. A project focused on the use of reusable nappies in nurseries will be funded in 2023/24 through the North London Community Fund, dues to be completed and reported by December 2023. - Waste Prevention Community Fund – £250,000 committed to fund 17 community-based projects during 2023/24 focused on waste prevention activities at the community level, 5 of which will continue into 2024/25. 85% of targets will be met or exceeded by end of 2023/24 Q4. - Repair and upcycling events – At least 9 organisations planning to deliver repair/reuse-related projects in 2023-24, funded through NLWA’s North London Community Fund. Activity will include direct support through advice/practical sessions/training for north London residents. NLWA will work closely with these organisations to identify opportunities to scale up activity where possible beyond the original target communities of the projects. - Waste Prevention Exchange conference: this annual event will be delivered to bring together sector experts on a programme of topical waste prevention issues. | On track / part complete | - Working closely with NLWA on their initiatives and our comms team are advertising all of the schemes regularly on our social media platforms. - The pan-London food waste campaign went well, but limited increase food waste tonnage has been seen. - Bring It is a campaign that aims to encourage residents to use reusable coffee cups, bottles, bags, and containers to reduce single-use plastic. The campaign initially launched in Barnet and work is now being done to roll out the Bring It campaign to Camden, Enfield, Haringey, Hackney, and Islington – with Waltham Forest receiving it later in 2024/25. - Advertising school presentations on the hub and monitoring uptake - Still working with Wen (Women’s Environmental Network) on the Real Nappies Scheme offering £70 vouchers and seen a 5% increase this year - Waste Prevention Community Fund is currently live. This recently included £2500 funding for setting up a repair café. | - All activities help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 2.0 | Adoption of a new collection service 2019/20 | - Kerbside services: Enfield's new waste and recycling collection service launched in 2019 provided the minimum level of service to all properties, including separate food waste collections to kerbside properties. The six main dry recyclable items are already captured through the existing service. The introduction of alternate weekly residual waste and recycling in March 2020 aimed to maximise recyclable materials collected at the kerbside and increase the recycling rate. - The outcomes and recycling rate potential for the service changes were extensively modelled by an external consultancy. These outcomes were used to set our 49% recycling rate target. - Due to the Covid 19 pandemic and a national lockdown two weeks following the launch of our alternate weekly collection service, the results were not realised in the timescales originally set out. - This RRP details the steps we are taking in the next two years to make steps to achieving our original target. | On track / part complete | - The adoption of the new collection service has been completed. However, Covid-19 had a significant impact on the ability to carry out a communication campaign and an increase to recycling rates. - A number of staffing movements within the Recycling Team also affected the ability to carry out targeted communications. | - Recycling Rates for the last few years are as follows; - 2021-22, 30.9% - 2022-23, 34.2% - 2023-24, 33.0% - 2024-25, 33% - Aiming to increase this for 2025-26 |
| 2.1 | Diverting/ Recycling bulky waste from EfW | - NLWA operates a sorting facility (at Wembley) which sorts wood, mattresses, metal, cardboard and hardcore material. It is envisaged that 10,000 tonnes will be processed at the station per annum. We are recovering around 30% of materials for recycling and reuse. - We are investing in a residual pre-treatment facility (sorting facility) within the new RRF. This will process between 30,000 and 65,000 tonnes of residual waste, and we expect to recover 30% of materials for reuse and recycling. We have engaged consultants this year (2022) to carry out a best practice review across Europe, with a view to installing a facility which will provide maximum value. We expect the materials processed to be like those at Wembley, with additional waste streams such as plastics, but this is dependent on the best available technology. | On track / part complete | - In 2023/24, the construction of the Resource and Recovery Facility (RRF) at the Edmonton EcoPark continued. The site went into operation on 15th March 2024 and will begin accepting borough waste from April 2024. - The RRF, which has capacity to manage 374,000 tonnes of waste annually, is designed to bulk recycling and organic waste for onward transport to processors, extract recyclables from residual waste and prepare bulky waste for energy recovery. - Space has been allocated to the new RRF to support recycling and reduce waste. In 2023/24, NLWA engaged with consultants to review best practice in the UK, culminating in two reports exploring the feasibility of installing pre-sort technology in the RRF. Following the outcomes of the reports and decisions taken by a working group developed to support this work, NLWA plans to conduct further research into technological innovations for managing waste to understand the best use for this space. |  |
| 2.2 | Contamination of recycling in kerbside properties | - Enfield is committed to reducing contamination from wheeled bins. - A recent project aims to revert to Enfield’s existing contamination policy; rubbish-and-recycling-information-recycling-contamination-policy.pdf (enfield.gov.uk) - A significant increase has been seen since the Covid 19 pandemic of recycling loads delivered to the materials recycling facility being rejected, due to over 20% contamination within the material. - The ongoing project aims to reduce the number of rejected loads to pre covid 19 levels - The exercise looks to educate on the importance of clean, correct recycling | On track / part complete (Delayed) | - Contamination continues to be an issue in Enfield, causing the council a significant budgetary impact. - Enfield has the highest contamination rate in North London and one of the highest across the capital. | - Working on plans to reduce contamination and the affects it causes. See para 5.4. - Working hard to ensure Recycling Rates are rising and campaigns are ongoing to continue with these improvements including more outreach events and comms on our social media. |
| 2.3 | Improving recycling at communal properties | - Enfield has piloted the ReLondon flats recycling package in Enfield Housing communal properties; https://relondon.gov.uk/resources/toolkit-flats-recycling-package - The best practice detailed within the flats recycling package has been applied to several Enfield Housing sites to improve on recycling infrastructure, education residents and improve signage - Enfield is looking to improve and introduce food recycling in communal properties - Enfield is committed to continuing to improve recycling in communal properties and is seeking approval and adequate funding and resource to continue this project - Enfield is looking to establish a strategy for recycling in privately managed communal properties - Enfield is committed to reviewing and adopting a strategy to achieve 50% recycling in the Meridian Water Development and any future communal developments; Meridian Water ¦ A major 20 year regeneration programme led by Enfield Council. Bringing 10,000 homes & 6,000 jobs to Enfield, next to the beautiful Lee Valley Regional Park - Funding for the above projects is yet to be secured | (Delayed) | - The introduction of food waste bins to estates has been delayed due to a number of changes in staffing across the Recycling Dept. Roll out is now not planned until early 2026. - Flats above shops have had further rollout delays and unlikely to start before mid-2026. - All funding has been confirmed and budgetary plans are now being put into place. | - Delays will affect and delay the council’s ability to increase its recycling rate. |
| 2.4 | Flats above shops (FAS) | - Enfield operates a sack service, this is mixture of kerbside properties with limited space for bins and flats above shops - The current recycling offering to these properties is an opt in recycling sack service - Enfield is looking to improve on this opt in service, and investigate options - Ascertain data on flats above shops on sacks collections - In addition to looking at ensuring that all flats above shops that have communal bins are offered recycling where possible | (Delayed) | - Flats above shops have had further rollout delays and unlikely to start before mid-2026. | - Delays will affect and delay the council’s ability to increase its recycling rate. |
| 2.5 | Increasing recycling from kerbside properties | - Enfield is awaiting the completion of a waste composition analysis, being carried out by the North London Waste Authority - To ascertain how waste behaviours have changed post covid. - The latest waste composition analysis was carried out in 2017 - Enfield plans to establish, alongside a suite of communications material including new videos, a communications and outreach plan to increase recycling material captured from wheeled bins | (Delayed) | - The waste composition analysis was completed in Autumn 2024 and has helped in the planning of future recycling communications. - New works has been delayed due to a number of changes in staffing across the Recycling Dept. | - These activities will help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 2.6 | Barrowell Green Reuse and Recycling Centre | - Enfield is committed to working in partnership with our existing contractor Suez, to increasing recycling at the Barrowell Green Reuse and Recycling Centre - Hard to recycle materials such as mattresses, carpets, paint and hard plastics are being diverted for recycling when markets allow, and Enfield is committed to establishing stable outlets for these items. - The team are operating ‘black bag splitting’ at the centre to maximise recycling material capture - Communications will be key to educating centre users on maximising what can be recycled at the centre | (Delayed) | - Council website lists recyclable materials onsite and it regularly updated. - Due budgetary constraints Suez are no longer ‘black bag splitting’ and diverting the recyclable waste. | - Barrowell Green Recycling Centre is a well used recycling centre. - Even though the Edmonton Eco Park recycling centre is now fully open, it has not significantly affected the number of visitors at Barrowell Green - Barrowell Green is achieving a 66% diversion rate of waste to recycling. |
| 2.7 | Small WEEE and textile recycling | Enfield is exploring options on offer kerbside small WEEE and textile recycling | (Delayed) | - TRAID textiles collections are now taking place and TRAID is now well advertised on the Enfield Council website and regularly on social media. - Kerbside small WEEE collections are currently on hold as other projects are being carried out. | - These activities will help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 2.8 | Non household recycling collections | - Enfield is carrying out a trial for commercial recycling - If successful, will roll commercial recycling out more widely - Will look at food collections in the future | On track / part complete | - Trials ongoing – has been successful with very little issues. - Food waste and further recycling provisions to be introduced as part of Simpler Recycling scheme in the next year, offering all businesses food waste and DMR collections. | - These activities will help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 2.9 | Recycling of street cleansing material | - Enfield will explore options to extract recycling from the street cleansing service - Areas of focus are litter, hand barrows and street sweepings | (Delayed) | - Funding opportunities are being continuing to be explored by Street Cleansing Team | - These activities will help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 2.10 | Parks recycling | - Enfield are trialling split litter and recycling bins in four parks and open spaces - If successful, Enfield will look to expand on this service | Delayed / on-hold / no progress to date | - Bins found to just be heavily contaminated so removed at present. - Looking at other options - Funding opportunities are being continuing to be explored by Street Cleansing Team |  |
| 3.0 | Commitment to electric fleet | - Enfield is committed to replacing 60% of the Council fleet with electric vehicles. | Delayed / on-hold / no progress to date | - Approx.. 20% of fleet now electric with all officer vans and 4 RCVs. - Infrastructure will need to be updated/expanded to allow for more. There are no current plans to extend this infrastructure. Decisions delayed to 2026/27. |  |
| 3.1 | NLWA commitment | - We are currently carrying out a review looking at alternative fuels for vehicles with London Energy Ltd (LEL). The ambition ultimately is to have a zero-carbon emissions fleet. This will be dependent on having the appropriate technology to provide a sustainable service. - The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are now all ULEZ compliant. - It is a requirement of the main waste contract with LEL to use Euro IV vehicles as a minimum. LEL have initiated a vehicle replacement programme to ensure vehicles comply with ULEZ. All vehicles are now Euro VI, leading to a significant reduction in NOx emissions. - NLWA are currently reviewing the environmental impact of the fleet with LEL and potential improvements which can be made. NLWA have transitioned its vehicles from diesel to an electric. We have an electric Volkswagen golf and a Peugeot, and Volkswagen van (petrol). The aim is to replace the petrol van in 2022. - The contractor has been instructed to install an additional 370(no) solar PV panels at the new RRF. These additional panels will provide a 20% increase in total output for the whole system from 755kWp to 905kWp. There will now a total of 2235 solar panels at the RRF. | On track / part complete | - The vehicle fleet of NLWA’s current main waste transfer, treatment, and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. Since 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. - The new RRF at the EcoPark features 2,235 solar panels on its saw-tooth rooftop which were switched on in late 2023/24. The EcoPark Array will produce renewable energy, equivalent to powering 300 homes yearly with electricity, and has been added to the site as part of the North London Heat and Power Project (NLHPP). There are also plans for solar panels to be installed on the new ERF once built. - NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the decarbonisation of the energy produced. |  |
| 3.2 | Climate Action Plan | - Our Climate Action Plan 2020 (PDF) explains how we will become a carbon neutral organisation by 2030, and a carbon neutral borough by 2040. It sets out our current carbon emissions (our baseline) and the action we need to take to achieve our net zero target - This new plan follows the previous successes we achieved through the delivery of our Sustainable Enfield Plan. | On track / part complete | - The Waste Department worked closely with the Climate Action team on the new plan and assisted to input into the planning side ensuring all new builds would have sufficient capacity for refuse, recycling and food waste. | - These activities will help to contribute to increase our overall recycling rate and reduce our waste tonnages |
| 3.3 | Sustainable Procurement | Enfield launched our new Sustainable and Ethical Procurement Policy earlier this year. This is underpinned by 4 core principles – Social Value, Ethical Practices, Supporting the local economy and local employment, and Climate Action. The Policy is mandatory for all procurement activity above Threshold and should also be considered for below Threshold contract opportunities (such as smaller construction projects that fall under the Works Threshold) or where there is a long-term contract agreement being put in place. | Complete/ ongoing |  | - The sustainable and Ethical Procurement Policy being used in the council's ongoing procurement activities |
| 4.0 | To maximise the local waste sites within Enfield | - Enfield as part of the North London Waste Authority, deliver all residual waste to London Energy situated within the Borough. Our recyclables contractor, Biffa, again is situated within the borough. This contract is in place until 2023. Any future procurements will be undertaken in line with Enfield's responsible procurement guidelines (2022-2026) which aims to meet the Council's guiding principles, as detailed in the corporate plan. These guidelines reference building on the local economy. | Complete |  | - Enfield Council is continuing to tip all of its waste within the borough and there are no current plans to change these tipping locations. |
|  | Barrowell Green Reuse and Recycling Centre | - Barrowell Green RRC is the only RRC within Enfield. This site is operated by Suez, and together planning will commence with regards to expanding the acceptance of some hazardous waste items, such as gas bottles, fire extinguishers and paint. The City of London hazardous waste collection arrangement is already in place for Enfield residents to use. This allows collection of hazardous items from the kerbside. Waste electrical and electronic equipment, automotive and non-automotive batteries, cooking oil and mineral oil are already accepted on site. | On track / part complete | - Edmonton Eco Park now open in the borough (RRC run by NWLA) - Hazardous waste items can be collected at the new site. - The new Barrowell Green contract has been delayed with decisions now due in early 2026. The effect of this contract are not yet known. | - Enfield residents having access to the new site will help to contribute to increase our overall recycling rate and reduce our waste tonnages |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| 5.1 | Food waste caddy liner trial | To trial the introduction of food waste caddy liners to 15,000 properties, along with a food waste promotion, restickering of refuse and recycling bins, in attempt to reduce food waste being placed in wrong bin | Increase amount of food waste diverted to recycling | Trial to take place throughout Autumn 2026 |
| 5.2 | Larger bin policy review | To review the policy around the provision of larger bins ,to residents who require additional refuse capacity, e.g. because of larger families or complex medical needs. The increase from 140 litre bins to 240 litre bins | To complete review and implement | By early 2026 |
| 5.3 | Community Recycling Days | At a Community Recycling Day a mini recycling centre will be set up within one of the estates most affected by the lack or recycling centre provision. Residents will be able to dispose of Mattresses; Garden Waste; electricals; Wood; Metal; Furniture – limit to non POPs; Bric-a-brac. This enables 100% of items to be either recycled or reused. With plans to trial this across 8 estates in total. | To reduce flytipping and increase cleanliness of estates | Started July-25 |
| 5.4 | Contamination Reduction | To trial a number of ways to reduce contamination including: - Website improvements - Retraining of crews - Improved communications on contamination - Social media surveys and myth busting - Infographics on the cost and negative effects of contamination - Improved bin hangers - Improved leaflets - Additional outreach work. | Reduce contamination | Started July-25 |
| 5.5 | Bartec in-cab technology improvements | Bartec is not currently used to its full potential. This results in inefficiencies, missed opportunities for proactive communication, and some residents receiving collections they are not entitled to. There are two parts of this project: - Maximising use of the current system: - Improved crew time management and route optimisation - Enhanced data reporting and crew KPI tracking - Reduction of duplicated tasks and inefficiencies - Better contamination management through improved reporting and targeted outreach - Stronger controls to avoid collecting missed bins that were not actually presented - Procuring and integrating system upgrades: - Enhanced resident portal with better collection calendars, subscription management, and issue reporting - Automation of chargeable services (e.g., garden waste), enabling residents to manage subscriptions, pay online, and request additional bins - Advanced route optimisation tools for increased operational efficiency This project aims to modernise and fully utilis LBE’s in-cab technology to improve service efficiency, resident experience and data driven decision making across waste operations. | Improve usage of technology | Started Sept-25 |
| 5.5 | Communication campaign | Communications will be an important part of all the projects and communications will support these throughout. The major part of this communication campaign will be a door knocking campaign aiming to target 60% of households in the borough and 75% of flat properties. There will also be additional school visits educating around waste the importance of recycling. This project will also several smaller projects including: - Improved residential communications - Improved data tracking allowing targets recycling improvement campaigns - Free textile recycling collection promotion. - Waste reduction projects including reusable nappies and home composting. - Working in partnership with Planning to improve recycling provision for new builds - Investigating recycling on the go. | Increase communications and increase the council’s recycling rate | Started Oct-25 |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| 1.0 | Kerbside collection | The Council already offer all kerbside properties the collection services to meet national Simpler Recycling requirements | Complete | Complete |
| 1.1 | Food waste in flats | - The introduction of food waste bins to estates has been delayed due to a number of changes in staffing across the Recycling Dept. Roll out is now not planned until early 2026. - Flats above shops have had further rollout delays and unlikely to start before mid-2026. - All funding has been confirmed and budgetary plans are now being put into place. | To increase the amount of food waste and recycling diverted from flats | Delayed to early 2026 |
| 1.2 | Flats above shops | - Flats above shops have had further rollout delays and unlikely to start before mid-2026. | To increase the amount of food waste and recycling diverted from flats above shops | Delayed to mid-2026 |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026