- RRP Dashboard update:

| - Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 337.43kgs/head | 320kgs/head | 324.2kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 461.91kgs/hh | 450kgs/hh | 442.3kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 53kgs/head | 45kgs/head | 49kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56%. If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 48.6% | 50% | 44.1% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 49.04% | 51% | 43.4% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 97% | 100% | 97% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 97% | 100% | 97% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 82% | 100% | 82% | 88% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 15% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| RBK #1 | Promote reusable nappies | - Seek to promote the use of reusable nappies in the borough to reduce the level of disposable nappies in the residual waste stream. Options include but are not limited to, local nappy libraries, reusable nappy vouchers, cashback schemes and offering general reusable nappy advice on our website. | - On track / part complete | - Partnered with Real Nappies for London to offer 66 £50 vouchers to residents and 3 in-person outreach events - This partnership will continue in 2025/26, with 60 vouchers being offered to residents along with 3-in person outreach events. | - 56 vouchers were claimed by residents |
| RBK #2 | Improve and increase council building recycling | - Review range of collected recyclable materials from council buildings and introduce additional materials to the recycling stream where feasible. These materials include expanding on the dry mixed recyclables we currently collect, as well as food waste. | - On track / part complete | - Audited council buildings for improvements in recycling services during 2024/25 in preparation for Simpler Recycling. - Food waste collected from main council offices during 2024/25. - Food waste collections expanded to all council buildings in 2025/26. - Dry mixed recycling collections rolled out to remaining council buildings in 2025/26. | - 0.28 tonnes of food waste recycling collected during 2024/25. |
| RBK #3 | Deliver alternative collection of textiles, small WEEE and batteries | - In light of our proposed new EV vehicles not having the space to collect textiles, small WEEE and batteries, alternative means of collection are being explored. These include free home collections and recycling banks for textiles and small WEEE and local recycling drop-off points for batteries. The previous cages on the vehicles were also small and so limited collections were possible. Therefore we anticipate an increase in recycling tonnages through an alternative arrangement. | - Complete | - We continued to promote Traid’s textiles and small electricals collection service during 2024/25. - We continued to collect batteries from participating libraries during 2024/25. - For 2025/26 we will continue to promote the charitable doorstep collections. We will also look to trial textiles banks at housing estates and will submit a funding bid for small electrical recycling collections from public buildings. | - 4 tonnes of textiles collected by Traid. - 0.1 tonnes of small WEEE collected by Traid. - 0.1 tonnes of batteries collected in 2024/25. |
| RBK #4 | Review Kingston First recycling | - Kingston First is a business improvement district covering Kingston town centre. We are reviewing their recycling practices to ensure food waste is recycled in the marketplace. We are also reviewing their long-term recycling and waste strategy to promote increased recycling and waste reduction initiatives | - On track / part complete | - Kingston First continued to operate the Business Improvement District and offer a commercial recycling service through their waste partners First Mile. - For 2025/26, a new marketplace operator will manage the marketplace. Food waste recycling will be introduced for vendors in the marketplace. | - No impact |
| RBK #5 | Establish a Library of Things | - Establish a Library of Things to enable residents to borrow infrequently used household items, reduce unnecessary consumption and minimise waste. | - Cancelled | - We were unable to identify continued resource funding to support the long-term running of a Library of Things as part of the council’s operations. | - No impact |
| RBK #6 | Flexible Plastics trial | - Kingston will participate in a 2 year flexible plastics recycling trial, organised by Suez. The trial will initially involve 5% of Kingston households, before moving to 25% in the final year of the project. - Households participating in the trial will be expected to present a plastic bag full of their flexible plastics inside their dry mixed recycling bin. This will be collected by our contractor but separated at the sorting facility, before being collected by Suez for recycling. | - Cancelled | - We were unable to further develop due to operational complexities sorting flexible plastics after collection. At the scoping stage it had been planned that flexible plastics could be transported together with our dry mixed recycling to be separated at our MRF. However it was not possible to find a feasible operational solution satisfactory to all parties so we had to withdraw. | - No impact |
| RBK #7 | Review council waste pages | - Update the council web pages on waste to provide additional information. The focus will be more on how residents can reduce waste, improve recycling behaviours, consume less to reduce their environmental impact and signposting residents to different local places where they can take their waste to be recycled / reused. | - Complete | - Website pages were updated in 2024/25 but the focus was on streamlining content. - Planned content updates for 2025/26, including greater guidance on communal waste and recycling. | - 107,890 views with 59,166 active users on Kingston’s waste and recycling web pages. |
| RBK #8 | Monthly waste reduction and recycling communications | - Twice a month posts on council communication channels specifically targeting ways in which residents can reduce their waste, increase recycling, address behaviours to reduce their environmental impact and inform residents of local and national waste reduction and recycling initiatives. - Posts thus far have included the Material Focus recycle battery campaign and vape research, as well as advising on water refill stations to reduce single-use plastics. | - On track / part complete | - Monthly communications continue to be delivered on council platforms encouraging residents to reduce, reuse and recycle various items of waste during 2024/25. Posts varied from promoting projects and local initiatives, to promoting campaigns and behaviour change. - Monthly communications campaigns will continue in 2025/26. | - Rough engagement on monthly communications has around 36,000 reach across the borough, on our social media platforms. |
| RBK #9 | Implement reusable container scheme at the marketplace | - Explore wide-scale implementation of reusable container schemes to reduce use of single-use plastic. Option being explored is a reusable cup scheme for the Christmas Market 2023. | - Complete | - A reusable cup scheme was in place during the Christmas market for 2024/25. - No current proposals to implement a further reusable cup scheme in 2025/26. | - No data was made available to log the impact. |
| RBK #10 | Review schools and commercial recycling package | - Review schools recycling in the borough and our commercial recycling package. Schools will be contacted to review current waste practices and areas for improvement will be suggested. Information on the Veolia commercial waste service will also be provided. | - On track / part complete | - We contacted schools and businesses ahead of the business simpler recycling legislation deadline and promoted our commercial waste service. - Promotions will be ongoing in 2025/26. | - 35 new leads from time of promotion through to April 2025. |
| RBK #11 | Provide food waste recycling service to flats above shops that receive a bags service | - 82% of flats above shops have storage space for bins and therefore receive the same collection service as kerbside properties. However, the remaining properties (285 in total) on a bags service do not. Therefore, the trial introduction of food waste recycling for these properties to fulfil Resources and Waste Strategy policy requirements is proposed to ensure that all households in Kingston have access to the food waste recycling service. This will involve the use of on-street bin storage units for both refuse and food waste. | - On track / part complete | - Scoped locations for a food waste trial during 2024/25. - A trial will be delivered for 2025/26, targeting 6 streets with flats above shops. The trial will involve installing food waste housing units on the pavement for flats above shops to use to recycle their food waste. | - No impact during 2024/25. |
| RBK #12 | Introduce community composting at local sites | - Introduce community composting at various local sites. Potential sites to be explored consist of local waste sites and communal housing estate grounds. | - Delayed / on-hold / no progress to date | - No developments in 2024/25. - A survey of a local site, identified for community composting, is being carried out in 2025/26. This will inform the improvements required and its suitability as a community composting site. | - No impact during 2024/25. |
| RBK #13 | Review council events policy to explore ways to reduce waste, increase recycling & lessen the environmental impact of events | - Review council events policy and consider measures which can be introduced to ensure more waste is reduced and recycled. Options include reusable containers for food and drink. Recycling on the go bins, with adequate signage and volunteers to support proper recycling and reduce contamination. Setting food waste reduction targets. Local procurement of goods to reduce the overall emissions of the event. Procurement of environmentally friendly goods. - We are also running a trial with Sunray Recycle, a local community group to explore how much recycling can be generated through their voluntary events waste management support, to see what further support we can provide to community events in the future | - On track / part complete | - Support was provided to 3x event organisers to help them recycle their waste at their community events during 2024/25. - For 2025/26, support will be provided to 5x event organisers to help them recycle their waste. We will also look at developing an events recycling package for event organisers where they can set up recycling facilities for their events. | - 7x 360L dry mixed recycling and 3x 360L paper/card wheelie bins collected from 3x events during 2024/25. |
| RBK #14 | Reduce contamination and excess waste in households | - Veolia our waste contractor engages in a number of activities to help reduce household contamination and the presentation of excess waste. These include bin tagging, sending letters and doorknocking, providing stickers, leaflets and informing residents about their bulky waste service. | - On track / part complete | - During 2024/25, Veolia delivered tags and contamination letters to residents who were consistently contaminating their recycling or who were putting out excess amounts of waste for collection. A resident visit was scheduled if a fifth repeat contamination occurred. - This process will continue in 2025/26. | - 5000+ contamination letters sent to residents. This lead to: - 1st Contamination Totals = 14710 - 2nd Repeat contamination totals = 5374 - 3rd Repeat contamination totals = 2783 - 4th Repeat contamination totals = 1490 - 5th Repeat contamination totals = 745 - 6th Repeat contamination totals = 337 |
| RBK #15 | Garden waste service promotion | - Veolia leads on promoting our garden waste recycling service and managing the renewals process. Activities include sending letters, digital marketing and organising a competition where residents can win a free yearly subscription. | - On track / part complete | - Veolia delivered their promotion and renewal process for Kingston’s Garden waste service during 2024/25. - They will continue to promote the renewal service in 2025/26. | - We had 15,180 subscribed for the garden waste service in 2024/25. - We collected 4891.253 tonnes of garden waste during 2024/25. |
| RBK #16 | Food waste participation | - Deliver interventions to kerbside properties to increase use of the food waste recycling service. Two low performing rounds have been targeted and residents will be provided with a sticker and leaflet informing them of what they should do with their food waste. - Households who have previously taken part in this project, are being targeted with food waste reduction messaging. This also includes a sticker and leaflet encouraging them to waste less food. | - On track / part complete | - During 2024/25, we targeted Alpha Road Estate (368 properties). The estate had food waste but frequently had contamination issues. We purchased Metrostor food waste units and delivered communications, caddies and liners to residents to address contamination and boost food waste participation across the estate. - For 2025/26, Veolia will target two out of four kerbside rounds with a food waste participation campaign. Letters, liners and leaflets will be delivered and stickers put on bins. | - The Alpha Road Estate project delivered a 165% increase in food waste captured across the estate. |
| RBK #17 | Carbon reduction - Plastics recycling comms | - Targeted communications to encourage further plastics recycling and prevent plastics ending up in the residual waste stream | - Complete | - The campaign was delivered in 2024/25 using a mixture of out of home advertising and social media campaigns. | - 52,906 reach - 183,172 impressions - 1.4% click through rate - 2599 link clicks - £0.42 cost per click |
| RBK #18 | Reduce Reuse Recycle Roadshow Events | - Conduct events encouraging people to reduce, reuse and recycle. Events include hosting stalls at local events, facilitating swap events and conducting school assemblies. | - On track / part complete | - During 2024/25, recycling outreach stalls were held at local events. Veolia also ran MRF tours for residents. Recycling Rockstars school assemblies were also held. - For 2025/26. 6 Roadshow events, 2 Recycling Rockstar assemblies and 1 MRF tour will be delivered. | - 5 schools visited. - 2 outreach events attended. - 4 MRF tours were held. |
| RBK #19 | South London Partnership - Zero Waste Map | - Together with Richmond and Wandsworth, Croydon and Sutton councils, Kingston has developed a Zero Waste Map which identifies all of the places where residents can buy goods with minimal or no waste. The map also highlights where residents can borrow, repair and share goods. It also identifies where residents can take items to be recycled. | - Complete | - The South London Partnership’s Zero Waste Map has been completed and is live on their website. We continued to promote this map through our communications channels during 2024/25. - We will continue to update and promote this in 2025/26. | - This map has 65,242 views since being uploaded. |
| RBK #20 | Rollout of Electric Fleet Waste Collection Vehicles | - We will be replacing our ULEZ compliant waste collection vehicles with fully electric ones. As part of this, we will move away from twin stream recycling collection vehicles to single chamber vehicles but with the same separation of recycling commodities with food waste to be collected in a separate vehicle. Moving to single chamber vehicles will reduce disruption to the recycling service as our twin stream vehicles occasionally broke down, meaning two household recycling collections were affected. There will also be a stronger focus on driving participation in the food waste service through targeted communications. | - Complete | - The electric waste vehicle fleet was rolled out in Autumn 2023. - As part of the new waste and street cleaning contract recommissioned during 2024/25, a mix of electric and sustainable Hydrotreated Vegetable Oil fuelled street cleaning vehicles will be introduced in 2025/26. This means there will be no diesel operated vehicles in the waste and street cleansing service, bringing the borough closer to its Net Zero. | - The waste fleet emitted 349 tonnes of CO2e during 2024/25. |
| RBK #21 | Trial recycling on the go bins | - Recycling on the go bins have been installed as part of a trial to capture recyclable materials from general waste litter bins in the borough. Two sets of bins were installed in July and another two sets will be installed in October 2022. | - Complete | - Recycling on the go bins continue to be in operation at the main train stations in the borough during 2024/25. - They will continue to operate in 2025/26 with no plans for expansion due to high levels of contamination. | - Specific tonnage data for these bins is not collected. |
| RBK #22 | Explore recycling and reuse at Kingston’s cemeteries | - Kingston’s cemeteries have been generating waste which they have identified could be reused and/or recycled. - Explore options for reuse and recycling, including engaging with community groups to undertake reuse of these materials. | - Cancelled | - Initiative cancelled due to a lack of volunteers. | - No impact. |
| RBK #23 | Create Restart repair network for Kingston | - Create and promote a repair network on the Restart website incorporating community groups and residents interested in repair. The network will be used to promote repair cafes in the borough, engage residents to encourage them to repair goods, identify volunteers who have skills to repair as well as share advice and knowledge. | - Complete | - Restart network is now managed by Transition Town Kingston as they run monthly repair cafes in the borough. | - The group has 24 volunteers as part of the network. |
| RBK #24 | Fly Tip Task Force | - A regular group of officers from various departments meet to resolve fly-tipping issues in the borough. Part of this involves addressing hot spots and educating residents in what to do with bulky waste they wish to dispose of. Enforcement officers are also engaging with businesses who are not upholding their waste duty of care and informing them of how they should dispose of their waste. The main aim is to reduce fly-tipping and ensure waste is properly managed and disposed of to keep Kingston’s streets clean and to make it possible to recycle as much waste as possible. | - Complete | - The group continued to meet bi-monthly during 2024/25 to discuss and address fly-tipping hotspots. Initiatives included coordinating on-site meetings, sending letters to residents and installing signage on estates to deter fly-tipping. - The group will continue to meet during 2025/26. | - Fly-tipping reduced by 95 in 2024/25. |
| RBK #25 | Villiers Road Infrastructure Project | - Kingston’s waste site is undergoing a redesign options appraisal to ensure better use and access of the site. This will ensure we can maximise the recycling and reuse potential of the site, as well as reduce the overall carbon impact of the site. | - On track / part complete | - The redevelopment project is at the design stage, with a final costed design expected to be ready in Summer 2026 with a view to works starting on site in Autumn 2026. | - No impact. |
| RBK #26 | Waste and Street Cleansing Contracts Recommissioning | - Kingston has begun scoping requirements for the recommisioning of the waste and street cleansing contract. Engagement work is being undertaken to shape the service and identify what improvements can be made. As part of the discussion, we are exploring how we can continue to reduce waste, improve the level and quality of recycling, reduce carbon impacts of our waste service and improve our local household recycling and reuse centre. | - Complete | - The waste and street cleansing contract was awarded to incumbent Veolia and will commence from 1st April 2025. As part of the new contract, street cleansing vehicles will transition to a mix of electric and HVO vehicles, reducing our transport emissions. A dedicated Education, Communications and Outreach team will be assigned to Kingston as well, supporting the council’s efforts to engage residents in waste reduction, reuse and recycling. | - New contract commissioned to commence in April 2025. |
| RBK #27 | Flats recycling packages for Managing Agents | - Veolia will develop a three tiered recycling package (Bronze, Silver & Gold) for managing agents to apply and implement at flats in the borough. The choice of package is determined by the managing agent and flat requirements. Gold packages will be limited. Packages will consist of a range of measures, with Gold involving the most interventions. | - On track / part complete | - The managing agents pack was developed in 2024/25 through trials across the South London Waste Partnership. In Kingston, Veolia delivered the food waste project at the Alpha Road Estate to develop the food waste aspects of their Managing Agents pack. - For 2025/26, Veolia will use learnings to update 5 communal bin stores in Kingston. | - The Alpha Road Estate project delivered a 165% increase in food waste captured across the estate. |
| RBK #28 | Improved processes for accessing planning requirements for waste in flats | - New processes in place for developers and managing agents to ensure waste requirements dependent on the number of units being built, are taken into account by signposting them to the new technical planning guidance document prior to ordering new containers. Furthermore, for major developments (10 or more units) they should contact the waste team to discuss requirements in further detail. | - Complete | - Planning guidance for waste and recycling updated in 2023/24. | - 448 page views during 2024/25. |
| RBK #29 | Deliver ‘Eco Refill’ shops in primary schools | - Work with Pupils Profit to deliver ‘Eco Refill’ shops across primary schools in Kingston. The refill shops will be run by students in the primary school and will sell household cleaning products once a month. The school community will be invited to purchase goods using their own refillable containers. | - On track / part complete | - 6 primary schools participated in the Eco Refill programme, delivering zero waste shops to reduce plastic waste. - A total of 8 primary schools will participate in the programme during 2025/26. | - There were a total of 19 shop openings with 673 plastic bottles saved from using refillables. |
| RBK #30 | Participate in Eat Like a Londoner campaign | - Participate in a pan-London food sustainability campaign, with the aim to reduce food waste and encourage a more planet friendly diet. As part of this campaign, an online platform will be created which features recipes and tips to help residents achieve those outcomes. The campaign will consist of 3 social media and out of home advertising bursts, advertising the Eat Like a Londoner platform. | - Complete | - Kingston participated in 2023/24 but did not participate in 2024/25. We will not be participating in 2025/26 either. | - No impact during 2024/25. |
| RBK #31 | Encourage reuse of council furniture from office building decommissioning | - Some Council buildings are being decommissioned as part of its Future Workplace programme. As a result, a large amount of furniture will no longer be required. Options will be explored to ensure as much gets reused where possible, with the rest recycled and as little sent to incineration. | - Complete | - Work completed during 2023/24. | - No impact during 2024/25. |
| RBK #32 | Deliver upcycling and repair workshops for textiles and electricals | - Deliver upcycling and repair workshops for textiles and e-waste to encourage residents to reduce the amount of textiles and electrical waste they are producing. The workshops will teach residents how to repair goods and upcycle them into something new. - Traid will host quarterly free workshops on repair and upcycle of textiles and electrical goods. - For 24/25, we will partner with Loom to facilitate monthly textiles upcycling workshops. | - On track / part complete | - During 2024/25, Loom delivered monthly textiles upcycling workshops in local libraries and community centres. - The monthly workshops will continue in 2025/26, with 12 in total scheduled across the year. | - 8 workshops delivered in 2024/25, teaching residents different skills in textiles upcycling. |
| RBK #33 | Deliver electrical repair lesson kits to students | - For 24/25, we will partner with Team Repair to deliver electrical repair kits to schools. This is to teach repair skills to children and to nurture their interest in STEM education and sustainability. | - On track / part complete | - 250 repair kits were subsidised for 6 schools to teach pupils how to repair electrical gadgets during the 2024/25 academic year. - We will explore our participation in the scheme during 2025/26. | - 250 repair kits were delivered to 6 schools teaching repair skills. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| RBK #34 | Set up textiles banks on Kingston’s housing estates to increase reuse and recycling of textiles. | - For 2025/26 we are looking to set up a 6 month trial of textiles banks on a select number of housing estates across the borough. If successful, we will roll this out to further housing estates. | - Minimum of 60 tonnes of textiles collected for reuse / recycling, expected during the trial. | - Trial during 2025/26. - Expand to more housing estates during 2026/27. |
| RBK #35 | Set up public small electrical drop-off points across the borough to increase reuse and recycling of small electrical devices. | - Submit a funding bid with Material Focus to set up public small electrical drop-off points across libraries, leisure centres and community centres. | - Minimum of 4 tonnes of small electricals per year collected for recycling. | - Submit funding bid during 2025/26. - Commence project if successful with bid in 2026/27. |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| RBK #36 | Rollout food waste to 6000+ communal properties who currently don’t use the food waste service. | - During 2024/25, we audited all communal properties to see which properties had access to food waste recycling. - In 2025/26, we will introduce a food waste service to 25% of these properties, install housing units to encourage uptake and deliver communications, liners and caddies to support the rollout. We are aiming to deliver the rest of the 75% of properties in 2026/27. | - We would expect a minimum of 392 tonnes of food waste collected for recycling and for the residual waste to be reduced by the same amount. | - Roughly 25% of properties will be delivered a food waste service in 2025/26. - Roughly 75% of properties will be delivered a food waste service in 2026/27. |
| RBK #37 | Reintroduce recycling bins to 1259 communal properties who currently do not have access to recycling bins | - During 2024/25, we audited all communal properties to see which properties had access to food waste recycling. - We aim to reintroduce recycling bins to these properties in the next two years to ensure all communal properties have access to recycling bins. | - We would expect to capture 181.48kgs/household/year of dry recycling across both waste streams. | - To be completed by the end of 2026/27. |
| RBK #11 | Provide food waste recycling service to flats above shops that receive a bags service | - As mentioned above, a food waste recycling trial will be delivered in 2025/26 to 6 sites (roughly 33% of flats above shops without a food waste service). - We aim to deliver the remaining sites in 2026/27. | - We would like to achieve 30kgs/household/year of food waste recycling. | - To be completed by the end of 2026/27. |
| RBK #38 | Introduce a flexible plastics collection to all properties | - In 2025/26, discussions taking place with contractors with regard to preparations for collecting, treatment and disposal of flexible plastics from 2027 and reviewing best practice from FlexCollect trial. | - Pending agreement of collection methodology to determine expected outcomes. | - To be completed by April 2027. |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026