- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head)* | 235.2 kgs/head | 241.7 kgs/head | 204.8 kgs/head | Defra stats (Ex BVPI84a) The figures are calculated using population of 316,920and household number of households 148,470 |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household)* | 365.3 kgs/hh | <375 kgs/hh | 300.4 kgs/hh | Defra stats (Ex NI191) The figures are calculated using population of 316,920and household number of households 148,470 |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 77kgs/head | 73.15 kgs/head | 37.4kgs/head** | Borough to estimate based on own waste composition data. **Based on a waste composition analysis from 2023 which included avoidable food waste classification. Residual - 20.9%, Food waste - 55.8%, Mixed Dry - 3.5%. Population 316,920 |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 31.7% | 37% | 31.5% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 22.7% | 35%* | 19.9% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 58%* | 8.5% | 8.5% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 0% | 0% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update (new updates in blue):

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| 1 | - Waste Reduction - Reducing Environmental Impact - Maximising Recycling | Lambeth’s Waste Strategy Review 2023 | - Complete | - A consultation took place in summer 2023 on a draft revised waste strategy which included reference to introducing fortnightly collections. The consultation also gathered information more widely on the waste service. 7000 responses were received. - The Lambeth Waste Strategy was reviewed to take into account the feedback and agreed in September 2023. - The fortnightly residual waste collection service was implemented in April 2024 - We will be looking at the feasibility of Anaerobic Digestion for communal food waste as this waste will be collected as food waste only by dedicated vehicles | - As part of the launch for fortnightly collections there was a surge in uptake of food waste bins which has favourably affected the recycling rate for this stream. - Approximately 70957 kerbside properties are now offered the food waste service. - This has generated an additional 319 tonnes of food waste recycling when comparing 23/24 to 24/25 |
| 2 | - Waste Reduction | Lambeth’s Excess Waste Strategy | - Delayed / on-hold / no progress to date | - Outreach officers are collecting intelligence on resident behaviour and engaging with residents where there is excess side waste through door knocking and leaflets/comms - Enforcement action is not being taken at this stage but this may be reviewed in the future - Our primary focus for residents is on education, however we acknowledge the impact of the use of bags on town centres so we will be supporting appropriate enforcement activities where needed. Engagement work with residents is currently being reviewed. This may lead to a range of interventions targeted at different problems. | - For now, we are focusing on educating residents on waste management. The impact of this will be monitored with any follow up actions implemented at a later date. There will be an improvement in the enforcement in our time banded locations. - Following introduction of fortnightly collection and increasing capacity for recycling, monitoring has shown very little excess waste being presented. |
| 3 | - Waste Reduction | Using bin weighing to target waste reduction initiatives | Cancelled | - We started a project in partnership with a bin tag supplier, but the results were not reliable despite several attempts to reset the project, so the work was discontinued. | - N/A |
| 4 | - Waste Reduction | Circular Economy Action Plan | - On track | - Work on circular economy is continuing with several workstreams being co-ordinated by the Climate Change Team. These include: - A series of repair cafes for electrical goods. The repair café is open on the first Saturday of each month in Brixton. - A green economy growth strategy which supports businesses including providing business support for circular economy businesses, investing in workspace for the sector and encouraging the use of the council’s Key Industrial Business Areas for circular economy technologies - The Lambeth Climate Partnership (LCP) connects the public, private, and third sectors to facilitate knowledge exchange as part of its mandate to inspire and accelerate action in the borough. As part of this, the LCP hosted a Climate Day event on repair for residents in 2024 and a business-focused talk event in February 2025, focusing on repair, recycling, and reuse, which reached over 190 in-person attendees. Recent support - Supported by the UK Shared Prosperity Fund, the council provided grants for space improvement and a business support programme at the Remakery - a co-operative workshop and hot desk space offering business support for local people looking to learn making skills or launch repair businesses, working with reused materials. To find out more about the space available at the Remakery and upcoming events, please visit: https://www.remakery.org/ Upcoming support - Supported by the UK Shared Prosperity Fund, the council are working with ReLondon to deliver the London-wide ‘High Streets Beyond Waste’ programme. Lambeth businesses can access one-to-one support with a business advisor to create a bespoke waste reduction plan and have the opportunity to apply for a £5,000 grant to implement their intervention. Businesses have until the 31st July to apply for the programme: https://bit.ly/3TIayVG - In the coming months, we will be hosting another event on circularity for organisations and are currently scoping how to amplify Circular Economy Week. | - The council is supporting businesses and residents to move towards a circular economy - 190 attendees reached at the business focussed event - Over the past year, Repair Café Lambeth has expanded its volunteer base to become the largest in the borough of Lambeth, now comprising over 300 active volunteers from the local community. In June, the organisation marked its second anniversary, celebrating two years of impactful service. - Since its inception, Repair Café Lambeth has welcomed a total of 5,552 visitors. Through its repair initiatives, the café has successfully diverted 1,646 kilograms of waste from landfill and prevented 14,154 kilograms of CO₂ emissions—an environmental benefit equivalent to planting one hectare of trees in Brixton. - The café has maintained a high success rate, repairing 91% of the items brought in. These include a wide range of objects such as family heirlooms, essential laptops, heaters, and various other household items. - In the 2024–2025 period, the organisation has experienced a significant increase in activity, averaging 267 visitors per event, reflecting both growing community engagement and the continued relevance of its mission. |
| 5 | - Waste Reduction | Promote home composting | - On track | - £2,500 Funding was allocated to compost bins for 24/25 - Incredible Edible worked with Estate residents to put in place a composting system on several Lambeth Estates | - As the company providing the compost bins has changed hands – it has not been possible to get figures for compost bins for 24 25 - Composting rolled out by Incredible Edible to 14 Estates |
|  | - Waste Reduction | Reduce avoidable food waste | - On track | - There have been multiple social media campaigns carried out by our Education and Outreach (ECO) team highlighting avoidable food waste and giving tips for preventing it - This is also highlighted by face-to-face contacts by the ECO team such as at the Lambeth Country show - We are highlighting resources for redistributing food in our communications to businesses about food waste recycling |  |
| 6 | - Waste Reduction | Promote reusable nappies | - On track | - The contract with Real Nappies is continuing this year | - 54 vouchers for starter packs were distributed in 2024/25, 35 of these were redeemed, leading to a redemption rate of 56% |
| 7 | - Waste Reduction | Support refresh of WRWA Waste Management Policy | - Complete | - This process has started and we expect the consultation relating to the strategy to start in September/October with the strategy being finalised towards /early next year. As one of the four constituent boroughs, Lambeth had input into the draft strategy and the associated consultation materials. | - This process was concluded in February 2025. Lambeth fed into the draft and facilitated the internal governance process. The Joint Municipal Waste Management Strategy has now been published |
| 8 | - Waste Reduction | WRWA’s educational programme and resources for schools and residents | - On track | - The WRWA education programme continued in 24 25 | - 16 Lambeth Schools visited Smugglers Way site for a tour & educational talk during 24/25. Some of those schools had more than 1 class attending, so a total of 34 classes visited. There were also 6 adult group visits (including a visit inside the MRF) |
| 9 | - Waste Reduction | WRWA’s Reuse and ReWork services at Smuggler’s Way | - On track | - The rework facility continues to repurpose both furniture and WEEE received from residents - Re-work also has its own website for selling refurbished white goods Products – Rework London | - The amount of repurposed furniture apportioned to Lambeth for the period 24/25 was approximately 15 tonnes with an additional 6 tonnes of repurposed electrical goods. - This was a notable increase from 23/24 when approximately 4 tonnes of furniture with 3.5 tonnes of repurposed electrical goods. |
| 10 | Waste Reduction | Emmaus bulky waste collaboration | - On track | - This service started in September 2023 and involved the integration of LBL’s existing service telephone service with a direct contact to Emmaus. - The promotion and operation of the service has been continuously developed resulting in improvements and the intention is to expand further. | - In the first year of operation (Sept- Aug 2024), 4.039 of goods were collected for reuse. - In the second year 4.761 tonnes were collected. |
| 11 | Waste Reduction | Ensure reuse of bulky items collected by Grimebusters | - On track | - White Goods such as Fridges, Freezers and televisions are taken to Vale Street - There needs to be more work done to take reusable furniture for reuse – the team will be trained to identify suitable items and opportunities for reuse. No change | - We are still working towards increasing the amount of materials that are repurposed by the work of Grimebusters. |
| 12 | Maximising Recycling | Kerbside assisted textiles collections | - no progress to date | - Assisted collections of textiles has been rolled out to Lambeth residents - There hasn’t been take up of the service although it is advertised on the recycling web pages and was promoted to all assisted collection users when it was launched in 2022. - We will review how the service is promoted and try and improve takeup in the next financial year. |  |
| 13 | Maximising Recycling | Roll out kerbside small electricals and batteries collections | - Complete | - Kerbside collection of WEEE was rolled out in 2022 and will be continued into the future | - 1.16 tonnes of small WEEE were collected via the kerbside collection in 2024/25 - This was an increase of 0.24 tonnes |
| 14 | Maximising Recycling | Flats Recycling Improvements | - on-hold | - The flats recycling package was successfully delivered to 1,081 properties from March to May 2023. This is approximately 1.5% percent of the c 70,889 flats on estates. Unfortunately, the capital required to deliver the package to further properties is not available in the short term and so this programme is on hold. | - The flats that have received the service (which historically had poor recycling performance) have more capacity for recycling, a tidier estate and better signage than previously. |
| 15 | Maximising Recycling | Food Waste in Flats | - Delayed | - Food waste collections were rolled out to an additional 3000 properties in April 2023 so a total of 6000 properties have the service. - The roll out of food waste to Estates has been delayed until June 2026 because of the lead time for provision of collection vehicles. - The flats above shops (FLASH) pilot happened in November 2025 and will be rolled out to all FLASH this financial year. | - A total of 132.7 tonnes of food waste was collected from the 6000 flats in 24/25. |
| 16 | Maximising Recycling | Increase Commercial Recycling Rates | - Delayed | - The commercial team has been prioritising and discounting the commercial recycling service in order to drive up the recycling rate. - They will continue to do this to reach higher recycling targets - From April 2025, businesses will be required to have contracts for a food waste service | - The provisional commercial recycling rate for 24 25 is 19.8% |
| 17 | Maximising Recycling | Ensuring adequate space and facilities for recycling in new developments in Lambeth | - On track | - This code is reviewed and looked at yearly - The code of practice is being reviewed again in light of the upcoming roll out of food waste to flats, however, when last revised, the rollout of food waste to communal flats was anticipated and so recommendations on this were included in the last revision. | - The ACOP was updated stating that developers had a responsibility to ensure there was adequate space for recycling, including space for food waste caddies. This will make all new dwellings fit for purpose in terms of their waste and recycling management |
| 18 | Maximising Recycling | New on-the-go smart litter and recycling bins and #InTheLoop campaign | - Complete | - Initially 80 ‘smart’ bins were installed in town centre locations in 2022 - The bins had clear graphics which were part of the #InTheLoop campaign. - The success of these bins resulted in some smaller metal ‘dual’ bins being added in town centres in March 2024 - The success of the bin design has led to further bins being put in place in town centres | - Hubbub carried out an evaluation of the smart bins and found that on average the amount of recycling increased from 33% to 80% - The contamination of the recycling bins reduced on average from 67% to 20% |
| 19 | - Reducing Environmental Impact | Increase proportion of electric vehicles in the waste and street cleansing fleet | - On track | - The charging infrastructure is partially completed in the depots but is awaiting further capital input - Electric vehicles continue to be procured where funds are available | - 34% of the core fleet are electric. Of the 117 core vehicles, 40 are electric, the remainder diesel. |
| 20 | - Reducing Environmental Impact | Work with WRWA and the other partner boroughs to explore options for minimising waste, increasing recycling, and reducing the carbon impact of waste treatment through the current disposal contract | - On track | - The initiatives listed are being continued - The response to this section is embodied in the WRWA JMWMS | - Decreased carbon emissions associated with Lambeth’s waste management |
| 21 | - Maximising local waste sites | Continue to promote Smugglers Way and Vale Street Household Waste and Recycling Centres | - On track | - Promoted throughout the communications for fortnightly residual collections - The Lambeth Website promotes these facilities so residents can use the facilities for whatever they need to recycle or dispose of. | - The communications issued as part of the move to fortnightly residual waste collection raised awareness of Vale Street and the other RRCs. This was sent to all kerbside residents of the borough. |
| 22 | - Maximising local waste sites | Seek to increase reuse and repair at Rework Reuse workshop at Smugglers Way | - On track | - The Technical Officer continues to attend meetings at the WRWA and has had input into the JMWMS. | - The amount of repurposed furniture apportioned to Lambeth for the period 24/25 was approximately 15 tonnes with an additional 6 tonnes of repurposed electrical goods. - This was a notable increase from 23/24 when approximately 4 tonnes of furniture with 3.5 tonnes of repurposed electrical goods. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
|  | Rolling out of food waste to estates | The planning for the roll out has taken some time as it has involved assessing all estates and private blocks of flats and working out positioning and capacity for food waste bins. The next step is to carry out routing for the vehicles and order the bins. The vehicles have been ordered but they will not be available until June 2026. | Commence food waste service to all purpose built flats | Due in May - July 2026 |
|  | Rolling out food waste to flats above shops (FLASH) | All the locations for the on-street bins have been mapped out. A pilot for this service took place in November 2025.This will be followed by the rollout throughout the borough by the end of the financial year. | The trial will Inform us what resources are needed to scale up the service | Full rollout by March 2026 |
|  | Collection of Flexible plastics | Planning a trial to find out how well the WRWA MRF separates the plastics and also to observe resident behaviour |  | TBC |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026