London Borough of Haringey RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| HGY1 | Destination 50% Strategy | The Council has embedded a new way of working entitled the “Haringey Deal.” The “Deal” is at core, about relationships between the Council, residents and partners that are founded in trust and where power is shared. It means getting a better understanding and responding to residents’ need, by taking a strength or asset-based approach and addressing barriers to service access, with a view to achieving more equitable experience and outcomes. It is also about operating within a challenging financial context, in which we must change the way we operate to protect outcomes and meet social need with less budget. At the start of 2023, the Council engaged with residents to get views on the waste services and ways to improve re-use and recycling in the borough. With over 8,000 responses the engagement will be taken forward to help shape Haringey’s waste strategy. As part of our commitment to co-production, the results arising from the engagement should be used to co-design the development of the recommended waste strategy along with its associated policy and service proposals. The Strategy (April 24) will incorporate key priorities for the next 7-10 years and set out a pathway towards reaching our target 50% recycling rate. As part of this the Council has modelled the potential impact of changes to services, to help reach the target, as well as reviewing changes to street cleansing practices and other initiatives. The RRP will be updated following the strategy production in April 2024 to reflect fully the Destination 50% path | On track/Part complete | - Haringey has fed into the development of the NLWA Joint Waste Strategy, which provides a joined-up approach for the 7 boroughs. Due to this, Haringey has decided not to publish its own waste strategy. - Instead, Haringey has developed an Action Plan, showing our key Priorities for the next 10 years, and the key actions to deliver during time frame. - A key part element of this is to ensure services are delivered in accordance with Simpler Recycling, and using modelling to determine the best collection system, from 2027 when our current contract expires with Veolia. - Our Action Plan will go to Cabinet in October / November with a wider package of decisions on from our wider Service Review. | - These contribute to the targets in the dashboard |
| HGY 2 | Destination 50% - Improved recycling at Council buildings, libraries and community centres | We are adding more materials to the range of recycling already accepted at council managed buildings including batteries, printer cartridges and keys and other items as appropriate. These are free of charge services so are not dependent on additional funding. So far, all Haringey’s libraries have domestic battery recycling facilities with three having printer cartridge recycling containers. Key recycling points have been agreed, as has one library where book recycling will be trialled. These will be promoted using the council website and social media. | On track/Part complete | - All 9 of Haringey’s libraries have recycling facilities for: - Household batteries 3 libraries also have printer cartridge facilities. The following materials will be implemented at all libraries in July/ August - Keys - Printer cartridges - Light bulbs - Vapes Two of the larger libraries will also have book and textiles recycling containers. Getting stakeholder agreement about the container types to be used, the appropriate collection arrangements in place, and use of Western Road as a delivery point has resulted with delays in getting this service in place. | - 35 kgs of batteries were collected in 2023/24. We knew tonnages would be low and this is more about raising awareness about recycling. |
| HGY 3 | Destination 50% - Schools and community hubs dry and food recycling | We are promoting existing recycling services to schools and educational facilities on a regular basis and planning to add more recyclable materials including textiles. There are 126 schools and educational facilities in Haringey - All schools and colleges in Haringey - GOV.UK - Find and compare schools in England (compare-school-performance.service.gov.uk) All schools have dry mixed recycling (DMR) facilities and 51 have food waste collections. The aim is to promote the DMR service, improve its performance and increase uptake of food waste collections as well as have a textile provider. The services will be promoted using targeted comms and digital channels. There will also be school’s competitions and services pledges to drive up performance. A textile collection trial from a small number of schools is to be undertaken with Veolia and /or TRAID in 2023. | On track/Part complete | - We’re working with NLWA and KBT on their school’s engagement policy which was launched earlier this year, https://www.nlwa.gov.uk/article/north-london-waste-education-hub and one Haringey school (Ferry Lane) has been selected as part of the policy approach. - We have procured recycling boxes for schools to use in the classrooms to support recycling and met with Haringey’s south Tottenham community engagement team see how we can improve recycling in the schools in that area. - Veolia has also promoted the food waste service, assisted with litter pick events (both ad-hoc and as part of the Great British Spring Clean), promoted their Sustainability Fund to encourage applications, and did a Recycle Week video with some school children to raise awareness and encourage people to recycle. - We contacted all schools in February 2024, to publicise our partnership with TRAID and to get in touch about textile recycling. We had 3 responses to this with one recycling bank being installed. | - Food waste collections are now happening at 87 of the Boroughs schools compared with 51 in 2022/23. |
| HGY 4 | Destination 50% -Contamination | We are using targeted actions and communications to tackle contamination in food and garden waste and DMR on an on-going basis (more details are provided in section 7 &12) We commissioned ReLondon to undertake a comprehensive review of Haringey’s recycling contamination policy options and this work was completed in August 2022. We are using the report to assess what will work best in Haringey with a view to introducing the first measures (automated letters) in 2023 /24 The timescale for this has moved due to changing legislation and production of the NLWA joint waste strategy. The new date for the strategy is April 2024. The new policy is initially targeted at kerbside properties with communal household measures to be considered later. Where contamination occurs, a bin will be tagged, followed by a series of escalating letters if the contamination continues. The outcome as to whether bins will be removed, enforcement action taken, or charges applied is still to be determined. The Veolia data management system (ECHO) has been updated so that letters can be automatically generated once the policy goes live. Veolia staff are also being encouraged to visit the MRF more regularly so that there is a better understanding of the impact of contamination further down the line. They are also reviewing their own staff training and recording of contamination incidences so we understand the scale of the problem in relation to the new contamination policy and the resources that will be required to apply it. | On track/Part complete | - The contamination policy deadline has moved to September / October 2024 in line with Haringey’s waste strategy. The approach is agreed, the data management system has been updated so it can generate 3 stages of letters and the potential costs of implementing this have been calculated. The details are now being finalised. - We developed a stickering campaign (keep your bin happy) to advise residents what can and cannot not be accepted for recycling to reduce contamination and to promote food waste recycling. This was developed in early 2024 and implemented in May 2024. - We worked with NLWA on their ‘Together we recycle campaign’ to target contamination on estates. Also see HG7. - Outreach activities (leafleting, doorstepping, meetings with managing agents) take place throughout the year, where there are reported persistent contamination issues. - Promotion of ‘bincidents’ on social media were posted throughout August 2023 to encourage residents to dispose of flammable items correctly. | - Recycling contamination rates in 2023/24 remain at 17%, the same as the previous year. With the outlined communications approach and once the contamination process goes live, we estimate the various contamination interventions could contribute a combined total (food and DMR) of up to 695 tonnes p.a. |
| HGY 5 | Destination 50% - Street cleaning | Haringey already segregates some recycling from its street sweeping service (split barrows and dual litter bins) and we are continually monitoring new initiatives in other Boroughs and containers such as solar powered compaction bins to see where we could make improvements to what we are already doing. Contamination of this waste stream is significant so there is potentially more to gain through back-end sorting which we are encouraging NLWA to investigate. The Council is committed to replacing single litter bins with dual litter and recycling bins and the latest replacement programme will be rolled out along Wood Green High Street in Summer 2023 | On track/Part complete | - Recycling on the go (ROTG) litter bins were installed on Wood Green High Street in Dec 23/Jan 24 replacing some of the older dual litter bins. They have different apertures and signage to encourage residents to recycle and reduce contamination. - Funding has also been obtained from Hubbub to trial 18 ‘recycling on the go’ bins in Tottenham, targeting plastic bottles and cans. This trial went live in July 2024 and will be running for 12 weeks. This trial is being evaluated by regular waste composition analyses so data will be available. | - Ongoing |
| HGY 6 | Trade waste | The commercial service promotes recycling in its service offer to schools and businesses and recycling collections are offered at a lower price than residual collections to encourage and maximise recycling. We have completed our pricing structure review. Bin hire costs have been separated from the collection costs and are now a weekly stand-alone charge. All fees and charges have been aligned with neighbouring boroughs and local competitor’s private contractors. We are currently working through a programme of switching our pre-paid sack customers to contracted services. This will assist in customer retention and reduce unregulated waste. We have rolled out the first phase of the “Customer Hub” our online customer interface. The second phase roll out is scheduled to be scoped in Q3, 24/25; it requires our contractor Veolia to integrate the current system with its Salesforce platform. When fully online Customers will be able to fully manage their contracts through the Customer Hub | On track/Part complete | - For bagged commercial waste calculated using bag volume to weight apportionment only, 2023/24 achieved 19% recycling compared to 23% the year previous. Commercial bin tonnages are not delivered to the NLWA but show a commercial bin recycling rate of approximately 13% - To date, we have 479 customers (out of a total of 1,510) registered on the Hub and have converted 141 bag customers to contracted Direct Debit payments. - The 2nd phase of the Customer hub roll out is due in Qtr 4 2024/25, following the Veolia ECHO Commercial roll out in Qtr 3. - It is our intention to switch all remaining pre-paid sack purchase customers to contract in 2025/26. | - Below in red is what we put in the last RRP - It is estimated that DMR will increase by 155 tonnes by 2024/25 |
| HGY 7 | Destination 50% - Estates | We are reducing contamination and increasing recycling on estates through a range of measures including different types of bins and targeted communications. We are also reviewing and auditing waste management facilities on estates and this work started in May 2023. We are working with our contractor Veolia and our Housing department to implement a series of actions to reduce contamination and increase participation and have set up monthly meetings to focus on this work area. We are trialling reversible lids on DMR bins, pedal food waste bins and using different types of messages to motivate people to recycle on estates. This work started in September 2022 on 5 estates and is being extended to Broadwater Farm in the summer 2023. Monitoring is undertaken before the improvements and bin weighing equipment is used to capture accurate performance data. Broadwater Farm already has food waste bins but not the bin housing units with pedals, so tonnages will not increase in the way they did in the first trial. We have recently started working proactively working with our Housing team (with limited resource) to identify where we can increase caddy liner outlets, increase the range of recycling materials, and engage more effectively with residents through TRA meetings and local newsletters etc. On this basis, a new work programme for estates will be developed for 2023. | On track/Part complete | - We promoted the NLWA ‘Together we recycle campaign’ (TWR) in Summer 2023, which aimed to reduce contamination on estates by using collection crews and MRF staff in the communications. - We extended a recycling contamination and food waste trial that we ran on 5 estates in 2022/23 to Broadwater farm in June 2023. This involved the installation of 51 reverse lid green 1,100 litre recycling bins and 11 food waste bins in pedal operated bin housing units. - Based on the outcome of the trials referred to above, it was agreed that green reverse lid recycling bins would be issued as standard for replacements and new locations. - We secured funding from Material Focus for 4 WEEE banks on estates. These were implemented in February 2024 although one has since been stolen. - Veolia putting ‘no vapes’ stickers on communal bins where there are known issues to reduce contamination and fire risks. - Garden waste containers for use by communal properties were trialled on one estate in Haringey (Hamilton Close). - We are also trialling a communal bin which is wheelchair accessible at a sheltered housing unit in the Borough. Initial feedback has been positive. - A bin audit of communal properties was completed in early 2024 and the data from this has been used to provide a workplan to target estates without food waste. This work is due to start in Autumn 2024 as resources are not available until then. | - During the TWR campaign, the recycling tonnage increased by 0.07 tonnes p/w over the 12-week trial period, but the contamination did not decline. - Over the trial period (approx 16 weeks) the change of recycling bin colour and reversible lids led to an increase in use, although contamination rates were variable. - The food waste bins were used but at the start of the trial there was some contamination present in the form of plastic bags, however, this decreased during the trial and the food waste tonnage by 789 kgs. - No collections from the new WEEE banks were undertaken in 2023/24. |
| HGY 8 | Destination 50% - HMOs recycling | The recent MEL waste composition analysis (Spring 2022) has indicated that there is a significant amount of residual waste presented by HMO’s (21-29kgs p/hh/pw) with 51% being potentially recyclable. There are also waste storage issues so a focus on improving recycling and the general waste management at these properties will be reviewed and a more targeted approach be developed. We will aim to improve recycling in HMOs through a range of measures such as targeted communication and a review of the provision of recycling containment to ensure residents have the facilities to recycle. We are about to recruit additional communications and engagement support into the waste team and have identified additional funding specifically for comms and engagement work over the next 2 years. A new plan will be developed as part of this (2024) | On track/Part complete | - We have worked with our private sector housing team and designed a leaflet specifically for HMO’s. This was launched at an annual private rental landlord’s forum in January 2024. - The leaflet was also delivered to approximately 8,000 HMO households which are registered with Haringey. - In the leaflet we asked what support tenants needed to help them recycle which generated 18 responses. - The contamination policy for low rise properties also includes a letter to landlords as well as the tenants at the 2nd letter stage of the process to make them aware that their tenants are not recycling properly and to also act to rectify this. The additional communication and engagement resource has not yet been recruited but we are still expecting this to happen in Autumn 2024. | - Data so far does not indicate any significant impact on the contamination rates or recycling tonnages. |
| HGY 9 | Destination 50% - Textiles recycling | We will be promoting TRAID’s London wide free household collection service and subject to procurement agreement will also work with TRAID to promote textile recycling at schools and hold textile repair and upcycling events. | On track/Part complete | - We started a partnership with TRAID in September 2023 and have been actively promoting their home collection service using social media posts and in our annual service guides which were delivered Boroughwide in January 2024. - We have also been working with them to help increase textile initiatives on estates and with schools, although ‘take up’ of the service in these areas has been low. - TRAID also held 3 repair workshops in 2023/24 and are committed to running 4 events per year in Haringey. | - Kerbside textile collections in the Borough have increased and we saw 24.7 tonnes recycled (Sept to March 2023/24) compared with 13.2 tonnes for the same period the year before. If the monthly average is applied to the 2023/24 data, the annual tonnage would equate to 42 tonnes. - A combined total of 31 people attended these events, and 34 items were repaired, and 10 people shown how to make draught excluders. |
| HGY 10 | Destination 50% - WEEE recycling | We are increasing the opportunities for residents to recycle WEEE across the Borough through kerbside collections, additional on street drop off points and using targeted and digital communications to promote the services. A kerbside WEEE trial was implemented at the same time as the textiles in February 2022. This service was to be replicated in the Autumn along with the textiles but both trials were delayed and since then a bid for funding from Material Focus was submitted for 4 additional WEEE banks and an electric vehicle and operative to offer a Boroughwide kerbside small WEEE service. The funding was granted on 1/6/23 and implementation will be over the Summer 2023. | On track/Part complete | - The kerbside WEEE collections were implemented on 12/02/24 and operate from Monday to Friday using a booking system. The development of the microsite to allow resident to book a collection is what led to the service being delayed. A promotional leaflet was delivered all kerbside properties around the time of the launch. - Additional WEEE banks were installed on 4 estates and the residents in the surrounding areas were leafleted, - The new facilities were also promoted on social media and on digital boards and banners. | - From the start of the kerbside service in February 2024 until the end of March 2024, we recycled 0.38 tonnes of small WEEE. - This is far less than we projected although we only launched the service in February 2024 so we will continue to promote the services and consider other ways of increasing this tonnage. |
| HGY 11 | Destination 50% - Garden waste recycling | We want to increase the number of subscribers to the chargeable garden waste service. A comprehensive targeted communications campaign which included digital media, external comms such as banners and adverts and doorstepping was undertaken at the start of 2022 and resulted in an increase of approximately 300 subscribers by the end of December 2022(total of 10,532). We will continue to promote the service to fit in with seasonal activities such as leafling and in spring when plant growth begins. We will also use GIS data to identify which addresses have gardens and send targeted letters for those residents who have not yet subscribed to the service. We are investigating the feasibility of introducing garden waste services for estate properties who do not currently have access to the scheme. | On track/Part complete | - There is regular promotion of the garden waste service and letters are sent to every existing service subscriber each year as well as reminder letters. - There is targeted door stepping and leaflet drops to those who have gardens but don't currently subscribe. GIS data is used to identify these properties. - We are trialling garden waste collections on one estate to understand the challenges with this and how we can roll this out Boroughwide. - We provide collections to community gardens on request, and we also promote Christmas tree recycling over the festive period, | - Garden waste tonnages have increased to 2,897 tonnes in 2023/24 compared with 2,279 tonnes in 2022/23 - In 2023/24 there were 10,838 garden waste subscribers compared with 10,532 in 2022/23. |
| HGY 12 | Destination 50% - Food waste | We promote the Boroughwide food waste service through digital and external communications on an ongoing basis to increase participation and reduce contamination for all property types. We implemented a food waste collection trial for flats above shops at three locations in March 2023. Due to staff turnover, we do not have enough data yet to assess the performance of the trial so far. For estates we have extended the trial implemented on 5 estates in 2022 using different container types with pedals to increase participation, to Broadwater Farm estate. This will be accompanied by a communications campaign using different motivational messages and in Turkish to see which have the most impact. For kerbside households we trialled different communication messages and used ‘No food waste and how to recycle food waste’ stickers on residual waste and DMR bins in early 2023 We will be weighing the food waste produced to understand the impacts of these interventions. If successful, some or all of these measures will be considered for other areas of the Borough. | On track/Part complete | - Regular promotion of the food waste service was undertaken throughout the year and a specific campaign ‘Keep your bin happy’ was developed to promote the kerbside food waste service. - Seasonal messaging about food waste leftovers at Christmas was posted on social media. - BWF trial update (see HG7) - Use of the bin audit information to identify estates where we can implement food waste (See HG7) | - Food waste increased from 3,309 tonnes in 2022/23 to 3,459 tonnes in 2023/24. |
| HGY 13 | Destination 50% - Reuse and recycling centre | We have noticed a reduction in productivity at Haringey’s Western Road recycling centre, both in foot fall and tonnages and want to increase use of the recycling centre now that COVID restrictions have been lifted. Tonnages from the recycling centre in Western Rd have decreased since pre - Covid times. In 18/19, NLWA tonnages made up 6.2% of our 30.2% recycling rate, but this has reduced to 3.5% and 3.7% of the 20/21 and 21/22 rates, respectively. In November 2023, the NLWA removed the booking system for all vehicles except for vans. Mattresses will continue to be collected for recycling and discussions are taking place to provide services to recycle crisp packets. The textile recycling contract has been renewed with a view to increasing the scope of textiles and carpets that are accepted at the RRCs network. This offer is hoped to be in place by end 2023. In April this year, NLWA have recently implemented a new reuse service at the site. Residents can now take items that will be diverted for reuse. Initially the items will go to the shop at Waltham Forest, but we are currently developing a feasibility study as part of our Corporate Plan commitments with the aim of setting up a reuse and repair hub in the Borough | On track/Part complete | - Recycling performance at Western Road was mixed in 2023/24 and figures are not yet confirmed. Initial data shows an increase in dry recycling, garden waste and electricals but residual waste has also grown, and mattress recycling has decreased compared with the previous year. - Although not specific to Western Road recycling centre, in 2023/24 NLWA continued to expand the range of materials collected at their RRCs. - The introduction of legislation in January 2023 requiring Waste Upholstered Domestic Seating (WUDS) to be consigned as POPs, meant that a proportion of bulky waste that would have ordinarily been recycled, is now shredded and sent to energy from waste. This limits the ability to recycle or reuse certain types of bulky waste. - NLWA saw an increase in the number of mattresses collected compared to 2022/23, with around 9,000 mattresses being processed per month. Recycling of hard plastics increased to 104.89 tonnes in 2023/24. - In late 2023, NLWA launched a carpet recycling initiative at three RRCs which captured 26 tonnes of material between November 2023 and the end of March 2024. The Expanded Polystyrene (EPS) scheme grew in 2023/24, collecting 5.34 tonnes up from 0.9 tonnes in 2022/23. NLWA launched a new trial service to encourage reuse at two RRCs in Waltham Forest and Barnet to offer a place for residents to deposit unwanted DIY materials and take free of charge. In 2023/24 between the two sites, 91.79 tonnes of DIY materials were diverted for reuse. | - RRC recycling at Western Rd in 2023/24 is variable and although total tonnages at the site have increased compared with 2022/23 it looks (unconfirmed) as though the site's recycling rate has decreased. |
| HGY 14 | Destination 50% - Bring sites | Haringey does not have on street recycling sites apart from 4 WEEE and 4 textile banks. We would like to extend the number of WEEE banks and have been awarded some funding by Material Focus for 4 additional banks to be located on estates. There is also an opportunity for additional WEEE banks (other than the ones mentioned above and HGY10) through the new WEEE contract with ERP managed by NLWA which began 01/06 23. The number to be implemented will be dependent on suitable locations and available funds, as there is a purchase cost although collections remain free. The introduction of red routes and cycle lanes have made this more difficult as the banks need to be accessible for servicing and the collection vehicle needs to be close to them as the banks are emptied manually | On track/Part complete | - 4 WEEE banks were installed on estates in February 2024 although one was stolen shortly after delivery so there is now a total of 7 WEEE banks in the Borough. - We have worked with TRAID to identify new textile bank locations which has resulted in several sites being considered but only 1-2 deemed suitable. - Changes with the main textile bank provider in Haringey, (LM Barry who have sold part of their operational business to Astco) has meant a review of textile bank provision in the Borough, and a new approach to how new on street recycling sites are agreed, is being developed for 2024/25. - There are currently a total of 9 textile banks in Haringey. (8 Astco and 1 TRAID) - Please also see HGY7 and HGY 9 | - The textile bring banks generated 25.33 tonnes in 2023/24. - The WEEE bring banks produced 3.04 tonnes in 2022/23 compared with 3.13 tonnes in 2023/24. The installation of the new banks was delayed until February 2024 so there is no tonnage data to report yet. |
| HGY 15 | Destination 50% - Bulky waste | We are working with NLWA to increase bulky waste recycling at their bulky waste recycling facility so they can extract as much as possible from the residual waste stream and divert for recycling. The sorting station at Wembley (Seneca) is currently in operation. 10,000 tonnes go through the station per annum, and around 30% of materials are recovered for recycling and reuse. NLWA are investing in a residual pre-treatment facility (sorting facility) within the new resource recovery facility (RRF). This will process between 30,000 and 65,000 tonnes, and NLWA expect to recover 30% of materials for reuse and recycling. A best practice review across Europe is being undertaken by consultants, with a view to installing a facility which will provide maximum value. | On track/Part complete | - In 2023/24, the construction of the Resource and Recovery Facility (RRF) at the Edmonton EcoPark continued. The site went into operation on 15th March 2024 and will begin accepting borough waste from April 2024. - The RRF, which has capacity to manage 374,000 tonnes of waste annually, is designed to bulk recycling and organic waste for onward transport to processors, extract recyclables from residual waste and prepare bulky waste for energy recovery. - Space has been allocated to the new RRF to support recycling and reduce waste. In 2023/24, NLWA engaged with consultants to carry out reviews of best practice in the UK which culminated in two reports that explored the feasibility of installing pre-sort technology in the RRF. Following the outcomes of the reports and decisions taken by a working group developed to support this work, NLWA plans to conduct further research into technological innovations for managing waste to understand the best use for this space. | - Ongong and activities will contribute to the targets in the dashboard. |
| HGY 16 | Destination 50% - Bulky waste | Work collaboratively with a local charity to collect and resell unwanted reusable bulky waste items, such as furniture, to encourage reuse and waste reduction. We have agreed with NLWA, a reuse drop off point at Western Road RRC for residents to deposit good quality reusable items which was introduced in Spring 2023. We are agreeing the joint comms (with NLWA) to promote the service and associated reuse activities. We are also establishing a reuse and repair hub for small scale repair or exchange of broken or unwanted goods, promoting re-use, recycling and waste reduction. This will create learning and skills opportunities in refurbishment. (December 2023) | On track/Part complete | - In early 2024, the Restart Project developed a feasibility study assessing the viability of a Reuse and repair Hub in Haringey. They drafted the preliminary report and the financial modelling spreadsheet which provide a solid foundation and an overview of how we envisage the project for the next phase in 2024/25 - A suitable premises for the reuse hub has been identified in Wood Green, although details about the lease need to be clarified before the site can be secured. | - Ongoing and activities will contribute to targets in the dashboard. |
| HGY 17 | Destination 50% - Digital transformation | We are working with Veolia to improve the waste contract data management system so we can easily identify poor performing recycling areas and agree plans to tackle them. The provision of a microsite where residents and businesses are able to order new containers, report problems and get more online support for their recycling services making them more accessible and easier to use went live in February 2023. | Complete | - Veolia’s data management system is a work in progress and has seen several improvements to the dashboard and more information on contamination incidents. - The microsite has seen an increase in use, resulting in less calls and emails coming into the Contact Centre. The number of full-time equivalent staff in the team was subsequently reduced by one, with a view to a second reduction in the coming months, as part of the Council's wider savings programme. - 24/7, self-serve micro website has performed as per expectation, with very few teething problems. - Having consistently achieved between a 30-35% reduction in calls since bedding in period, the call handling staff pool have been reduced in line with savings target, i.e. reduced by 2 handlers. - Online booking for small WEEE collections was added to the self-serve facility ~4months ago | - The main outcomes of this action are complete, and the existence of the microsite will help customers easily access what they need to use the recycling services and contribute to the targets in the dashboard. |
| HGY 18 | Haringey Corporate Plan | The Haringey Corporate Plan has 3 actions specifically relating to waste reduction through reduction of single use plastics, working with Haringey environmental action groups to develop programmes to put us on a zero-waste trajectory and a New Local Plan policy which changes in the way that buildings are designed, built, operated and deconstructed in order to minimise residual waste from development. To this end we are: - Working with Veolia on an on-going basis to tackle contamination and increase recycling on a targeted local level using contract performance data and trialling different communication messages and service approaches such as reversible lids. - We evaluated a business case for implementing a Library of Things in Haringey and it was decided not to proceed at this time. - We are seeking local businesses that we can support to reduce single use plastics - We are in discussions with a local community group (Haringey Fixers) and possibly other partners to set up a reuse project at Western Rd recycling centre - We are reviewing and making improvements to all aspects of our waste and recycling services from our communications and waste and recycling campaigns to the collection infrastructure and contract data information systems where budgets permit. - Continuing to work with planners on updating planning guidance about waste and recycling storage requirements ensuring there is adequate provision to maximise recycling. - We will continue to promote waste reduction activities such as ‘swishing’ and jumble trails as well as circular SMEs to residents, including signposting via the council’s and NLWA web pages. | On track/Part complete | - Throughout the year we have worked with Veolia on the contamination policy for low rise properties. This included updating the contract management system, working with crews to improve contamination reporting and linking in with the private sector housing team concerning HMOs. - We have agreed the materials and container types to be installed for the library recycling hubs. Agreement of these, the collections and disposal outlets took time due to the different partners involved so they will be launched in Summer 2024. - A single use plastic policy has been drafted and is due to be launched in August 2024. This will include a communication campaign including businesses, with support from our regulatory services and economic development teams. - We liaised with NLWA on their Bring it Barnet campaign to encourage the use of reuseable containers at retail outlets. This will be introduced in Haringey at the end of July 2024. - In 2023 we invited reuse/ repair organisations to apply for funding to provide a feasibility study for running a reuse/ repair hub in the Borough. Haringey Fixers and Restart were the successful applicants, Theys have provided a preliminary report, and we are now working on the next steps and looking for suitable locations as the one initially earmarked is not available long-term. - We have updated our supplementary planning guidance for waste and recycling, and this was published last year and is available online - https://www.haringey.gov.uk/planning-and-building-control/planning/planning-policy/local-plan/supplementary-planning-documents-spds#wastestorage - We continued to promote waste prevention activities, mainly those led by NLWA and as outlined HGY 19 | - Ongoing and activities will contribute to the recycling target. |
| HGY 19 | NLWA waste prevention plan | A new residual waste reduction plan is being prepared by NLWA for 2022-24 which Haringey is contributing to. In the meantime, NLWA has an agreed programme of activities. These include but are not limited to: A 2-year pan-London Food Waste Campaign will be delivered in partnership with ReLondon, London Boroughs and London Waste Disposal Authorities to support individuals to reduce their personal food footprint. The campaign will use inspiring messages and practical advice to build on the success of past campaigns such as TRiFOCAL (the ‘Small Change, Big Difference’ campaign) and existing campaigns such as Food Wave. - Haringey will incorporate this into their existing waste and recycling communications work. - Low Plastic Zones (LPZs): Business engagement will continue in existing and new zones, and a review of the project by NLWA will be undertaken to ensure approach and scope are as effective as possible. - There is a low plastic zone in Crouch End which operates independently from the Council, and this will be used as a model for any prospective LPZs in the Borough Education: Continued development of an online Education Hub on nlwa.gov.uk, promote and provide central point for teachers to access a wide range of educational resources and case studies. Engage at least 15 schools to collate feedback on the effectiveness of existing waste prevention education resources and identify what NLWA could develop and deliver to fill identified gaps. Work with boroughs to gain an understanding of the waste and recycling services on offer and promote to schools. Reusable nappy scheme: NLWA has increased the subsidy to £70 from Q1 2023/24 per baby to parents/carers in north London who use reusable nappies rather than disposable ones. A project focused on the use of reusable nappies in nurseries being funded in 2023/24 through the North London Community Fund, due to be completed and reported by December 2023. The voucher scheme is administered by Real Nappies for London (RNfL) and includes as all north London boroughs as members. - Haringey is subscribed to the reusable nappies scheme and promotes reusable nappy demonstrations and pop-up shops held by Real Nappies for London and taking place in the Borough. - NLWA will run an advertising campaign to raise awareness of and increase participation in north London’s reusable nappy scheme and Haringey will amplify these messages through their communications channels. Waste Prevention Community Fund: £250,000 is committed to fund 17 community-based projects during 2023/24 focused on waste prevention activities at the community level. 85% of targets will be met or exceeded by end of 2023/24 Q4. NLWA will work closely with these organisations to promote their projects and identify opportunities to scale up activity where possible beyond the original target communities. Three of the funding recipients cover Haringey. Repair and upcycling events: At least 9 organisations are planning to deliver repair/reuse-related projects in 2023-24, funded through NLWA’s North London Community Fund. Activity will include direct support through advice/practical sessions/training for north London residents, which will be promoted through NLWA channels. Waste Prevention Exchange conference: this annual event will be delivered to bring together sector experts on a programme of topical waste prevention issues. Campaign to promote the reuse shop at Kings Road Reuse and Recycling Centre. This will include a promotional event at the shop, social media advertising and a press release. Production of six videos that show what happens to north London’s waste and recycling. Some videos will follow items of household recycling from the home, through the recycling process, until they are turned into something new. Videos will be published on NLWA and borough social media channels, and promoted through a targeted, paid-for social media campaign. Recycling campaign – Behaviour change communications campaign tackling recycling on estates will be commenced in Q2 2023-24, using personalised messaging from local collection crews. Campaign tactics will include leaflets delivered by crews, PR campaign launch sharing ‘local hero’ stories about recycling collection staff, and outdoor and social media advertising with artwork and video content featuring real crew members sharing stories and anecdotes, as well as recycling tips. Campaign targets are to generate 12,000,000 impressions through outdoor and social media advertising; reach 800,000 people via social media advertising; gain 10 pieces of positive press coverage. For communal recycling rounds receiving personalised leaflets, targets include 10% tonnage increase and 5% reduction of contamination following campaign delivery. Reusable period products – Behaviour change project to increase the purchase and use of reusable period products will be delivered in 2023/24, focusing on waste prevention and the benefits of cost savings associated with switching to reusable period products. Will include a digital communications campaign and information webpage on nlwa.gov.uk, discount voucher offers for residents, and in-person and digital outreach and engagement. Procurement of contractor currently in progress and specific campaign targets to be agreed in Q2 2023/24, once contractor confirmed. Advertising campaign to raise awareness of and increase attendance at reuse and recycling centres | On track/Part complete | - The North London Waste Prevention Plan was published in January 2023. The plan was developed through collaboration with residents, environmental specialists, borough staff, councillors, and campaigners. The development of the plan involved engagement sessions, meetings, and conversations to provide insight into local priorities and identify where NLWA activities can support partners to achieve shared ambitions. The plan is developed to set out the approach to working whilst the next North London Joint Waste Strategy, owned by the constituent boroughs and NLWA, is being developed. - Projects delivered or launched in 2023/24 as part of the plan include: - Together We Recycle - Eat like a Londoner - Reusable period products campaign - Education plans - Bring it.LPZ trial in Barnet to be rolled out to other Boroughs including Haringey in Summer 2024. - Reusable nappy subsidy Together We Recycle The Together We Recycle campaign ran from 28 August to 15 October. The campaign shone a light on what happens to waste after it is collected, aiming to improve the relationship between crews and boroughs, increase recycling tonnage and reduce contamination. A dedicated campaign webpage received 13,573 page views and tonnages increased by 13.9% over the campaign period. However, there was little impact on contamination. Eat Like a Londoner NLWA is a delivery partner and steering group member for the Eat Like a Londoner campaign on behalf of the 7 north London boroughs. It is a pan-London communications campaign to encourage and inspire residents to waste less food and eat more sustainably. In 2023/24 the campaign was promoted at events across all boroughs and was complemented by four behaviour change workshops which included a low-waste cooking demonstration. Participants weighed their food waste to monitor their progress and provide crucial data to evaluate the effectiveness of the intervention. The campaign is now ongoing, with plans to build on the campaign in the coming months. Reusable period products NLWA committed to promoting reusable period products as an alternative to single-use options. The ‘Reduce, Reuse, Your Cycle’ campaign was designed through the application of behavioural science and seeks to increase the purchase and use of reusable period products in north London. The campaign aims to decrease the purchase and use of single-use period products, leading to a reduction in the generation of single-use plastic waste and the negative environmental consequences associated with their consumption. The campaign has achieved the following across north London: - 9000 website visitors - 2.9 million impressions on social media - 7000 click throughs from social media campaign - 200 locations for outdoor advertising - 145 sign ups discount codes Bring it....... Bring It is a campaign that aims to encourage residents to use reusable coffee cups, bottles, bags, and containers to reduce single-use plastic. The campaign initially launched in Barnet and work is now being done to roll out the Bring It campaign to Camden, Enfield, Haringey, Hackney, and Islington – with Waltham Forest receiving it later in 2024/25. Reusable nappy subsidy In 2023/24, NLWA increased the reusable nappy vouchers available for north London parents/carers to £70 per baby. In the year, 1,131 people signed up to the scheme, which is a 31% increase on the previous year. There is an assumption that whilst a person has redeemed a voucher their baby will continue to use reusable nappies for at least two years, therefore the benefit of disposable nappy waste is experienced for more than one year. It is estimated that in 2023/24, 813 tonnes of disposable nappy waste was avoided. Education hub In 2023, the North London Waste Education Hub was launched, pulling together some of the best existing teaching resources on waste. The Education Hub is regularly promoted through social channels, email marketing, and features a new blog post each half term. Through consultations with borough officers and schools, a brand-new outreach Primary school programme has been developed to be launched in 2024. 21 schools applied to take part in the first year of the programme, and one school per borough has been chosen to participate. Through an initial intensive trial delivery approach, various whole school waste prevention interventions will be tested including: - Waste audits - Waste infrastructure reviews - Pupil engagement - School stakeholder workshops with senior leaders, governors, teachers, premises staff, catering staff, and PTAs - All-staff survey (pre and post intervention) to measure the change of behaviour and culture - Internal communications review | - All activities will contribute to the targets in the dashboard. - RNFL - In Haringey 151 vouchers were issued in 2023/24 compared with 138 in the previous year which is a 9% increase. - During Reusable Nappy week Haringey had 9,537 impressions and 135 link clicks compared with 70 in 2022/23 70 (meta-advertising). - Together we recycle – see HGY 7 |
| HGY 20 | Veolia fleet collection arrangements | All fleet used in the Haringey waste contract are ULEZ compliant. There is a service review which will consider alternative fuels 2022/23, the outcome of this review will form part of the decision on the future service delivery approach. | On track/Part complete | - We have completed a full review of the options to move to EVs or HVO as an intermediatory fuel. This has included a detailed assessment of the wider infrastructure requirements to transition to a full EV fleet at our current depot - A decision will be made in October/November with a wider package of decisions on from our wider Service Review. | - The decision which should have been made last year has been postponed due to the delays in the Government response to Simple Recycling. We took the decision to delay several related decisions (including the re-procurement), so that all changes would happen together. |
| HGY 21 | Sustainable procurement (Procurement Strategy 2020-2025) | The Strategy has reference to environmental priorities including the following "increasing sustainability and reducing use of plastics reduces the waste we produce and increases longevity of our resources across the planet". This strategy will be referred to when procuring for waste services and products. https://www.minutes.haringey.gov.uk/documents/s111643/Procurement%20Strategy%202019-2022_17.54_appendix%201.pdf |  | - This is ongoing until 2025 but has not been used in 2023/24 | - N/A |
| HGY 22 | North London Waste Authority disposal arrangements | The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, London Energy Ltd (LEL) and those of LEL’s subcontractors are now all ULEZ compliant. It is a requirement of the main waste contract with LEL to use Euro IV vehicles as a minimum. LEL have initiated a vehicle replacement programme to ensure vehicles comply with ULEZ. All vehicles are now Euro VI, leading to a significant reduction in NOx emissions. NLWA are currently reviewing the environmental impact of the fleet with LEL and potential improvements which can be made. As part of the NLWA’s and LEL’s sustainable strategy, consideration is being given to prioritize a transition to alternative fuels, A collaborative executive committee has been set up with several specific sustainable tangible goals. In addition to operating several fully electric light good vehicles the committee has provided a business case that has been approved to procure a fully electric Heavy Goods Vehicle (HGV) waste bulker to support its operations. LEL currently operate 13 bulker vehicles with leases that expire in late 2024. It is currently proposed that the electric HGV vehicle becomes part of the fleet around this time. The contractor for the new resource recovery facility (RRF) has been instructed to install an additional 370(no) solar PV panels. These additional panels will provide a 20% increase in total output for the whole system from 755kWp to 905kWp. | On track/Part complete | - The vehicle fleet of NLWA’s current main waste transfer, treatment, and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. Since 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. - The new RRF at the EcoPark features 2,235 solar panels on its saw-tooth rooftop which were switched on in late 2023/24. The EcoPark Array will produce renewable energy, equivalent to powering 300 homes yearly with electricity, and has been added to the site as part of the North London Heat and Power Project (NLHPP). There are also plans for solar panels to be installed on the new ERF once built. - NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the decarbonisation of the energy produced. | - All activities will contribute to the targets in the dashboard. |
| HGY 23 | NLWA Joint waste strategy | NLWA are currently developing a new Joint Waste Strategy with us and the other constituent boroughs, and as part of that work there will be modelling, including a detailed composition analysis, of EPR and DRS. This will enable us to have a better understanding of future waste service requirements. Two workshops have now been held with key stakeholders to discuss the proposed aims and objectives for the new NLJWS as a group. The NLJWS will inform how NLWA manages its operations and shapes policy – from initiatives to increase recycling, to reducing residual waste and carbon emissions. It will provide clear direction to enable NLWA to deliver excellent services for North London residents. The strategy is due for completion by 2025. | On track/Part complete | - The writing of the new North London Joint Waste Strategy began in early 2023, led by NLWA in collaboration with the north London boroughs. A public listening exercise was undertaken in summer 2023 to understand north London residents’ priorities, which has fed into the drafting of the strategy. - NLWA commissioned a waste composition analysis for all boroughs, which was completed across 2022 and 2023 and has been used to inform the strategy. - It is currently still in the drafting process, with the draft strategy expected to go to public consultation in summer 2024, and the final strategy expected to be adopted in 2025. - As part of the strategy development, a Strategic Environmental Assessment and Equality Impact Assessment are being produced and will go out for consultation alongside the draft strategy. | This will be better understood once the strategy has been developed further. |
| HGY 24 | Adoption of NLWP | Adoption of the NLWP will help the Council to manage waste in line with objectives to reduce, reuse and recycle which contribute to a cleaner, greener Borough, and to drive growth and employment through directing new waste facilities to appropriate employment locations. In particular it contributes to Haringey’s Borough Plan outcome 10 – A cleaner, accessible and attractive place through promoting the waste hierarchy of minimising waste and recycling and reducing the amount sent to landfill and will safeguard existing waste sites. Reference Briefing for: (haringey.gov.uk) | Complete | - The NLWP was adopted by Haringey in July 2022 and the Boroughs have agreed to monitor the NLWP annually through a lead borough agreement. Monitoring indicators include waste arisings, management capacity, location of new facilities and imports/exports. - Documents and monitoring reports relating to the NLWP are available at North London Waste Plan (nlwp.net) | N/A |
| HGY 25 | NLWA transfer stations and bulky waste recycling facility | A temporary bulky waste facility (TBWF) which became operational in April 2022 has allowed us to transfer organic and recyclable materials for processing and extract some for recovery and reuse. Resource Recovery Facility - The sorting station at Wembley (Seneca) is currently in operation with a throughput of 10,000 tonnes per annum. Approximately 30% of these materials are recovered for recycling and reuse. - The NLWA’s new state of the art Resource Recovery Facility (RRF) at the Edmonton Eco Park is planned to open in the late summer 2023, with a proposed sorting solution for pre-treatment / separation for certain waste streams within the building. This mechanical and automated application will process between 30,000 and 65,000 tonnes of residual waste, and we expect to recover 30% of materials for reuse and recycling and will be operational in 2024. The NLWA are continuing to engage with consultants to deliver the best technical solution based on the preliminary findings of a recent waste composition analyses undertaken by the authority in addition to considering the future legislative requirements. | On track/Part complete | - In 2023/24, the construction of the Resource and Recovery Facility (RRF) at the Edmonton EcoPark continued. The site went into operation on 15th March 2024 and will begin accepting borough waste from April 2024. - The RRF, which has capacity to manage 374,000 tonnes of waste annually, is designed to bulk recycling and organic waste for onward transport to processors, extract recyclables from residual waste and prepare bulky waste for energy recovery. - Space has been allocated to the new RRF to support recycling and reduce waste. In 2023/24, NLWA engaged with consultants to review best practice in the UK, culminating in two reports exploring the feasibility of installing pre-sort technology in the RRF. Following the outcomes of the reports and decisions taken by a working group developed to support this work, NLWA plans to conduct further research into technological innovations for managing waste to understand the best use for this space. | - All activities will contribute to the targets in the dashboard. |
| HGY26 | NLWA Contractor MRF | NLWA are working with Biffa (its material recycling provider) to establish a compliant and sustainable UK partner to recycle all types of grades of plastic films. They are working with Biffa to evaluate markets options and find a viable solution. |  | - There is no update on this. | - N/A |