London Borough of Bromley RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| LBB #1 | Maintain virtually 'zero waste' to landfill, 2%. | - Continue to work with contractor through regular contract meetings to ensure that Waste Disposal contractual targets of 2% to landfill are achieved for the remaining contract term and where possible exceeded. - Non-recyclable refuse to be diverted to Kemsley Energy Recovery Facility, Southeast London Combined Heat and Power facility and Refuse Derived Fuel facilities in Greenwich and Kent. | On track | - 0% of non-recyclable refuse was sent to landfill in 2023/24 - Majority of non-recyclable refuse sent to EfW facilities in London and south east England and to RDF | - Indicative recycling rate for 2023/24 51% |
| LBB #2 | Championing food waste reduction initiatives | - Work in partnership with our Service Provider to promote food waste minimisation through a digital programmatic campaign and other communication channels aimed at engagement to reduce amount of food waste disposed of per household - Organise food prevention workshops in person at community events and virtually. - Explore partnership and local promotion of Olio, Kitche & the 'Too Good To Go' apps in the borough | Delayed | - Campaign delayed due to other service priorities. - Food waste minimisation promoted at roadshows held on Bromley High Street, 3 held during April-June 2023 - Further roadshows, with information and advice on food waste minimisation, will be held May-July 2024 - Further roadshows, with information and advice on food waste minimisation, held Sept-Oct 2024 - Focus on improving webpage content with a waste minimisation page- go live January 2025 - Explore partnerships 2024/25 | - 3 roadshows April-June 2023 - 3 roadshows May-July 2024 |
| LBB #3 | Support Home Composting | - Continue to work with Get Composting to offer discounts to residents that wish to take up composting at home. - Review and adapt the information provided through our website to promote the home composting scheme and provide advice on how to home compost. - Encourage residents to join the home composting scheme through Environment Matters newsletter and outdoor advertising. | On track | - Contract with Get Composting was renewed in October 2023 with the offer of half price compost bins - Web site updated in October 2023 with signposting to Recycle Now and Gardeners World for advice on how to compost at home - Home composting offer promoted in Environment Matters | - 18 householders have taken up the offer and purchased compost bins - Ongoing |
| LBB #4 | Continue to explore options to restrict non-recyclable refuse capacity for households | As part of the Council’s Transformation Programme, options to restrict non-recyclable refuse capacity will continue to be reviewed during 2023/24. | Part complete | - The restriction of non-recyclable refuse capacity for kerbside properties was reviewed in 2023/24 with options considered but no further action taken. - A further appraisal of the options will be carried out by 2027 to coincide with the next phase of the Veolia contract (8 years plus 8 years) | - If implemented, reduction in non-recyclable refuse per household and potential increase in recycling |
| LBB #5 | Reduce plastic consumption | - Work with BID managers, local businesses with the aim of creating single-use plastic free areas/zones. - Environment officers to provide training to council staff who regularly engage with local businesses and BIDs e.g., environmental health, trading standards etc to raise awareness of Refill London scheme membership, including providing communications materials - Promote a cultural change at the Council's offices and buildings to lead through setting an example. - Plastics reduction campaign | Part complete | - Action due, in the main, April 2025 - All vending machines have been removed from the council offices - Catering at meetings utilise crockery and cutlery, no single-use plastics used - A number of businesses in Bromley are signed up to the Refill scheme - Plastic reduction campaign- delayed, due April 2025 - Engagement with BID managers and local businesses to create plastic-free zone- April 2025 - The team will work with Carbon Management and Facilities Management to ensure the new Civic Centre has a full office recycling service and look at other waste reduction initiatives- March 2025 | - Refill scheme – April 2025 - Plastic-free Council – April 2025 - Plastic reduction campaign – April 2024 |
| LBB #6 | Support and Promote Bromley Town Centre Library of Things and Reuse/ Repair workshops | - Promotion of Library of Things through the Councils communication channels - Work in Partnership with Library of Things or other organisations to deliver and promote reuse/ repair workshops. | Part complete | - Library of Things was promoted via the council’s social media platforms August to December 2023 (2 posts per month) - Promoted in July and December 2023 editions of Environment Matters - Reuse/repair workshops were delivered independently by Greener & Cleaner (local sustainability charity) | - Target met with 10 posts on social media platforms, featured in council printed publication. - Greener & Cleaner hold regular textile mending clinics |
| LBB #7 | Encourage waste reduction, reuse and repair | - Partner an organisation to deliver some alternative wrapping ideas in preparation for festive periods, with an aim of reducing wrapping paper that cannot be recycled through our current recycling schemes e.g., glittery paper. - Partner an organisation to deliver some reuse and repair workshops, this could be Library of Things. - Promote sustainable lifestyle and purchasing through events, social media and promotion of sites such as The Mindful Shopper. - Support national and regional campaigns | Delayed | - Due to lack of resource, both officer time and budget, the delivery of workshops has not been completed and this part of the action cancelled. - The website is currently being reviewed and will include pages promoting sustainable lifestyle choices. Website update- March 2025 - Review promotion of relevant sites via council communications channels, including community JCDecaux boards and vehicle sides- March 2025 | - Workshops not held during 2023/4 |
| LBB #8 | Use of Sustainable Procurement Policy within all Council Procurement Exercises | - Work towards gaining Council adoption of the Sustainable Procurement Policy - Promote the sustainable procurement policy to all Council Officers involved in procurement and contracts - Ensure that the Sustainability section of all committee reports related to decisions on procurement is fully considered. | Completed | - Sustainable Procurement Policy in place. - ‘Efficient use of resources by minimising waste’ forms part of Social value outcomes | - Sustainable Procurement Policy supports overarching procurement strategy of LBB. Officers must consider sustainable procurement, specifically the environment, social and economic implications of their purchasing decision |
| LBB#9 | Improving recycling and reducing contamination at flats and estates through implementing various interventions | - Using three blocks of flats as a pilot, use interventions guided by the ReLondon Flats Recycling Package to drive up recycling and reduce contamination. This will include carrying out improvements to signage and working with managing agents on communications. - Following the pilot, review the campaign and identify the next steps to further expanding the recycling campaign to other blocks of flats within Bromley. | Completed | - Interventions completed on 3 blocks of flats in 2023/24. - Flats recycling communication materials were refreshed. A webinar for housing providers was developed to promote the materials and to discuss the interventions as per the ReLondon Flats Recycling Package. The major housing providers in the borough were all invited to attend. Unfortunately, no provider signed up. Through this process, all the major housing providers were contacted and made aware of the updated communication materials and can contact the team for copies. Actions to be carried out 2024/25: - Review webpage to include dedicated page for communal collections with communications assets readily available to housing providers - Review communal collections contamination process- July 2024 - Create contamination specific communications for flatted properties- December 2024 - Work with one estate and introduce interventions and campaign to improve recycling, reduce contamination and reduce amount of fly tipping- March 2025 | - Action completed with estates interventions in place by September 2023 - Contamination levels in the paper & card and mixed container bins reduced in all 3 blocks by an average of 10% (visual) - Development and expansion of flats recycling communication materials to share with housing providers -April 2024 |
| LBB #10 | Make recycling easier for footway properties and blocks of flats with limited provision. | - Following the results of the footway recycling pilot that took place in 2020/21, partner service provider to review options around the provision of recycling to 1,500 footway properties and any blocks of flats that do not have sufficient capacity for recycling - Implement solutions where this is viable financially and environmentally to support residents in footway properties and blocks of flats to recycle. - Engage with managing agents, housing associations, residents’ associations and residents living in blocks of flats about any expansion of recycling facilities on a block-by-block basis. - Consider providing a supplementary recycling collection service (textiles, small electrical items, and batteries) for blocks of flats | No progress to date | - Action due in 2024/25 - The results of the ReLondon trial will be reviewed once published. Any suitable and appropriate recommendations to providing the service to flats above shops will be implemented | - Recycling options review – April 2025 - Solution implementation – March 2026 - Supplementary recycling – September 2025 |
| LBB #11 | Increased participation in green garden waste collection service | - Annual communications plan to include promotion of the garden waste scheme through promotional post cards, adverts, digital marketing, and outdoor advertising - Continue to send targeted letters to be sent to potential customers to encourage participation in the scheme each spring. - Expand on the 2022 programmatic marketing campaign in 2023 | Completed | - During March and April 2024 11,430 letters were sent to residents, targeting properties that were: detached, or semi-detached, in roads with a sign up rate of over 35%, and that were not contacted in 2022 and 2023 - A paid advertising campaign ran for 6 weeks during April and May mainly through social media platforms - The garden waste collection service was also advertised on JCDecaux boards, adverts in the councils publication (x 2), a leaflet with the council tax letter, and is promoted via recycling roadshows | - 1,387 new customers signed up during the campaign period - 4,876 clicks from digital campaign - The current number of subscribers is 47,178. In June 2023 it was 45,228, an increase of 1,950 |
| LBB #12 | Expansion of commercial waste service to offer dry mixed recycling and food waste collections | - Expand Bromley’s Commercial waste service offer to include dry mixed recycling and food waste services by working with Service Provider to review options to enable this. - Targeted communications to businesses, Bromley Charter Market, and local BIDs in three months prior to introduction of services - Roll-out of expanded recycling service to local schools | Delayed | - Options to enable the expansion the commercial waste offer to include recycling and food waste was reviewed during 2023/24. The current recycling and food waste collection services/rounds are unable to accommodate a significant increase in collections and tonnages. It has, therefore, been decided that a commercial waste recycling service will be sub-contracted out to Veolia’s C&I division - A new recycling sales officer has been recruited, to start in October 2024 - Service offering (to potential customers) and communications developed- December 2024 - Service to be rolled out- February 2025 | N/A |
| LBB #13 | Maintain and increase participation in recycling services and quality of recycling through promotion | - Encourage residents to recycle through articles in the twice-yearly newsletter (Environment Matters), e-newsletter, website, social media, and outdoor advertising. This will be included in the annual communications plan - Continue to implement the contamination process for kerbside properties and look to expand this to blocks of flats. - Conduct specific and timely recycling campaigns e.g., promotion of service changes to enable the Resource and Waste Strategy proposals to be implemented. - Continue to work with schools in the delivery of the ‘Recycling Heroes’ programme. The programme aims to empower primary school pupils to recycle more and waste less | Complete | - Environment Matters continued to be delivered to all households in the Bromley twice per year in 2023/24 - 1,177 1st contamination letters sent out, only 182 follow on letters were required - 9 Recycling Heroes sessions delivered in 7 schools, engaging with 450 pupils - 1,600 kerbside properties were targeted in July 2023, to promote the recycling services. All properties received a service leaflet and 277 households were engaged with directly. 52 extra recycling and food waste containers were delivered. The tonnage collected in the area increased slightly by 2% (compared to same period last year) - 3 roadshows April-June 2023, promoting food waste minimisation and recycling Actions to be carried out in 2024/25 - 3 roadshows held during May-July 2024 with further roadshows in Sept-Oct 2024 - Continuation of the Recycling Heroes programme within schools, engaging with at least 4 schools - Engagement with scout and beaver groups to carry out workshops and RRC visits - Environment Matters published three times a year - Improving reporting consistency for contamination in kerbside collections through crew training, feedback and reviewing on board reporting system | - Indicative recycling rate for 2023/24 51% - Improved reporting of contamination and therefore improvement in quality of recycling - At least 4 schools engaged with - Increased awareness of the recycling services and waste minimsation |
| LBB #14 | Expand the range of materials and amount of material that can be accepted for recycling | - Continue to work with service provider to increase the types of materials that can be accepted within our collection services; for example, investigate options for recycling plastic film as the capacity for this type of recycling increases - Consider pan-London doorstep textiles collections as an alternative method of providing textiles collections whilst enhancing the capacity to collect other supplementary recycling materials i.e., batteries and small electrical items | No progress to date | - Bromley currently provide a supplementary kerbside collection service for textiles, small WEEE and batteries. - End markets for plastic film remain poor and the MRF is unable to accept this material. Bromley will work with the service provider to implement collections as per Simpler Recycling regulations | - Ongoing |
| LBB #15 | Increase capacity for dry recycling | - Continue to explore options to increase recycling capacity for paper and card, and glass, cans, and plastic. - Ensure that communication materials include the promotion of the option to order additional recycling boxes to enable a household to recycle more. | On track | - Action due April 2025 - Link to order recycling containers a ‘top task’ on recycling, rubbish and waste pages of website and prominent on wasteworks (platform for residents to check collection days and report missed collections) - As part of the Council’s Transformation plan, a full service review will take place which will identify recommendations for improvements in service delivery methodologies and to ensure we maximise income and reduce costs associated with the management of the flow of waste. This will include options to increase recycling capacity. | - Options Appraisal – April 2025 |
| LBB #16 | Promotion and implementation of updated policy on waste and recycling storage | - Internal promotion of the updated policy on waste and recycling storage - External promotion of the updated policy on waste and recycling storage | On track | - Updated policy on waste and recycling storage in draft form - Liaising with service provider and reviewing offering to new purpose built blocks of flats | - 100% new build properties meeting waste and recycling storage guidelines – December 2025 |
| LBB #17 | Encourage recycling in the Council’s Parks and Green Spaces | - Pilot recycling infrastructure in Queens Gardens in conjunction with our Parks Service Provider. - Deliver a campaign to encourage recycling in Queens Gardens and to reduce littering. - If the pilot is successful, consider introduction of recycling at other parks and open spaces within Bromley | Cancelled | - Project was reviewed and, due to the cost of bins, sacks, promotional campaign, it was deemed unviable and not provide any financial benefit to the council. - Recycling from on-the-go litter bins can be of poor quality - DRS is due to be implemented October 2027 which will, hopefully, see a reduction in drinks containers within litter bins. Investing in litter bins for recycling at this stage would not be cost effective and bins would either be made redundant or require modification and relabelling as target materials change. | N/A |
| LBB #18 | Support Bromley Charter Market in recycling more and minimising waste | - Introduce a voluntary sustainability market ‘pledge’ for all market traders to encourage traders to make their businesses more circular. - Work with market traders and waste service provider to explore options for a recycling service for the market | Delayed | - Expansion of commercial waste recycling service delayed. Expected date for roll out- February 2025 - Communications developed- December 2024 - Engagement with Market- December 2024- March 2025 | - N/A |
| LBB #19 | Explore options to increase recycling and re-use of bulky items collected from households | - Work in partnership with service provider to identify whether there are any options available to increase reuse and recycling of bulky items. - Establish partnership with local re-use charity to provide good quality items collected via council ‘bulky’ collections for onward reuse. | No progress to date | - Storage space, to enable reuse of bulky items, has not been identified at either RRC. - As the depot infrastructure works progress, this action will become difficult to achieve. The works at the waste transfer station (#21) will require the closure of one RRC to accommodate displaced waste from collections and to ensure services are maintained. The works will place pressure on operations, and any additional services are unlikely to be implemented until the works are complete. - Establishing a partnership with a local re-use charity still to be explored. Charities that accept furniture are promoted on our webpages. How LBB can support and promote these charities further will be explored - September 2025 | - N/A |
| LBB #20 | Expand the range of materials that can be accepted for recycling at the RRC, and explore Virtual Reuse shop | - Work with service provider to increase the types of materials that can be accepted at the RRC e.g., rigid plastics and PVC - Assess feasibility of a virtual Reuse shop with third sector partner to sell good quality items deposited at site which are suitable for reuse, such as bicycles, sofas, bric-a-brac, clothing etc. | Part complete/ongoing | - Paint re-use scheme introduced July 2024 - Vape recycling bins installed August 2023 - Continue to work with service provider and investigate outlets for rigid plastics and PVC- March 2025 - Feasibility of virtual Reuse shop still to be actioned. As described in action #19, the upcoming works to the waste transfer stations will place pressure on operations, and any additional services are unlikely to be implemented until the works are complete | - Combined recycling rate at the RRCs for 2023/24 55% |
| LBB #21 | Maintain and invest in the Council’s two Waste Transfer Stations through a Depot Improvement Programme | - Improve the drainage and repair hard standing at the Waste Transfer Station to ensure that in meets the standards that are required by the Environment Agency for this site. - Manage the capital works with minimum service disruption and an aim of continuing to maintain the same level of recycling at the site. - Consider further alterations to the design of the Household Reuse and Recycling Centre to assist residents and businesses to maximise recycling and reuse. - Maintain local waste sites in accordance with the South East London Waste Planning Group technical paper. | Delayed | - Procurement for the capital works programme delayed. Contract award- September 2024. Works to commence January 2025 - Localised drainage repair work and re-surfacing completed March 2024 | - Action delayed - Combined recycling rate at the RRCs for 2023/24 55% |
| LBB #22 | Deliver the Council’s target to have net zero carbon emissions by 2027. | Work with Carbon Management colleagues to plan and implement measures in the waste and street services that will enable the Council to meet its net zero carbon emissions target | No progress to date | - The waste services fleet does not contribute to the Council’s net zero carbon emissions target - The team will work with Carbon Management and Facilities Management to ensure the new Civic Centre has a full office recycling service- March 2025 | - Ongoing |
| LBB #23 | Transition towards to a more sustainable waste collection fleet | - When installing new advertisement panels on RCV fleet, ReActivair Coating is used to help cleanse the air of VOC’s and Nox - Continue to ensure that all waste vehicles are compliant with current standards as a minimum and maintain 6 electric supervisor vehicles. - Work with partners including current service providers to increase the number of electric vehicles within the waste and street cleaning fleet. - Work with parks service provider to consider sustainable options for the parks fleet that are responsible for collecting litter in parks. - Assess the infrastructure requirements for a fully electric fleet. - Explore options such as hydrogen for waste site plant and larger vehicles. | On track/part complete | - 100% of waste and street cleaning fleet meet Euro VI standards and FORS. - 2 electric vehicles within Highways Division, 2 hybrid Mayoral Cars - Charging points installed at Central Depot and (old) Civic Centre. Plan prepared for charging points at new Civic Offices - Electric vans for service provider’s Environmental Managers in use - As part of a pilot towards operating a fleet of waste collection eRCVs, the joint procurement of 1 eRCV with service provider is progressing. | - Contributing towards the Mayor’s zero carbon city 2030 target |