- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/25 | Actual performance 2023/24 |
| --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 216.7 | 212.7 | 249.29 |
| Total annual household residual waste collected per household (kgs/household) | 395.7 | 388 | 344.82 |
| Total annual household avoidable (edible) food waste (kgs/head) | 77 | 74 | 77 |
| Annual household waste recycling rate (% by weight) | 25.9% | 35% | 29.1% |
| Annual LACW recycling rate (% by weight) | 21.5% | 26% | 23.4% |
| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/25 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | 100% | 100% |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 100% | 100% | 100% | 100% |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 50% | 100% where practicable | 50% | 100% |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | TBC | 0% | 100% |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 89% | 100% | 100% | 100% |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% |

- 2024/25 RRP Action update:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| Camden #01 | Drive waste reduction and reuse across Camden | - Develop and deliver comprehensive annual communications strategy to include: - Ongoing promotion via website, social media, Recycling Rewards and Veolia newsletters - Subsidised home composting bins - Real Nappies for London voucher scheme - Furniture collection for reusable items - Repair and reuse events - Targeted communications - Deliver Future Neighbourhoods project, Phase 1 & 2, in Somers Town to develop: - Circular economy market stalls - Community larder - Upskilling residents to repair/ reuse - Food redistribution - Support provision of and promote Kentish Town Library of Things and seek to introduce an additional Library of Things in the Borough - Increase Camden school staff and pupil knowledge on waste minimisation through communications and 2 outreach events per month. - Provide 3 Waste Electric and Electronic Equipment (WEEE) repair workshops per annum - Develop local repair community group partnerships - Support delivery of Veolia Camden’s Sustainability Fund, which provides not-for-profit organisations and community groups funding for waste reduction, reuse and other environmental improvement projects. Estimated 6 projects supported per annum. | - Complete - Complete - Complete - Complete - Complete - Complete | - 2024/25 Annual communications plan developed with key aims: increase recycling/ reduce contamination, improve street cleanliness/ reduce fly-tipping, raise awareness of waste minimisation and moving towards a circular economy, with the following key work delivered: - Provision of 51 subsidised compost bins - Promotion of Real Nappies voucher scheme via paid for online advert. - 89 vouchers issued with 53 redeemed - Promotion of partner furniture collection services - c.108k service leaflets distributed to households across Borough. 106 social media posts, 3 local newspaper features - Targeted campaigns covered in actions #03, #05, #06, #07, #09, #12 - Targeted kerbside contamination project - Estates recycling: Continued testing of ReLondon toolkit interventions - Targeted fly Tip Action Plan and comms campaign. - Targeted food waste project (on low performing round) - WEEE repair and recycling – ongoing partnership events and comms - Waste reduction – ongoing outreach events and comms. - 2025/26: Communications plan to include: - Updating contamination procedure based on auto-contamination process - Further work on estates recycling using the ReLondon toolkit and learnings from Phase 1 - Continue Phase 7 of the fly tip action plan - Develop and deliver Phase 4 of the food waste participation project - Ongoing partnership with the Camden Fixing Factory for events and communications - Ongoing outreach and community events to promote waste reduction - Future Neighbourhoods Phase 2 concluded on 31 March 2024. Future Neighbourhoods final phase delivered in 2024/25, with continued focus and support of Phase 2 projects. - Ongoing partnership with community leads on waste reduction initiatives such as Lifeafterhummus clothes swap rails and community surplus food café at 5 Pancras Square (see Action #09) - Camden supported delivery of the Kentish Town and Kilburn Library of Things (LoT) through promotion and partnership. 4,571 residents were signed up to LoT newsletters by 31 March 2025, an increase of 40% from the previous year. - See Action #08. - 6 x repair events (2 for Repair Week 2025) - Ongoing partnership developed with Veolia, Camden Fixing Factory and Think & Do (community organisation) - 2025/26: Target – hold 3 events by 31 March 2026 - 9 community projects supported through Sustainability Fund in 2024/25 - 2025/26: Sustainability Fund 25/26 target – support 6 community projects, for delivery by 31 March 2026, with up to £1,000 per project | - Raised awareness to increase participation in services - Potential to divert 8.85 tonnes organic waste from disposal per annum (WRAP) - Estimated 5,954kg CO2eq and 29.8 tonnes saved from avoiding use of disposable nappies. - Raised awareness to increase participation in services. - Increased local awareness and participation in circular economy activity - 2,308 items borrowed in 2024/25. - Increased attendees and items repaired from last year: 158 attendees with 46 items repaired - Funding provided for following projects in 25/26: - Likewise Community well-being - Laptops for refugees - Creating a greener community at AIC - Communitrees - Re-craft Workshop - Sidney Boyd recycling project - Donkeys at Parliament Hill School - Cinema viewing of Wilding - St Paul’s garden restoration |  |
| Camden #02 | Minimise single-use plastic and other items in Camden | Own estate (Camden office buildings): - Carry out review, post covid, of single-use items used in council buildings, replacing with reusable alternatives. - Conduct an internal waste composition audit. - Develop a communications campaign encouraging staff to reuse, e.g., coffee cups, and participate in local schemes such as CLUBZERO, which provides reusable food/ beverage containers for participating outlets in King’s Cross. Residents: - Support existing and develop new local campaigns encouraging residents to refuse single use items. - Continue to deliver Refill Station Camden market stall, seeking opportunities to expand product range and outlets. - Promote Refill London scheme to increase participation by businesses, enabling residents, workers and visitors to use refillable water, coffee and food containers, and do plastic-free shopping. - Encourage reuse at Camden’s street markets Schools: - Continue work with schools and school caterers to minimise single-use plastic - Support ‘Know Your Onions’ schools food growing scheme. Business: - Work with partners (Camden Climate Change Alliance and Veolia) to promote reduction of single use items to member businesses. - Work with NLWA (North London Waste Authority) to continue to delivery of the West Hampstead Low Plastic Zone and scope out potential for expansion | - Complete - Complete - On track - Complete - Complete - Complete - Complete - Complete - Complete - Complete - Complete | - Action completed. Majority of buildings no longer have single-use items. Where single-use cups are still occasionally required (e.g. training centres), recyclable or compostable are used. - Waste composition analysis completed Summer 2024. Results are feeding into staff waste reduction campaign, due for 2026. - Internal communications campaign will be developed encouraging staff to reduce waste through reuse and maximise recycling. - Camden has also worked with One World Living to develop a Work with London Councils to develop a Single-Use Plastics Pledge to encourage minimisation of single use plastic, due for launch Summer 2025 - Partnership events with local groups such as Think&Do held to promote waste minimisation and other sustainable behaviours including a Plastic Free July resident workshop - Through support from Refill Station Camden, refill options are now located in Queen’s Crescent Market (delivered by Fair-Well) and in Chalton Street (Flori Canto), which featured in NLWA ‘Bring It’ communications campaign. Refill Station Camden will therefore conclude in 2025. - Refill London promoted ongoing via Camden website and channels. - Partnering with Raze, launched reusable bag incentive scheme which includes QR code to collect points each time Raze bag is used at participating markets stalls. Points can be used to spend with popular brands. - Schools are encouraged to sign the Camden Schools Charter via the Camden Climate Change Alliance (CCCA), which contains 10 commitments covering a range of sustainability topics including single use plastics, waste, food sustainable procurement and circular economy. - In partnership with School Food Matters, facilitated provision of a stall enabling pupils to sell school grown food on a Camden street market. - Through website and newsletters, Camden Climate Change Alliance (CCCA) showcased member collaborations to its 526 members on a wide range of sustainability initiatives throughout the year. CCCA initiatives delivered include: - CCCA Climate Connectors programme, supporting circular economy by matching businesses to local community groups and schools to mobilise local climate action - CCCA Green Dragon’s Den initiative, working with local business to fund schools projects to reduce waste - Developed into new ‘Bring It’ campaign (see Action #04) | - Single-use plastic use minimised across own estate. - Audit will establish a baseline and determine focus of communications campaign. - Increase staff awareness and participation to minimise waste, maximise reuse and recycling. - 38 events held in 2024/25 engaging with 845 residents engaged. 2 Plastic Free July events held with 40 participants. - Raise awareness of waste minimisation, reuse, circular economy to local shoppers. - Raise awareness to encourage reuse. - 5,000 bags distributed to market traders - 23 schools signed Camden Schools Charter - Stall held at Inverness Street Market in July 2024 - Includes upcycling initiative at a local secondary school, building planter beds on the school grounds from old hose bins from a construction company. - Includes £400 grant donated by Camden-based Troup Bywaters & Anders and Sheppard Robson & Anthesis to support a clothes swap event at a primary school. |  |
| Camden #03 | Reduce fly-tipping across the Borough | - Deliver targeted fly-tip reduction campaign, focussing on hotspot areas on a ward-by-ward basis, aligning messaging with other local projects e.g. enforcement, beautification interventions and waste reduction/ reuse. 3 areas per annum (reduced to 1 area in 2024/ 25 as the aligning ‘No More Rubbish Excuses’ fly-tipping comms campaign also targeted hot spot areas) - Increase awareness of the right thing to do with waste, and the fines associated with fly-tipping through ongoing communications campaign via website and social media. - Refresh Camden’s Love Clean Streets (LCS) app campaign promotion. - Evaluate 2022-23 fly-tip ‘beautification’ project, where interventions such as planters are installed to design-out fly-tipping. Scope out potential to expand to other hotspot areas. | - On track - Complete - Complete - Complete | - The seventh targeted fly tip reduction plan was developed based on the learnings of the previous phase and delivered in Kentish Town North between February 2025-April 2025 using assets from the ‘No More Rubbish Excuses’ campaign. Interventions and monitoring will continue into April and May 2025. - 2,018 leaflets distributed - 30 signs/stickers installed - 2025/26: The Fly-Tip Action Plan will continue to target hotspot areas, reduced to 1 area in 2024/25 as aligned with the ‘No More Rubbish Excuses’ fly-tipping comms campaign targeting fly-tipping, littering and anti-social behaviour. - Ongoing promotion and improvements made to Love Clean Streets app to enhance user experience. - Evaluation report completed in May 2023 for the 7 beautification sites. - 2025/26: Beautification projects being introduced in hotspot areas | - 76 residents engaged via door knocking - Unique users increased to 5,502 in 2024/25. - Reduced fly-tipping and increase in unwanted items being correctly disposed of |  |
| Camden #04 | Work in partnership with NLWA to deliver the North London Residual Waste Reduction Plan 2022-25 | Partnership projects proposed in Plan: - Participate in pan-London food waste campaign. - Low Plastic Zones: Business engagement will continue in existing and new zones - Waste minimisation education: - Deliver the Waste Prevention Community Fund with total fund of £120k, available for not-for-profit organisations for projects that support waste prevention in North London - Deliver repair and upcycling events. - Deliver annual Waste Prevention Exchange conference for sector experts, covering topical waste prevention issues. - Advertising campaign to raise awareness of and increase attendance at reuse and recycling centres. | - Complete - Complete - Complete | - Eat Like a Londoner campaign launched 2023 (across 7 boroughs) - 3.1 million social media impressions/ 90,000 video views - 9254 click throughs to the website - 5 behaviour change workshops across 4 boroughs (including Camden) - Developed into ‘Bring It’ behaviour change campaign, which launched in 2024 encouraging residents to use reusable coffee cups, bottles, bags and containers to reduce single-use plastic. Over 9.3 million impressions, reaching over 4.1 million residents and resulting in over 53,500 landing page views. Out of home advertising targeted residents when visiting the high streets, where 350 local businesses had signed up to the campaign. The Flori Canto shop refill wall, located in Camden, was featured in the communications campaign. - 3 projects funded in Camden to raise awareness of waste prevention, which delivered 45 recycled art sessions with 54 unique attendances. - 17 community repair events were delivered. 2 specialised textile events were held and 1 Restart Party focused on electricals. - Other partnership campaigns delivered 2024/25 include: - Eat Like a Londoner (waste less food): Social media received 3.1 million impressions, 90,000 video views, 9254 website visitors. 5 workshops held across 4 boroughs (including Camden) - Reusable period products campaign, with 42 events held across 7 North London boroughs engaging 1,800 members of the public - ‘Bring it…’ behaviour change campaign to encourage reuse of coffee cups, bottles, bags and containers. Social media had 9.3 million impressions with 53,500 website views. 350 local businesses across 7 boroughs signed up to campaign. - In The Know schools outreach programme on waste prevention and circular economy - Education Hub (range of waste prevention interventions tested) | - Evaluation of the campaign demonstrated that 60% of respondents have reported to take action as a result of the campaign (waste less food/ eat more plant based) - Support reduction of residual waste and consumption-based carbon emissions - Analysis of the campaign highlighted high levels of engagement in 6 out of 7 reuse behaviours - Increased awareness and participation in waste reduction. 100% attendees said the project has helped them reduce their waste at home. - Food waste reduction: 60% of target audience surveyed reported to have take action to reduce food waste - Waste reduction: 96% of participants would recommend reusable products to friends and family - Waste reduction, particularly of single-use plastic - Engaged with 1 Camden primary school |  |
| Camden #05 | Increase recycling and reduce contamination from kerbside properties | - Tackle contamination by developing automated kerbside contamination communications that informs residents why their bin has not been collected and how to rectify the issue. - Residents will be educated on what materials can be recycled in Camden, with repeat contaminators written to with increasing severity, culminating in a site visit - Veolia to deliver crew contamination toolbox talks with the aim of improving reporting and tagging of contaminated recycling - Promote garden waste and bulky waste services via annual leaflet, Recycling Rewards newsletter, website and social media comms | - On track - On track - Complete - Complete | - Delays to automation process but currently in development for 2025/26. - Focussed outreach carried out to reduce contamination, targeting high prevalence streets with letters, bin stickers and door knocking with 4 targeted intervention activities carried out across the year: - 2025/26: Targeted campaigns will continue, building on learning from long-term evaluation - Toolbox talks carried out with crews. - Garden waste and bulky waste services promoted in annual service leaflet and educational letters to residents as well as on the website. - Service rounds reviewed and changes to collection days proposed which will result in increased efficiency of rounds and reduced emissions. Changes introduced in April 2025 | - Reduction in kerbside contamination - 468 letters delivered, 42 households engaged with directly at doorstep. Resulted in 40% reduction in contamination - 2795 subscribers as of 31 March 2025 - Reduced vehicle emissions from increased efficiency of rounds |  |
| Camden #06 | Increase recycling and reduce contamination from communal estate properties | - General promotion of services to estate households - Trial use of bin weighing data to target low performing estates for recycling and contamination. - Develop an estate leader board hosted on the Camden website for residents to compare their recycling performance against other estates, linking in with Recycling Rewards scheme. - Conduct residual/ recycling capacity audit by Summer 2024 - Develop targeted communications for lower performing estates. - Expand the resident contamination feedback process trialled during 2021-22 - Incorporate measures recommended in ReLondon Flats Recycling Package where appropriate - Conduct periodical estate waste facility audits to ensure container provision is optimised - Deliver collection crew contamination toolbox talks with the aim of improving reporting and tagging of contaminated recycling | - Complete - Cancelled - Complete - Complete - Complete - Complete - Complete - Complete | - Service leaflet promoting recycling and rubbish services provided to all estate households annually, alongside social media, EcoPoints scheme and Housing newsletter. - Weighing resource is currently limited and is being prioritised for specific services, therefore this action has been replaced with other actions to improve estates recycling, outlined below. - Review of facilities is ongoing, with improvements made to recycling and waste containerisation on low performing estates, such as new containers and housing. - Targeted communications developed based on ReLondon recommended interventions. Low performing estates now targeted in ongoing periodical campaigns. Interventions installed include new containers and signage and tailored communications to encourage the use of the service. - Ongoing - Ongoing - 2025/26: - Develop service to enable food waste collection for non-participating estates | - Support increased recycling rate. - Reduced contamination, increased recycling. - Improved recycling and decreased contamination - Increased awareness/ participation, reduced contamination - Align with upcoming Simpler Recycling requirements by 31 March 2026 |  |
| Camden #07 | Increase recycling and enhance service provision for flats above shops | - Develop communications for flats above shops residents, to increase participation in recycling minimise contamination and reduce residual waste. Delivered via annual leaflet, targeted letters and website. - Expand trial of on-street storage for waste to additional areas, expanding to 2 new areas, covering c.100 properties - Scope potential for inclusion of recycling and food waste, producing an options appraisal report by Spring 2024 | - Complete - Complete - Complete | - Flats above shops residents receive a bespoke annual leaflet highlighting services and have delivery of recycling and residual waste bags twice a year. - On-street residual waste (grit bin) storage expanded to a further 15 locations, covering around 1,150 flats above shop households. - 2025/26: Continue with rollout to appropriate sites. Develop a container cleansing programme - Recycling provision to stay as current (in clear sacks put out on-street on collection day) with further development of bespoke leaflet and communications. Proposal for food waste provision for flats above shops developed - 2025/26: Design food waste provision for flats, informed by officer knowledge best practice and recommendations from ReLondon to align with Simpler Recycling requirements. | - Leaflets and bags distributed to all c.5,000 flats above shops residents. - Positive feedback received from local councillors, crews and residents for reducing bags on street - Enhance provision for flats above shops residents and align with upcoming waste reforms |  |
| Camden #08 | Increase recycling in Camden schools | - Increase school staff and pupil knowledge on recycling through Veolia’s Sustainable Schools programme - Provide education packs for primary schools and competition for secondary schools - Deliver workshops, litter picks and waste audit sessions for schools - Support schools to consider the waste hierarchy in delivery of school services and activities through the Camden Schools Charter and Camden Climate Change Alliance - Conduct periodical reviews of school waste facilities | - Complete - Complete - Complete | - Veolia Camden: - Delivered 16 school visits and 1 MRF tour. - Delivered an ECO Leaders programme with a primary school to raise awareness locally of fly-tipping issue - Delivered Veolia Orchard programme. - 2025/26: - Veolia Orchard will open for applications in September 2025 with aim for 2 schools to be supported. - Schools are encouraged to sign the Camden Schools Charter via the Camden Climate Change Alliance (CCCA), which contains 10 commitments covering a range of sustainability topics including single use plastics, waste, food sustainable procurement and circular economy. - 2023/24 review complete. | - 761 students engaged - 4 anti-fly tipping signs designed by students installed in the local area - Provided 10 fruit trees and 70 fruit plants to 9 schools - Funding provided for compost and a greenhouse to support school growing and knowledge with students - 23 schools signed Camden Schools Charter - 58 schools visited and new contracts signed. |  |
| Camden #09 | Increase food waste recycling | Household (kerbside and communal) - Expand Food Waste Recycling Project, providing targeted messaging and caddy liners to residents on a targeted low-participation kerbside collection round. - Refresh digital campaign to encourage recycling participation and food waste minimisation. - Develop outreach work including food waste roadshows and community workshops. - Increase the number of estates collecting food waste. - Increase the number of outlets where free caddy liners can be collected by residents (budget permitting) Schools - Increase uptake of food waste collection service via officer visits and targeted communications Sustainable food - Develop an Action Plan by Summer 2023 which contributes to Camden’s Food Mission that, by 2030, everyone eats well every day with nutritious, affordable, sustainable food - Participate in ReLondon’s Circular Food Procurement Group | - Complete - On track - Complete - Complete - Complete - On track | Household (kerbside and communal) - Veolia Camden carried out Phase 3 of the Food Waste Recycling Project targeting households in a low performing round. This included doorstepping, letters and a starter pack (kitchen/ outdoor caddies, liners and ‘how to’ letter) - 2025//26: Deliver Phase 4 of the Food Waste Recycling Project, targeting a low-participation round, by March 2026 - Options for food waste collections to estates not currently participating in service, scoped out. - 2025/26: Develop proposal to align with Simpler Recycling requirements. - Caddy liners provided to residents via libraries and sports centres. Schools - Complete Sustainable Food - Food Mission Action Plan developed in 2023 with planning and delivery ongoing - Lifeafterhummus in partnership with Camden opened a community café based at the 5 Pancras Square library in February 2025. The café provides affordable nutritious meals made from surplus food collected by volunteers which is then prepared in the local community kitchen. - Collaboration with ReLondon – ongoing - Food Buying standards for Camden developed, including a section on reducing packaging and food waste - 2025/26: - Launch of ‘Challenge Prize’ in Summer 2025, providing funding for a project exploring/ offering solutions to reduce food waste from Camden businesses. - Review and refresh of Food Mission | - 21.43% increase in food waste caddy presentations - 371.4% increase in food waste tonnage on the round - 3.9% increase in caddies requested compared to Phase 2 - 176 residents engaged - Increase participation of service to increase food waste tonnage collected - Increase participation of service to increase food waste tonnage. - Raise awareness of food waste reduction whilst providing work experience opportunities for young people. - Reduction of food waste and packaging across council catering contracts (no baseline data available) |  |
| Camden #10 | Increase WEEE and bulky waste recycling | - Develop local community group partnerships to produce a range of waste reclaim and collection events for Camden residents to recycle WEEE and selected larger bulky waste items. - Develop communications campaign to raise awareness on the importance of recycling WEEE and Camden’s kerbside WEEE recycling and bulky waste collection services | - Complete - Complete | - Working with local stakeholders and Veolia Camden, 4 community skip events were held in 2024/25 offering collection of a range of recyclable items including WEEE, textiles and garden waste, plus bulky waste. - 2025/26: Deliver minimum of 4 community skip events by March 2026. - Alongside ongoing ‘Do the right thing with your waste’ communications promoting recycling services, focused communications on reducing WEEE waste provided in EcoPoints and Veolia newsletters, Annual Service Leaflet and social media, promoting Camden Fixing Factory, Fix and Do repair events and Library of Things. | - 171 attendees. WEEE collected: 126 electrical items, 8 bags of cables/ batteries, 19 bags of textiles, 10 bags mixed recycling, 44 bulky waste items and 9 bags of garden waste - See Action #01 |  |
| Camden #11 | Increase uptake of commercial waste service | - Develop new commercial communication assets to engage customers on the importance of recycling. - Expand food, glass and card recycling streams via new service product offering. - Continue data analytics to identify high-weight customers and engagement with them to introduce food recycling collections. - Review and refresh commercial contamination process to reduce contamination and better inform customers on how to recycle. - Introduce waste audits and waste training for customers and their employees | - Complete - Complete - Complete - On hold - Complete | - Welcome guide, bin posters and stickers, training packs and MRF tour slides developed. Welcome email sent as standard to all new customers and existing contracts that have amended their contract. MRF tour visits being completed for high-value customers with new staff members getting trained on hosting. Engagement events hosted at customer sites, and commercial team are participating in community events. - New food, glass and card services set up on systems with full integration between sales and operational platform. New food caddy services successfully live from March 24. New glass slim jim services, live from March 24 for select customers, will be fully rolled out in 25/26. - Monthly over-weight report produced, with subsequent visits to identified customers with collections either increased or services amended (e.g. adding food collection service). Developing systems and platform to allow for overweight charging in 25/26. - On hold due to other workstreams taking priority as the impact of commercial contamination is not significant. - Trialled with a number of customers and now BAU for any customers that request them. | - Public visibility of the commercial arm of Camden’s waste service and engagement with businesses we don’t currently work with. Providing a better-quality service to new customers, and higher engagement of existing ones - increases retention and improves partnership working. - 188 food customers in total, with 37 customers onboarded to new food caddy service. 94 glass customers in total, with 7 signed up to new slim jim service. - Slight increase in food and glass services as a result but have difficulties enforcing change by businesses without any financial impact. Expect this to grow once overweight charges for refuse are fully implemented in 25/26. - Will improve quality of recycling, reducing the risk of rejection at the MRF. Will see financial improvements due to correct disposal for waste stream. - Increased recycling rates from our high value and high-profile sites. Engagement with customers leads to higher retention. |  |
| Camden #12 | Develop and deliver communication campaigns and projects to minimise waste and increase recycling from all sectors across the Borough | - Deliver annual service leaflets to all Camden properties (FAS every 6 months with bag delivery) - Deliver seasonal communications via digital media and print - Deliver Recycling Rewards incentives scheme to residents, including monthly newsletter. - Veolia Camden to conduct annual resident satisfaction survey - Continue to collect and recycle single-use cups from Camden streets and businesses as part of the Camden Recycles Cups project. - Support ongoing regional and develop local campaigns that promote recycling in Camden | - Complete - Complete - Complete - Complete - Complete - Complete | - See #07 - Seasonal communications campaigns developed and promoted on social media, leaflets, events, newsletters and local newspapers e.g. Christmas tree recycling - Contract renewed and scheme now includes sustainable transport and other EcoPoints incentive scheme - Survey carried out every April and report provided to Camden - Separation of coffee cups from street sweeper bags on selected beats is now business as usual. - In partnership with NLWA, promoted a range of campaigns through communications channels – see Action #04 | - c.9,000 trees collected and composted via promoted collection points. - Steady increase of residents signed up to scheme, to around 16,343 by 31 March 2025. - Results feed into improving service delivery - 67 containers of cups collected in 2024/25, resulting in estimated 46,900 cups recycled. - See Action #04 |  |
| Camden #13 | Work in partnership with NLWA to reduce waste and increase recycling | NLWA Resource Recovery Facilities (RRFs) - NLWA operates a sorting facility (at Wembley) which sorts wood, mattresses, metal, cardboard and hardcore material. It is envisaged that 10,000 tonnes will be processed at the station per annum from across the 7 constituent boroughs and are recovering around 30% of materials for recycling and reuse. NLWA are investing in a residual pre-treatment facility (sorting facility) within the new RRF. This will process between 30,000 and 65,000 tonnes of residual waste and is expected to recover 30% of materials for reuse and recycling. A Temporary Bulky Waste Facility (TBWF) became operational in April 2022 which allows the transfer of organic and recyclable materials for processing and extract some for recovery and reuse. The new RRF facility is expected to come into use in Feb 2023, at which point the TBWF will no longer be required. - A new Joint Waste Strategy is currently being developed with the 7 constituent boroughs to cover the period of 2024 – 2040 | - On track - On track | - In April 2024, the Resource Recovery Facility (RRF) began welcoming borough vehicles, ramping up to full operations and enabling it to function as a modern waste management facility. In its first year of full operation, around 170,000 tonnes were processed through the facility including residual waste, bulky waste, food waste and garden waste. The expanded capacity of the RRF provides provision for north London to double its food waste collection ability, ahead of the planned compulsory food waste service for all residents across England by April 2026. - Space has been allocated to the new RRF to support recycling and reduce waste. In 2024/25, NLWA engaged consultants to conduct a review of existing mixed waste sorting operations in other countries to understand what might be possible in north London. Officers will use the findings of this report, along with knowledge of other innovations in the waste sector, to determine how best this space could be used to increase recycling and reduce the carbon impact of the residual waste stream. - The Edmonton EcoPark Reuse and Recycling Centre opened to the public in July 2024. It is the first major public facility delivered as part of the Project and allows north London residents to bring their recycling directly to the EcoPark for the first time. - EcoPark House, NLWA’s new visitor and education centre, was opened to the public and welcomed its first school visit in 2024/25. EcoPark House will provide events catering to NLWA's key target groups: schools, community groups and north London’s residents. - In 2024/25, NLWA launched a dedicated disposable vape recycling service across RRCs to promote the safe disposal of these products. - The new North London Joint Waste Strategy has been developed over the past three years, with writing beginning in early 2023. Following public consultation, constituent boroughs will approve the final draft through individual governance processes in summer 2025, which will commit each to the content of the Strategy. The NLWA will then adopt the Strategy as policy in late 2025. | - Increased recycling - The scheme captured a total of 830 kilograms of material in its first year of operation, equivalent to approximately 39,500 individual disposable vapes diverted from litter, street and kerbside bins. |  |
| Camden #14 | Work towards greening waste collection and cleansing fleet | - Scope potential to green the collection and cleansing fleet by exploring the range of alternative fuels available, in use by other boroughs and develop options for consideration. | - Complete | - 14 electric RCVs introduced for start of Environment Services Contract renewal from 1 April 2025 with remainder to transition to electric when capacity available. - 3 e-cargo bikes being introduced from 1 April 2025 to support street cleansing in targeted areas | - Improvement of localised air quality |  |
| Camden #15 | Support delivery of outcomes in Camden’s Clean Air Action Plan 2022-26 | - Encourage resident uptake of garden waste service via ongoing communications through a range of channels to reduce air quality impacts of burning garden waste - Encourage businesses to use a delivery or waste consolidation service to reduce vehicle emissions associated with business operations via the Camden Climate Change Alliance communications channels | - Complete - Complete | - Promoted to residents via annual service leaflet, social media channels. Garden waste rounds were reviewed in early 2025 and rerouted starting 1 April 2025 to improve efficiency and reduce vehicle emissions. Promoted London Wood Burning Project to raise awareness of burning garden waste - Business communications via ongoing CCCA newsletter. | - 5,641 garden waste subscribers (March 2025). - Ongoing |  |
| Camden #16 | Expand the range of materials that can be accepted for recycling at the RRC | - NLWA will continue to collect and recycle mattresses and extended polystyrene and will seek outlets for other hard to recycle items. Look to increase the scope of textiles and carpets that are accepted | - Complete | - NLWA saw a 7% increase in number of mattresses collected for recycling. - 56% increase in the amount of Expanded Polystyrene collected for recycling across all NLWA reuse and recycling centres (RRCs). - Carpet recycling launched at RRCs | - Across all NLWA boroughs, c. 8,512 mattresses recycled per month - 213 tonnes captured across all NLWA borough RRCs |  |
| Camden #17 | Develop a strategic direction/ approach toward embedding circularity | - Set up a Circular Economy Panel to determine how the circular economy is currently working in Camden and what more can be done within the Council and to support activity in the community. | - Complete | - Circular Economy Panel established. A series of meetings have been held with council officers, leading experts, key stakeholders, and engagement with residents to determine best practice and focus areas to research and develop recommendations. - 2025/26: Circular economy to be a key focus with Camden’s upcoming Climate Action Plan 2026-30 | - Support transition towards a circular economy in Camden |  |
| Camden #18 | Ensure all developments optimise resource efficiency by reducing waste and minimise materials required through planning Policy CC5: Waste | - Assess all planning applications for 10+ homes or non-domestic schemes over 1000 m2 internal floor area to ensure align with Policy CC5. Where the demolition of a building cannot be avoided, developments are expected to divert 85% of waste from landfill by reusing materials on-site or salvage appropriate materials to enable their reuse off-site. | - Complete | - All relevant applications are assessed by waste specialists, including waste operations contractor managers. Planning guidance for developers is currently being updated to include Simpler Recycling and other legislation changes. - Waste proforma by end of 2025 for use by planners and developers. - 2025/26: Update planning technical waste guidance to include new legislation changes | - Ensure all relevant applications align with Planning Policy CC5 - Enhance understanding of requirements in relation to Policy CC5 |  |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
|  |  | Note – new or ongoing actions for delivery in 2025/26 are included within ‘Action Progress update’ columns of Section 2 above. |  |  |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Camden #19 | Ensure in-scope businesses are aware of 31 March 2025 requirements | - Include flyer explaining requirements in 2025 business rates mailout - Veolia Camden to introduce new food caddy service and glass Slim Jim services (for select customers) - Engage with main private waste collector companies to ensure business compliance | Compliance with Simpler Recycling and increase in collected food waste and dry recycling tonnages | Completed February 2025 Food caddy service introduced March 20205. Slim Jim service to be rolled out over 2025/26 Meetings held in 2024, with ongoing engagement |
| Camden #20 | Review round capacity | - Monitor rounds to determine if additional resource is required | Ensure sufficient capacity to manage increase in tonnages | Ongoing |
| Camden #21 | Provide food waste collection facilities so all households can recycle food waste | - Trial on-street communal food waste collection facilities, available for flats above shops and estate residents not currently covered by a service. Develop using learning from ReLondon trials. - Expand on-street food waste collection facilities based on evaluation of trial and ReLondon report - Deliver communications campaign to encourage participation in service (aligning with Action #09) | Compliance with Simpler Recycling and increase in collected food waste tonnage Increase participation in service | Complete by Spring 2026 Expansion from April 2026 Spring 2025 |
| Camden #22 | Ensure micro-businesses are aware of 31 March 2027 requirements | - Include flyer explaining requirements in 2027 business rates mailout - Veolia Camden to deliver comms and support to ensure customer compliance | Compliance with Simpler Recycling and increase in collected food waste and dry recycling tonnages | February 2027 Spring 2027 |