- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 284.4 kgs/head | 281 kgs/head | 278.9 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 489.3 kgs/hh | 483 kgs/hh | 458.1 kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 52.6 kgs/head | 37.9 kgs/head | 46 kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70% Unavoidable food waste in residual: 30% Avoidable food waste recycled: 44% Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 23.7% | 29% | 22.8% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 22.7% | 28% | 21.1% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 0% | 2.6% | 6.8% | 96%+ | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 0% | 0.4% | 95%+ | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 98.4% | 98.6% | 98.6% | 98.6% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 0% | 0% | 90%+ | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 0% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| Wandsworth #1 | Secure supplies of HVO | Seek to source waste cooking oil locally for HVO to fuel new waste collection fleet | Complete | - Waste collection fleet transitioned in 2024 to standard HVO not sourced from local waste cooking oil as that proved impractical. | - Up to 90% reduction in net CO2eq emissions achieved; Improved local air quality |
| Wandsworth #2 | Waste service provision for the four years commencing Q1 2024/25 | Determine new service provision arrangements including borough-wide weekly food recycling collections and fortnightly garden waste collections (subject to Council decision) | Part complete | - New arrangements determined and implemented. - Weekly food recycling collections implemented for kerbside households with front gardens/driveways. - Weekly food recycling collections rolled out to c. 13.2% of flats using communal bins as at end of March 2025 with the process continuing (c. 35% of these premises covered at the time of writing in August 2025). - Suitable arrangements for weekly food waste collections for flats above shops and other households with no off-street space to store/present containers being investigated. - Garden waste collection arrangements yet to be determined. | - New fleet in operation with standard rather than split back RCVs for refuse and mixed recycling. - Average of 66 tonnes food waste recycled per week during Q4 2024/25. - Significant boost to dry recycling after launch of new fleet and kerbside weekly food collections. - 30.2% household recycling rate achieved in Q4 2024/25. |
| Wandsworth #3 | Roll out new food waste collection trial | Implement expanded Southfields food waste collection trial (+ 118 households) Implement new Bedford Hill/Balham food waste collection trial (+c. 5,000) Roll out new community composting approach | Part complete | - Implement expanded Southfields food waste collection trial: Completed - Implement new Bedford Hill/Balham food waste collection trial: Completed - Roll out new community composting approach: Cancelled (due to the strategy of encouraging community organisations to submit bids for funding such approaches having been unsuccessful). | - 409 tonnes food waste recycled via these trials prior to the introduction of borough-wide kerbside collections for households with front gardens/driveways in June 2024. |
| Wandsworth #4 | Improve waste minimisation and awareness communication and engagement | Commission a dedicated waste and recycling engagement team to carry out waste communications, behaviour change and engagement activity Develop and implement behaviour change campaign, communications, and engagement activities to promote waste minimisation and support the food waste collection trial | Complete | - Commission a dedicated waste and recycling engagement team to carry out waste communications, behaviour change and engagement activity: Completed Q3 2023/24 - Develop and implement behaviour change campaign, communications, and engagement activities to promote waste minimisation and support the food waste collection trial: A new Cleaner Borough Plan commenced from 1 April 2024 with an associated communications campaign which start in the run up to it and throughout the first year of the new approach, to deliver consistent messaging and behaviour change. Keep Britain Tidy were hired to carry out communication on estates to avoid contamination of black bags, with the new comms campaign starting ahead of the new contract. | - 20,512 properties across 158 estates were visited at least once, and a further 9,298 properties were visited a second time, making a total of 29,810 visits. A contact rate of 49% was achieved, with 10,046 residents being successfully engaged. Data on barriers to recycling was also obtained. - New “Recycle Right” campaign and branded materials delivered with a focus on food waste for kerbside households with front gardens/driveways. - Quarterly recycling performance improved from 21.2% at the start of the RRP period to 30.2% at the end. |
| Wandsworth #5 | Procure new waste fleet | Procure new waste fleet which will be lower emission than the previous waste fleet (subject to decision at February Environment Committee) Establish infrastructure needs for an EV heavy waste fleet | Complete | - Procure new waste fleet which will be lower emission than the previous waste fleet: Completed Q1 2024/25. - Establish infrastructure needs for an EV heavy waste fleet: Following the completion of the fleet transition plan by consultants Cenex, a vehicle decarbonisation strategy was developed in collaboration with Procurement and Finance. The strategy formalises the process for decarbonisation the fleet, including the centralisation of all vehicle procurement through the Procurement team, scrutinising the need for vehicles, and ensuring new vehicles are electric vehicles. The strategy was approved at Directors Board in October 2024 (after the new refuse fleet had been ordered). The centralisation of vehicle procurement will enable the monitoring of the decarbonisation of the fleet. A paper on the Phase 1 Options Appraisal of electric charging points to operational buildings went to Directors’ Board in March 2024. This paper detailed the site selection for Wandsworth and the number and types of electric chargers to be installed at these sites. Load testing has been conducted in all the sites, and there is enough capacity at each site for delivery of the charging points and to maintain operations. A fire risk assessment has also been completed for each site. Once installation is complete on these sites, the project will be rolled out to other operational sites. | - Procure new waste fleet which will be lower emission than the previous waste fleet: Fleet now operating on HVO achieving up to 90% net reductions in CO2eq emissions. - Establish infrastructure needs for an EV heavy waste fleet: Progress towards enabling a future heavy waste collection fleet to be EVs. |
| Wandsworth #6 | Reduce rejection of contaminated loads from communal recycling | Cease practice of collection crews treating communal recycling bank contents they think may be too contaminated as refuse, only reject loads subject to quality inspection at WRWA, Smugglers Way. | Complete | Implemented from start July 2023. | - Combined with other measures to improve dry recycling performance at communal bin premises, the percentage of waste collected for dry recycling increased from 17.3% in Q1 2023/24 to 22.4% in Q4 2024/25. After allowing for contamination, the communal bin dry recycling rate rose from 12.2% to 17.2%. This has not led to an increase in material delivered for recycling being rejected from the process. |
| Wandsworth #7 | Support and promote the reuse and repair of electricals | Continue to take part in London Councils One World Living programme and support the electrical workstream Support and promote repair cafes and restart parties in the borough Take part in London Repair Week Identify pilot projects to progress locally as part of the One World Living programme | Complete | The first Reuse and Repair Fair took place during Circular Economy week in October 2023. | This event brought together 14 local repair businesses, fixing café's, sewing groups, artists and charities for a day at the Royal of College art. Over 200 residents attended the fair and learnt about local circular economy initiatives as well as the chance to have items triaged and fixed, upcycle their own denim draught excluder and make a collage from solely upcycled and recycled materials. To support the event a poster which doubles as a resource that shared national and local repair services was created and shared online, and in physical spaces and digital boards around the borough. |
| Wandsworth #8 | Reduce single use plastic use | Continue to take a lead role in plastics workstream of London Councils One World Living programme Introduce a single use plastics charter Create advice for businesses on reducing and avoiding single use plastic Engage in cross-borough work on refill mapping Run ECO Refill projects in schools, promoting refill | Complete | Continue to take a lead role in plastics workstream of London Councils One World Living programme: A Single Use Plastics Pledge has been developed through a working group of officers from partnering boroughs of the One World Living programme, as well as representatives from Ellen MacCarthur Foundation, City to Sea, ReLondon, and the West London Waste Authority. (As at February 2025) The One World Living Councils pledge on single use plastic is progressing through a pan-London working group, to understand the barriers boroughs face and work together, learning from best practice examples from other cities and countries, to create a methodology and actions to enable borough activity against plastics. This revised pledge is due to be published in early 2025, and we expect to be an early signatory of the pledge. This has now launched and early signatories will form a working group for the next 12 months to research and commit to baselining guidance and target setting, with a full pledge and action plan for all boroughs launched in December 2024. Schools eco refill shop project launched and run successfully across two terms so far in 7 schools. This initiative has been well received, proving popular with both schools and parents, who would like to see this develop into broader climate action for this demographic. (As at August 2025) The Council was amongst the first to sign the pledge. | Continue to actively engage in the plastics workstream of London Councils One World Living programme: As of June this year we have signed the Single-Use Plastics pledge and committed to taking action on eliminating problematic and unnecessary plastics. We have identified the actions we will take, and will be reporting against these in mid-2026. Run ECO Refill projects in schools, promoting refill: we continue to run the ECO refill shops within schools, widening the reach of plastic-reduction behaviours. |
| Wandsworth #9 | Reduce textiles waste | Work with RCA’s Textiles Circularity Centre to support their innovative work on textiles Explore increased textiles recycling collections Develop and implement a schools engagement programme on circular textiles. Work with other London boroughs to reduce textiles waste and consumption, including the delivery of at least three pan-London borough workshops. Continue to co-lead the textiles theme of the One World Living Programme | Part complete | Work with RCA’s Textiles Circularity Centre to support their innovative work on textiles: The Council has worked with the RCA’s Textiles Circularity Centre (TCC) on a range of projects, including the promotion of their newly developed “repair app”. The RCA also hosted the Council’s 2023 Reuse and Repair Fair, which had a number of market stalls for people to learn more and take part in practical activities around reuse and repair. Explore increased textiles recycling collections: Wandsworth joined Richmond’s contract with Traid for the provision of textile recycling bank services late November 2023 and Traid replaced Scope’s banks on Council land at that time. This contract contains provisions to increase the tonnage recycled through the further development of textile recycling bank services. The Council also endorses and promotes Traid’s free, on-request doorstep textile collection service. Develop and implement a schools engagement programme on circular textiles: The council is developing an engagement programme with schools on circular textiles. Work with other London boroughs to reduce textiles waste and consumption, including the delivery of at least three pan-London borough workshops: The Council has hosted a workshop with other London boroughs (the first of a series of planned workshops) to work together to develop a pan London circular textiles action plan. Continue to co-lead the textiles theme of the One World Living Programme: As co-lead of the textiles workstream for the One World Living programme, the council has developed education packs on the circular economy and textiles for primary and secondary schools. The council also took part in the TRAID refresh campaign to encourage the use of TRAID clothes collections across the borough. | Work with RCA’s Textiles Circularity Centre to support their innovative work on textiles: Contributes towards positively influencing the textile supply chain to decarbonise. Explore increased textiles recycling collections: The quarterly tonnage recycled increased from 114 tonnes in Q1 2023/24 to 163 tonnes in Q4 2024/25. Develop and implement a schools engagement programme on circular textiles: Work with other London boroughs to reduce textiles waste and consumption, including the delivery of at least three pan-London borough workshops: Reduced textile waste (not measured- no recent residual waste composition analysis). Continue to co-lead the textiles theme of the One World Living Programme: Contributes towards positively influencing the textile supply chain to decarbonise and lower impact textile related behaviours by consumers. |
| Wandsworth #10 | Promote sustainable food | Continue to take part in London Councils One World Living programme and support the food workstream Engage and promote monitoring of food waste reduction to businesses Support a pan London sustainable and healthy diet awareness campaign Take part in London Circular Food Procurement Working Group to develop sustainable food approaches Include food sustainability in Children’s Food Strategy | Part complete | As part of the One World Living programme (co-lead of the textiles workstream), the council has continued its involvement and support of the food workstream. For example, the council supported and promote the Eat Like a Londoner campaign, which aimed to encourage the uptake of more sustainable and healthy diets, with a London -wide campaign which included posters in train stations and outside supermarkets alongside extensive social media presence. (As at February 2024) The council is currently developing a new Food Strategy, which will include a focus on sustainable food and the promotion and access to sustainable and health food across the borough. A new School Food Strategy was brought to Children’s Committee in June 2023 (Paper 23-182) which included a section on Sustainability which sets out how schools will reduce food waste as well as increasing recyclable and compostable materials as part of the catering supply | Continue to take part in London Councils One World Living programme and support the food workstream: Engage and promote monitoring of food waste reduction to businesses: Support a pan London sustainable and healthy diet awareness campaign: Take part in London Circular Food Procurement Working Group to develop sustainable food approaches: Include food sustainability in Children’s Food Strategy: |
| Wandsworth #11 | Support the Circular Economy | Launch the borough’s first Library of Things Take part in London Circular Economy week | Complete | Launch the borough’s first Library of Things: Library of Things soft launched at the end of November 2023 in partnership with the Southside shopping centre, with a hard launch in January 2024. The unit has 40 household items available to hire and is agreed on a two-year contract at the site. Take part in London Circular Economy week: Officers supported and presented as part of the One World Living (OWL) borough event in October 2023 to coincide with Circular Economy week. showcasing our work in this area and linking initiatives with other themes to. | Launch the borough’s first Library of Things: The Library of Things has continued to perform well and is consistently in the top 3 performing locations across the UK every month. We have extended the library’s contract so this provision will continue for at least a further 12 months. Take part in London Circular Economy week: Council’s work in this area showcased / momentum around circular economy activities built |
| Wandsworth #12 | Take part in London Repair week | Draw together local stakeholders working on circular economy processes and practices to deliver a local event during repair week Co-ordinate educational and informational comms about local repair services and actions via digital campaign during the week. Signpost and support local groups working within this space to increase engagement and participation in repair and rework practices. | Complete | To achieve this, we held the first Reuse and Repair week during Circular Economy week in October 2023. This event brought together 14 local repair businesses, fixing café's, sewing groups, artists and charities for a day at the Royal of College art. Over 200 residents attended the fair and learnt about local circular economy initiatives as well as the chance to have items triaged and fixed, upcycle their own denim draught excluder and make a collage from solely upcycled and recycled materials. To support the event a poster which doubles as a resource that shared national and local repair services was created and shared online, and in physical spaces and digital boards around the borough. | • Draw together local stakeholders working on circular economy processes and practices to deliver a local event during repair week: • Co-ordinate educational and informational comms about local repair services and actions via digital campaign during the week: • Signpost and support local groups working within this space to increase engagement and participation in repair and rework practices: |
| Wandsworth #13 | Ensure suitable space for waste & recycling storage at developments | Progress review of the Council’s SPD relating to refuse to ensure maximisation of provision for greater capture of recycling materials. | Complete | A revised waste related supplementary planning document was adopted and published in July 2025. | Improved recycling performance through the provision of additional space for waste storage in developments to accommodate Simpler Recycling requirements including containers for food recycling and green waste bins for households with gardens. |
| Wandsworth #14 | Programme to review refuse and recycling provision within housing developments | Develop and implement a programme to review refuse and recycling provision, estate cleansing services and fly-tip reduction within Council managed housing estates, to identify & implement bespoke improvements at each (e.g. bin store improvements, container capacity, condition & signage, optimising locations, communications, re-usable bag provision), drawing on ReLondon’s research and guidance in this area, work with residents to improve recycling performance. | Part complete | Estates Improvement Officer has been recruited and started. A contract for the supply of external bin housing units is in place and these have been installed on many estates. An additional article for the Homelife publication sent to all residents of Council managed estates/premises was published. Estate side waste collection was implemented, ensuring that recycling material dumped next to communal bins is recycled rather than being cleared as fly-tipping. This improvement work is continuing with officers from the Waste Team and Housing Estates Team working together with the aim of achieving improved recycling performance, reduced fly-tipping and improved estate cleanliness. This work will include more coordinated use of CCTV, a review of resource for fly-tip removal, and cross-working to manage bin washing schedules. The installation of bin housing units and food waste will ensure ReLondon minimum standards are delivered. Council estates have been prioritised for the food waste roll out. | Combined with other measures, this has resulted in the proportion of waste collected for dry recycling from households using communal wheeled bins increasing from 17.3% in Apr-Jun 2023 to 22.4% in Jan-Mar 2025. After allowing for contamination the rate increased from 12.2% to 17.2%. As at March 2025, over 9,000 flats using communal wheeled bins or skip compactors were receiving weekly food recycling collections (c.13.2% of the total), rising to over 23,500 as at August 2025 (c.35.3% of the total). The quantity of residual refuse collected during Jan-Mar 2025 fell by over 400 tonnes compared to Apr-Jun 2023. |
| Wandsworth #15 | Home composting (container supply) | Promotion of and provision of discount offers on equipment for residents. | Part complete | The Council’s long-standing promotion of GetComposting’s supply and delivery service for home composting equipment continues however no discounts on their standard pricing have been offered. | Recent sales data indicates in the region of 5 composters ordered per quarter. |
| Wandsworth #16 | Recycle Western Riverside | This provides free guided MRF tours for all, fully funded curriculum linked workshops, assemblies and waste audits for schools and waste reduction and recycling related campaigns. | Complete | This is ongoing. Following staff shortages, WRWA’s Education Team is up to full capacity again ready to engage with local schools from September 2025 and liaise with the Council’s waste team to coordinate and support each other’s efforts. | Improved schools recycling performance incl. food recycling service take-up and reduced waste arisings (tonnages not measured independently of other household recycling however 66 schools had taken up the Council’s weekly food waste service offer as at June 2025). |
| Wandsworth #17 | Food waste recycling: Access to processing facility | Continue to work with WRWA and neighbouring boroughs to enable access to facilities for separately collected food waste suitable for processing the likely quantities associated with borough-wide service provision. | Part complete | In the short-medium term a food waste consolidation point is not viable at one of the existing WRWA waste transfer stations and current arrangements will prevail. WRWA are reviewing longer-term plans to assess whether a consolidation point would work, following guidance provided by the Wandsworth Local Plan and London Plan. In the meantime, the Council has contracted suitable arrangements for the direct delivery of food waste for recycling to an anaerobic digestion plant in Mithcham. | No significant issues with securing food waste reprocessing capacity for the foreseeable future. |
| Wandsworth #18 | Utilise waste heat @ Belvedere energy-from-waste incinerator | Cory, the GLA and the LB Bexley are working together to try to secure outlets for the waste heat from the Belvedere EfW incinerator, potentially to a number of new large housing estates planned for the area. | On track | Cory have partnered with Vattenfall which advises that over 25,000 homes and businesses across the London Borough of Bexley and the Royal Borough of Greenwich will be connected to a low carbon heat network over the next ten years commencing 2026. | Substantially improved energy efficiency and carbon performance of Cory’s energy from waste incinerator in Belvedere, Bexley. |
| Wandsworth #19 | Local Plan | Employment and Industry Document 2018, Policies EI8. Site Specific Allocations Document 2016. Policy EI8 - appropriately located sites for waste management are identified in the Site Specific Allocations Document to provide the capacity to meet, over the plan period, the borough’s waste apportionment figure as set out in the London Plan 2015. The Policy also provides development criteria for waste management sites. Waste management sites are allocated in the Local Plan to meet the waste apportionment figure of the London Plan 2015. This means that the Council has enough sites to be considered to achieve net self-sufficiency in accordance with the London Plan. | Complete | The Employment and Industry Document 2018 was superseded by the Wandsworth Local Plan (July 2023), with Policies E18 superseded by Policy LP13 (Circular Economy, Recycling and Waste Management). Table 15.6 states that Wandsworth has a waste management capacity gap (based on the London Plan (2021) apportionment targets). Wandsworth commits to working toward closing the capacity gap by identifying the most suitable locations for new waste facilities. A draft new London Plan is expected for consultation by the end of 2025, followed by an examination in public in 2026-2027, with an intended adoption date of 2027. The new London Plan will include forecast arisings of household, commercial and industrial waste by borough and borough-level apportionments of household, commercial and industrial waste for the plan period (likely to be to 2050). Conversations have recently been held with a consultant working on behalf of the GLA seeking to understand the basis of figures for Local Authority Collected Waste (LACW)/Commercial & Industrial Waste (C&I) recycling capacity in table 15.4 of the Wandsworth Local Plan along with the current position. | Net self-sufficiency for waste apportionment in accordance with the London Plan. |
| Wandsworth #20 | Food waste recycling collection service | Deliver on new Council administration’s manifesto commitment to “Bring in food waste collections borough wide as soon as possible” incl. expansion of the existing service covering the Southfields Grid and a further trial to include a wide range of housing types including Council managed premises using communal bins (Subject to Council decision & WDA contractual permission). | Part complete | Initially, the Southfields Grid trial was expanded to cover a contrasting area of kerbside housing in the Balham/Bedford Hill area as well as a number of purpose-built flats using wheeled bins. The trial was then further extended to cover a private estate in Putney using skip compactors for other waste streams. Following a further 4 year contract extension with Serco and the receipt of a new Council-owned collection fleet, weekly food recycling collections for all kerbside houses with front gardens/driveways commenced in June 2024. The service roll-out to purpose-built flats using communal wheeled bins commenced in December 2024 starting with Council managed estates. The focus is now shifting to privately managed premises and the focus will move on to other household premises once the communal bin roll-out is nearing completion. | 840 tonnes food waste recycled during Q4 2024/25 contributing 2.74% towards the improved overall household recycling rate of 30.23% for the quarter. |
| Wandsworth #21 | Home composting | Further trial of home composting (likely to include the placement of composters within community-based areas, such as the Council’s housing estates). | Cancelled | A strategy of encouraging suitable bids for grant funded projects from the community did not lead to any viable bids. | N/a |
| Wandsworth #22 | Utilise premise/premise specific weighbridge data to encourage improved performance (where available) | Provide regular feedback to premise managers and occupants of residential premises using waste compactor skips on their recycling performance, along with tips for improving. Extend this to the Tooting Grove Estate if and when separate weighbridge data for this becomes available. | Part complete | Provide regular feedback to premise managers and occupants of residential premises using waste compactor skips on their recycling performance, along with tips for improving: This commenced in Q3 2023/24 for all skip compactor sites (now 7 in total covering over 6,000 flats), using Q2 data. This led to further engagement at a number of sites, leading to improved signage being installed, recycling fliers being distributed to all households by the management and also to identifying solutions for retrofitting weekly food recycling collections. Closer analysis of weighbridge data also identified issues with the collection service at some locations. Feedback and engagement are ongoing. Extend this to the Tooting Grove Estate if and when separate weighbridge data for this becomes available: 25.4% of waste was collected for recycling during 2024/25. No contamination sampling data available but actual recycling performance likely to be significantly lower. | Provide regular feedback to premise managers and occupants of residential premises using waste compactor skips on their recycling performance, along with tips for improving: After engagement with the management and addressing servicing issues, the proportion of waste collected for recycling at one site increased from 7% in Q2 2024/25 to 36% in Q4. For skip compactor sites overall, the proportion increased from 16.4% to 24.4%. However, levels of contamination in recycling compactors remain high. Extend this to the Tooting Grove Estate if and when separate weighbridge data for this becomes available: Quarterly data did not become available, so no regular feedback was possible and no related interventions occurred. |
| Wandsworth #23 | Chargeable garden waste service | Introduce fortnightly chargeable garden waste collection service (subject to Council decision) | Delayed | No Council decision has yet been made and implementation is likely to be delayed. However, officers are actively examining options for this service. | c. 2.9% added to the household recycling rate once implemented. |
| Wandsworth #24 | Undertake a feasibility study for a commercial waste service | Subject to Council decision to explore options and in response to the key mayoral priority to achieve his municipal recycling rate target by 2030 - Consider the introduction of a commercial waste service, catering for different size businesses | Cancelled | The Council currently has no plans to alter its existing approach to pricing its commercial waste collection services which has led to it having no customers since 2002. | N/a |
| Wandsworth #25 | Transition the Council’s vehicle fleet to low and zero emission vehicles | • Develop a detailed vehicle decarbonisation plan in collaboration with procurement and all relevant teams (including vehicle replacement schedules and EV charging infrastructure) and finance on costs. • Implement vehicle decarbonisation plan. • Replace vehicles at end-of-life with EVs. • Set decarbonisation targets between now and 2030 and track progress on vehicle decarbonisation. | Complete | Following the completion of the fleet transition plan by consultants Cenex, a vehicle decarbonisation strategy was developed in collaboration with Procurement and Finance. The strategy formalises the process for decarbonisation the fleet, including the centralisation of all vehicle procurement through the Procurement team, scrutinising the need for vehicles, and ensuring new vehicles are electric vehicles. The strategy was approved at Directors Board in October 2024 (after the new refuse fleet had been ordered). The centralisation of vehicle procurement will enable the monitoring of the decarbonisation of the fleet. A paper on the Phase 1 Options Appraisal of electric charging points to operational buildings went to Directors’ Board in March 2024. This paper detailed the site selection for Wandsworth and the number and types of electric chargers to be installed at these sites. Load testing has been conducted in all the sites, and there is enough capacity at each site for delivery of the charging points and to maintain operations. A fire risk assessment has also been completed for each site. Once installation is complete on these sites, the project will be rolled out to other operational sites. | Improved air quality and health |
| Wandsworth #26 | Reduce waste from Wandsworth Council sites | • Improve recycling facilities/services for all Council sites. • Explore a pilot for food waste collection from council premises. • Sign up to the One World Living plastics pledge to reduce single use plastic across the organisation. • Reduce consumption by exploring a staff ‘Library of Things’ where resources can be shared. | Part complete | Improve recycling facilities/services for all Council sites: The Council office recycling scheme was refreshed with new containers. Explore a pilot for food waste collection from council premises: Facilities Management are progressing implementation of this service in Council buildings. Sign up to the One World Living plastics pledge to reduce single use plastic across the organisation: The One World Living Councils pledge on single use plastic is progressing through a pan-London working group, to understand the barriers boroughs face and work together, learning from best practice examples from other cities and countries, to create a methodology and actions to enable borough activity against plastics. This revised pledge has now been signed by the Council. Reduce consumption by exploring a staff ‘Library of Things’ where resources can be shared: Library of Things has been promoted to staff, including discount codes to increase take-up. There has been positive feedback from staff that have used it and there have been initial discussions around sharing and reuse approaches among staff. | Improve recycling facilities/services for all Council sites: Improved recycling performance in Council offices (not quantified) Explore a pilot for food waste collection from council premises: Food recycling for Council offices: In progress. Sign up to the One World Living plastics pledge to reduce single use plastic across the organisation: Reduce consumption by exploring a staff ‘Library of Things’ where resources can be shared: |
| Wandsworth #27 | Deliver the Cleaner Borough Plan | • Introduce weekly food waste collections across the borough. • Introduce kerbside collection of batteries and WEEE. • Deliver waste communications plan to support introduction of new collections, promote recycling and waste minimisation | Complete | Introduce weekly food waste collections across the borough: The first phase of the Cleaner Borough Plan has been delivered. This guaranteed weekly waste collections, saw the rollout of a new, modern fleet which will see a reduction in costs of over £1m per year which will be reinvested into services. New arrangements to stabilise collections and increase crew supervision are seeing results. Solutions for weekly food waste collections from flats above shops are now being worked on. Introduce kerbside collection of batteries and WEEE: Small WEEE collections for all low-rise households commenced in June 2024. However, loose and removable batteries are excluded from this service. WEEE banks have been installed in libraries along with 20 external ones across the borough. The service was promoted during international WEEE week in October 2024. Deliver waste communications plan to support introduction of new collections, promote recycling and waste minimisation: New “Recycle Right” branding was developed for a communications campaign to support the roll-out of food recycling services and boost dry recycling performance, supported by a dedicated fixed term communications officer. In October 2024, Executive approved the investment of £1.5 million in 2024/25 and £1.2m in 2025/26 to deliver Phase Two of the Cleaner Borough Plan. This includes more contract monitoring capacity and targeted communications for affected residents. The Council is now recruiting a waste Campaign Manager. | Introduce weekly food waste collections across the borough: Highlights include: - Household recycling rate hit 30.2% in Q4 2024/25 - Over 72,000 kerbside households with front gardens/driveways now receiving weekly food waste collections plus over 9,000 flats with communal bin systems as at March 2025 (over 23,000 at the time of writing in August 2025 with the roll-out now in full swing). As at August 2025, over 61% of households receive weekly food waste collections. - Food waste recycling tonnages averaged 66 tonnes/week during Q4 2024/25 and have since exceeded 80 tonnes/week on occasion. Introduce kerbside collection of batteries and WEEE: New recycling services for small WEEE generated 7.46 tonnes of small WEEE for recycling in Q4 2024/25, rising to 9.6 tonnes in Q1 2025/26. Deliver waste communications plan to support introduction of new collections, promote recycling and waste minimisation: Helped towards improved recycling performance of 30.2% in Q4 2024/25 but the contribution of the campaign towards this cannot be isolated. |
| Wandsworth #28 | Reduce carbon emissions from waste collection | • Complete roll out of new HVO waste collection fleet. • Complete a waste fleet decarbonisation analysis. • Explore the feasibility of an e-cargo bike waste collection scheme for businesses. | Part complete | Complete roll out of new HVO waste collection fleet: The new fleet switched from using diesel to HVO Autumn 2024. Complete a waste fleet decarbonisation analysis: (As at February 2025) Waste fleet decarbonisation draft report received, currently under review. This looks at options for further reductions in carbon emissions from the fleet, including options for electrification. Explore the feasibility of an e-cargo bike waste collection scheme for businesses: Cancelled for the time being | Complete roll out of new HVO waste collection fleet: Net carbon emissions associated with operation of household waste collection vehicles reduced by up to 90%. Complete a waste fleet decarbonisation analysis: Practicable pathway identified for potential switch to electric power for next waste collection fleet. Explore the feasibility of an e-cargo bike waste collection scheme for businesses: Not implemented. |
| Wandsworth #29 | Improve waste collection and recycling on housing estates | • Trial project to improve waste collection and recycling facilities on nine housing estates. • Get all council managed estates up to the ReLondon minimum standard guidance for waste and recycling. | Part complete | - See #14 above. | - See #14 above. |
| Wandsworth #30 | Support the Circular Economy | • (Continue to) support the newly launched Library of Things through promotion of the service and monitor performance. • Support the development of a community led furniture reuse and repair service. • Explore the development of a circular economy hub for the borough. | Part complete | (Continue to) support the newly launched Library of Things through promotion of the service and monitor performance: The Council has continued to promote this to residents and staff incl. the use of discount codes. Support the development of a community led furniture reuse and repair service: Officers are exploring how more furniture can be repurposed. There have been extensive conversations with Richmond Furniture Scheme (RFS) on expanding their highly successful approach into Wandsworth e.g at Mega Skip events. The Council has also worked with Freegle to increase the free local exchange of unwanted furniture. Explore the development of a circular economy hub for the borough:.There has been initial exploration of a circular economy hub for Wandsworth, although a detailed proposal has not yet been developed. | (Continue to) support the newly launched Library of Things through promotion of the service and monitor performance: This has continued to perform well and is consistently in the top 3 performing locations across the UK every month. Support the development of a community led furniture reuse and repair service: Local Freegle activity rehomed c. 125 tonnes of unwanted items avoiding c. 63.9 tonnes of CO2eq emissions. Explore the development of a circular economy hub for the borough: Not yet implemented. |
| Wandsworth #31 | Support and promote the reuse and repair of electricals | Provide support for local repair groups/events. Explore options for increasing the infrastructure for reuse and repair in the borough, including pursuing the development of a Fixing Factory for the borough. |  | The council has provided another 40 laptops to Power2Connect to recycle and provide to residents to ensure they have digital access. More laptops are needed as demand exceeds supply at the moment. |  |
| Wandsworth #32 | Reduce single use plastic use | • Sign up to the One World Living councils pledge on reducing single use plastic and take action to reduce single use plastic in the organisation. • Develop pilot approaches to reducing single use coffee cups in the borough and a pilot to reduce single use plastic from lunchtime economy. • Develop and support awareness campaign on single use plastics |  | Sign up to the One World Living councils pledge on reducing single use plastic and take action to reduce single use plastic in the organisation: The pledge has now been signed. Develop pilot approaches to reducing single use coffee cups in the borough and a pilot to reduce single use plastic from lunchtime economy: Develop and support awareness campaign on single use plastics: | Sign up to the One World Living councils pledge on reducing single use plastic and take action to reduce single use plastic in the organisation: We have signed up to the pledge and will be progressing our actions for reporting in mid-2026. Develop pilot approaches to reducing single use coffee cups in the borough and a pilot to reduce single use plastic from lunchtime economy: This project has been well researched and scoped, but is currently on hold as we look to coordinate with ReLondon and partners to perhaps explore this at a greater scale. |
| Wandsworth #33 | Reduce textiles waste | Work with RCA’s Textiles Circularity Centre to support their innovative work on textiles Explore increased textiles recycling collections Develop and implement a schools engagement programme on circular textiles. • Work with other London boroughs to reduce textiles waste and consumption, including the delivery of at least three pan-London borough workshops. Continue to co-lead the textiles theme of the One World Living Programme | Complete | The Climate Change and Sustainability Team has met regularly with the RCA’s TCC to get updates on their work and identify potential opportunities for collaboration. As co-lead for London Council’s One World Living (OWL) textiles theme, the team has contributed to the development of a London Textiles Action Plan. This Plan identifies key actions between now and 2030 to reduce consumption-based emissions from textiles in London. As part of the development of the London Textiles Action Plan, the team co-hosted (with London Councils, ReLondon, West London Waste Authority, and the GLA) three workshops for London boroughs to contribute to the development of the Plan. Within the borough, the team is continuing to promote textiles collections through its partnership with Traid and has developed a schools engagement programme on circular textiles. This includes four projects: a panLondon project to set up Uniform Swap Shops in schools; running workshops with schools (confirmed Love Not Landfill will workshops to train 16-18 year olds to run swap events); development of how-to-guides for free use by school on a range of circular textile initiatives; and working with social services on provide free, second-hand clothes for children in need. Feedback from schools is that their existing uniform recycling and re-use schemes are working well and that disadvantaged children are well catered for. We continue to innovate and improve our offer turning to digital options of support for our families – we are looking into developing uniform repair videos to support schools and families. The Council continues to promote Traid’s free home collection service and works closely with Trade to increase textile recycling locally. | Work with RCA’s Textiles Circularity Centre to support their innovative work on textiles: Explore increased textiles recycling collections: The tonnage of textiles recycled via Traid’s home collections increased from 5.6 tonnes in Q1 2023/24 to 10.16 tonnes in Q2 2025/26. New collection activity by Anglo Doorstep Collections increased the Q2 tonnage by a further 13.13 tonnes. Overall, textile recycling increased from 114 tonnes in Q1 2023/24 to 147 tonnes in Q4 2024/25 and 163 tonnes in Q1 2025/26 and c. 173 tonnes in Q2 2025/26. Develop and implement a schools engagement programme on circular textiles: Work with other London boroughs to reduce textiles waste and consumption, including the delivery of at least three pan-London borough workshops: No recent WRWA residual waste composition survey is available to confirm whether the presence of textiles in residual waste has decreased. Continue to co-lead the textiles theme of the One World Living Programme: |
| Wandsworth #34 | Promote sustainable food | • Support the development and delivery of the new Wandsworth Food strategy to ensure the sustainability of food is included. • Support phase 2 of the Eat like a Londoner campaign promoting low carbon diets and reducing food waste. • Join the London Circular Food Procurement Working Group to improve knowledge and bets practice on sustainable food procurement. | Complete | The Wandsworth Council Food Plan is in place and outlines a wide range of actions to ensure healthier food spaces for all residents, providing fair access to nutritious food, and involving communities in planning food accessibility. A system-wide strategy is being developed, with plans for strategic engagement in the autumn to maximise impact. To build further collaboration with the sector on food and to deliver on the Council Food Plan, a Food Workstream was established in July within the Cost-of-Living programme governance structure. This workstream facilitates engagement and coordinated action, and plans are being developed to revitalise the Wandsworth Food Partnership. As engagement is being kickstarted, the council remains committed to enhancing food accessibility, promoting healthy eating, and supporting residents through the Council Food Plan, School Food Plan, and Healthy Eating, Weight and Nutrition Plan. While we develop our strategic approach, the Cost-of-Living programme continues to provide immediate support and funding voluntary and community sector organisations. The Food Workstream brings together leads from across the council, who cover different elements of food policy, including representatives from the Climate and Sustainability Team to support the oversight and delivery of the Wandsworth Food Strategy. The Food Workstream developed a successful bid for the Cost-of-Living Fund to establish the Wandsworth Food Partnership Incubator Programme. This initiative will create a food partnership to coordinate food policy activities across the borough. The programme will improve collaboration within the food system, adopting a holistic and integrated approach to food, including considerations around food sustainability. The programme will include a dedicated fund of £100,000 to support the implementation of the Wandsworth Borough Food Strategy, building upon the Wandsworth Food Plan. The Eat Like a Londoner campaign has continued throughout 2024, with proposals for a further campaign in 2025 in development. | Support the development and delivery of the new Wandsworth Food strategy to ensure the sustainability of food is included: Support phase 2 of the Eat like a Londoner campaign promoting low carbon diets and reducing food waste: No recent WRWA residual waste composition survey is available to confirm whether the presence of food waste in Wandsworth’s household waste stream has reduced. However, the introduction of weekly food waste collections for most households will have significantly decreased the presence of food waste in the residual stream, with over 4,000 tonnes diverted since the roll-out of kerbside collections in June 2024. Join the London Circular Food Procurement Working Group to improve knowledge and bets practice on sustainable food procurement: |
| Wandsworth #35 | Introduce recycling services for small waste electricals (WEEE) | Introduce small WEEE recycling services: - Weekly kerbside collections - 20 x public recycling banks - 11 x library recycling banks | Complete | - Weekly kerbside collections commenced Q1 2024/25. - Public recycling banks introduced Q1 2024/25. - Library recycling banks introduced Q2 2024/25. | - The kerbside service has only generated minimal WEEE tonnage to date. - 6.7 tonnes WEEE recycled via banks in Q4 2024/25 rising to 8.8 tonnes in Q1 2025/26. - 0.76 tonnes WEEE recycled via libraries in Q1 2024/25. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Wandsworth #36 | Deliver the Decarbonisation Strategy to reduce emissions from Council Buildings | • Finalise the Decarbonisation Strategy • Develop programmes of works based on the pathway to carbon neutral 2030 in the Decarbonisation Strategy • Deliver already planned and underway works in the programme. | • Decarbonisation strategy delivered. • Programmes of works finalised • Programme of works delivered | Q4 2025/26 |
| Wandsworth #37 | Deliver the Cleaner Borough Plan | Deliver the second phase of the Cleaner Borough Plan to bring our recycling rate to 30% including: - Weekly collections - Crackdown on fly-tipping - Cleaner town centres - Pride in our estates | • Improved household recycling rate: Target 30.5% for 2025/26 • Reduced highway fly-tipping reports & street cleansing tonnage • Improved performance against street cleansing and fly-tip related KPIs. • Improved residents’ satisfaction with cleanliness. | Q4 2025/26 |
| Wandsworth #38 | Reduce carbon emissions from waste collection | • Monitor progress on new HVO waste collection fleet. • Complete a waste fleet decarbonisation analysis. • As part of the new WRWA Strategy, explore ways to reduce Scope 3 emissions associated with our spend on WRWA | Monitor progress on new HVO waste collection fleet: Up to 90% reduction in net CO2eq emissions from operation of waste collection fleet. Complete a waste fleet decarbonisation analysis: (See #28 above) As part of the new WRWA Strategy, explore ways to reduce Scope 3 emissions associated with our spend on WRWA: Improved understanding of total downstream carbon impacts and how best to minimise them. | Q4 2025/26 |
| Wandsworth #39 | Improve waste collection and recycling on housing estates | • Continue waste collection improvement work on housing estates, including more coordinated use of CCTV, a review of resource for fly-tip removal, and cross-working to manage bin washing schedules. • Install housing units and introduce food waste collection to get all council managed estates up to the ReLondon minimum standard guidance for waste and recycling | Continue waste collection improvement work on housing estates, including more coordinated use of CCTV, a review of resource for fly-tip removal, and cross-working to manage bin washing schedules: See #14 & #29 above / reduced fly-tipping on Council managed estates / All Council supplied bins reliably washed at least twice annually with limited capacity for additional ad hoc washes to address any issues that come to the attention of officers. Install housing units and introduce food waste collection to get all council managed estates up to the ReLondon minimum standard guidance for waste and recycling: Further improvements to recycling performance on communal bin collection rounds. | Q4 2025/26 |
| Wandsworth #40 | Support and promote the reuse and repair of electricals | • Provide support for local repair groups/events. • Explore options for increasing the infrastructure and capacity for reuse and repair in the borough. • Communicate and promote repair and reuse events | Increased local reuse and repair activity. | Q4 2025/26 |
| Wandsworth #41 | Reduce textiles waste | • Continue to identify and works with partner organisations (such as the RCA) to reduce emissions associated with textiles and support the actions of the London Textiles Action Plan. • Explore increased textiles recycling collections. • Deliver a schools engagement programme on circular textiles. • Roll out projects from the London Textiles Action Plan locally • Continue to co-lead the textiles theme of the One World Living Programme | Reduced textile related emissions and waste, increased recycling and awareness. | Q4 2025/26 |
| Wandsworth #42 | Promote sustainable food | • Support and develop a Wandsworth Food Partnership to deliver a borough-wide strategy focused on sustainability. • Explore proactive solutions with the Food Partnership to address food waste, support local food businesses in becoming more sustainable, and identify opportunities for borough-wide campaigns on sustainable food practices • Support phase 3 of the Eat like a Londoner campaign promoting low carbon diets and reducing food waste. | Reduced food waste and related impacts. | Q4 2025/26 |
| Wandsworth #43 | Reduce waste from construction | Require construction, demolition, and excavation (CDE) waste management plans from developers detailing how they will reuse, recycle, or recover 95% of construction and demolition waste, and find beneficial uses for 95% of excavation waste in accordance with Local Plan policy LP13 C | Improved waste management during the construction phase of developments. | Q4 2025/26 |
| Wandsworth #44 | Improve recycling/re-use from Mega Skip events” | Maximise recycling/re-use at Mega Skip events through working with suitable partners such as the Richmond Furniture Scheme and Collect 4 Reuse. | Increased recycling and re-use from these events | Q4 2025/26 |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Wandsworth #43 | Introduce weekly food waste collections | (See also #2, #20 & #27 above) Wandsworth remains on track to offer weekly food recycling collections to all households and non-domestic premises it collects from by 31/03/25. However, detailed arrangements for flats above shops and other premises without suitable external space for rigid containers are still being considered and some premise managers may seek to block the installation of communal food recycling containers. | Between 4-6% added to household recycling rate. | Q4 2025/26 |
| Wandsworth #43 | Introduce separate garden waste collection service | Options for this service are now being considered. | Between 2-3% added to household recycling rate. Less garden waste collected if service is chargeable & combined with cessation of the “5 sacks garden waste free per week” policy along with promotion of home composting. | Q1-2 2026/27 |
| Wandsworth #44 | TEEP assessment | Produce TEEP assessment with a view to continuing to collect paper/card for recycling co-mingled with containers. | Fully co-mingled recycling collections continue. Adverse impacts associated with switching to twin stream collections avoided. | Q4 2024/25. |
| Wandsworth #45 | Add aerosols, foil, plastic/metal tubes to co-mingled recycling stream | Adding these materials to the co-mingled recycling stream is dependent on WRWA’s MRF being upgraded to cope with them and for aerosol cans, being able to successfully manage any associated H&S risks. | Less than 1% added to household recycling rate. | Non-domestic premises: Asap Domestic premises: Q4 2025/26 |
| Wandsworth #46 | Plastic films | Adding these materials to the co-mingled recycling stream is dependent on WRWA’s MRF being able to accept them which they have now confirmed. | Less than 1% added to household recycling rate. | Q4 2026/27 |
| Wandsworth #47 | Premises still without dry recycling collections | Some flatted premise managers have blocked the installation of communal bins for recycling and some may simply have no space for anything more than a single communal refuse bin. Work is being undertaken to confirm locations and numbers along with potential solutions. | Less than 1% added to household recycling rate. | Q4 2025/26 |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026