- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 240.68 kgs/head | 252.17 kgs/head (TARGET HAD BEEN ADJUSTED UP FOLLOWING 21/22 DATA) | 221.79 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 310.92 kgs/hh | 291.66 kgs/hh | 271.03 kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 76 kgs/head | 60 kgs/head | 35.56 kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70%, Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44%, Unavoidable food waste recycled: 56%. If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 50.35% | 50% (WAS 55% AT TIME OF ORIGINAL RRP*) | 48.72% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 34.89% | 50% | 33.93% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 5% | 38% | 38% | 90% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 20% | 25% | 20% | 20% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| Ealing #1 | Restricting residual waste capacity | Following the successful implementation of the alternate weekly collection service in 2016, the residual waste wheelie bin capacity has been restricted, from 240 litres to 180 litres for standard kerbside properties. Containers are delivered to replace existing bins when residents request containers. All standard bins in the borough will be replaced with this smaller size across the life cycle of the original bins. | - On track / part complete | When residents request new wheeled bins when moving into a property, where there isn’t one, or a replacement container(s) is required after any damage the address is supplied with a 180 litre bin, rather than a 240 litre bin. During 2024/25 1,073 x 180 litre rubbish bins have been delivered. Deliveries will continue over subsequent years. | - These smaller bins have resulted in a reduction of 64,380 litres per fortnight for rubbish collection, WRAP evidence indicates that recycling services perform better where both frequency and capacity are restricted. By restricting the residual waste capacity further, this should encourage a further reduction in residual waste arisings and an increase in recycling. |
| Ealing #2 | Revisiting larger bins criteria | The team have revisited the criteria for larger bins and the capacity provided for Houses in Multiple Occupation (HMOs), with the idea of reducing capacity or encouraging the sharing of bins. This will be on a case by case basis taking into account individual needs. Any change in capacity will be supplemented with engagement and education on how to dispose of waste and recycling correctly and in line with the waste hierarchy. Liaison takes place with Property Regulation on individual cases and issues, including reviewing capacity at particular properties. There are also 2 new officers in post to enforce against all waste issues at HMOs. | - On track / part complete | Residents can request additional bins; each request is assessed by a member of the team against the criteria. If the household meets those requirements a larger bin will be provided. During 2024/25, 600 x 360 litre wheeled bin for rubbish were delivered. This increases the capacity for rubbish disposal by 180 litres. In addition, 1,172 x 360 litre wheeled bins were delivered for recycling capacity, giving these homes an extra 120 litres of recycling per fortnight. | - These larger rubbish bins resulted in an additional capacity of 108,000 litres per fortnight for rubbish collection if the bins are always full. - The larger recycling bins have provided an additional 140,640 litres of capacity for recycling. |
| Ealing #3 | Commercial waste service | The commercial waste service offers residual waste collection (bins and sacks) and a dry mixed recycling service (introduced in November 2019 – sacks only and also a cardboard collection, see Maximising recycling section). Businesses are encouraged to consider overall waste management, including waste reduction, and then an appropriate and fit for purpose contract for the waste and recycling that they do produce. - When on site with a person of authority, the commercial waste sales team review how much waste a business is producing, the type of containers used, storage available and what collection frequency can be recommended. When gaining an understanding on the type of waste being produced, the commercial waste sales team advise the business (if appropriate) that there is an environmental and cost saving opportunity by reviewing their suppliers on how they package the goods which are sold to the business and advise the business further that if their suppliers use less packaging, this will cause less waste being produced, meaning less commercial waste costs to the business and much ‘greener’ for the environment too. These activities encourage waste to be managed in line with the waste hierarchy as far as possible. Waste arisings should reduce with increased education, and there will also be a positive impact on waste collected for recycling. - Commercial food waste collection trial - Bin weighing project to data capture information on volumes of waste Ealing Council is collecting commercially vs what is contractually agreed with businesses. | - On track / part complete - Delayed - On track / part complete | - Territory Sales Executive and Customer Support team advise businesses of service options including promoting the Saturday DMR sack and Cardboard collection service. In 2024/25 there was a very slight drop in the unit sales of Dry Mixed Recycling sacks vs 23/24 of 3.9%. Reasons may be that local businesses may have opted to use alternative service providers who offer a more comprehensive recycling collection service at this time however, we cannot quantify this. It may also have been that more businesses were reducing packaging and so saw a drop in how much they had to (dry mix) recycle. Cardboard sticker (packs of) sales did increase vs 23/24 by approx. 9%. - A food waste trial has been discussed with Greener Ealing Ltd to better understand the demands of current customer base, volumes of food waste produced commercially and cost / savings to service once removed from residual waste. Approximately 85% of current commercial waste customers are microbusinesses. Officers are engaging with the larger business customers to introduce food waste recycling services to them. - Using two commercial waste crews a bin weighing project was conducted to capture individual weights of customer bins. This data is to be used in contacting customers who are producing overweight bins to discuss and advise of reducing their waste volumes - why and how. Also, advising of diverting recyclable material into appropriate recycling (DMR and Food) streams. Potential opportunity to weigh bins as part of service operation with investment in technology in the future to monitor all bin weights on every collection. | - An approximate reduction of 2 tonnes in Dry Mixed Recycling was collected, though cardboard sticker sales increased by 10%. - The impact will be measured once the trial has been completed though with Simpler Recycling in effect, this service will roll out on demand. - Highlighted that approx. 50% (plus) of contracted commercial waste bin customers are producing overweight bins and so the need to divert food waste and DMR from residual collections is urgent. |
| Ealing #4 | Circular Economy Strategy and activities | - Stakeholder mapping currently being undertaken to identify local businesses and charities that support a circular economy and encourage their addition to a virtual circular economy hub run with WLWA. - Encourage reuse and repair by promoting local forums (e.g. Repair Café) and Repair week each year. - Explore the introduction of reuse hubs where repairs, reuse and prevention of waste can occur. - Build relationships with local charities and provide information to residents to encourage diversion of reusable items directly to organisations/people that can keep them in use. - Discussions with WLWA and Property Services regarding the feasibility of supporting temporary pop-up repair events and longer-term repair spaces by providing access to empty properties and community buildings. - Encourage swishing in the community http://getswishing.com/ - Trial a low waste/circular neighbourhood in one area of the borough. | - On track / part complete - On track / part complete - On track / part complete - On track / part complete - On hold - On track / part complete - On track / part complete | - Zero waste map – a number of organisations have been identified and added to our new map which is available here - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council - Refill – 7 schools have set up refill shops with the support and encouragement of Pupils Profit. Repair events – Ealing Council funded the Circular Economy Hub at Acton market during 2024/25. There were 19 events across the year. - Ealing are working on the creation of a circular economy hub in Acton, a lot of work is on-going on this behind the scenes. Due to issues with electrical supply and infrastructure the construction work has been delayed until late 2025. - Ealing works with TRAID for textiles and small electricals reuse and recycling and signposts residents to local apps/websites and organisations to reuse household items. - Discussions are currently on-hold due to changes in staff. Options in several locations have been considered but were not feasible. - Details are available on the Ealing website. Relationships are slowly being built with community groups, no swishes have taken place yet. - The trial area is in Acton. In this area almost 1300 food waste caddies were delivered, set out monitoring has been undertaken and 19 events have taken place to encourage reuse, repair and recycling. There were 736 visitors to these events. | - It is very difficult to measure the exact impacts of waste prevention activities. Methods for calculating carbon saved are evolving over time and it is hoped we may be able to use these in the future. - At the Acton market events 3.44 tonnes of carbon and 414 litres of water were saved by the reuse activities. At these events: - 20 items of clothing were repaired - 168 items of clothing were donated to be swapped (Halloween costumes, Christmas jumpers, dressing up costumes), 115 were taken to new homes - 39 t-shirts became bags - 20 draft excluders were made from upcycled jeans and stuffed with unwearable clothing scraps - 115 books were swapped - 104 bikes were mended - 74 pre-loved bikes were sold d) Officers have met with various groups and various barriers have been identified. |
| Ealing #5 | Home composting promotions | Ealing Council works with Straight Plc and Get Composting to offer discounts to residents that wish to take up composting at home. Work towards community composting is continuing with advice being given to residents and community groups. In addition, Christmas tree recycling points are provided over the festive season within open spaces and parks; this material is composted. Information on home composting is available on the Ealing Council website and WLWA website. The team will investigate the feasibility of running further engagement events around composting. | Complete | Get composting is now ‘Great Green Systems’ From July 2024 – June 2025 – 18 compost bins/equipment have been purchased from GGS. | It has been estimated by WRAP that a home composting bin can divert approximately 150 kg per household per year of organic waste. 18 more residents using compost bins equates to approximately 2.7 tonnes of food waste being composted at home. |
| Ealing #6 | Bulky/waste reuse | - Ealing Council previously worked with the London Reuse Network and Furnish on a bulky reuse collection service. Unfortunately, this ceased. The Council are looking at alternative ways to encourage bulky waste reuse locally and in partnership with WLWA. - With WLWA, explore the feasibility of introducing a material collection service which supports the collection of reusable items from homes. Use technology to support a quick and responsive service to collect items that are no longer wanted from peoples’ homes. - The Council signposts residents to the reuse and recycling centre, and other local charities that collect or accept items for reuse. This activity will help towards reducing waste arisings. - Continue to explore alternative ways to encourage bulky waste reuse locally. - Discussions ongoing with WLWA, including separating bulky waste for reuse. - Abandoned bikes in Ealing collected and repaired/reused as part of the 'Let's Go Southall' programme for residents to become more active in this area. - Discussions taking place with Ealing Housing and Void Clearance Teams to ensure that items that are reusable or recyclable are separated from items for disposal where practicable. | - n/a - On track / part complete - On track / part complete - On track / part complete - On hold - On track / part complete - Delayed / on-hold | The Council signposts residents to the reuse and recycling centre, and other local charities that collect or accept items for reuse. Discussions on separate collections of bulky waste for reuse are paused due to the need for infrastructure repairs. |  |
| Ealing #7 | Plan for the Environment (Adopted) | Developers are required to refer to the Plan for the Environment (Adopted), National Planning Policy for Waste, SPG4 Refuse and recycling and complete the Sustainability Checklist when submitting planning applications to the Council. Developers also refer to the Council's Waste management guidance for developers. The handling of waste arising from the construction and operation of development should maximise reuse/recovery opportunities (e.g. bulky items) and minimise off-site disposal. Sustainable development maximises reuse/recovery and recycling, contributing to waste reduction and increased contribution to recycling targets. Continued engagement with planning officers and developers to ensure that reuse (e.g. bulky items) and recycling is designed in to developments. | - On track / part complete | Officers comment on developer waste management plans and provide advice on specific proposals, where required. This should ensure that developments meet the requirements for waste management. The guidance will need to be updated once the plans for EPR, DRS and simpler recycling are confirmed. | Not applicable |
| Ealing #8 | Championing waste reduction initiatives | - Work in partnership with WLWA to promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events. Food prevention workshops held at community events and schools; engagement to reduce amount of food waste disposed of per household. - Explore partnership and local promotion of Olio, Kitche & the 'Too Good To Go' apps in the borough. - Ealing will be part of the Pan-London sustainable food campaign which will run from 2022-24. The scope is to design and deliver a pan-London awareness-raising campaign to inform and empower individuals to reduce their personal food footprint. The campaign will use inspiring messages and practical advice to build on the success of past campaigns such as TRiFOCAL (the ‘Small Change, Big Difference’ campaign) and existing campaigns such as Food Wave. The project will develop a new, London-specific campaign built on relevant insights and delivered across a minimum of two years. Taking this approach would deliver a high impact, engaging and focused campaign designed to achieve exactly what stakeholders require. - Advertise the Mindful Shopper website via the Council website, social media channels and at events. The Mindful Shopper is a guide to products and services which help people reduce waste as part of a more sustainable lifestyle. https://mindfulshopper.co.uk/ | - On track / part complete - Part complete - On track / part complete - On track / part complete | - Officers have attended 25 events, speaking to over 275 people, at these LFHW messaging has been included alongside service information. - This action has been on-hold as our plans for circular economy activities have been developed. Residents are signposted to appropriate sharing apps such as Olio and Too Good to Go. - Ealing has taken part in the pan-London Eat Like a Londoner campaign. The communications reach of campaign was good. Further evaluation is being undertaken at a London level. - Mindful Shopper is publicised on - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council Ealing Council have supported local group Ealing 135 with a reusable party kit to hire out to local residents. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the resident engagement cannot easily be measured. - - - There was good engagement with the Eat Like a Londoner campaign assets in Ealing. - Since hires of the party kit began in December 2024, 390 single use items have been saved from the rubbish. |
| Ealing #9 | Reusable nappies | - Promoting WLWA’s reusable/washable nappy trial packs https://westlondonnappies.com/ via the Council website. - Investigating options to house washable nappy trial packs in public buildings around the borough or developing local volunteers to promote and loan out packs (subject to funding). - Explore opportunities to provide a financial scheme to enable families to afford washable nappies (subject to funding). - Look into the feasibility of providing information to all parents registering a new birth about opportunities to reduce waste and save money as a new parent including washable nappies, second hand opportunities. Liaise with Hillingdon Council, who were trialling a leaflet in early 2022. | - Complete - On track / part complete - On-hold - On-hold | In Autumn 2024, local group Ealing 135 have launched a reusable nappy bank, they have different brands so residents can find the brand and style that suits them. It’s £25 for a three week hire, plus advice and guidance is included. After the three weeks, return the nappies clean and provide feedback! | No data is available for this initiative. |
| Ealing #10 | Partnership with social enterprise to develop a library of things | Partnership with a social enterprise, such as the Library of Things, third sector organisation or WLWA (to be confirmed) to develop an object lending library to help residents reduce waste and save money by renting tools and electronics rather than purchasing new, including locating an appropriate space such as a library, community centre or town centre retail space. Work with partner to stock range of tools and equipment for hire and ensure robust arrangements in place with suppliers. | - On track / part complete | Library of Things opened a kiosk in the Ealing Broadway Centre in July 2024. In the 9 months it has been open, 886 items have been borrowed by 840 unique borrowers. This has saved the purchase of these items. | The impacts of borrowing instead of buying new using Library of Things are: - 6.5t of waste saved (items bought and not used) - 18.7t of carbon saved by avoided production - 6.2t of electricals reused |
| Ealing #11 | Development of the Council’s Climate Emergency and Sustainability Strategy | The aim to make Ealing carbon neutral by 2030 has been considered in two parts – first, where the council has direct control over policies and resources and second, where the council is able to influence and advise. The Council is gathering data to establish current carbon emissions across the various sectors within the borough including Council’s own estate, schools, homes, business and transport. - Strategy developed and adopted by Cabinet in January 2021. Updates to be presented to Cabinet – timescale, to be confirmed. | - On track / part complete | Ealing’s Climate and Ecological Strategy was published in 2021. Annual reports have been completed for the actions. These are available on the Ealing Council website. | The 2025 report will be published in Autumn available on the website. |
| Ealing #12 | Courtauld Commitment 2025 | Aim to become a signatory to the Courtauld Commitment 2025. Use the reports, guides, tools and case studies created by WRAP to work with third sector companies and commercial organisations to reduce food waste and packaging. | - Delayed / on-hold / no progress to date | Officers are working to understand the commitments needed to become a signatory. Officers have received details of the requirements to be a signatory of the UK Food and Drink Pact and are exploring whether Ealing meets the criteria. | Not applicable |
| Ealing #13 | Plastic waste reduction | There are 8 water fountains installed so far in the borough of Ealing through various partnerships and funding streams, including the Mayor's Office, Thames Water and #OneLess. - Officers will continue to encourage the reduction in use of single-use plastic, refilling and reusing (and recycling e.g. plastic bottles when applicable). This activity should help towards reducing plastic waste arisings. Funding opportunities to be sought for installing further water fountains across the borough. - Raise awareness of local businesses and Council Officers that regularly engage with businesses of Refill London scheme membership Refill London - Refill - Staying hydrated in the capital - Continue to work with colleagues in the Sustainability team and Facilities Management across all Council buildings to remove single use plastic cups where possible. The head office complex in Ealing does not use plastic cups. Staff are encouraged to bring reusable cups/mugs/bottles for cold and hot drinks. - Work with WLWA to promote ways to encourage reduction in plastic use; West London Waste ¦ Plastics | a) On track / part complete b) On track / part complete c) On track / part complete On track / part complete | - There is advice about reducing single-use plastic on the Ealing Council website - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council 7 schools started Pupils Profit refill shops in September 2024. - Funding has been received through the Carbon Offset Fund to become a Refill Destination. This is expected to begin in Autumn 2025. - Worked has started to increase awareness of waste prevention and reduction. Initially this has focused on clothing. - Discussions have taken place with a BID, there is uncertainty over whether this is of interest to their businesses. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available on the website cannot be measured. The results for the first year of Pupils Profit will be available in Autumn 2025. - Not applicable - Not applicable - Not applicable |
| Ealing #14 | Alternate weekly collection service | - It is important to ensure that residents participate fully in the waste and recycling services available. Using ReLondon communications assets, boroughwide engagement (Around Ealing magazine, targeted social media) is planned to remind residents ‘which bin is for which material’. This will help to improve participation in services and reduce contamination, ensuring quality recyclate. - A doorknocking campaign to encourage residents to use the food waste recycling service has started (August 2022). The campaign focuses on kerbside properties in 6 lower performing (low participation) rounds and is scheduled to complete in March 2023. - In partnership with WLWA, waste composition analysis will be carried out approximately every 15 months, with results used to inform communication campaigns and potential service changes. | - On track / part complete - Complete - On track / part complete | - There were 2 articles in Around Ealing magazine and 1 on the digital website. The Ealing Recycles Facebook account posted 44 times about recycling related topics including a dedicated 2 month campaign to tackle contamination in October and November 2024. - The campaign was completed in March 2022/23. - A composition analysis took place in November 2024. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. - Results reported in last year’s update |
| Ealing #15 | Increased participation in the garden waste collection service | Annual communications to promote the garden waste collection service, also with regular communications to subscribers, and communications specifically around the half yearly discount offer in October each year. | Complete | The garden waste service had 16,662 subscribers in 2024/25. In 2024/25 the service offering changed to include a winter pause from December to February without the half-yearly discount. In March 2025 a survey was sent to all subscribers to understand their views of the service. | - The garden waste service collected 3572.5 tonnes of recycling. |
| Ealing #16 | Improving recycling quality and reducing contamination of dry mixed recycling from flats | Signage across bin stores will be reviewed in line with the ReLondon Flats Recycling package and posters provided in communal spaces where practical. | On track / part complete | Recycling communications have been re-designed this year: - The stickers for rubbish and recycling bins are now clearer - The contamination tags now link to a new webpage giving residents further information about what to do if they find a tag on their bin. - There are new service leaflets for kerbside and communal properties with updated information and clearer lists of what can and cannot be recycled now. These have started to be distributed to residents. | Not applicable |
| Ealing #17 | Reinvigorate flats food waste collection service and introduction of service to further blocks of flats | - Encourage take up of food waste recycling service at existing flats by communicating and reminding residents of the service via leaflets, and targeted social media. - Rolling programme introducing food waste recycling to the remaining blocks of flats in the borough. | - On track / part complete - On track / part complete | - In Spring 2024 there was a dedicated Around Ealing article about using the food waste service. There have also been social media posts to encourage food waste prevention and use of the service. - 2297 properties in blocks of flats have been added to the food waste recycling service. Surveying and data collation is continuing to enable all the properties to have the service by the end of March 2026. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. - Not applicable |
| Ealing #18 | Schools recycling | Regular communications to schools about recycling and food waste recycling. Reinvigorate schools recycling with a communications campaign (using WRAP resources) to ensure that recycling services are being used to their full potential. | - On track / part complete | Two presentations have been given to the Green Schools Network about recycling and food waste recycling. In March 2025, food waste was rolled out to over 70 schools within the borough. Over 200 140 litre brown food waste bins were delivered to schools. Some primary schools were also provided the indoor kitchen caddies as a one off for their classrooms. All schools were provided with a new and up to date poster that explained how to make the most of the service and included materials that were/were not accepted. | - Crews will begin monitoring the school food waste fill rates from June 2025 |
| Ealing #19 | Expansion of commercial waste service to offer further dry mixed recycling services and trial food waste collections | Commercial customers are currently offered a dry mixed recycling sack collection, which was introduced in November 2019. - Current commercial waste customers are being targeted for uptake of the recycling service as well as new businesses that may not have used the Council service previously due to a limited recycling service offer. The recycling service is more cost effective and environmentally friendly and evidences the customer's own sustainability credentials and therefore should drive uptake. - Simpler Recycling survey actioned to capture data from current residual waste bin customers to understand how many would take on a dry mixed recycling and now also food bin service too. - Commercial properties / customers are currently not charged for overweight bins collected. A bin weighing project has taken place to help identify customers who may require more bins, a collection schedule increase and higher food waste producing sites so contact can be made and advise of the Simpler Recycling legislation (if the business falls in the current mandatory category). | a) On track / part complete b) On track / part complete c) On track / part complete | - In 2024/25 8 less orders were placed for our recycling service. During 2023/24 there were 138 orders placed for rolls of recycling sacks vs 130 orders placed in 2024/25. Dry Mixed Recycling collected from Ealing Council commercial waste customers resulted in approx.19.630t of recyclables collected for 2023/24. We have seen a reduction in recycling collected from our commercial waste customers down to 17.694t for 2024/25. - The survey was completed, there was a low response rate, so further communications are going to take place. - Scoping and contract negotiations are underway. Review of data captured to take place and contact with customers is to be made once review is complete. Discussions of next steps with customers can then take place to reduce waste or improve recycling volumes. | - Reduction of 3.9% units of Dry Mixed Recycling sacks /rolls ordered but an increase of approx. 9% units of cardboard stickers ordered. - Identified a want of service from those who did respond. - Weight data needs to be calculated before any definite answer can be provided. |
| Ealing #20 | Flats above shops food waste recycling trial | Introduce a pilot to trial food waste collections from flats above shops along one high-street/parade in the borough, accompanied by a targeted communication campaign. Discuss with ReLondon and other boroughs to learn from best practice. Should the pilot be successful, and subject to what government will require as part of Consistency policy, funding will be sought to roll out this service. This could also include flatted properties that may be unsuitable for the current communal food waste recycling service being rolled out and require a different solution. | On track / part complete | There are152 properties in 5 locations currently participating in a flats above shops food waste and rubbish containment trial. There is also one location with just a rubbish containment trial taking place, no food waste recycling trial. This location is Grove Road, W5. This trial has been underway since March 2024. A number of lessons have been learned including the need to make sure there are litter bins close by to reduce the amount of single use drinks cups and bottles placed in the food containers. | - Increased availability of food waste recycling services to residents, therefore maximising recycling. - Target 1kg/hh per week of food waste. |
| Ealing #21 | Waste management guidance for developers to be updated in line with best practice | Developers refer to the Council's Waste management guidance for developers. Update in line with ReLondon’s report Making recycling work for people in flats 2.0 and example supplementary planning guidance. Ensure that developments make sufficient provision for waste management and promotes good design to secure the integration of waste management facilities with the rest of the development and, in less developed areas, with the local landscape. This includes providing adequate storage facilities at residential premises, for example by ensuring that there is sufficient and discrete provision for bins, to facilitate a high quality, comprehensive and frequent household waste and recycling collection service. The handling of waste arising from the construction and operation of development should maximise reuse/recovery opportunities (e.g. bulky items) and minimise off-site disposal. Sustainable development maximises reuse/recovery and recycling, contributing to waste reduction and increased contribution to recycling targets. Continued engagement with planning officers and developers to ensure that reuse (e.g. bulky items) and recycling is designed in to developments. | On track / part complete | Officers comment on developer waste management plans and provide advice on specific proposals, where required. This should ensure that developments meet the requirements for waste management. The guidance will need to be updated once the plans for EPR, DRS and simpler recycling are confirmed. | Not applicable |
| Ealing #22 | Expand the range of materials that can be accepted for recycling at the kerbside | - Textiles and household batteries continue to be collected from kerbside properties by the Council’s Local Authority Trading Company, Greener Ealing Limited. Reuse of items such as textiles where suitable. - Promote the doorstep collection of textiles, e-waste and bric-a-brac using the existing TRAID collection services https://traid.org.uk/collect/ - Promote battery recycling facilities in local shops and other spaces, where collection is not available from home. - Promote the recycling of soft/flexible plastics in local supermarkets www.recyclenow.com/repeatthecycle | - Complete - On track / part complete - On track / part complete - On track / part complete | - Collections continue of textiles and batteries - Information is available on the Ealing Council website - The information available needs to be reviewed - Once there is further clarity over EPR and simpler recycling the type of work we do on this will expand. | - 26.38 tonnes of textiles were collected from homes by TRAID in 2024/25 an increase of 13% on the year prior. - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. |
| Ealing #23 | Expand the range of materials that can be accepted for recycling at the HRRC, and explore reuse/repair activities | - Expansion of the range of materials that can be accepted, including recent partnering with Terracycle to trial collecting hard to recycle items such as toothpaste tubes and pringles tubes from the Household Reuse and Recycling Centre in Greenford. - Introduction of a laptop repair and reuse scheme with dedicated drop off point at the Household Reuse and Recycling Centre in Greenford. - HRRC improvements project to review layout, refresh signage and allow pedestrian access to the site. - Develop great communications about using the HRRC sites so residents can maximise their separation for recycling and reuse e.g. videos showing how a resident would use the site, profiles of different materials and what happens to them after the resident leaves them at site - Provide more information about performance on site including recycling rates, reuse rates. - Review (with Greener Ealing Limited) the gatekeeping at residual waste containers to encourage maximum sorting of materials. - Work in partnership with other WCA and WLWA to trial collections of hard to capture materials e.g. flexible plastics, rigid plastics. | - On track / part complete - Complete - On track / part complete - On track / part complete - Delayed - Delayed - On-hold | - Vapes have been a collected at the site since April 2024. Terracycle have withdrawn their HRRC trial with local councils. The collection of Pringles Tubes, oral care items, plastic tea and coffee packaging and biscuit/cake/cracker wrappers is continuing. Residents no longer need to download a label and bring items in a labelled bag. During 2024/25 Ealing Council partnered with the Ealing allotments group to divert gardening equipment and pots/ornaments from the HRRC and re-distributed these to local groups. - A collection point was added to the site, laptops were collected and sent to The Fixing Factory at the Brent HRRC (operated by Restart) for repair and re-distribution. The Fixing Factory trial ended in October 2023, the evaluation of the scheme demonstrated that the laptops collected from HRRC’s had little reuse/repair value. - Signage has been refreshed on site including signs explaining what happens to many of the materials after they’ve been taken away from site, new road markings and new speed bumps were installed throughout the site. It has not been possible to allow pedestrian access to the site, an in-depth health and safety review that looked at the crossing points and routes on the access road concluded that because of the many large vehicle movements as a result of the bus depot next door and the depot housing the waste fleet and highways fleet it would be too dangerous. - Following the installation of new signs last year, no further signage has been needed in 2024/25. - No update for 2024/25. - The implementation of POPs segregation at site has meant that part of the space allocated for gatekeeping of the residual waste containers is currently being used for residents to deposit items containing POPs. GEL are working on moving other items around on site to accommodate the POPs containers, once this has been completed the work of gatekeeping can move forward. - This work is dependent on the progress on the EPR legislation. | - Approximately 100 garden items have been kept in use. - The laptops were not suitable for repair, all were sent for recycling. - The HRRC recycling rate decreased by increased by 2.26% in 2024/25. This is likely due to less space to check the rubbish due to the separate POPs storage, a reduction in garden waste received at the HRRC and a 20% increase in construction waste - Impact measured as part of the site recycling rate, see (c). |
| Ealing #24 | Neighbourhood sites for recycling electricals and textiles/shoes | The Council operates 22 neighbourhood recycling sites with facilities to reuse/recycle items that cannot always be recycled from home, such as textiles and e-waste. Continue to promote these facilities and expand where appropriate (e.g. into schools). | - On track / part complete | There are currently 20 neighbourhood recycling sites, during 2024/25, there has been an increase in flytipping around textile banks and theft from e-waste banks. Two of the e-waste banks have had their locks removed, replacements are on order. The locations are available on the Ealing Council website. - E-waste and textiles webpages. | Tonnage recycled from neighbourhood recycling sites - Textiles – 644.5 tonnes were collected through textile banks, an increase of 117 tonnes on the previous year - E-waste – 6.98 tonnes was collected in 2024/25, an increase of 1 tonne from the previous year |
| Ealing #25 | Shift towards to HVO and electric waste collection fleet | - Discussions are taking place with Greener Ealing Limited regarding the potential use of HVO and a trial of an eRCV. Timescales and funding to be confirmed. - Electric panel vans operational from July 2020 for part of the fleet. Charging point infrastructure at the Council depot has been delayed. Further vehicles to be ordered once timeline confirmed. | - Part complete - Part complete | - Work with Greener Ealing Limited to switch to an alternative fuel source (HVO) has been explored. Whilst the vehicles are capable of using HVO without requiring a conversion. The price difference per litre will result in a price increase that is not affordable with current local authority funding. An investment programme over up to 10 years would be required. The target for LGV conversion is 2040. Work to explore conversion for smaller vehicles will be conducted within the Mayor of London’s 2030 emission target. - Work to introduce small electric vehicles has been postponed. Extensive surveying has identified that Greenford depot does not have suitable infrastructure to support the conversion of the environmental services fleet. Other options are being explored Council-wide/corporately. An electric 360 material handler is being used at the HRRC. | Not applicable |
| Ealing #26 | Reducing carbon impact | The Emissions Performance Standard tool highlighted areas in need of improvement. - Commercial waste recycling is currently highlighted as low. This is being addressed by the introduction of the commercial waste dry mixed recycling bin service in 2023 and a commercial food waste recycling trial. Procurement of ULEZ compliant vehicles, electric vehicles where possible, the use of HVO and further optimisation of fleet journeys will contribute to reducing carbon impact. Further introduction of food waste recycling collections from flats will be positive. - Consider pre-sorting of residual waste, where prior sorting of certain waste streams takes place prior to being sent to the energy recovery centre. Discussions to take place with West London Waste Authority. - Address MRF reject rate and improve with communications with residents, and ensuring contamination is removed during the bulking process, where practicable. - Collect fleet data (miles, fuel use etc.) to feed into the process of delivering more effective rounds (in partnership with Greener Ealing Limited). - Review data around collections to ensure the sources are correctly identified and the performance of each collection road can be measured to enable targeting of communications about how to use services and what materials are accepted at low performing rounds. - Use vehicle tracking data to identify potential changes to collection rounds to improve efficiency. - With WLWA, investigate the potential use of sensors in the creation of collection rounds for blocks of flats, on-street banks and litter bins to provide responsive services. | - On track / part complete - Complete - On track / part complete - On track / part complete - Complete - Complete - Complete | - The below table relates to GELs overall fuel, mileage and CO2 totals from the use of the refuse, recycling, grounds maintenance, parks and street cleansing fleets. These figures are slightly higher this year. This is likely due to an increasing workload following the introduction of additional properties on to recycling rounds and, increased flytipping and street cleansing workloads. Fuel (L); Mileage; CO2 KG. Total 2022; 695,860.00; 976,412.23; 1,809,236.00. Total 2023; 688,891.21; 931,503.70; 1,791,117.15. Total 2024; 702,948.15; 969,411.00; 1,827,665.19. Change from 2023; +14,056.94 +2.04%; +37,907.30 +4.07%; +36,548.04 +2.04%. Change from 2022; 7,088.15 +1.02%; -7,001.23 -0.72%; 18,429.19 +1.02%. - Pre-sorting takes place at the waste transfer stations prior to disposal. Material from all 6 WLWA boroughs are mixed together at the waste transfer station. - Contamination is removed where practicable at the bulking area by GEL operatives. Contrary tags are issued by the collection operatives where contamination is seen. These tags have been re-designed in 2024/25, the new tags have a QR that links to a webpage created to provide further useful information to residents about how to correctly dispose of the items they’ve incorrectly put in their recycling bin. Further communications are issued to residents where contamination is an issue. Contamination is still continuing, more work for communal locations is still required. - This is underway and is being used to calculate carbon emissions, as shown in the table above. - The digital twin project commenced in 2024/25, this will enable more accurate identification of collection rounds and tonnage performance. Progress to date has involved creating links between systems to enable real time data to be analysis and work around data cleansing. - Changes were made in 2023/24 which resulted in fewer miles travelled. Further routing options will be looked at in the digital twin project. - WLWA ran a sensors project on behalf of several boroughs, the results demonstrated that at the moment, for Ealing, the benefit doesn’t yet outweigh the cost of the technology. Investment at this point doesn’t represent value for money. | - 1.02% increase in CO2 since 2022 - Not possible to measure - – - 7001 fewer miles driven since 2022 - – - – - – |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| #27 | Food waste services – Schools | Ahead of the legislation change all schools were contacted and encouraged to review the use of their current food recycling bins as schools have had access to this service for a number of years. Usage will be monitored and schools then supported to make full use of the service. | Increased usage of the service and tonnage collected | From April 2025 through the school year September 2025 to July 2026. |
| #28 | Food waste services – Surveying of blocks of flats and flats above shops to assess suitability for food waste collection | This work began in September 2024. Surveys will continue through to Autumn 2025. The results will be used to identify the types and quantities of food waste bins needed. Bins will be procured and the service will be rolled out to as many locations as possible. Survey results will also be used to inform service development for locations where traditional collection methods are not appropriate. | Expansion of the food recycling service to over 90% of properties in Ealing. Increased tonnage of food collected for recycling. | September 2024 to March 2026 |
| #29 | Recycling service provision - Surveying of blocks of flats and flats above shops to identify gaps in service provision for dry mixed recycling services. | This work is being conducted alongside the food waste service surveying. Any gaps identified will be filled using the appropriate existing service. | 100% coverage of the DMR service. | September 2024 to December 2025 |
| #30 | TEEP assessment | Conduct an in-depth analysis of service provision to meet the requirements of the legislation. Ealing will put together all collection data to create a digital twin of existing services to use as the basis for the analysis. Any procurement of outlets for recycling will include consideration for potential changes to service provision following the analysis. | A completed assessment and an action plan for moving forward | April 2025 to commence work March 2026 for assessment to be complete |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026