London Borough Ealing RRP Annual Update 2023/24:

| Ref # | Action title | Action description | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2023/24 against this action - How this action is going to be further delivered across 2024/25 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2023/24, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
| --- | --- | --- | --- | --- | --- |
| Ealing #1 | Restricting residual waste capacity | Following the successful implementation of the alternate weekly collection service in 2016, the residual waste wheelie bin capacity has been restricted, from 240 litres to 180 litres for standard kerbside properties. Containers are delivered to replace existing bins when residents request containers. All standard bins in the borough will be replaced with this smaller size across the life cycle of the original bins. | - On track / part complete | When residents request new wheeled bins when moving into a property where there isn’t one or replacement containers after damage the address is supplied with a 180 litre bins, rather than a 240 litre bin. During 2023/24 1,124 x 180 litre rubbish bins have been delivered. Deliveries will continue over subsequent years. | - These smaller bins have resulted in a reduction of 67,440 litres per fortnight for rubbish collection, WRAP evidence indicates that recycling services perform better, and where frequency and capacity. By restricting the residual waste capacity further, this should encourage a further reduction in residual waste arisings and an increase in recycling. |
| Ealing #2 | Revisiting larger bins criteria | The team have revisited the criteria for larger bins and the capacity provided for Houses in Multiple Occupation (HMOs), with the idea of reducing capacity or encouraging the sharing of bins. This will be on a case by case basis taking into account individual needs. Any change in capacity will be supplemented with engagement and education on how to dispose of waste and recycling correctly and in line with the waste hierarchy. Liaison takes place with Property Regulation on individual cases and issues, including reviewing capacity at particular properties. | - On track / part complete | Residents can request additional bins, each request is assessed by a member of the team against the criteria. If the household meets those requirements a larger bin will be provided. During 2023/24, 572 x 360 litre wheeled bin for rubbish were delivered. This increases the capacity for rubbish disposal by 180 litres. In addition 1235 larger wheeled bins were delivered for recycling capacity, giving these homes an extra 120 litres of recycling per fortnight. | - These larger rubbish bins resulted in an additional capacity of 102,960 litres per fortnight for rubbish collection if the bins are always full. - The larger recycling bins have provided an additional 148,200 litres of capacity for recycling. |
| Ealing #3 | Commercial waste service | The commercial waste service offers residual waste collection and a new dry mixed recycling service (introduced in November 2019, see Maximising recycling section). Businesses are encouraged to consider overall waste management, including waste reduction, and then an appropriate and fit for purpose contract for the waste and recycling that they do produce. - When on site with a person of authority, the commercial waste sales team review how much waste a business is producing, the type of containers used, storage available and what collection frequency can be recommended. When gaining an understanding on the type of waste being produced, the commercial waste sales team advise the business (if appropriate) that there is an environmental and cost saving opportunity by reviewing their suppliers on how they package the goods which are sold to the business and advise the business further that if their suppliers use less packaging, this will cause less waste being produced, meaning less commercial waste costs to the business and much ‘greener’ for the environment too. These activities encourage waste to be managed in line with the waste hierarchy as far as possible. Waste arisings should reduce with increased education, and there will also be a positive impact on waste collected for recycling. - Liaison with ReLondon and available communications materials that could be used to support face to face visits around waste education. - ReLondon toolkit on commercial food waste recycling services and potential food waste trial for businesses in selected area/s of the borough. | - On track / part complete b) Complete c) On track / part complete | - Territory Sales Executive and Customer Support team advise businesses of service options including promoting the Saturday DMR sack collection service. In 2023/24 an additional 10 businesses took on the Dry Mixed Recycling Saturday sack collection service. Other businesses may have opted to use alternative service providers who offer a more comprehensive recycling collection service at this time however, we cannot quantify this. - A new promotional service leaflet has been created and also an electronic newsletter to communicate service and businesses duty of care was sent to all in the council’s database to receive business updates. - Scoping and contract negotiations are underway. There is a Commercial DMR collection of recycling sacks from businesses and we will look to expand the offering to bins using a larger vehicle. Discussions with GEL to take place to see how we can make this work with potentially only a small number of customers initially. | - An extra 2 tonnes of recycling was collected. |
| Ealing #4 | Circular Economy Strategy and activities | - Stakeholder mapping currently being undertaken to identify local businesses and charities that support a circular economy and encourage their addition to a virtual circular economy hub run with WLWA. - Encourage reuse and repair by promoting local forums (e.g. Repair Café) and Repair week each year. - Explore the introduction of reuse hubs where repairs, reuse and prevention of waste can occur. - Build relationships with local charities and provide information to residents to encourage diversion of reusable items directly to organisations/people that can keep them in use. - Discussions with WLWA and Property Services regarding the feasibility of supporting temporary pop-up repair events and longer-term repair spaces by providing access to empty properties and community buildings. - Encourage swishing in the community http://getswishing.com/ - Trial a low waste/circular neighbourhood in one area of the borough. | - On track / part complete - On track / part complete - On track / part complete - On track / part complete - On track / part complete - On track / part complete - On track / part complete | - Zero waste map – a number of organisations have been identified and added to our new map which is available here - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council - Repair events – Ealing Repair café are promoted by Ealing Council. Ealing also funded 4 electrical item fixing events. 33 residents attended and 21 items were fixed. - Ealing are working on the creation of a circular economy hub in Acton, a lot of work is on-going on this behind the scenes and the new site is scheduled to open in 2024. - Ealing works with TRAID for textiles and small electricals reuse and recycling and signposts residents to local apps/websites and organisations to reuse household items. - Discussions are taking place with WLWA and Property Services regarding the feasibility of supporting temporary pop-up repair events and longer-term repair spaces by providing access to empty properties and community buildings. Ongoing discussions in 2024/25. - Details are available on the Ealing website. The work planned for 2024/25 around building relationships with community groups will cover this activity. - The trial area has been chosen and work will commence in 2024/25. | - It is very difficult to measure the exact impacts of waste prevention activities. Methods for calculating carbon saved are evolving over time and it is hoped we may be able to use these in the future. - The 21 items fixed, avoided the need to buy 21 new items. d) 23.46 tonnes of textiles were collected from homes by TRAID in 2023/24 an increase of 23.51% on the year prior. |
| Ealing #5 | Home composting promotions | Ealing Council works with Straight Plc and Get Composting to offer discounts to residents that wish to take up composting at home. Work towards community composting is continuing with advice being given to residents and community groups. In addition, Christmas tree recycling points are provided over the festive season within open spaces and parks; this material is composted. A yearly compost event is also carried out to promote and advise residents. Information on home composting is available on the Ealing Council website and WLWA website. The team will investigate the feasibility of running further engagement events around composting. | - On track / part complete | Get composting is now ‘Great Green Systems’ From April 2023 – June 2024 – 76 compost bins/equipment have been purchased from GGS. In February 2024 a competition was launched for residents to win a compost bin. We had 157 entries and provided 5 winners with 220L compost bins | It has been estimated by WRAP that a home composting bin can divert approximately 150 kg per household per year of organic waste. 81 more residents using compost bins equates to approximately 12 tonnes of food waste being composted at home. |
| Ealing #6 | Bulky/waste reuse | - Ealing Council previously worked with the London Reuse Network and Furnish on a bulky reuse collection service. Unfortunately, this ceased. The Council are looking at alternative ways to encourage bulky waste reuse locally and in partnership with WLWA. - With WLWA, explore the feasibility of introducing a material collection service which supports the collection of reusable items from homes. Use technology to support a quick and responsive service to collect items that are no longer wanted from peoples’ homes. - The Council signposts residents to the reuse and recycling centre, and other local charities that collect or accept items for reuse. This activity will help towards reducing waste arisings. - Continue to explore alternative ways to encourage bulky waste reuse locally. - Discussions ongoing with WLWA, including separating bulky waste for reuse. - Abandoned bikes in Ealing collected and repaired/reused as part of the 'Let's Go Southall' programme for residents to become more active in this area. - Discussions taking place with Ealing Housing and Void Clearance Teams to ensure that items that are reusable or recyclable are separated from items for disposal where practicable. | - On track / part complete | The Council signposts residents to the reuse and recycling centre, and other local charities that collect or accept items for reuse. This work will continue in 2024/25. | Not applicable |
| Ealing #7 | Plan for the Environment (Adopted) | Developers are required to refer to the Plan for the Environment (Adopted), National Planning Policy for Waste, SPG4 Refuse and recycling and complete the Sustainability Checklist when submitting planning applications to the Council. Developers also refer to the Council's Waste management guidance for developers. The handling of waste arising from the construction and operation of development should maximise reuse/recovery opportunities (e.g. bulky items) and minimise off-site disposal. Sustainable development maximises reuse/recovery and recycling, contributing to waste reduction and increased contribution to recycling targets. Continued engagement with planning officers and developers to ensure that reuse (e.g. bulky items) and recycling is designed in to developments. | - On track / part complete | Officers comment on developer waste management plans and provide advice on specific proposals, where required. This should ensure that developments meet the requirements for waste management. The guidance will need to be updated once the plans for EPR, DRS and simpler recycling are confirmed. | Not applicable |
| Ealing #8 | Championing waste reduction initiatives | - Work in partnership with WLWA to promote waste reduction activities such as Love Food, Hate Waste through public stalls at community events. Food prevention workshops held at community events and schools; engagement to reduce amount of food waste disposed of per household. - Explore partnership and local promotion of Olio, Kitche & the 'Too Good To Go' apps in the borough. - Ealing will be part of the Pan-London sustainable food campaign which will run from 2022-24. The scope is to design and deliver a pan-London awareness-raising campaign to inform and empower individuals to reduce their personal food footprint. The campaign will use inspiring messages and practical advice to build on the success of past campaigns such as TRiFOCAL (the ‘Small Change, Big Difference’ campaign) and existing campaigns such as Food Wave. The project will develop a new, London-specific campaign built on relevant insights and delivered across a minimum of two years. Taking this approach would deliver a high impact, engaging and focused campaign designed to achieve exactly what stakeholders require. - Advertise the Mindful Shopper website via the Council website, social media channels and at events. The Mindful Shopper is a guide to products and services which help people reduce waste as part of a more sustainable lifestyle. https://mindfulshopper.co.uk/ | - On track / part complete - On track / part complete - On track / part complete - On track / part complete | - Ealing officers have taken part in 2 events to raise awareness of food waste reduction. The first in June 2023 was at the Ealing Broadway Centre https://vimeo.com/reddoorfilmandmedia/review/843803628/993405ed94. The second was a talk and workshop with students at the University of West London in January 2024. - This action has been on-hold as our plans for circular economy activities have been developed. Residents are signposted to appropriate sharing apps such as Olio and Too Good to Go. - Ealing has taken part in the pan-London Eat Like a Londoner campaign. The results of the London wide campaign are being evaluated. Ealing will continue to be of the campaign during 2024/25. - Mindful Shopper is publicised on - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the 2 LFHW events cannot easily be measured. - - - Re:London have modelled the potential impacts on food waste and carbon of the Eat Like a Londoner campaign, for Ealing their model indicates 3,468 tonnes of CO2e have been saved in Ealing as a result of the campaign. |
| Ealing #9 | Reusable nappies | - Promoting WLWA’s reusable/washable nappy trial packs https://westlondonnappies.com/ via the Council website. - Investigating options to house washable nappy trial packs in public buildings around the borough or developing local volunteers to promote and loan out packs (subject to funding). - Explore opportunities to provide a financial scheme to enable families to afford washable nappies (subject to funding). - Look into the feasibility of providing information to all parents registering a new birth about opportunities to reduce waste and save money as a new parent including washable nappies, second hand opportunities. Liaise with Hillingdon Council, who were trialling a leaflet in early 2022. | - On-hold | WLWA are no longer actively running a nappy pack scheme. Ealing Council are exploring how this could work with local community groups instead. In 2024/25 alternatives and possible relationships with local groups will be explored. | Not applicable |
| Ealing #10 | Partnership with social enterprise to develop a library of things | Partnership with a social enterprise, such as the Library of Things, third sector organisation or WLWA (to be confirmed) to develop an object lending library to help residents reduce waste and save money by renting tools and electronics rather than purchasing new, including locating an appropriate space such as a library, community centre or town centre retail space. Work with partner to stock range of tools and equipment for hire and ensure robust arrangements in place with suppliers. | - On track / part complete | This year a location has been secured for the kiosk, it will be located in the Ealing Broadway Shopping Centre. Funding has been awarded from the Carbon offset fund which covers the capital cost. The official procurement process in complete and a contract with Library of Things signed for 2 years of operation. An installation date will be confirmed shortly, it is anticipated that the Library of Things will be open before August 2024. | The impacts will be measured using a series of KPI’s once the service is up and running. |
| Ealing #11 | Development of the Council’s Climate Emergency and Sustainability Strategy | The aim to make Ealing carbon neutral by 2030 has been considered in two parts – first, where the council has direct control over policies and resources and second, where the council is able to influence and advise. The Council is gathering data to establish current carbon emissions across the various sectors within the borough including Council’s own estate, schools, homes, business and transport. - Strategy developed and adopted by Cabinet in January 2021. Updates to be presented to Cabinet – timescale, to be confirmed. | - On track / part complete | Ealing’s Climate and Ecological Strategy was published in 2021. Annual reports have been completed for the actions. These are available on the Ealing Council website. | The 2023 report is available on the website. It includes carbon savings resulting from solar panels installed at many schools in the borough, 10 new food growing spaces and 2500 trees planted a year. |
| Ealing #12 | Courtauld Commitment 2025 | Aim to become a signatory to the Courtauld Commitment 2025. Use the reports, guides, tools and case studies created by WRAP to work with third sector companies and commercial organisations to reduce food waste and packaging. | - Delayed / on-hold / no progress to date | Officers are working to understand the commitments needed to become a signatory. | Not applicable |
| Ealing #13 | Plastic waste reduction | There are 8 water fountains installed so far in the borough of Ealing through various partnerships and funding streams, including the Mayor's Office, Thames Water and #OneLess. - Officers will continue to encourage the reduction in use of single-use plastic, refilling and reusing (and recycling e.g. plastic bottles when applicable). This activity should help towards reducing plastic waste arisings. Funding opportunities to be sought for installing further water fountains across the borough. - Raise awareness of local businesses and Council Officers that regularly engage with businesses of Refill London scheme membership Refill London - Refill - Staying hydrated in the capital - Continue to work with colleagues in the Sustainability team and Facilities Management across all Council buildings to remove single use plastic cups where possible. The head office complex in Ealing does not use plastic cups. Staff are encouraged to bring reusable cups/mugs/bottles for cold and hot drinks. - Work with WLWA to promote ways to encourage reduction in plastic use; West London Waste ¦ Plastics | a) On track / part complete b) Cancelled c) On track / part complete d) Delayed | - There is advice about reducing single-use plastic on the Ealing Council website - Other ways to reuse and recycle ¦ Other ways to reuse and recycle ¦ Ealing Council Funding has been awarded to introduce Pupils Profit refill shops to 7 schools in the borough, this will start from September 2024 - Ealing Council is no longer part of the Refill London scheme specifically. This action is therefore cancelled. Work is planned with existing commercial waste customers and the BIDs (see point d). - Now staff are returning to the office, the team will restart this activity in 2024/25. - Planned for 2024/25 to work with existing commercial waste customers and the BIDs on practical measures to reduce single use plastic and encourage refill. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available on the website cannot be measured. - Not applicable - Not applicable - Not applicable |
| Ealing #14 | Alternate weekly collection service | - It is important to ensure that residents participate fully in the waste and recycling services available. Using ReLondon communications assets, boroughwide engagement (Around Ealing magazine, targeted social media) is planned to remind residents ‘which bin is for which material’. This will help to improve participation in services and reduce contamination, ensuring quality recyclate. - A doorknocking campaign to encourage residents to use the food waste recycling service has started (August 2022). The campaign focuses on kerbside properties in 6 lower performing (low participation) rounds and is scheduled to complete in March 2023. - In partnership with WLWA, waste composition analysis will be carried out approximately every 15 months, with results used to inform communication campaigns and potential service changes. | - On track / part complete - Complete - On track / part complete | - There were 4 articles in Around Ealing magazine and 6 on the digital website. The Ealing Recycles Instagram account posted 35 times during 2023/24 covering a range of topics such as: composting, food waste, electrical repair events, Ealing repair café and other re-use and recycling initiatives, textiles/Traid, recycling materials, collections overall, waste reduction, eat like a Londoner, carbon calculator, contamination, buy nothing new month, food waste action week and repair week. - The campaign was completed in March 2022/23. 23,510 properties were visited across seven low performing food waste rounds, total there was a successful contact rate of 26.2%, with 5,002 residents engaged with on the doorstep, the majority of residents contacted (67.5%) reported they use the food waste service. Main reasons identified for not using the food waste service, was not having a food waste bin (67.3%, and no information received (19.0%), subsequently 2,062 food waste bins were ordered at the doorstep. Of those who admitted to contaminating their dry mixed recycling, the main contaminant identified was ‘dirty food and drink containers’ (53.4%), followed by ‘textiles/clothes/shoes’ (30.8%). Positively, only a minority of respondents (17.3% reported that they would not do anything differently as a result of the conversation at the doorstep. - A composition analysis took place in December 2023. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. - 2062 food caddies were delivered following the door knocking, for the year 2023/24 if all the people who order a caddy started using it weekly for 1kg of food waste the impact would be an extra 2 tonnes collected each week ~ 104 tonnes a year - Not applicable |
| Ealing #15 | Increased participation in the garden waste collection service | Annual communications to promote the garden waste collection service, also with regular communications to subscribers, and communications specifically around the half yearly discount offer in October each year. | - Complete | The garden waste service had 13744 subscribers in 23/24, an increase of 2.5% on the previous year. | - The garden waste service collected 3694.92 tonnes of recycling, an increase of 13.97% on the year before |
| Ealing #16 | Improving recycling quality and reducing contamination of dry mixed recycling from flats | Signage across bin stores will be reviewed in line with the ReLondon Flats Recycling package and posters provided in communal spaces where practical. | - Delayed | This work will take place in 2024/25 | Not applicable |
| Ealing #17 | Reinvigorate flats food waste collection service and introduction of service to further blocks of flats | - Encourage take up of food waste recycling service at existing flats by communicating and reminding residents of the service via leaflets, and targeted social media. - Rolling programme introducing food waste recycling to the remaining blocks of flats in the borough. | - On track / part complete - On track / part complete | - In Spring 2023 there was a dedicated Around Ealing article about using the food waste service. Throughout the year there have been 10 news articles about food growing, and food redistribution which have included top tips to reduce food waste. In 2024/25 further communication is needed with flats about the food recycling service. - In early 2024 over 5,000 properties were surveyed for suitability for food waste recycling. Surveying and data collation is continuing to enable up to 10,000 more properties to be added to the service in 2024/25. | - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. - Not applicable |
| Ealing #18 | Schools recycling | Regular communications to schools about recycling and food waste recycling. Reinvigorate schools recycling with a communications campaign (using WRAP resources) to ensure that recycling services are being used to their full potential. | - On track / part complete | Regular communications and liaison with schools (including the Green School Network) about recycling and food waste recycling. | Not applicable |
| Ealing #19 | Expansion of commercial waste service to offer further dry mixed recycling services and trial food waste collections | Commercial customers are currently offered a dry mixed recycling sack collection, which was introduced in November 2019. - Current commercial waste customers are being targeted for uptake of the recycling service as well as new businesses that may not have used the Council service previously due to a limited recycling service offer. The recycling service is more cost effective and environmentally friendly and evidences the customer's own sustainability credentials and therefore should drive uptake. - The survey will capture data from current residual waste bin customers to understand how many would take on a dry mixed recycling bin service. - Commercial properties are not currently offered a food waste collection service. The development of this service has unfortunately been delayed due to the pandemic. We are looking to introduce a trial food waste collection service. Discussions to take place regarding a commercial food waste collection trial in selected area/s of the borough where known food waste production is at its highest to gain data on how this could work and logistically how effective this may be. Trial data to be used to understand on the demand business have for this service, how viable a commercial food waste service is operationally for businesses and the cost/saving opportunity to the council whilst working toward the recycling rate targets. | a) On track / part complete b) On track / part complete c) On track / part complete | - In 2023/24 an additional 10 businesses joined our recycling service. During 2023/24 there have been 42 orders for rolls of recycling sacks. Dry Mixed Recycling collected from Ealing Council commercial waste customers resulted in approx.17.31t of recyclables collected for 2022/23. We have seen an increase in recycling collected from our commercial waste customers up to 19.31t for 2023/24. - The survey was completed, there was a low response rate so further communications are going to take place. - Scoping and contract negotiations are underway. There is a Commercial DMR collection of recycling sacks from businesses and we will look to expand the offering to bins using a larger vehicle. Discussions with GEL to take place to see how we can make this work with potentially only a small number of customers initially. | - An extra 2 tonnes of recycling was collected. |
| Ealing #20 | Flats above shops food waste recycling trial | Introduce a pilot to trial food waste collections from flats above shops along one high-street/parade in the borough, accompanied by a targeted communication campaign. Discuss with ReLondon and other boroughs to learn from best practice. Should the pilot be successful, and subject to what government will require as part of Consistency policy, funding will be sought to roll out this service. This could also include flatted properties that may be unsuitable for the current communal food waste recycling service being rolled out and require a different solution. | - On track / part complete | There are 5 locations currently participating in a flats above shops food waste and rubbish containment trial, these 152 properties are on: - Allenby Road, UB1 - The Vale, W3 - Bilton Road, UB6 - Rectory Parade, UB5 - The Avenue, W13 There is also one location with just a rubbish containment trial taking place, no food waste recycling trial. This location is Grove Road, W5. There have been some initial issues, a variety of interventions are being tried in areas with problems. In May/June 2024 residents will be asked for their feedback. The service will be reviewed and a recommendation made about potential expansion after the feedback and monitoring data has been analysed. | - Increased availability of food waste recycling services to residents, therefore maximising recycling. - Target 1kg/hh per week of food waste. |
| Ealing #21 | Waste management guidance for developers to be updated in line with best practice | Developers refer to the Council's Waste management guidance for developers. Update in line with ReLondon’s report Making recycling work for people in flats 2.0 and example supplementary planning guidance. Ensure that developments make sufficient provision for waste management and promotes good design to secure the integration of waste management facilities with the rest of the development and, in less developed areas, with the local landscape. This includes providing adequate storage facilities at residential premises, for example by ensuring that there is sufficient and discrete provision for bins, to facilitate a high quality, comprehensive and frequent household waste and recycling collection service. The handling of waste arising from the construction and operation of development should maximise reuse/recovery opportunities (e.g. bulky items) and minimise off-site disposal. Sustainable development maximises reuse/recovery and recycling, contributing to waste reduction and increased contribution to recycling targets. Continued engagement with planning officers and developers to ensure that reuse (e.g. bulky items) and recycling is designed in to developments. | - On track / part complete | Officers comment on developer waste management plans and provide advice on specific proposals, where required. This should ensure that developments meet the requirements for waste management. The guidance will need to be updated once the plans for EPR, DRS and simpler recycling are confirmed. | Not applicable |
| Ealing #22 | Expand the range of materials that can be accepted for recycling at the kerbside | - Textiles and household batteries continue to be collected from kerbside properties by the Council’s Local Authority Trading Company, Greener Ealing Limited. Reuse of items such as textiles where suitable. - Promote the doorstep collection of textiles, e-waste and bric-a-brac using the existing TRAID collection services https://traid.org.uk/collect/ - Promote battery recycling facilities in local shops and other spaces, where collection is not available from home. - Promote the recycling of soft/flexible plastics in local supermarkets www.recyclenow.com/repeatthecycle | - Complete - On track / part complete - On track / part complete - On-hold | - Collections continue of textiles and batteries - Information is available on the Ealing Council website, a new communications plan will be devised in 2024/25 - The information available needs to be reviewed, a new communications plan will be devised in 2024/25 - This is on-hold until there is further clarity over EPR and simpler recycling. | - 23.46 tonnes of textiles were collected from homes by TRAID in 2023/24 an increase of 23.51% on the year prior. - It is clearly documented that knowledge and information can lead to behaviour change. The impact of the information available cannot be measured. |
| Ealing #23 | Expand the range of materials that can be accepted for recycling at the HRRC, and explore reuse/repair activities | - Expansion of the range of materials that can be accepted, including recent partnering with Terracycle to trial collecting hard to recycle items such as toothpaste tubes and pringles tubes from the Household Reuse and Recycling Centre in Greenford. - Introduction of a laptop repair and reuse scheme with dedicated drop off point at the Household Reuse and Recycling Centre in Greenford. - HRRC improvements project to review layout, refresh signage and allow pedestrian access to the site. - Develop great communications about using the HRRC sites so residents can maximise their separation for recycling and reuse e.g. videos showing how a resident would use the site, profiles of different materials and what happens to them after the resident leaves them at site - Provide more information about performance on site including recycling rates, reuse rates. - Review (with Greener Ealing Limited) the gatekeeping at residual waste containers to encourage maximum sorting of materials. - Work in partnership with other WCA and WLWA to trial collections of hard to capture materials e.g. flexible plastics, rigid plastics. | - Complete - Complete - Part complete - Part complete - Delayed - Delayed - On-hold | - The trial with Terracycle to collect Pringles Tubes, oral care items, plastic tea and coffee packaging and biscuit/cake/cracker wrappers has been in place for 23/24, the response has been low with no collections from the site needed yet. The scheme will be reviewed in 2024/25 to see whether it can be made easier to participate and increase the material collected. From April 2024 vapes can be recycled at the HRRC alongside the small electricals recycling. - A collection point was added to the site, laptops were collected and sent to The Fixing Factory at the Brent HRRC (operated by Restart) for repair and re-distribution. The Fixing Factory trial ended in October 2023, the evaluation of the scheme demonstrated that the laptops collected from HRRC’s had little reuse/repair value. - Signage has been refreshed on site including signs explaining what happens to many of the materials after they’ve been taken away from site, new road markings and new speed bumps were installed throughout the site. It has not been possible to allow pedestrian access to the site, an in-depth health and safety review that looked at the crossing points and routes on the access road concluded that because of the many large vehicle movements as a result of the bus depot next door and the depot housing the waste fleet and highways fleet it would be too dangerous. - The new signage includes what happens to the materials. Video produced for and shared on Instagram with the materials/signage on site. More work to be carried out in 2024/25 to improve the wider communications about using the site. - This work will commence in 2024/25. - This work will commence in 2024/25. - This work is dependent on the progress on the EPR legislation. | - 13 residents have applied for labels under the scheme, no collections have taken place yet. - The laptops were not suitable for repair, all were sent for recycling. - The HRRC recycling rate increased by 1.53% in 2023/24. - Impact measured as part of the site recycling rate, see (c). |
| Ealing #24 | Neighbourhood sites for recycling electricals and textiles/shoes | The Council operates 22 neighbourhood recycling sites with facilities to reuse/recycle items that cannot always be recycled from home, such as textiles and e-waste. Continue to promote these facilities and expand where appropriate (e.g. into schools). | - On track / part complete | There are currently 20 neighbourhood recycling sites, during 2023/24, one e-waste bank was destroyed by arson, the other was removed due to vandalism and flytipping issues. The locations are available on the Ealing Council website. | Tonnage recycled from neighbourhood recycling sites - Textiles – 527 tonnes, an increase of 70 tonnes on the previous year - E-waste – Almost 6 tonnes was collected in 2023/24, |
| Ealing #25 | Shift towards to HVO and electric waste collection fleet | - Discussions are taking place with Greener Ealing Limited regarding the potential use of HVO and a trial of an eRCV. Timescales and funding to be confirmed. - Electric panel vans operational from July 2020 for part of the fleet. Charging point infrastructure at the Council depot has been delayed. Further vehicles to be ordered once timeline confirmed. | - Part complete - Part complete | - Work with Greener Ealing Limited to switch to an alternative fuel source (HVO) has been explored. Whilst the vehicles are capable of using HVO without requiring a conversion. The price difference per litre will result in a price increase that is not affordable with current local authority funding. An investment programme over up to 10 years would be required. The target for LGV conversion is 2040. Work to explore conversion for smaller vehicles will be conducted within the Mayor of London’s 2030 emission target. - Work to introduce small electric vehicles has been postponed. Extensive surveying has identified that Greenford depot does not have suitable infrastructure to support the conversion of the environmental services fleet. Other options are being explored Council-wide/corporately. It has been possible to replace a diesel 360 material handler for a fully electric version. Performance is being evaluated. | Not applicable |
| Ealing #26 | Reducing carbon impact | The Emissions Performance Standard tool highlighted areas in need of improvement. - Commercial waste recycling is currently highlighted as low. This is being addressed by the introduction of the commercial waste dry mixed recycling bin service in 2023 and a commercial food waste recycling trial. Procurement of ULEZ compliant vehicles, electric vehicles where possible, the use of HVO and further optimisation of fleet journeys will contribute to reducing carbon impact. Further introduction of food waste recycling collections from flats will be positive. - Consider pre-sorting of residual waste, where prior sorting of certain waste streams takes place prior to being sent to the energy recovery centre. Discussions to take place with West London Waste Authority. - Address MRF reject rate and improve with communications with residents, and ensuring contamination is removed during the bulking process, where practicable. - Collect fleet data (miles, fuel use etc.) to feed into the process of delivering more effective rounds (in partnership with Greener Ealing Limited). - Review data around collections to ensure the sources are correctly identified and the performance of each collection road can be measured to enable targeting of communications about how to use services and what materials are accepted at low performing rounds. - Use vehicle tracking data to identify potential changes to collection rounds to improve efficiency. - With WLWA, investigate the potential use of sensors in the creation of collection rounds for blocks of flats, on-street banks and litter bins to provide responsive services. | - On track / part complete - Complete - On track / part complete - On track / part complete - Complete - Complete - Complete | - The below table relates to GELs overall CO2 Saving in 2023 compared to 2022. This is as a result of minor round optimisation reducing mileage travelled by approximately 45,000 in a year and changing the material handler from diesel to electric. Fuel (L); Mileage; CO2 KG. Total 2022; 695,860.00; 976,412.23; 1,809,236.00. Total 2023; 688,891.21; 931,503.70; 1,791,117.15. TOTAL CO2 SAVING; 6,968.79; 44,908.53; 18,118.85. CO2 Saved this year compared to 2022 = 1.01%. - Pre-sorting takes place at the waste transfer stations prior to disposal. Material from all 6 WLWA boroughs are mixed together at the waste transfer station. - Contamination is removed where practicable at the bulking area by GEL operatives. Contrary tags are issued by the collection operatives where contamination is seen. Further communications are issued to residents where contamination is an issue. A large project to further reduce contamination will begin in Summer 2024. - This is underway and is being used to calculate carbon emissions, as shown in the table above. - The digital twin project is commencing in 2024/25, this will enable more accurate identification of collection rounds and tonnage performance. - Changes were made in 2023/24 which resulted in fewer miles travelled. Further routing options will be looked at in the digital twin project. - WLWA ran a sensors project on behalf of several boroughs, the results demonstrated that at the moment, for Ealing, the benefit doesn’t yet outweigh the cost of the technology. Investment at this point doesn’t represent value for money. | - 1.1% reduction in CO2 - Not possible to measure - – - 45,000 fewer miles driven - – - – - – |