- RRP Dashboard Update:

| Performance Targets | Baseline Performance (2019/20) | Performance Target 2025/26 | Actual performance 2023/24 | Anticipated performance by 1 April 2027 | Metric Guidance / Data source |
| --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 227.27 kg/head pa | 211.8 kg/head pa | 239.7 kg/head pa | < 211.8 kg/head pa | Current RRP target. Defra stats (Ex BVPI84a) |
| Total annual household residual waste collected per household (kgs/household) | 353.02 kg/hh pa | 295.3 kg/hh pa | 331.4 kg/head pa | < 295.3 kg/hh pa | Current RRP target. Defra stats (Ex NI191) |
| Total annual household avoidable (edible) food waste (kgs/head) | n/a | n/a | n/a | n/a | Information not available |
| Annual household waste recycling rate (% by weight) | 31.6% | 36% | 30.3% | 36% | Current RRP target. Defra stats |
| Annual Local Authority Collected Municipal Waste (LACMW)21 recycling rate (% by weight) | 20% | 39% | 22% | Target not set | Defra stats |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) and separate food waste | 100% | 100% | 100% | 100% | Islington Council data |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) | 100% | 100% | 100% | 100% | Islington Council data |
| % of flats (communal collections and flats within commercial buildings, excluding flats above shops) collecting six main dry materials and separate food waste | 52% | 100% | 100% | 100% | Islington Council data |
| % of flats (communal collections and flats within commercial buildings, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays). | 100% | 100% | 100% | 100% | Islington Council data |
| % of flats above shops collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)) and separate food waste collection | 3% | 100% | 3% | 100% | Islington Council data |
| % of flats above shops collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)). | 100% | 100% | 100% | 100% | Islington Council data |
| Proportion (%) of waste fleet heavy vehicles that are ULEZ compliant | 100% | 100% | 100% | 100% | See www.tfl.gov.uk/modes/driving/ultra-low-emission-zone |

- Reduction and Recycling Plan 2023-25 Year Two Update

| Ref | Theme | Action title | Action Description | Status | Action progress update | Impact of action |
| --- | --- | --- | --- | --- | --- | --- |
| Please note that this update should be read in conjunction with Islington’s RRP Year One update. Updates relate to progress achieved in year two of the RRP period. |  |  |  |  |  |  |  |
|  |  |  |  | Complete | Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in section 4. RRP Actions? |
|  |  |  |  | On track / part complete |  |  |
|  |  |  |  | Delayed / on-hold / no progress to date |  |  |
|  |  |  |  | Cancelled |  |  |
| Objective 1: Waste reduction |  |  |  |  |  |  |  |
| Isl 1 | Waste reduction | Food waste reduction | Actively encourage more residents to recycle their food waste, while also encouraging all residents to reduce the amount of food waste they have in the first place. | Complete | In September 2024 a major boroughwide communications campaign "Do amazing things with your food waste” was delivered to encourage food waste reduction and recycling. It consisted of social media content, a cooking video using leftover food, posters in libraries, articles and wraps on Islington life (borough wide distributed magazine), The leaflet contains a page focussing on tips to reduce food waste and directed residents to the Eat like a Londoner website. NLWA is a delivery partner and steering group member for Eat Like a Londoner - a pan-London communications campaign to encourage and inspire residents to waste less food and eat more sustainably. The social media campaign in NLWA boroughs alone, generated over 3.1 million impressions, approximately 90,000 video views, a reach of nearly 30,000, resulting in 9254 clicks to the ELAL website. An evaluation of the campaign demonstrated that 3 in 20 of the target audience 21–44-year-olds and 1 in 10 parents of children under 12 recalled seeing the campaign. Of those approximately 60 percent reported to have taken action, by wasting less food, eating more plant-based foods, and eating less meat and dairy. To complement the campaign, NLWA ran behaviour change workshops which assisted residents with tackling their food waste and provided them with the knowledge and skills required. Participants weighed their food waste to monitor their progress. There was a significant positive difference in households' food waste following the workshops, demonstrating that the workshops success. Five workshops were delivered across Barnet, Camden, Enfield and Islington in 2024/25. Participants reported increases in awareness of the impact they can have by reducing household food waste, their understanding of how to reduce their food waste and gained the skills required, making it reportedly easier to reduce their household food waste. 94 percent of participants said they were likely or very likely to implement food waste prevention behaviours following the workshop. | Islington Life Magazine featured 4 pages of campaign content, which was delivered to 114,000 homes in Islington. Our online magazine received 1,415 impressions and 746 reads. The campaign resulted in 20,000 “Latest News” email subscribers, with a 48% open rate and a 3% click rate. On social media, we posted 25 times, reaching 6,700 people with an engagement rate of 1.59%. The doorstep communications and engagement campaign targeted 9,986 households, visited 2,396 homes, provided 2,087 kitchen caddies and delivered 1,488 ‘sorry we missed you’ packages. Participation counts in targeted areas increased from 16% to 26% while the percentage of overall waste collected as food waste increased from 4% to 5%. |
|  |  |  | Deliver a costed and resourced behaviour change programme, engaging directly with residents to encourage real changes in food waste behaviours. | Complete | A major borough-wide campaign was conducted between September 2024 and March 2025 to encourage the diversion of food waste from residual waste to recycling and to promote the reduction of food waste. The campaign utilised social media, door-knocking, feedback surveys, intensive distribution of missing equipment and communication materials, along with tonnage analysis and participation counts to establish effectiveness. The campaign aimed to achieve a measurable increase in the number of households actively recycling their food waste and in the tonnage of food waste collected for recycling. It also sought to provide valuable data for evaluating the impact of targeted behaviour change campaigns related to food waste recycling. Attitudinal insights obtained from residents will assist in developing more effective future communications and systems. Improvement works have been undertaken on estates to ensure there is sufficient capacity and improved bin enclosures to encourage usage (see thriving communities work). The campaign was funded by the increased profits for LEL resulting from higher energy prices during 2023. | 10,000 street property households received a door-knocking campaign, along with equipment and leaflet distribution. Additionally, 1,000 households received leaflets only, while a final 1,000 households served as a control area with no interventions. A total of 2,400 conversations were conducted. Sample/control area analysis reveals that participation in food waste recycling increased by 61% in households that engaged in a conversation, by 29% after receiving leaflets only, and by 9% where residents had equipment left on their doorstep with leaflets. In total, 2,084 caddies and 1,796 outside food waste boxes were delivered to 2,018 households where recycling equipment was missing. Overall, there was a reduction in refuse and an increase in food waste recycling, except in the control group, which remained consistent. Similar work was undertaken in blocks and estates involving door knocking and engagement with residents. Feedback was qualitative and helps to drive improvements in the front line service. |
|  |  |  | Actively promote the annual Food Waste Action Week | Complete | Food Waste Action Week has been supported annually through the sharing of national campaign assets and messaging both internally to council staff and externally to the general public. | Local impact not measurable. |
|  |  |  | Increase the number of residents and businesses using food sharing apps such as Olio and Too Good To Go. | On track / part complete | Islington and NLWA, continue to promote a range of sharing and reuse Apps, through website presence, newsletters and other channels. | It has not been possible to track local App user numbers effectively. |
|  |  |  | Work with the Family Kitchens programme as part of Islington’s adult education programme to deliver cookery courses that help participants to reduce food waste and make more sustainable as well as healthy food choices. | Complete | The lessons plans have been updated to include food waste prevention and recycling. Leaflets packs to reinforce that message have been developed and now handed to all participants of the programme. All the venues used for workshops have a food waste recycling service. | No measurable impact. |
|  |  |  | Through the NLWA’s waste prevention programme, we will continue to reach out at community events to promote the food waste prevention message. | Complete | The North London Community Fund awarded grants of up to £15k to 20 different community groups including two projects operating in Islington. Two large scale projects grants of up to £100k each were also during 2025, one of which operates in Islington and focusses on reducing food waste. | The North London Community fund project aims to be an intervention-based approach with a behaviour change focus with appropriate evaluation, monitoring, reporting and the ability to tell the story of the investment. |
|  |  |  | Work as a member with the Circular Food Procurement working group, convened as part of London Council’s One World Living Action Plan. | On track / part complete | Islington's new school food contract requirements will incorporate London Circular Food Procurement recommended text for tenders or contracts. We have worked in partnership with Manor Gardens Welfare Trust and ReLondon to launch a new community café at the Jean Stokes Community Centre to help tackle food waste and provide affordable and sustainable meals for residents. | Outputs being developed as part of tender procurement. |
| Isl 2 | Waste reduction | Reduce single use plastic | Reduce the use of single use plastic in Islington and our own operations. | On track / part complete | Following the launch of the ‘Bring it’ campaign in Barnet between January and March 2024, NLWA extended the scheme to other Boroughs including Islington, running for 12 weeks from August 2024. Each Bring It campaign included out-of-home advertising on one high street a social media campaign on Facebook and Instagram that directed residents to the landing page www.bringitnorthlondon.co.uk. | The Islington campaign was focussed on Upper street. 57 businesses signed up to support the campaign. Islington campaign focussed social media posts had a reach of 1,074,287 and achieved 2,211,394 impressions. The campaign final report concluded that ‘, the campaign has shown promising results, appearing to positively influence attitudes towards avoiding single-use plastics, increase positive intentions to use and borrow and return reusable containers and increasing engagement in reuse behaviour. These outcomes contribute to reducing single-use plastic waste across north London.’ |
|  |  |  | Support the use of the Refill App that provides the locations of free water refill points including water fountains and retailers | Complete | Refill Day is supported annually through our media channels. | No recorded impact. |
|  |  |  | Encourage the use of reusable, washable nappies to Islington residents through our support of The Real Nappies for London reusable nappy scheme | Complete | Real Nappies for London carried out advertising during 22-28 April 24 (Reusable Nappy Week) which resulted in a reach of 2,884 and 4536 impressions. A monthly reusable nappy and baby clothes swap is held at Islington Ecology Centre where residents can obtain used nappies and baby clothes free. It also provides peer to peer support and advice from Real Nappies for London. | From 1 April 2024 to 31 March 2025 117 nappy vouchers have been issued (compared to 126 the previous year). As of 31 March 2025 68 vouchers have been redeemed with the remainder still valid for 6 months from issue. The final figures will be available from 30 September 2025. 343 children within the borough are participating in the reusable nappy scheme during this this financial year potentially avoiding 101.26 tonnes of nappy waste from residual bins (compared to approximately 119 tonnes the previous year). These figures are based on the number of children who were issued with a nappy voucher at some point who are not yet potty trained. |
|  |  |  | Continue to support Low Plastic Zones (subject to a review of their effectiveness) | Cancelled | An NLWA review of LPZs concluded there was low impact and are changing the campaign focus to reuse, to avoid single use plastics, targeting consumers more than businesses. A new campaign (Bring It) has been developed which is referenced above. | The Bring It campaign is currently being evaluated. |
|  |  |  | Promoting refill options | On track / part complete | Please see reference to 'Bring It' campaign above. | Please see reference to 'Bring It' campaign above. |
|  |  |  | Use our progressive procurement policy to reduce unnecessary single use plastic | On track / part complete | We encourage commissioning clients to consider environmental implications of their requirements during new procurements. We have a refreshed toolkit on the intranet. All contracts over the tender threshold must have an EIA and the NZC Lead is now a member of the Commissioning and Procurement Board to advise on Climate Action and other environmental improvement opportunities within new procurements presented at the board which is anything with a whole life value of £250k or more. | N/A |
| Isl 2.1 (new) |  |  | Encourage use of reusable period products | Complete | The Reduce, Reuse, Your Cycle campaign launched in January 2024. It was designed through the application of behavioural science, seeking to increase the purchase and use of reusable period products in north London. The project has involved a holistic approach of outreach workshops, school assemblies, discount codes and digital and out-of-home communications to improve the knowledge of, and access to, reusable period products. Two bursts of comms ran across 2024, with channels including a bespoke, branded campaign website, organic and paid social media, outdoor advertising, media outreach, email marketing and google advertising. The most successful channels were the website, (over 41,000 page views to date) and paid Meta advertising (over 5 million impressions). Evaluation showed that digital communications were the most effective way of reaching audiences, so that will be the focus of the campaign from now on. We have also developed a brand toolkit to share the campaign with interested partners, beginning with East London Waste Authority who are expecting to do an RPP campaign with our branding in 2025. | 42 events have been delivered to date across 7 boroughs, engaging 1,800 members of the public. This included 16 workshops, 4 school visits, 18 engagement stalls, 2 teacher training sessions and 2 ambassador training sessions. 96% of participants said they were likely to recommend RPPs to friends and family, while the most common motivation cited for using RPPs over disposables was the money saved (19% of survey respondents). |
| Isl 3 | Waste reduction | Support community composting | Support community gardening clubs Advice and information Access to compost bins at reduced prices Collections of excess garden waste that can’t practically be managed on site | On track / part complete | Significant work continues to be done as part of the Thriving Neighbourhood programme to support gardening groups and to provide advice and information, and this has enabled the continuation of support for those groups. We have also secured funding from New Build and CIL a dedicated community gardener on the Andover Estate. We are also working with Friends of Parks group to support them with onsite composting options. | 21 Estate based gardening groups or TRAs are being actively supported. Advice and information is being provided to a further 12 groups. More significantly horticultural guidance is being provided to Housing and New Build teams so that more informed and sustainable decisions are taken. For example changing planting specifications so that organic fertilisers of the correct macro and micro nutrients are used, identifying what type of turf contains plastic and so to avoid. Compost bins and leaf bins installed at 8 sites. Six groups using team to remove green waste. Grounds Maintenance team removing green waste for communal gardens. |
| Isl 4 | Waste reduction | Library of Things | Reopen the first Library of Things. Seek funding to support the opening at least one more Library of Things and increase the number of items borrowed | Delayed / on-hold / no progress to date | It has not been possible to reopen a new Library of Things. Several locations have been reviewed including library locations, leisure centres and shopping areas, with none suitable or cost effective. We will continue to review any options that arise. Two ‘Borrow It’ library of things have opened with support from Peabody and Clarion Housing Associations. These facilities are currently targeted at housing association residents. | N/A |
| Isl 5 | Waste reduction | Repair Cafes | Deliver six Repair Cafes during each year | Complete | Our programme of reuse and repair events has continued throughout 2024//25 in partnership with a number of local businesses and community groups. | In 23/25: - 48 events (the target was 12) were delivered over the time of this programme (23/25 - 2 financial years). - Almost 2900 people registered to attend these events and over 1430 took part to swap or repair items. - Approximately 500 pieces of clothing has been repaired or upcycled, - Over 4500 items had been swapped or repaired (clothing, electrical and electronic as well as furniture). - 428 Electrical items had been brought to the Islington Fixers events over the time of the programme with 188 fixed, 136 repairable (advice given how to repair these i.e. spare parts needed) that resulted in almost 500kg CO2e saved. - The events were often the most clicked through items featured in the council bulletins. |
| Isl 6 | Waste reduction | Restricting residual waste | Explore the feasibility of collecting residual waste fortnightly, with weekly collections of recycling, food and garden waste | On track / part complete | The feasibility of collecting residual waste fortnightly is under ongoing review. However, more work needs to be done relating to the practical issues relating to this in a densely populated Borough like Islington, the risks relating to financial benefit and improvement in recycling rates before a move to fortnightly collections can be considered. | N/A |
| Isl 7 | Waste reduction | NLWA Waste Prevention Plan | Work in partnership with NLWA to develop and deliver the NLWA Waste Prevention Plan | Complete | In January 2023 NLWA published Preserving Resources, Driving Change, which sets out NLWA’s approach to community engagement, communications and policy work. The aim for this ambitious programme is to draw on the collective expert experience of NLWA and constituent boroughs, apply behaviour change methodologies, use existing research and test and evaluate approaches as work is developed and delivered. The priorities are to: - Enable communities to deliver change on the ground by providing residents with prevention, reuse, and repair opportunities - Campaign for change - Work in partnership - Educate and inform residents - Support our boroughs - Work with businesses | N/A |
| Isl 7.1 (new) | Waste reduction | Support Goodmine App and service development | Work with Goodmine to support development of waste reuse App | Complete | Officers worked extensively with Goodmine through 2024 to provide advice and support. The App is not yet launched and is subject to further development and testing. | No outcomes to date, pending completion and launch of App. |
| Objective 2: Maximising Recycling |  |  |  |  |  |  |  |
| Isl 8 | Maximise recycling | Recycling ambition for 2030 | Develop further robust and costed proposals for achieving a 40% recycling rate by 2030, which we will agree and begin to implement during the course of this Plan. | On track / part complete | Proposals will being developed for implementation for 2026/27 onwards. Approval has been given for expansion of the food waste service to flats above shops utilising the New Burdens funding. | N/A |
| Isl 9 | Maximise recycling | Recycling site improvements on estates | Invest in improving recycling on estates and ensure that All estates have enough space in their recycling bins so residents can recycle at all times Wherever possible, recycling sites for estate residents are conveniently located within the grounds of those estates Local recycling facilities are kept to at least the Flats Recycling Package standard We engage with residents to help achieve higher levels of recycling on our estates. | On track / part complete | A significant investment and behaviour change is underway to transform the recycling experience across Islington's Council Estates. £2m has been allocated over three years, as part of Islington's 'Thriving Neighbourhoods' estate improvement programme. A small team of three Estate Recycling Officers are delivering a range of recycling, food and waste site infrastructure and capacity improvements, supported with communications and engagement to increase recycling rates. | So far, over £1.2m has been invested in improving recycling facilities for over 4,200 households. Resident feedback has been extremely positive with most residents reporting that the investment has made recycling easier, improved their local estate and either made them recycle the same or more than before. Bin data is also being gathered to monitor recycling rates. Data gathered so far indicates an increase in recycling on sample estates where facilities have been improved and capacity increased. |
| Isl 10 | Maximise recycling | Recycling site improvements on estates | Review on a case by case basis, whether refuse chutes offer the best option for sustainable waste management, and whether alternative recycling and refuse arrangements might help to provide better services and higher recycling rates | Delayed / on-hold / no progress to date | A small cross-service area project team has been established to identify trial areas where withdrawal of refuse chutes may bring benefits, including relating to fire safety and maintenance costs and to identify the correct procedures and learn lessons to be applied elsewhere. However, other priorities have resulted in a delay in initiating this project, while an additional project budget may be required. | No outcomes to date. |
| Isl 11 | Maximise recycling | Make recycling sites more accessible | Include bins with greater accessibility, where appropriate, into proposals for improvements to recycling sites on estates | Complete | Islington’s award winning development of accessible recycling bins are now incorporated into new build recycling site designs, estate recycling improvements, and new planning guidelines. In 2024/25, NLWA and Islington opened a pedestrian drop-off zone at the Hornsey Street RRC to allow cyclists and residents arriving on-foot to make use of the services offered by the RRC. In 2024/25, working with the London Borough of Islington and LEL, NLWA opened a dedicated pedestrian and cyclist zone near the entrance to Hornsey Street RRC. As 67% of Islington households do not own a car or van, this upgrade makes it easier for Islington residents to bring small recyclable materials to the centre and supports the use of low-carbon modes of transport to access RRC services. The new Edmonton EcoPark RRC has an accessible entrance for pedestrians and cyclists to drop off items for reuse and recycling. | Accessible bin are now being included by default in new recycling facilities. The new dedicated drop off zone enables pedestrians to drop-off and recycle nine different material streams and bring books, textiles and bric-a-brac for reuse. |
| Isl 12 | Maximise recycling | Improving the quality of recycling from estates and reducing contamination | Drive down levels of contamination in recycling bins | On track / part complete | Policies are in place to leave contaminated communal recycling bins uncollected and for landlords to be contacted to resolve the situation. Communications materials are offered to landlords to assist. Reverse lidded bins are used by default and investment in improved recycling infrastructure on estates is helping. Routine sampling carried out at the MRF provides valuable data on non-recyclables collected with recycling. | Policies and actions in place mean that no recycling loads have been rejected or downgraded from Islington during 2024/25 and Islington’s non-recycling rate is the lowest of all NLWA Boroughs. |
|  |  |  | direct and targeted behaviour change actions | Complete | The Together We Recycle campaign ran from 28 August to 15 October. The campaign shone a light on what happens to waste after it is collected, aiming to improve the relationship between crews and boroughs, increase recycling tonnage and reduce contamination. | The campaign provided useful messaging and reusable assets, though it wasn’t possible to verify any significant impact. |
|  |  |  | camera systems on our recycling collection vehicles | On track / part complete | Islington is trialling the use of AI technology fitted to vehicle cameras to identify non-recyclable items collected with recycling. This has the potential to automatically identify non-recyclable items, as well as hazardous items such as rechargeable batteries. | The trial has demonstrated the ability to identify the most common non-recyclable items placed in recycling bins. The system is being integrated with bin weighing and bin chipping to effectively identify contaminated bin locations for targeted action. The system continues to be evaluated for its potential to support cost effective interventions to reduce non-recyclables before a decision is made whether to extend the system. |
|  |  |  | contaminated bin policy | Complete | Our Policy for managing contaminated communal recycling bins is in place. | See top of Ref Isl 12. |
|  |  |  | Expand our network of textile and small electrical recycling banks into estates | On track / part complete | A new textile and small WEEE bank has been added to the pedestrian drop-off site at Hornsey Street RRC. A textile banks has been included in new recycling facilities on the Bemerton Estate and is being considered for other estate improvements where suitable. | Around 150kg of textile are being collected monthly from the new site. |
|  |  |  | Separate cardboard recycling bins next to mixed recycling bins | On track / part complete | Islington is working with its main supplier of recycling enclosures to design and trial an entirely new design of enclosure specifically for cardboard which has been specifically developed for Islington. This new design will be tested at a handful of estate recycling locations through 2025. | N/A |
| Isl 13 | Maximise recycling | Food waste recycling for purpose built flats | Extend the food waste recycling service to remaining suitable private blocks and properties managed by social landlords | Complete | All suitable blocks of 7 households and over have communal food waste recycling where there is room to accommodate a food waste bin. | Residents received food waste caddies, instructions, compostable liners and communal food waste bins. The food waste is collected weekly. Tonnage has increase from an average of 57 tonnes per month when the expansion started in Feb March 2021 started to 102 tonnes per month in Jan-March 2024. |
| Isl 14 | Maximise recycling | Food waste for flats above shops | Provide a food waste recycling service to all residents in flats above shops if this is practicable and affordable and in line with any guidance expected from central government as part of its Waste and Resources Strategy | On track / part complete | Following the confirmation of capital and transitional funding from DEFRA, the extension of food waste recycling services to flats above shops is now underway and will be completed by April 2026. Urgent confirmation from the government of promised ‘new burdens’ revenue support funding is requested to ensure there is ongoing financial support to maintain the service. | Islington’s trial food waste collection service for flats above shops (the first of it’s kind in the country) collected: ~100kg collected per week ~0.38kg per household ~20kg per household per year This would equate to ~0.33% added to recycling rate if Borough wide The project however is aiming for 0.5kg per household per week and a contribution to the recycling rate of 0.5%. |
| Isl 15 | Maximise recycling | Recycling for flats above shops | Make it easier for residents living in flats above shops to get hold of recycling sacks, by introducing an online request and home delivery service | Complete | Following deployment of our new back office system, this service is now active for limited flats above shops properties, with the service to be extended to remaining FLASH properties by April 2026. This will support a review of recycling for flats above shops that is being carried out alongside the provision of food waste collections. | N/A |
| Isl 16 | Maximise recycling | Improving recycling in private rented accommodation | Work with social and private landlords to improve recycling: | Delayed / on-hold / no progress to date | This work continues on ad-hoc basis while focus remains on improving recycling facilities for Islington Council estate properties. | N/A |
|  |  |  | provide a range of communications materials and support, including leaflets, posters and template letters to landlords to use; | Complete | Leaflets and posters for use by landlords are available or download from Islington Council's website. | N/A |
|  |  |  | work with landlords to ensure the food waste recycling service is provided for their residents; | Complete | Landlords / managing agents / RSLs have been engaged with to ensure that food waste recycling has been introduced into purpose built blocks where there is room to do so. | Landlords/ managing agents that control purpose built flats now have food waste recycling within where there is room to accommodate the service. |
|  |  |  | require landlords to take responsibility for any non-recyclables in communal recycling bins, providing support where needed, and; | Complete | Our communal recycling bin contaminated bin policy is in place. | N/A |
|  |  |  | If necessary, and as a last resort, use appropriate enforcement measures to require landlords to provide adequate recycling facilities with enough capacity at their properties | Delayed / on-hold / no progress to date | To date, it has not been necessary to progress this action. The property licencing scheme includes clauses to oblige landlords to provide adequate recycling receptacles and the capacity. Furthermore, it requires landlords to ensure that all tenants understand how the waste management service works for their property. | N/A |
| Isl 17 | Maximise recycling | Recycling at markets | Improve levels of recycling at our markets, as well as encouraging reuse and waste reduction, focussing on Chapel Market | Delayed / on-hold / no progress to date | No progress has been made due competing priorities. There are no current plans to progress this. | N/A |
| Isl 18 | Maximise recycling | Plastic bags and wrapping collections | Work with NLWA to ensure that we can collect plastic bags and wrapping material for recycling by 2026-2027 or earlier. | On track / part complete | NLWA are working with the MRF operator regarding options for recycling this material and to establish a compliant and sustainable UK partner to recycle all types of grades of plastic films, to evaluate market options and to find a viable solution to ensure that Boroughs can collect flexible plastics within the timescale set out in Simpler Recycling regulations. Islington is ready to collect this material as soon as the material can be effectively processed for recycling. | N/A |
| Isl 19 | Maximise recycling | Mobile reuse and recycling centre | Develop proposals and seek funding for a mobile reuse and recycling centre, to collect materials that cannot be recycled through the normal mixed recycling route, but which can be recycled with the right recycling arrangement in place | Delayed / on-hold / no progress to date | Proposals for a revised bulky waste collection service and a mobile reuse and recycling centre are still at an early stage due to other competing priorities. In 2023/24, NLWA retendered a contract for the kerbside collection of large WEEE for all boroughs, excluding Haringey and Hackney. | The scheme collected 85 tonnes of WEEE for recycling across the five participating boroughs in 2023/24. |
| Isl 20 | Maximise recycling | Increase reuse and recycling of bulky waste | Develop proposals and seek funding so we can recycle and reuse a greater proportion of the material we collect | Delayed / on-hold / no progress to date | Proposals for a revised bulky waste collection service and a mobile reuse and recycling centre are still at an early stage. Due to other competing priorities. NLWA aims to maximise recycling and reuse opportunities across the seven RRCs to make better use of the materials handled by the authority. In 2024/25, NLWA continued to divert difficult-to-recycle materials from the residual waste bin, capturing even more material than in previous years. Following a trial period in 2023, a recycling facility for hard plastics, such as plastics children’s toys and garden furniture, was introduced at four of NLWA’s RRCs. However, this has since been withdrawn due to a lack of reprocessing markets. The carpet recycling service, originally operating as a trial at South Access Road RRC, was introduced at two more RRCs. NLWA operates a DIY reuse scheme at two RRCs which encourages residents to reuse DIY materials captured across the LEL RRC network, free of charge. In 2024/25, NLWA launched a dedicated disposable vape recycling service across RRCs to promote the safe disposal of these products. | In 2024/25, NLWA saw a 7% increase in the number of mattresses recycled across the RRCs and waste transfer stations compared to last financial year, collecting an average of 8,512 mattresses for recycling every month. Across the NLWA RRCs in 2024/25 the following were recycled: 170 tonnes of hard plastics 213 tonnes of carpet 56% increase in the amount of Expanded Polystyrene (EPS) DIY for reuse increased from 91.8 tons in 2023/24 to 104.2 tons in 2024/25. 108 tons of paint were collected for reuse in 2024/25, up 35 tons compared to 2023/24 830 kilograms of vapes. This is equivalent to approximately 39,500 individual disposable vapes diverted from litter, street and kerbside bins. |
| Isl 21 | Maximise recycling | Increase reuse and recycling of bulky waste | Encourage residents on estates and elsewhere to consider alternative ways of reusing or repairing their unwanted items through effective communications and signposting. | On track / part complete | A project will be developed and delivered in Q2 2025 to trial separate reuse areas on estates, and to signpost residents to effective and convenient reuse options. We are working with suppliers to design and produce a sheltered bulk waste storage option. We are working with communications team to design appropriate signage and communication strategy to reach residents with this message | N/A |
| Isl 22 | Maximise recycling | Behaviour change | Seek funding to deliver a programme of behaviour change, door knocking and community led engagement events that will, over time, help Islington reach its ambition of recycling 40% of household waste | Complete | A major food waste communications campaign was delivered in the second half of 2024. Please see reference to this under Ref Isl 1. | Please see reference to this under Ref Isl 1. |
| Isl 23 | Maximise recycling | Behaviour change – recycling champions | Sign up at least 200 Recycling Champions, with representation from across our communities and housing types | Delayed / on-hold / no progress to date | The Recycling Champions scheme is being reviewed to consider new ways to engage volunteer residents in promoting recycling. | There are currently 114 subscribed 'Recycling Champions'. |
| Isl 24 | Maximise recycling | Behaviour change – incentive scheme | Seek funding to launch a recycling incentive scheme | Delayed / on-hold / no progress to date | We have not yet been able to identify funding to progress this action. | N/A |
| Isl 25 | Maximise recycling | Compulsory recycling | Review enforcement procedures in relation to communal recycling, food and residual waste bins | Complete | Enforcement procedures have been reviewed. Changes to the relevant legislation has made our common sense compulsory recycling policy difficult and time consuming to enforce. Alternative legislative options are now being used in relation to non-recyclables being placed in communal recycling bins. Further enforcement options remain limited, time consuming, costly and likely to be limited in their effectiveness. | N/A |
| Isl 26 | Maximise recycling | Recycling in and from parks | Trial the provision of litter bins with compartments for recyclable material and if these trials are successful, we will start to provide recycling bins for parks across the Borough | Complete | There are now 65 of dual litter/recycling bins in our parks with 10 more on order. We continue to expand the numbers based on available funds. We have also started to receive the new parks cleansing vehicles which have separate compartments to allow duel-collection of waste and recycling. Further improvements in parks litter recycling are being reviewed at larger sites, such as Highbury felds. | Operational feedback on the use of the bins indicate improved levels of recycling, reduced levels of contamination and improved operational efficiency and convenience. |
|  |  |  | Ensure that the compostable material from parks and tree maintenance is composted, either on site, or through local composting facilities | Complete | Green waste from local parks is either composted on site, or brought to the Hornsey Street Waste and Recycling Centre for onward transportation to an NLWA composting facility. | N/A |
| Isl 27 | Maximise recycling | Commercial waste recycling | Implement our Commercial Waste Strategy including Promotion of recycling and food waste service to current and potential customers Delivery of process, reporting and customer experience improvements to ensure high quality service delivery Delivery of engagement and education activities to local businesses | On track / part complete | The commercial waste service continues to work hard to increase its customer base, and in particular to increase the proportion of contracts and amount collected that relates to recycling. The differential in disposal costs for residual waste, mixed dry recycling and, in particular, food waste, provides and incentive for increased levels of commercial waste recycling. The service recycling target has been amended to 28% for 2024/25. | 27% recycling rate for 2024/25 33% market share |
| Isl 27.1 (new) | Maximise recycling | NLWA Joint Waste Strategy (JWS) | Work in partnership with NLWA and Boroughs to support the development of the NLWA Joint Waste Strategy (JWS) | Complete | The new North London Joint Waste Strategy has been developed over the past three years, with writing beginning in early 2023, led by NLWA in collaboration with the north London boroughs. It is a joint Strategy across all eight partners. A public listening exercise was undertaken in summer 2023 to understand north London residents’ priorities, which has fed into the drafting of the strategy. This was followed by a formal public consultation on the draft Strategy undertaken between November 2024 and January 2025. These engagement pieces reflected diverse views across north London’s communities and show robust findings in support of the content of the Strategy. Following the public consultation exercise, NLWA produced a revised version of final draft of the Strategy, taking into account the responses to the consultation surveys, comments from north London environmental groups, feedback from the Greater London Authority (GLA) and from the borough scrutiny committees. The changes made to the Strategy have been shared with the Joint Waste Strategy Evaluation Group and borough officers and members. Their comments and feedback have been further incorporated into the draft document. Once the document is finalised, each of the individual boroughs and NLWA will be asked to take a decision under their own governance arrangements to approve the final draft in summer 2025 (the majority at Cabinet meetings). Assuming each borough and NLWA gives this subsequent approval, this will commit each to the content of the Strategy. Finally, NLWA will adopt the Strategy as NLWA policy (programmed for an NLWA authority meeting in late 2025). | N/A |
| Isl 27.2 (new) | Maximise recycling | Textile bank contract | Textile bank retendering | Complete | We now have new contractual arrangements in place enabling us to carry on with the current arrangement until end of 25/26. | The textile bank collects around 262 tonnes of textiles each year. |
| Isl 27.3 (new) | Maximise recycling |  | Communications events | Complete | The team have attended 31 events in 2024/25, engaging directly with around 1000 residents. This is in addition to the wide range of other communications activities and campaigns undertaken both by Islington and NLWA and wider campaigns that we support. | 31 events attended. ~1000 residents engaged with. |
| Isl 27.4 (new) | Maximise recycling | Community and schools engagement | There are many active and vibrant community and resident groups across Islington, including voluntary, faith based and cultural organisations and schools and we will (together with our partners in NLWA) engage with these groups to raise awareness of recycling and encourage these groups to raise awareness of recycling among their communities. | On track / part complete | Islington has a recruited a new Schools Recycling Education Officer who is working with schools across Islington. The posts objectives are: - To ensure that effective and compliant recycling and waste reduction systems are in place in all schools and promoted to support their usage - To support and amplify the North London Waste Authority education programme - To devise and deliver a programme of age appropriate educational workshops to primary and secondary schools in line with the national curriculum and climate change policies - Promote and advise on schemes that to help reduce waste in schools - Promote recycling and waste minimisation within homes through engagement with schools and pupils In the Know Launched in September 2024, In the Know is NLWA’s innovative outreach programme for primary schools. Over the past year, officers have collaborated with seven schools to elevate the importance of waste prevention and the circular economy. This initiative has included engaging assemblies, interactive staff workshops, thorough waste audits, and insightful senior leadership and subject sessions. In its first year, the programme has successfully engaged over 2,600 pupils and staff. Schools worked with during the 2024/25 year are: - Barnet: Monkfrith Primary School - Camden: Rosary Catholic Primary School - Enfield: Merryhills Primary School - Hackney: Parkwood Primary School - Haringey: Ferry Lane Primary School - Islington: Ambler Primary School - Waltham Forest: Parkside Primary School Building on this initial success, officers are doubling the programme’s capacity, working with 14 primary schools from September 2025. In its second year, the programme will introduce CPD sessions for subject leads, facilitating an exercise to map the national curriculum against waste and the circular economy, and identify opportunities to enhance in-school teaching. In March 2025, officers developed a partnership with the Lightyear Foundation to ensure all NLWA school activities are inclusive. Over the coming year, officers will collaborate with a local Specialist school for students with Special Educational Needs and Disabilities (SEND) to co-design a new workshop. Education Hub NLWA’s Education Hub, an online resource hub for pupils and teachers, has also been revitalised. The Hub now features a wealth of bespoke resources tailored to north London, including ready-to-go lesson plans. Initially developed for primary schools, the Hub now boasts a new secondary area, complete with a series of career profiles that highlight how a background in science can lead to careers in waste management. In the coming year, we will continue to expand the Education Hub, adding more resources and exploring opportunities to signpost students towards work experience, volunteering, and apprenticeship opportunities. Other school activity Additionally, NLWA ran a photography competition for secondary schools across the seven boroughs. The theme, ‘Nature’s Resilience’, invited students to capture moments of nature reclaiming spaces or recovering from human activity as studies have shown that connection to nature can increase engagement in waste prevention behaviours. The competition saw 46 students from 16 schools participate, with a winner and two runners-up selected. Their artwork will be proudly displayed at EcoPark House during the Opening Ceremony. | The officer started in Islington in February 2025, so there are no specific outcomes. |
| Objective 3: Reducing Environmental Impact |  |  |  |  |  |  |  |
| Isl 28 | Reduce environmental impact | Emissions Performance Standard | Use the EPS tool to monitor the impact of our waste and recycling operations. | Cancelled | The use of the EPS tool has not been continued. The model is too complex to provide to be kept up to date and Islington does not have the resource or expertise to use the tool. Changes to Islington’s waste management arrangements are not likely to generate a meaningful change to the EPS output. | N/A |
| Isl 29 | Reduce environmental impact | Fleet emissions – electric vehicles | All of our recycling and refuse fleet will be zero tailpipe emissions by 2030. | On track / part complete | Of the 64 vehicles allocated to our waste operations currently 23 are full battery electric vehicles (BEV). Of these 23 vehicles 11 are RCVs 18t or over. The vehicle fleet of NLWA’s current main waste transfer, treatment and disposal contractor, LEL, and those of LEL’s subcontractors are all ULEZ compliant. From 2022, all vehicles are Euro VI, leading to a significant reduction in NOx emissions. | 11 different RCVs utilised across different collection operations has given the opportunity to test how full BEV RCVs operate in real world conditions and has allowed the gradual introduction of electric vehicles across waste operations. The vehicles have also been able to deliver improved environmental performance with zero tail pipe emissions as well as cost reductions in fuelling of vehicles. |
|  |  |  | all new cars and vans (less than 3.5 tonnes) will be zero emission from 2026 | On track / part complete | We have already committed to all new cars under 3.5t being BEV as per the latest Fleet procurement strategy 23-26. Currently total fleet that is BEV stands at 22%. However, this includes 99 vehicles currently on-hire. Of the total owned fleet the percentage of BEV grows to 27%. With the current planned vehicle purchases over the next 2 years the total owned fleet increases to 30% (an additional 30 BEVs are currently on order). The reason the number of BEVs may not reach the target is due to an increased number of hired vehicles and pressure on available funds for the procurement of electrical vehicles which has slowed down the rate of vehicle replacement. | The impact of this action is that it will deliver a fleet of vehicles which provide a wide-array of environmental benefits. BEV reduce both local air pollution and carbon dioxide emissions by being zero emissions at the tailpipe. There are also wider benefits in the operation of these vehicles including less noise pollution, reduced health impacts to drivers operating the vehicles and likely operational cost reduction in reduced fuelling and maintenance costs |
|  |  |  | all heavy goods vehicles (greater than 3.5 tonnes) will be fossil fuel-free from 2030 | On track / part complete | Significant progress has been made on transitioning HGVs to BEV. To date the number of electric vehicles in the HGV class include: 11 x RCVs, 6 x 7.5t cage tippers, 6 x Accessible community transport buses & 3 x 4.5t street sweeper | The impact of this action is that it will deliver a fleet of vehicles which provide a wide-array of environmental benefits. BEV reduce both local air pollution and carbon dioxide emissions by being zero emissions at the tailpipe. There are also wider benefits in the operation of these vehicles including less noise pollution, reduced health impacts to drivers operating the vehicles and likely operational cost reduction in reduced fuelling and maintenance costs |
|  |  |  | no fossil fuelled vehicles of any size will be purchased after 2030 | Complete | This commitment has already been established. In the latest fleet procurement strategy 23-26 the council has committed to only purchasing battery electric vehicles from now on. | Please see comments above. |
| Isl 30 | Reduce environmental impact | Fleet emissions – electric vehicles | Complete the vehicle charging infrastructure upgrade at the Waste Recycling centre | Complete | Action completed | The completion of this action has enabled the council to pursue it's programme of electrification for the fleet. The new upgrade provides the electrical infrastructure to enable the electrification of all HGV vehicles (and others) at the council's primary depot. This ensures frontline service vehicles of all types can be transitioned to electric by 2030 |
|  |  |  | Work with vehicle manufacturers who have vehicle to load capabilities in their vehicles | On track / part complete | This is an ongoing action but we continue to work with manufacturers who are implementing vehicle to load and vehicle to grid. Two previous V2L vehicles have been upgraded to V2G and have been used on megawatt charging system to discharge energy to grid. We also have an active trial of AC V2G systems operating at council sites to ensure we are keeping up-to-date on both AC and DC V2G systems. | The completion of this action ensures that as we transition to a full electric fleet we are able to make use of the latest and best technologies. In the case of V2L this ensures battery capacity of vehicles can be utilised intelligently to reduce the overall energy demand that would be required at our main depot. This is part of a suite of technologies including renewable generation and zero emission heating that can be used to intelligently manage the council's overall energy demand. |
|  |  |  | Use solar panels as an energy source to store power either directly back to vehicles or within the battery storage system on vehicles | Complete | Solar PV at our main site the Waste & Recycling Centre is used to offset the buildings total power demand including power used to charge vehicles so renewable energy is used in vehicle charging. Solar energy is now being generated by the Edmonton EcoPark solar array located on the roof of the RRF. 2,235 photo voltaic panels cover the size of a football pitch and generates energy that is distributed to the EcoPark for waste operations and construction commissioning activities. Up to and including Sunday 4 May, the power produced by the solar panels totaled 759,123.47 kWh with an average kWh per day of 1668.4. 2 June 2024 saw the highest power producing day in the past 12 months. | The completion of this action ensures that as we transition to a full electric fleet we utilise all energy intelligently to reduce the overall energy demand that would be required at council sites delivering both environmental and financial benefits. |
|  |  |  | Install smart chargers which can charge vehicles and install fast and rapid chargers across all main council buildings | On track / part complete | This is an ongoing action but we continue to install a range of smart chargers across all council sites. We currently have 73 smart chargers installed across 10 locations. We have recently started to utilise smart charging functionality to test how we can best reduce the financial and carbon impact from our electric vehicle charging. | The delivery of this action is central to the delivery of the overall electrification programme ensuring that the most appropriate charging technology is introduced alongside vehicles to ensure the transition to electric vehicles is smooth and limits any operational impact of transitioning to a new vehicles technology. |
| Isl 31 | Reduce environmental impact | Fleet safety | Join the DVSA Earned Recognition Scheme | On track / part complete | It remains Islington’s aim to join the Scheme. This will be progressed once other critical fleet operational and system updates have been completed. A pre-audit inspection took place in April 2025 and Officers are reviewing and actioning the outcomes. | By joining the Earned Recognition scheme the council would further demonstrate that it is operating its fleet and managing its drivers in a way that leaves a minimum environmental impact, ensures the safe operation of the fleet and upholds the council's reputational responsibility. |
| Objective 4: Maximising local waste sites |  |  |  |  |  |  |  |
| Isl 32 | Maximise local waste sites | Waste management facilities | Continue to work in partnership with NLWA and the constituent Boroughs to deliver the waste management infrastructure needed to manage the waste we collect | On track / part complete | NLWA are replacing the current energy from waste facility at Edmonton EcoPark to continue to provide a responsible solution for the waste that is not recycled in north London. The new Energy Recovery Facility is currently under construction and will deliver a modern waste treatment plant with the cleanest and safest technology for controlling emissions. It contributes to a wider district heat network to ensure boroughs receive the most value out of the waste that is collected and improves the de-carbonisation of the energy produced. The new facility will meet the new requirements for permitting new facilities set out in Defra's residual waste capacity note published in December 2024. In 2024/25, construction of new facilities under the NLHPP continued, including the new Energy Recovery Facility (ERF). As of the end of 2024/25, LondonEnergy Limited (LEL) has completed the internal process to transfer the management of the RRF and RRC from construction to BAU operations, principally governed by the EcoPark South Operational contract. | The ERF will have the capacity to manage 700,000 tonnes of residual waste from the seven north London boroughs, future-proofing north London’s waste management infrastructure for a growing population. |
| Isl 33 | Maximise local waste sites | Waste management facilities – bulky waste pre-treatment | Support NLWA with the development of new treatment facility for bulky and other waste streams at Edmonton Ecopark | Complete | In April 2024, the Resource Recovery Facility (RRF) began accepting borough vehicles, ramping up to full operations and enabling it to function as a modern waste management facility. | In its first year of full operation, around 170,000 tonnes were processed through the facility including residual waste, bulky waste, food waste and garden waste. The expanded capacity of the RRF provides provision for north London to double its food waste collection ability, ahead of the planned compulsory food waste service for all residents across England by April 2026. |
| Isl 34 | Maximise local waste sites | Reuse and Recycling Centre, Edmonton Ecopark | Support NLWA with the development of a new Reuse and Recycling Centre at Edmonton Ecopark | Complete | The Edmonton EcoPark Reuse and Recycling Centre opened to the public in July 2024. It is the first major public facility delivered as part of the Project and allows north London residents to bring their recycling directly to the EcoPark for the first time. As the site enters BAU operation, NLWA are working with LondonEnergy Ltd to review opportunities to expand the reuse and recycling offer at the site. | In the first nine months of its opening, more than 16,000 vehicles visited the centre and around 1,700 tonnes of waste have been deposited by residents for reuse, recycling and recovery. |
| Isl 35 | Maximise local waste sites | Pre-treatment of residual waste | Work with NLWA to review of options for pre-treatment of residual household waste | On track / part complete | Space has been allocated to the new RRF to support recycling and reduce waste. In 2024/25, NLWA engaged consultants to conduct a review of existing mixed waste sorting operations in other countries to understand what might be possible in north London. Officers will use the findings of this report, along with knowledge of other innovations in the waste sector, to determine how best this space could be used to increase recycling and reduce the carbon impact of the residual waste stream. | N/A |
| Isl 36 | Maximise local waste sites | Education and visitors centre, Edmonton Ecopark | Support NLWA to deliver a new education and visitor centre contract | Complete | EcoPark House, NLWA’s new visitor and education centre, was opened to the public and welcomed its first school visit in 2024/25. As a sustainably built community asset, an educational facility and new home of the Edmonton Sea Cadets, EcoPark House will provide events catering to NLWA's key target groups: schools, community groups and north London’s residents. Having this permanent base at the EcoPark provides a long-term home for the highly successful NLHPP schools programme to provide social value to north London’s schools long after construction on the NLHPP ends. | N/A |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP or 2023/24 annual update.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Isl 37 | Development of a new Reduction and Recycling Plan from 2026 | Development of a new Reduction and Recycling Plan from 2026 in line with GLA guidance | n/a | Approval in summer 2026 |
| Isl 14 | Food waste for flats above shops | Provide a food waste recycling service to all residents in flats above shops if this is practicable and affordable and in line with any guidance expected from central government as part of its Waste and Resources Strategy | Islington’s trial food waste collection service for flats above shops (the first of it’s kind in the country) collected: ~100kg collected per week ~0.38kg per household ~20kg per household per year This would equate to ~0.33% added to recycling rate if Borough wide The project however is aiming for 0.5kg per household per week and a contribution to the recycling rate of 0.5%. | By April 2026 |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| n/a | Simper Recycling | Islington is already complying with most of the Simpler Recycling requirements. Food waste recycling will be provided to all remaining properties by April 2026. A written assessment will be undertaken in line with the requirements and within the required timeline. | n/a | n/a |