| Report title |  |
| --- | --- |
| Financial Position as at the end of December 2018 |  |
| Report to | Date |
| - Corporate Services DB - Commissioners BoardFire and Resilience Board | 22 January 2019 30 January 201912 February 2019 |
| Report by | Report number |
| Assistant Director, Finance | [LFC-0000] |
| Protective marking: NOT PROTECTIVELY MARKED Publication status: Published in full |  |

Summary

This report presents the London Fire Commissioner’s (LFC) financial position as at the end of December 2018 (Quarter 3). It provides information on financial performance against revenue and capital budgets.

- Recommended decision

- That the report is noted.

- To agree a revised capital budget for 2018/19 of £12,058k to reflect the net project slippage and changes of £29,207k as detailed in paragragh 33 below. The changes to future years budget will be reflected in the final 2019/20 budget report in March 2019.

- To agree the transfer of the initial capital receipt of £11,745k  for the sale of the former Southwark Fire Station to the Capital Expenditure Earmarked reserve. The accounting treatment for this additional income is being clarified with the external auditors and will be updated in the outturn report if required.

Background

- This report considers the financial position as at the end of December 2018, including a forecast of outturn at the financial year end.

- All departments review their actual income and expenditure on a regular basis, and provide an updated forecast of outturn and explanation of variances, against all their budgets, to the Finance Department. These returns then form the basis of reporting to the Corporate Service’s Directorate Board and from there on to the Commissioner’s Board.

Background to 2018/19 Budget

- The 2018/19 budget was approved by the previous Authority at its meeting on 29 March 2018 (FEP2825) and adopted as the budget for the London Fire Commissioner for 2018/19, with a net revenue budget of £401,087k. The budget included funding of £2,081k from earmarked reserves, £12,205k from specific grants as well as savings of £2,210k.

- This report sets out a summary position on both the revenue and capital budgets, and then provides more detailed explanations of variances.

- Revenue

- The forecast outturn position for 2018/19 on the revenue budget is an underspend of £2,505k (0.6%). The forecast underspend has decreased by £548k since last reported at Quarter 2 (LFC - 0084). The decrease in the underspend is mainly  due to additional expenditure against building maintenance budgets of £1,064k  due to the decision to progress a backlog of works aimed at improving the overall condition of the whole estate, including repairs, refurbishment and minor improvements to properties.This is offset by an increase to the forecast underspend on property rates (£784k) due to further successful appeals and revised rateable values for future year.

- There is additional spend on firefighter trainees of £375k to support reaching full establishment in 2019/20; a reduction in forecast customer and client receipts, largely due to the decision to fund community safety initiatives from departmental underspends in 2018/19 and carry forward any income received (£302k) by transferring it into an earmarked reserve; and an increase in the forecast overspend on compensation budgets of £341k, largely due to two historic mesothelioma cases. This is offset by an increase in the forecast underspend on FRS staff (£463k) and Operational staff (£262k) based on staffing numbers as at the end of December.

- As previously reported, the forecast underspend, now £2,505k, includes an underspend of £1,796k on operational staff budgets, based on expected operational staff numbers, reflecting forecasts for recruitment and leavers. There are also significant forecast underspends of £1,791k on FRS staff budgets  (increased by £463k since last reported) due to the number of vacant posts; £2,000k on property rates (increased by £784k since last reported) following further success in rate valuation appeals, completed with the estates management consultant, offset by additional spend of £1,721k on other Premises budgets (increased by £657k since last reported); and £541k on vehicle passthroughs due to a forecast lower number of repairs, and abatements on the vehicle and equipment contract (increased by £140k since last reported). This underspending is offset by additional overspends on compensation budget as set out above, and as previously reported on Employee related budgets of £1,360k mainly due to previously reported  expenditure to procure additional firefighter trainee courses at the Fire Service College, in order to achieve full establishment in 2019/20; on premises security (now £205k) due to extending security costs for surplus sites in Southwark, Mitcham, Clerkenwell and Lambeth; on energy costs (now £256k) due to increasing wholesale costs and changes to supply arrangements; and on rental costs (£140k) due to an increase for the ICT recovery site at Woking, additional payments at Northolt and Stanmore related to a telecommunications installation and the temporary cost of secure storage for museum exhibits.

- The key variances are explained in more detail from paragraph 12 below.

- Capital

- The 2018/19 approved capital programme (FEP 2825) was reviewed and updated following the 2017/18 outturn as well as being reviewed as part of in year budget monitoring.  A net budget change of £29,207k has been  proposed to reflect the current financial position. The change includes slippage, savings, new budgets and the removal of overprogramming which has been reported in Quarter 1 and 2 and also includes the changes for Quarter 3 as detailed below. There is a reduction £1,924k since last reported as at Quarter 2. The summary position is detailed in the table below. Additional detail on the capital programme is set out from paragraph 33 and detailed information on the variances is set out in Appendix 2 of this report.

- Summary Capital Expenditure Position

|  | Current Budget £000s | Current Spend £000s | Forecast Outturn Qtr 3 £000s | Previous Forecast Outturn Qtr 2 £000s | Movement from Qtr 2 Forecast £000s |
| --- | --- | --- | --- | --- | --- |
| ICT | 5,385 | 101 | 647 | 1,260 | (613) |
| Fleet & Equipment | 23,287 | 6,074 | 8.343 | 9,554 | (1,211) |
| Estates | 11,834 | 1,495 | 3,068 | 3,068 | 0 |
| Training Centre | 7,445 | (84) | 0 | 100 | (100) |
| Overprogramming | (6.686) | 0 | 0 | 0 | 0 |
| Total | 41,265 | 7,586 | 12,058 | 13,982 | (1,924) |

- The sale of the former Southwark Fire Station was completed at the end of December. The capital receipt has already been allocated as part of the current capital programme.

- Tables and Appendices to this report

- A number of tables and appendices provide additional detail on the financial position, as follows:

  - Table 1 provides a summary of the financial position for the revenue budget;

  - Table 2 provides the latest position on reserves;

  - Appendix 1 contains additional detail on the current and forecast financial position;

  - Appendix 2 reports on the forecast outturn on the capital programme;

  - Appendix 3 discusses the risks to the revenue and capital position that have not been quantified;

  - Appendix  4 meets the requirement to disclose all budget virements within the quarter under the LFC Scheme of Governance;

  - Appendix 5 provides an analysis of outstanding debt relating to charges for Shut in Lift attendances; and

  - Appendix 6 provides an update on expenditure approved in the Additional Resilience Requirements report (FEP2763).

- Table 1. Summary Financial Position

|  | Current Budget | Current Spend | Current Variance | Revised Budget | Forecast Outturn | Forecast Outturn Variance | Previous Forecast Outturn Variance | Movement between variance figures |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | £000s | £000s | £000s | £000s | £000s | £000s | £000s | £000s |
| Operational staff | 178,534 | 175,827 | (2,707) | 240,800 | 239,003 | (1,796) | (1,909) | 113 |
| Other staff | 41,666 | 42,250 | 584 | 57,222 | 55,776 | (1,446) | (1,136) | (310) |
| Employee related | 21,780 | 21,817 | 38 | 23,128 | 24,488 | 1,360 | 1,039 | 321 |
| Pensions | 15,426 | 15,369 | (58) | 20,445 | 20,435 | (10) | 146 | (156) |
| Premises | 32,840 | 31,520 | (1,320) | 38,048 | 38,066 | 18 | (174) | 192 |
| Transport | 15,560 | 15,445 | (115) | 16,363 | 15,857 | (506) | (318) | (188) |
| Supplies and services | 23,557 | 27,548 | 3,991 | 29,271 | 29,529 | 258 | 136 | 122 |
| Third party payments | 1,346 | 1,609 | 263 | 1,882 | 1,938 | 55 | 77 | (22) |
| Capital financing costs | 1,725 | 1,719 | (5) | 9,770 | 9,450 | (320) | (514) | 194 |
| Central contingency against inflation | 0 | 0 | 0 | 215 | 5 | (211) | (55) | (155) |
| Total revenue expenditure | 332,434 | 333,105 | 671 | 437,145 | 434,548 | (2,597) | (2,707) | 111 |
| Other income | (34,857) | (35,507) | (649) | (37,572) | (37,654) | (81) | (540) | 458 |
| Net revenue expenditure | 297,576 | 297,598 | 21 | 399,573 | 396,894 | (2,678) | (3,247) | 569 |
| Use of earmarked reserves | 0 | 0 | 0 | 11,937 | 12,187 | 250 | 250 | 0 |
| Financing Requirement | 297,576 | 297,598 | 21 | 411,510 | 409,082 | (2,428) | (2,997) | 569 |
| Financed by: |  |  |  |  |  |  |  |  |
| Specific grants | (11,957) | (16,980) | (5,023) | (13,040) | (13,117) | (77) | (56) | (21) |
| GLA funding | 0 | 0 | 0 | (398,470) | (398,470) | 0 | 0 | 0 |
| Net Financial Position | 285,620 | 280,618 | (5,002) | 0 | (2,505) | (2,505) | (3,053) | 548 |

Reasons for the Revenue Position

- Staff

- The budget for operational staff is forecast to underspend by £1,796k. This has decreased slightly by £113k from the Quarter 2 forecast position due to an increase in the forecast spend on firefighter trainees, offset by a revised forecast underspend on staff based on latest estimates. The latest forecast for operational staff numbers shows an average of 172 vacancies this year, against the budgeted vacancy margin of 84 vacancies.

- FRS staff budgets are forecast to underspend by £1,791k, 3.5% of the revised budget. There is an additional underspend of £463k from the position reported at Quarter 2 due to the continuing high level of vacant posts, with 148 vacant at the end of December, 16% of the establishment. There were 93 agency staff at the end of Quarter 3, partly offsetting underspend caused by the vacancies.

- Control staff budgets are forecast to overspend by £345k, an increase of £153k since last reported (LFC – 0084) due to additional overtime payments required to continue the current staffing model of eleven Control Officers per watch in order to maintain operational resilience.

- Employee Related

- There is an overspend forecast on employee related budgets of £1,360k, which has increased by £321k from the position at Quarter 2, largely due to the increase in the forecast spend on compensation (£341k) due to two historic mesothelioma cases and smaller increases in recruitment (£46k) and severance (£37k) forecasts. This is offset by an additional underspend on staff development budgets (£109k)  because a number of work streams on staff development schemes have not started yet and will therefore not incur expenditure this year. The remainder of the overspend includes previously reported expenditure to procure additional firefighter trainee courses at the Fire Service College (£899k), in order to achieve full establishment in 2019/20, and a revised forecast overspend on compensation budgets (£588k) offset by a revised forecast underspend on development budgets (£313k).

- Firefighter Pensions

- Firefighter pensions budgets include expenditure on injury pensions, ill health top ups and sanction charges, and are forecast to underspend by £10k in 2018/19. This is because there is now a forecast underspend on injury pensions (£200k) due to medical reviews and mortality which offsets the previously reported overspends on the budgets for ill health top ups (£148k) and sanction charges (£40k) this year.

- Premises

- Premises budgets are forecast to overspend by £18k, an increase in expenditure of £192k from a forecast underspend at Quarter 2. This is due to an increase in forecast expenditure on maintenance contracts of £1,064k due to the decision to progress a backlog of works aimed at improving the overall condition of the LFC estate, including repairs, refurbishment and minor improvements to properties. This is offset by an increase to the forecast underspend on property rates (£784k) following further successful appeals, with revised rateable values going forward. The forecast rates underspend is now £2,000k. There is also a forecast underspend on the facilities management contract with KBR (£231k) mainly due to KPI credits (£200k), as well as lower spend through the Intelligent Contact Centre, the cost of which is dependent on the number of work orders raised.

- The forecast outturn includes previously forecast overspends on premises security (£205k) due to extending security costs for surplus sites in Southwark, Mitcham, Clerkenwell and Lambeth, energy costs (£256k) due to increasing wholesale costs and changes to supply arrangements, and rents (£140k) due to an increase in rental cost for the ICT recovery site at Woking and additional payments at Northolt and Stanmore related to a telecommunications installation.

Transport

- Transport budgets are forecast to underspend by £506k, an increase of £188k since last reported. This is due to previously forecast underspends on the vehicle and equipment contract (now £300k) based on forecast abatement levels, on vehicle passthroughs (now £241k) due to delays to modifications programmes and a lower forecast cost of accident repairs, and on operational fleet insurance (£188k) due to lower premium cost. These are offset by the previously forecast overspend on fuel budgets (£191k) due to the rise in fuel prices and an increase in average usage.

Supplies and Services

- There is a forecast overspend of £258k on supplies and services budgets. Forecast expenditure has increased by £122k from the position reported at Quarter 2. The increase in forecast expenditure includes additional spend on operational equipment (£197k) largely due to a higher level of face mask requiring replacements  and a high level of replacement pads required on breathing apparatus harnesses, which have been in service for up to 8 years and are starting to fail; on professional services (£103k) mainly  due to overspends on portable hygiene unit costs, offset by £117k on smoke alarms budgets due to lower cost of alarm hardware per unit and an increased effort to replace faulty units at suppliers cost, and a slight underspend on clothing budgets of £73k.

- As previously reported, the remainder of the forecast overspend above relates to  professional services (£204k) due to expenditure to set up a people services service centre and on legal services, on hardware and software budgets (£229k) due to additional one off expenditure funding improvements to a range of ICT products including on a wallboard at Merton, improvements to Sharepoint and Farynor and printers at Union Street. These are offset by the previously reported underspend on hydrant maintenance budgets (£250k) due to difficulties encountered in the recruitment of qualified Hydrant Technicians resulting in a lower number of referrals to water companies.

Capital Financing

- There is a forecast underspend of £320k on capital financing costs based on the outturn capital expenditure in 2017/18, and reflecting the expected level of capital receipts being achieved in the current financial year. This has reduced from the previous forecast by £194k due to an update to the forecast minimum revenue provision for long term borrowing which has now been finalised for this financial year.

Income

- There is a forecast over recovery of £81k on income, a decrease of £458k from the forecast reported at Quarter 2. This reduction is due to a revised forecast on community safety income with spend on LIFE, cadets and crossfire initiatives being funded from the Fire Safety underspend (£302k), and a reduction in the forecast MFB Act income (£200k) due to a refund being due to an insurer after identifying an error in their return.

2019/20 Budget Update

- The Mayor’s Consultation Budget for 2019/20 was published in December 2018 and set out the Mayor’s proposed Revenue and Draft Capital Strategy for LFC, and presents a financially balanced budget for 2019/20. That report also included additional funding of £9.8m for the LFC over the next four financial years to 2022/23, reducing the budget gap to £14.6m over that period. The final budget for 2019/20 will be agreed by the LFC in March 2019. As part of the review of the budget variances set out in this report, consideration is given as to whether an ongoing saving is achievable. Where additional savings can be made they will be included in the final 2019/20 Budget report.

Position on Reserves

- The forecast position on reserves is set out in Table 2 below. Movements on the reserves applied in year together with the underspend for the year, lead to a forecast balance on the general reserve at the year end of £20,245k. This is £6,260k in excess of the stated minimum level of £13,985k, which is 3.5% of the net revenue expenditure budget.

- In the previous year the excess balance was transferred to the Budget Flexibility reserve to support the budget in future financial years, and this is also the intention in the current year but will be confirmed as part of the year end process.

Table 2. LFC Reserves for the 2017/18 Financial Year

| £000s | Opening Balance at 01/04/18 | Approved Movements | Underspend/ (Overspend) in 2018/19 | Use of Reserves in 2018/19 | Transfer between Reserves | Anticipated Balance at 31/03/19 |
| --- | --- | --- | --- | --- | --- | --- |
| Additional Resilience Requirements | 4,773 | (2,904) |  | (1,101) |  | 767 |
| Capital Expenditure Reserve | 0 | 0 |  | 11,745 |  | 11,745 |
| Community Safety Investment Fund | 101 |  |  | (101) |  | 0 |
| Compensation | 1,000 |  |  | 0 |  | 1,000 |
| Emergency Services Mobile Communication Programme | 178 |  |  | (57) |  | 121 |
| Emergency Medical Response | 830 | (536) |  | 0 |  | 294 |
| Firefighters' Pension | 1,172 | (1,172) |  | 0 |  | 0 |
| Fire Safety and Youth Engagement | 909 |  |  | (194) |  | 715 |
| Hazardous Material Protection | 18 |  |  | (18) |  | 0 |
| HMICFRS inspection regime | 0 | 149 |  | (128) |  | 21 |
| Hydrants | 462 |  |  | 0 |  | 462 |
| ICT Development Reserve | 1,310 | 600 |  | (750) |  | 1,160 |
| LFB Museum Project | 0 |  |  | 210 |  | 210 |
| London Resilience | 2,250 | (1,113) |  | (173) | (100) | 865 |
| London Safety Plan Initiatives | 4,635 |  |  | (557) | 100 | 4,178 |
| New Governance Arrangements | 300 |  |  | (300) |  | 0 |
| Organisational Reviews | 0 | 168 |  | 0 | 50 | 218 |
| Pension Early Release Costs | 400 | (400) |  | 0 |  | 0 |
| Property PFI | 1,912 | (1,912) |  | 0 |  | 0 |
| Recruitment/ Outreach | 418 | 83 |  | (380) | 250 | 370 |
| Sustainability | 235 |  |  | 0 |  | 235 |
| Vehicle & Equipment Reserve | 1,163 | 2,123 |  | (421) |  | 2,865 |
| Budget Flexibility | 11,469 | 7,229 |  | 4,413 |  | 23,110 |
| General | 20,356 | (2,315) | 2,505 |  | (300) | 20,245 |
| Total | 53,890 | 0 | 2,505 | 12,187 | 0 | 68,582 |

- The reserves table above includes the use of the Additional Resilience reserve that was established to meet forecast costs in 2017/18 arising from an initial assessment of the LFB additional resources requirement following the Grenfell Tower fire and terrorist incidents in 2017 (FEP 2763). £1,984k was spent in 2017/18 with the balance carried forward to 2018/19. The forecast use for this year includes expenditure of £425k on increases to the establishment in Fire Safety and £676k for additional legal investigation costs. £89k was forecast for spend on Fire Escape hoods, but this will now be funded from underspends, with the balance being carried forward to fund the cost of half masks now identified in 2019/20. £190k forecast for wicking t-shirts for station based staff is not expected to be incurred in this financial year, as work to clarify the requirement and specification is carried out, and so this funding will be carried forward to 2019/20. The remainder of the reserve will be spent on one-off costs associated with  training on the additional resilience equipment in 2019/20. Appendix 6 provides detailed information on the additional resourcing costs, and includes the forecast spend for 2018/19 and the budget for 2019/20 and future years.

- Other drawings from earmarked reserves in 2018/19 include:

- £750k from the ICT development reserve to fund re-phased expenditure from 2017/18,

- £557k for implementation of the London Safety Plan (LSP) 2017, including £502k for community safety pilots, and £55k for the staff surveys,

- £280k from the vehicle and equipment reserve to fund chargepoint implementation costs and £141k for the Ultra Low Emission Fleet (ULEF) programme ,

- £380k to support the recruitment outreach programme,

- £300k to support new governance arrangements,

- £194k to support a range of community safety pilots from the Fire Safety and Youth Engagement reserves,

- £173k from the London Resilience reserve for new equipment related to the flood response project,

- £128k to fund the LFC preparations for the HM Inspectorate of Constabulary and Fire & Rescue Services (HMICFRS) inspection regime,

- £101k from the Community Safety Investment Fund,

- £57k to fund the Emergency Services Mobile Communication Programme, and

- £18k from the Hazmat reserve.

- The above table also includes a transfer of £11,745k to a new capital expenditure reserve following the completion of the sale of Southwark Fire Station, the accounting treatment for that additional income is being clarified with the external auditors and will be updated in the outturn report if required. The table also includes a transfer of £250k to a new reserve to fund recruitment spend in 2019/20, a transfer of £50k to support a review of the training function and a transfer of £100k from forecast spend on a cold cutting device to the Firefighter Technology project which will consider this requirement.

- Risks to the financial position

- Appendix 3 includes an update on the risks to the revenue and capital financial position.

- Four risks have been removed from the list reported to LFC in the Quarter 2 Financial Position report (LFC 0084) and one new risk on pensions bulk transfer has been added. Risks removed are:

  - Community Safety Contributions - The forecast outturn has been updated to reflect the revised position.

  - Command Support System - This risk is no longer expected to impact on the 2018/19 financial position but will be monitored in relation to future year impact.

  - Cost of replacement property contracts – The forecast outturn now includes financial impact of the new contracts.

  - Building maintenance contracts - The forecast outturn now includes financial impact of the new contracts.

- One new risk has been added to Appendix 3 as work on the possible pension transfer relating to staff that joined MOPAC as part of the internal audit shared service nears completion.  This issue has been ongoing for some time but there is now an expectation that decisions on affected staff transferring accrued pensions will be taken this financial year.

Capital

- The 2018/19 approved capital programme (FEP 2825) was reviewed and updated following the 2017/18 outturn and has been further reviewed as part of the in year financial monitoring. The current forecast spend for 2018/19 is now £12,058k, a reduction of £1,924k since last reported at Quarter 2 (LFC-0084).

- The capital programme continues to be reviewed as part of the preparation of the LFC’s first Capital Strategy, as required by CIPFA’s Prudential Code and the Mayor’s Budget Guidance and new processes in the management and scrutiny of the programme continue to be developed.  The challenge to forecast delivery dates, to ensure these are not overly optimistic, has led to further re-phasing of budgets.

- As a result of the capital programme review, budget changes will be requested quarterly where appropriate to ensure that scheme forecasts are compared to the updated budget position. For Quarter 3, a net budget change of £29,207k has been requested for approval. This includes all changes from Quarter 1 to Quarter 3. The changes are summarised in the table below:

- Capital Budget Changes 2018/19

|  | - Current Budget 2018/19 | - Slippage | - New Budgets | - Savings | - Removal Over Programming | - Revised Budget 2018/19 |
| --- | --- | --- | --- | --- | --- | --- |
|  | - £k | - £k | - £k | - £k | - £k | - £k |
| - Original budget & slippage from 2017/18 | - 41,265 |  |  |  |  | - 41,265 |
| - Financial Position Qtr 1 LFC-0050-D |  | - (18,157) |  | - (1,320) | - 2,207 | - (17,270) |
| - Financial Position Qtr 2 LFC-0084 |  | - (11,273) |  | - (5,426) | - 6,686 | - (10,,013) |
| - Financial Position Qtr 3 |  | - (1,724) | - 158 | - (358) |  | - (1,924) |
| - Total | - 41,265 | - (31,154) | - 158 | - (7,104) | - 8,893 | - 12,058 |

- The movement of £1,924k since last reported at Quarter 2 relates to the following :

Budget savings – (£358k)

- Fleet Equipment Budget – (£358k)

Slippage to 2019/20 – (£1,724k)

- Fleet Equipment slippage– (£162k)

- Fleet – Purchase of vans  - (£782k)

- ICT – Business Intelligent Solution – (£354k)

- ICT – Mobile Data Terminals – (£71k)

- ICT – Virtual Desktop Technology – (£35k)

- ICT – Wireless Access Points – (£100k)

- ICT – Merton Data Centre Data Transferability – (£120k)

- New Training Centre – (£100k)

New Budget Requirement - £158k

- Portable Hygiene Units - £91k new requirement

- ICT – New Laptops - £67k

Fleet - Equipment and Vehicle Modifications – A meeting has been held with Babcocks to confirm the costs and quantity of the modifications and equipment purchases. This has resulted in  a saving of £358k in 2018/19.

Due to the delivery lead time for the forced entry equipment £162k has been slipped to 2019/20.

Fleet – New Vans – Due to the delivery lead times, the purchase of the vans will now complete in 2019/20.  Accordingly £782k has been carried forward to 2019/20.

ICT – Business Intelligence Solution  - Originally it was proposed to appoint one contractor to deliver the Data Platform for this project. This proposal has been reviewed and it is now proposed to deliver the platform in two stages, with the first phase being an in-house developed  data solution for all LFC’s data, withthe second phase appointing a contractor to deliver all other identified requirements using the conceptual design. The benefits of the new proposal are that there is now a more manageable approach to delivering the Data Platform, which will also enable the upskilling of LFC ICT staff, with minimal further delay in the project delivery as there is no requirement to go out to tender for the first phase on the Data Platform delivery. It is now envisage that the costs of £354k will slip into 2019/20.

ICT – Mobile Data Terminals  - The terminals are to be installed on the new pumping appliances and the series 3, batch 2 fit out to which this relates has been re-phased in order to minimise costs, with final timings to be confirmed. It is now expected that the MDT terminals will be installed in the first quarter of 2019/20 and accordingly, £71k has been slipped to the next financial year.

ICT – Virtual Desktop Technology – It is now expected that only £15k will be spent in the current year, therefore £35k has been deferred to 2019/20.

ICT – Wireless Access Points – It is now expected that the site survey work for this project will not be completed this year, with procurement process yet to be completed. The total budget of £100k  will now slip to 2019/20.

ICT – Merton Control Centre – Data Exchange Project - The current government supplier (ATOS) will not now deliver the solution in time for the expenditure to be incurred in the current financial year. The Capita Component (£75k) is however scheduled for delivery in the March 2019 Release but experience suggests sign off of that release will not occur in the current financial year. Therefore £120k has been carried forward to 2019/20.

New Training Centre  - The project is still expected to spend to budget, and for construction to be completed in 2022. The budget has been re-profiled, with £100k carried forward from 2018/19 to 2019/20. This is to account for the recharge to revenue of abortive feasibility costs. This recharge is not, however, expected to affect overall project spend.

Portable Hygiene Units (PHU) – Report LFC 0096 –The Workplace (Health, Safety and Welfare) Regulations 1992 cover the supply of toilets and washing facilities for staff and covers the welfare facilities for use at operational incidents. This provision was previously provided under contract which has now expired.  A full assessment of the various options to provide these facilities has been undertaken, with the most advantageous option being for LFC to purchase two portable hygiene units at a cost of £91k, with a third party supplier  to undertake the delivery, retrieval, servicing and cleaning of such facilities. The disposal of hazardous materials associated with PHUs would also be managed by the supplier thus removing a number of logistical and policy issues for the LFB.

ICT – New Laptops   - FEP2462 approved the purchase of new laptops for fire stations at a cost of £450k. The project has been rollout over the last two years and the final projected cost for the new laptops is £517k. The reason for the increase is that the demand for the laptops exceeded the original projected requirements as new user requirements have emerged as a consequence of the technology now on offer, which as resulted in the additional budget requirement of £67k.

Debtors

An analysis of debtors relating to Shut in Lift charges is provided in Appendix 5, and  includes a chart showing the level of Shut in Lift debts over the past 18 months. The total number of Shut in Lift debts has been falling gradually over recent years, from a peak in 2015, with the overall balance reduced from £300k at the end of September 2015 to £100k at the end of December 2018.

The continued joint effort by LFC staff has resulted in the positive progress made to date on Shut in Lift debts recovery. It does however continue to be a challenging process to recover a number of these debts.

Finance comments

This report is presented by the Assistant Director – Finance and there are no further comments.

Workforce comments

No staff-side consultations have been undertaken on this report.

General Council’s comments

The London Fire Commissioner has set in place a Scheme of Governance (Decision Number: LFC-0003-D). The Scheme of Governance sets out detailed governance arrangements for the Commissioner as the fire and rescue authority for London. It complies with the Greater London Authority (GLA) Group Corporate Governance Framework and is drafted to ensure that the high standards of governance and accountability continue to be achieved by the Commissioner.

Part 6 (Financial Regulations) of the Commissioner’s Scheme of Governance sets out detailed rules covering financial planning, monitoring, control, systems and procedures and insurance.  This report fulfils the obligations of section 8 of Part 6 which stipulates that, “Following consultation with the relevant Heads of Service the Director of Corporate Services will present budget monitoring reports to the relevant Board regularly.”

Sustainability implications

There are no direct sustainable implications.

Equalities implications

This report has no equality implications.

List of Appendices

| Appendix | Title | Protective Marking |
| --- | --- | --- |
|  | Financial Position, 2018/19 Forecast Outturn | Not protectively marked |
|  | Capital Programme 2018/19 | Not protectively marked |
|  | Risks to the Revenue and Capital Position | Not protectively marked |
|  | Scheme of Governance - Budget Virements | Not protectively marked |
|  | Outstanding LIFT debtors | Not protectively marked |
|  | Additional Resilience Requirements | Not protectively marked |

Consultation

| Name/role | Method consulted |
| --- | --- |
| Heads of Department | Departmental finance returns |

|  | Current Budget | Current Spend | Current Variance |  | Original Budget | Revised Budget | Forecast Outturn | Forecast Outturn Variance |  | Previous Forecast Outturn Variance (Q2) | Movement between Q2 and outturn variance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | £ | £ | £ | % | £ | £ | £ | £ | % | £ | £ |
| Operational Staff | 177,030,911 | 174,277,177 | (2,753,733) | (1.6%) | 237,484,871 | 238,795,611 | 236,489,816 | (2,305,795) | (1.0%) | (2,043,594) | (262,201) |
| Trainee Firefighters | 1,503,153 | 1,550,144 | 46,992 | 3.1% | 1,647,846 | 2,004,203 | 2,513,668 | 509,465 | 25.4% | 134,494 | 374,971 |
| Total Operational Staff | 178,534,063 | 175,827,322 | (2,706,742) | (1.5%) | 239,132,716 | 240,799,814 | 239,003,485 | (1,796,330) | (0.7%) | (1,909,100) | 112,770 |
| FRS Staff | 37,631,896 | 37,943,157 | 311,260 | 0.8% | 52,360,574 | 51,877,001 | 50,085,535 | (1,791,466) | (3.5%) | (1,328,428) | (463,037) |
| Control Staff | 4,034,564 | 4,307,089 | 272,525 | 6.8% | 5,500,716 | 5,345,497 | 5,690,881 | 345,384 | 6.5% | 192,500 | 152,884 |
| Total Other Staff | 41,666,460 | 42,250,246 | 583,786 | 1.4% | 57,861,291 | 57,222,497 | 55,776,416 | (1,446,082) | (2.5%) | (1,135,928) | (310,153) |
| Other Pension Payments | 660,000 | 627,309 | (32,691) | (5.0%) | 990,000 | 990,000 | 1,020,000 | 30,000 | 3.0% | 30,000 | 0 |
| Severance | 29,568 | 92,211 | 62,643 | 211.9% | 0 | 29,568 | 92,211 | 62,643 | 211.9% | 26,074 | 36,569 |
| Professional Development | 19,155,733 | 19,162,899 | 7,166 | 0.0% | 20,757,145 | 19,575,743 | 20,202,383 | 626,640 | 3.2% | 735,258 | (108,618) |
| Recruitment | 156,176 | 122,477 | (33,699) | (21.6%) | 197,500 | 194,330 | 220,519 | 26,190 | 13.5% | (20,225) | 46,415 |
| Employee Related Insurance | 215,000 | 243,696 | 28,696 | 13.3% | 190,000 | 215,000 | 243,696 | 28,696 | 13.3% | 0 | 28,696 |
| Compensation | 416,860 | 322,426 | (94,435) | (22.7%) | 555,813 | 555,814 | 1,143,613 | 587,799 | 105.8% | 247,175 | 340,624 |
| Medical and Welfare Expenses | 1,462,152 | 1,433,815 | (28,338) | (1.9%) | 2,096,536 | 1,949,536 | 1,947,866 | (1,670) | (0.1%) | 20,602 | (22,272) |
| Employee Capitalised Costs | (315,987) | (187,803) | 128,184 | (40.6%) | (631,974) | (382,000) | (382,000) | 0 | 0.0% | 0 | 0 |
| Total Employee Related | 21,779,502 | 21,817,028 | 37,526 | 0.2% | 24,155,020 | 23,127,990 | 24,488,288 | 1,360,298 | 5.9% | 1,038,884 | 321,414 |
| Firefighter Pension Scheme | 15,426,445 | 15,368,888 | (57,557) | (0.4%) | 20,445,260 | 20,445,260 | 20,435,260 | (10,000) | (0.0%) | 146,000 | (156,000) |
| Building Maintenance | 5,271,588 | 5,746,460 | 474,872 | 9.0% | 6,893,188 | 7,344,400 | 9,065,400 | 1,721,000 | 23.4% | 657,000 | 1,064,000 |
| Grounds Maintenance | 93,684 | 65,457 | (28,227) | (30.1%) | 146,396 | 120,984 | 105,984 | (15,000) | (12.4%) | 0 | (15,000) |
| Premises Security | 571,670 | 639,441 | 67,771 | 11.9% | 451,670 | 571,670 | 776,670 | 205,000 | 35.9% | 150,000 | 55,000 |
| Energy Costs | 1,268,154 | 1,475,770 | 207,616 | 16.4% | 2,034,205 | 2,034,205 | 2,290,205 | 256,000 | 12.6% | 200,000 | 56,000 |
| Rents | 8,074,779 | 8,203,150 | 128,371 | 1.6% | 8,143,116 | 8,331,856 | 8,472,429 | 140,573 | 1.7% | 93,631 | 46,942 |
| Property PFI Contract | 5,585,202 | 5,584,639 | (563) | (0.0%) | 5,585,202 | 5,585,202 | 5,515,202 | (70,000) | (1.3%) | (49,000) | (21,000) |
| Property Rates | 7,817,841 | 5,622,181 | (2,195,660) | (28.1%) | 9,088,111 | 9,088,111 | 7,088,111 | (2,000,000) | (22.0%) | (1,216,000) | (784,000) |
| Water & Sewerage Rates | 195,611 | 181,572 | (14,039) | (7.2%) | 263,515 | 263,515 | 263,515 | 0 | 0.0% | 0 | 0 |
| Fixtures & Fittings | 62,641 | 64,632 | 1,991 | 3.2% | 97,969 | 97,969 | 97,969 | 0 | 0.0% | (15,000) | 15,000 |
| Cleaning and Domestic Supplies | 1,396,465 | 1,336,441 | (60,024) | (4.3%) | 2,020,097 | 2,101,297 | 2,112,297 | 11,000 | 0.5% | 5,000 | 6,000 |
| Premises Insurance | 322,000 | 330,002 | 8,002 | 2.5% | 372,000 | 322,000 | 322,000 | 0 | 0.0% | 0 | 0 |
| Other Property Services | 2,180,717 | 2,270,669 | 89,952 | 4.1% | 2,464,908 | 2,186,583 | 1,956,458 | (230,125) | (10.5%) | 380 | (230,505) |
| Total Premises | 32,840,352 | 31,520,414 | (1,319,937) | (4.0%) | 37,560,376 | 38,047,791 | 38,066,239 | 18,448 | 0.0% | (173,989) | 192,437 |
| Running Costs | 2,282,686 | 2,406,749 | 124,063 | 5.4% | 3,071,571 | 2,649,464 | 2,711,158 | 61,694 | 2.3% | 128,395 | (66,701) |
| Vehicle and Equipment Contract | 10,921,404 | 10,800,180 | (121,225) | (1.1%) | 10,972,929 | 10,921,404 | 10,621,404 | (300,000) | (2.7%) | (200,000) | (100,000) |
| Vehicle Passthroughs | 617,419 | 459,045 | (158,374) | (25.7%) | 643,651 | 692,589 | 452,007 | (240,581) | (34.7%) | (200,000) | (40,581) |
| Maintenance and Repairs | 0 | 0 | 0 | 0.0% | 670,000 | 70,000 | 70,000 | 0 | 0.0% | 0 | 0 |
| Contract Hire & Operating Leases | 1,047,687 | 1,098,885 | 51,197 | 4.9% | 1,173,800 | 1,110,233 | 1,137,406 | 27,173 | 2.4% | 28,173 | (1,000) |
| Travel | 690,784 | 679,765 | (11,019) | (1.6%) | 1,108,859 | 919,171 | 864,732 | (54,440) | (5.9%) | (74,394) | 19,954 |
| Total Transport | 15,559,981 | 15,444,623 | (115,358) | (0.7%) | 17,640,810 | 16,362,861 | 15,856,707 | (506,154) | (3.1%) | (317,825) | (188,328) |
| Hydrants | 496,055 | 739,265 | 243,210 | 49.0% | 496,055 | 496,055 | 246,055 | (250,000) | (50.4%) | (250,000) | 0 |
| Operational Equipment | 1,375,430 | 1,578,186 | 202,756 | 14.7% | 2,991,620 | 1,716,910 | 1,948,274 | 231,364 | 13.5% | 34,452 | 196,912 |
| Smoke Alarms | 595,000 | 493,354 | (101,646) | (17.1%) | 700,000 | 700,000 | 532,404 | (167,596) | (23.9%) | (50,208) | (117,388) |
| Equipment Furniture and Materials | 248,643 | 339,648 | 91,005 | 36.6% | 287,727 | 340,869 | 387,815 | 46,946 | 13.8% | 15,372 | 31,574 |
| Lost & NFWT Operational Equipment | 111,425 | 116,965 | 5,539 | 5.0% | 111,425 | 111,425 | 70,000 | (41,425) | (37.2%) | (20,000) | (21,425) |
| Catering | 249,375 | 244,207 | (5,168) | (2.1%) | 298,990 | 314,436 | 301,874 | (12,562) | (4.0%) | (3,092) | (9,470) |
| Clothing & Laundry | 2,727,108 | 2,870,101 | 142,993 | 5.2% | 3,011,598 | 3,032,628 | 2,979,301 | (53,327) | (1.8%) | 19,581 | (72,908) |
| General Office Expenses | 509,009 | 441,920 | (67,088) | (13.2%) | 703,793 | 647,539 | 613,822 | (33,716) | (5.2%) | (29,595) | (4,121) |
| Professional Services | 8,849,591 | 9,281,716 | 432,125 | 4.9% | 8,950,632 | 9,562,685 | 9,869,955 | 307,270 | 3.2% | 203,803 | 103,467 |
| Postal Services | 42,761 | 82,156 | 39,396 | 92.1% | 61,255 | 61,055 | 61,055 | 0 | 0.0% | 0 | 0 |
| Communications | 2,920,959 | 3,963,100 | 1,042,141 | 35.7% | 3,682,073 | 3,933,950 | 3,949,760 | 15,810 | 0.4% | 15,810 | 0 |
| Hardware and Software | 4,731,814 | 6,744,717 | 2,012,903 | 42.5% | 7,056,685 | 7,465,092 | 7,707,042 | 241,950 | 3.2% | 228,807 | 13,143 |
| Staff Reimbursements | 181,572 | 162,804 | (18,767) | (10.3%) | 248,772 | 242,021 | 232,585 | (9,436) | (3.9%) | (471) | (8,965) |
| Grants and Subscriptions | 146,059 | 145,259 | (800) | (0.5%) | 235,643 | 232,643 | 208,803 | (23,840) | (10.2%) | (22,498) | (1,342) |
| Other Insurance | 250,000 | 242,279 | (7,721) | (3.1%) | 225,000 | 250,000 | 250,000 | 0 | 0.0% | 0 | 0 |
| Advertising | 90,126 | 62,867 | (27,259) | (30.2%) | 117,750 | 121,661 | 120,469 | (1,192) | (1.0%) | (5,240) | 4,048 |
| Other Supplies and Services | 31,648 | 39,356 | 7,708 | 24.4% | 38,976 | 41,947 | 49,955 | 8,008 | 19.1% | (400) | 8,408 |
| Total Supplies and Services | 23,556,574 | 27,547,900 | 3,991,326 | 16.9% | 29,217,993 | 29,270,916 | 29,529,168 | 258,253 | 0.9% | 136,320 | 121,933 |
| Other Agencies | 387,907 | 353,751 | (34,156) | (8.8%) | 318,700 | 387,907 | 387,907 | 0 | 0.0% | 0 | 0 |
| Other Local Authorities | 872,327 | 1,197,551 | 325,224 | 37.3% | 1,561,002 | 1,405,805 | 1,480,824 | 75,019 | 5.3% | 78,000 | (2,981) |
| Audit & Bank Charges | 85,750 | 57,723 | (28,027) | (32.7%) | 88,600 | 88,600 | 69,000 | (19,600) | (22.1%) | (600) | (19,000) |
| Total Third Party Payments | 1,345,984 | 1,609,026 | 263,041 | 19.5% | 1,968,302 | 1,882,312 | 1,937,731 | 55,419 | 2.9% | 77,400 | (21,981) |
| Debt Repayment | 0 | 0 | 0 | 0.0% | 6,282,000 | 6,282,000 | 6,050,000 | (232,000) | (3.7%) | (449,000) | 217,000 |
| External Interest | 1,724,600 | 1,719,326 | (5,274) | (0.3%) | 3,488,000 | 3,488,000 | 3,400,000 | (88,000) | (2.5%) | (65,000) | (23,000) |
| Total Capital Financing Costs | 1,724,600 | 1,719,326 | (5,274) | (0.3%) | 9,770,000 | 9,770,000 | 9,450,000 | (320,000) | (3.3%) | (514,000) | 194,000 |
| Budget for Non Staff Inflation | 0 | 0 | 0 | 0.0% | 561,219 | 561,219 | 0 | (561,219) | (100.0%) | (561,219) | 0 |
| Central Contingency | 0 | 0 | 0 | 0.0% | 40,934 | (62,776) | (0) | 62,776 | (100.0%) | 68,000 | (5,224) |
| Savings to Be Achieved | 0 | 0 | 0 | 0.0% | (339,250) | (370,903) | (14,211) | 356,692 | (96.2%) | 502,446 | (145,754) |
| Savings done by DA | 0 | 0 | 0 | 0.0% | 70,293 | 87,909 | 19,001 | (68,909) | (78.4%) | (64,409) | (4,500) |
| Central Contingency | 0 | 0 | 0 | 0.0% | 333,197 | 215,449 | 4,790 | (210,659) | (97.8%) | (55,182) | (155,477) |
| Total revenue expenditure | 332,433,962 | 333,104,773 | 670,811 | 0.2% | 438,084,965 | 437,144,891 | 434,548,084 | (2,596,807) | (0.6%) | (2,707,421) | 110,614 |
| MFB Act Income | (27,740,647) | (28,114,961) | (374,314) | 1.3% | (27,695,000) | (27,740,647) | (27,800,000) | (59,353) | 0.2% | (259,353) | 200,000 |
| Customer and Client Receipts | (6,928,831) | (7,140,029) | (211,197) | 3.0% | (8,801,309) | (9,431,700) | (9,399,179) | 32,521 | (0.3%) | (250,276) | 282,797 |
| Interest Receivable | (188,000) | (267,424) | (79,424) | 42.2% | (400,000) | (400,000) | (470,000) | (70,000) | 17.5% | (30,000) | (40,000) |
| Bad Debts | 0 | 15,585 | 15,585 | 0.0% | 0 | 0 | 15,584 | 15,584 | 0.0% | 0 | 15,584 |
| Total Other Income | (34,857,479) | (35,506,828) | (649,350) | 1.9% | (36,896,309) | (37,572,347) | (37,653,596) | (81,248) | 0.2% | (539,629) | 458,381 |
| Net revenue expenditure | 297,576,484 | 297,597,945 | 21,461 | 0.0% | 401,188,655 | 399,572,543 | 396,894,488 | (2,678,055) | (0.7%) | (3,247,050) | 568,995 |
| Use of Earmarked Reserves | 0 | 0 | 0 | 0.0% | (2,183,254) | 11,937,277 | 12,187,278 | 250,001 | 2.1% | 250,000 | 0 |
| Financing Requirement | 297,576,484 | 297,597,945 | 21,461 | 0.0% | 399,005,401 | 411,509,821 | 409,081,766 | (2,428,055) | (0.6%) | (2,997,050) | 568,995 |
| Financed by: |  |  |  |  |  |  |  |  |  |  |  |
| Specific grants | (11,956,972) | (16,980,135) | (5,023,163) | 42.0% | (12,205,401) | (13,039,934) | (13,116,768) | (76,834) | 0.6% | (56,000) | (20,834) |
| GLA Grant | 0 | 0 | 0 | 0.0% | (386,800,000) | (398,469,887) | (398,469,887) | 0 | 0.0% | 0 | 0 |
| Net Financial Position | 285,619,511 | 280,617,810 | (5,001,702) | (1.8%) | 0 | 0 | (2,504,888) | (2,504,888) | 0.0% | (3,053,049) | 548,161 |

| APPENDIX 1 – 2018/19 CAPITAL BUDGET – QUARTER 3 | 2018/19 Budget July 2018 | Budget Changes 2018/19 Proposed | Revised Budget 2018/19 Qtr 3 | Qtr 3 F/Cast 2018/19 |  | Qtr 2 F/Cast 2018/19 | Change from Qtr 2 |  | Spend to 31 Dec.2018 | To Spend |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ICT Projects | £’000s | £’000s | £’000s | £’000s |  | £’000s | £’000s |  | £’000s | £’000s |
| Records Management - Upgrade Operating System | 98 | (98) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Business Intelligent Solution | 654 | (354) | 300 | 300 |  | 654 | (354) |  | 187 | 113 |
| Control & Mobilisation System (CAMS) | 470 | (470) | 0 | 0 |  | 0 | 0 |  | (333) | 333 |
| Mobile Data Terminals Replacement | 71 | (71) | 0 | 0 |  | 71 | (71) |  | 0 | 0 |
| Replacement of the incident grounds communications | 1,800 | (1,800) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Home Fire Safety Database (linked to Farynor Project) | 130 | (130) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Replacement of laptops (FEP2462) | 45 | 67 | 112 | 112 |  | 45 | 67 |  | 112 | 0 |
| Emergency Services Network | 707 | (707) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| ICT – Accident (event) reporting solution | 62 | 0 | 62 | 62 |  | 62 | 0 |  | 58 | 4 |
| Online Payment Facility | 70 | (70) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| ICT – Virtual Desktop Technology | 250 | (235) | 15 | 15 |  | 50 | (35) |  | 0 | 15 |
| New telephone system equipment | 42 | 0 | 42 | 42 |  | 42 | 0 |  | 49 | (7) |
| New computer terminals | 41 | 0 | 41 | 41 |  | 41 | 0 |  | 28 | 13 |
| Core Switch Modules | 300 | (300) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Wireless Access Points | 853 | (853) | 0 | 0 |  | 100 | (100) |  | 0 | 0 |
| Data Centre Switches 3750 Replacement | 104 | (104) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Station Network Rewires | 200 | (200) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Network Storage | 750 | (750) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Farynor Replacement (linked to ICT Home Fire Safety) | 750 | (750) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Data transfer system for Joint Emergency Services Interoperability Programme | 195 | (120) | 75 | 75 |  | 195 | (120) |  | 0 | 75 |
| ICT Projects Over programming/to be allocated | -2,207 | 2,207 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| ICT PROJECTS | 5,385 | (4,738) | 647 | 647 |  | 1,260 | (613) |  | 101 | 546 |
| ESTATE PROJECTS |  |  |  |  |  |  |  |  |  |  |
| Fire Station Refurbishment (Middx FS) | 100 | (100) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Workplace Improvement Plan (WIP) Union Street | 60 | (60) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Plumstead Fire Station Redevelopment | 1,500 | (1,500) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| LFB Museum – Fit out | 30 | (30) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Refurbishment of Edmonton Fire Station | 100 | (100) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Heating at various stations | 1,411 | (1,266) | 145 | 145 |  | 145 | 0 |  | 86 | 59 |
| Window replacement at various stations | 510 | (376) | 134 | 134 |  | 134 | 0 |  | 104 | 30 |
| Rewiring of property at various fire stations | 600 | (550) | 50 | 50 |  | 50 | 0 |  | 0 | 50 |
| Minor Improvement Programme | 993 | 1 | 994 | 994 |  | 994 | 0 |  | 204 | 790 |
| Minor Refurbishment Works | 950 | (16) | 934 | 934 |  | 934 | 0 |  | 807 | 127 |
| Appliance Bay Doors (Phase 3) | 663 | (257) | 406 | 406 |  | 406 | 0 |  | 337 | 69 |
| Brigade wide Survey for Asbestos & Removal | 50 |  | 50 | 50 |  | 50 | 0 |  | 11 | 39 |
| Fire Safety Works at Fire Stations | 47 |  | 47 | 47 |  | 47 | 0 |  | 6 | 41 |
| Forecourts/Rear yards Refurbishment | 51 | (13) | 38 | 38 |  | 38 | 0 |  | 7 | 31 |
| Improve Security at all Fire Stations, Offices & HQ | 100 | (100) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| New Training Centre | 7,445 | (7,445) | 0 | 0 |  | 100 | (100) |  | (84) | 84 |
| Operations Support Centre Project (IELP) | 3,733 | (3,724) | 9 | 9 |  | 9 | 0 |  | 13 | (4) |
| West Hampstead Cottages Refurb (FEP2776) | 686 | (675) | 11 | 11 |  | 11 | 0 |  | 18 | (7) |
| Development costs | 250 |  |  | 250 |  | 250 | 0 |  | (50) | 300 |
| Other accrual reversals | 0 |  |  | 0 |  | 0 | 0 |  | (48) | 48 |
| ESTATE PROJECTS | 19,279 | (16,211) | 3,068 | 3,068 |  | 3,168 | (100) |  | 1,411 | 1,657 |
| FLEET & EQUIPMENT PROJECTS |  |  |  |  |  |  |  |  |  |  |
| Replacement of Fleet and Operational Equipment | 13,521 | (5,929) | 7,592 | 7,592 |  | 8,894 | (1,302) |  | 5,964 | 1628 |
| Respiratory Protective Equipment | 2,300 | (2,300) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| Early Replacement of ALP & HP | 3,750 | (3,750) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| CCTV on Pumping Appliances | 369 | (263) | 106 | 106 |  | 106 | 0 |  | 1 | 105 |
| Early Replacement of Fire Boat | 1,000 | (1,000) | 0 | 0 |  | 0 | 0 |  | 0 | 0 |
| 22mm Water Hose and Reel for Appliances | 1,014 | (507) | 507 | 507 |  | 507 | 0 |  | 92 | 415 |
| Portable Hygiene Units | 0 | 91 | 91 | 91 |  | 0 | 91 |  | 0 | 91 |
| Vehicle Security | 1,333 | (1,286) | 47 | 47 |  | 47 | 0 |  | 17 | 30 |
| FLEET & EQUIPMENT PROJECTS | 23,287 | (14,944) | 8,343 | 8,343 |  | 9,554 | (1,211) |  | 6,074 | 2,269 |
| Projected Underspend | (6,686) | 6,686 | 0 | 0 |  | 0 | 0 |  | 0 |  |
| CAPITAL EXPENDITURE TOTAL | 41,265 | (29,207) | 12,058 | 12,058 |  | 13,982 | (1,924) |  | 7,586 | 4,472 |

- Pay and Inflation

  - There is ongoing significant economic uncertainty as the Brexit negotiations continue. The impact of this is currently unclear, and so preparing forecasts for increases in general inflation remains difficult.

  - Brigade has made a budget provision for a 2% pay award for all staff in this year’s budget and an additional 1% for Operational and Control staff for the on-going pay negotiations from last financial year (also bringing this to 2%). All staff have now been awarded 2% awards in this financial year, within the budget, but negotiations are continuing on the national firefighters pay award for 2017. If there was no further award above the initial 1% already paid, this would increase the underspend.

- Pensions

  - Based on advice from the Pension Actuary, it is possible that LFC will incur pension transfer costs for staff that were transferred to MOPAC as part of the internal audit shared service. The actual cost falling to LFC will not be confirmed until final decisions are made by the individuals concerned and costs are calculated as at the transfer date.

- Capital Expenditure and Financing

  - The capital budget is subject to change during the year. Initial project specification is key as it is important to keep variations to projects to a minimum, as change once a project has been agreed and commenced may result in additional costs. However even a well managed project can be subject to re-phasing or deferral due to a number of unforeseen issues, such as failure or default on the part of the contractor or exceptionally adverse weather conditions. This can also impact on funding requirements which in turn may have a debt charge (cost of borrowing) revenue impact.

  - All capital projects will require third party collaboration to varying degrees over the project life. The programme depends heavily on external factors and therefore can be subject to variation with the potential for delays in project delivery and revised cash flow requirements. The capital programme is managed on a monthly basis and is reported quarterly to the CAPS group (Capital, Approval, Planning and Strategy Group, chaired by the Director of Corporate Services) where all changes to the programme are reviewed and substitution projects or re-financing proposals are assessed and agreed.

  - The debt charges arising from the capital programme have been calculated using the current forecast Public Works Loans Board (PWLB) rates. No allowance has been made in the capital programme for potential future capital grants or contributions and the Brigade will bid for available capital resources as and when such opportunities arise.

  - The Capital Programme for 2018/19 previously included a forecast capital receipt for the sale of Clerkenwell Fire Station. This receipt has now been deferred to 2019/20 and the future financing costs have been revised to reflect this change. If this property is not sold in 2019/20 this could result in an increased borrowing requirement and resulting capital financing costs estimated at £857k. This is based upon the current forecast capital programme and does not take account of any re-phasing or slippage that might occur.

  - The new LFB Training Centre project has a dependency on PEG moving out of Croydon and any delay to the PEG/BDC development may have a knock-on effect on the delivery of the Training Centre programme. The lease agreement for the new combined PEG/BDC facility (Integrated and Equipment Logistics Project – IELP) has been signed and the fit-out/adaptation works has started. The scope of the Training Centre project has been reviewed and it is now planned to refurbish the existing building to provide the training centre and still to create the new real fire training venue at the site.  The revised scheme design brings the project back within the approved budget of £15.5m.  Design fees relating to the original proposal have been removed from the project costs and recharged to revenue as abortive fees.  The new scheme will require planning approval and there is a risk that the design changes could result in a delay to obtaining the approval, which in turn could affect the phasing of the capital expenditure and opening of the facility.

  - The Operations Support Centre Project (formally IELP) -The tender responses received for the construction/fit out have been evaluated and an award is pending.  It is envisaged that the contract will be awarded by the end of January 2019 and works are planned to be completed by March 2020. Until the preferred contractor is appointed there is a risk that the project may slip if  approval is delayed past January 2019.

  - There is still uncertainty regarding Plumstead fire station, depending on a review of a new site. There is a risk that this new site may not be deemed suitable and therefore a decision will need to be made whether to instead refurbish the existing building, potentially with an extension. This uncertainty could result in delay and changes to the forecast spend for this project.

  - Edmonton/Middlesex fire station projects – Further feasibility work may result in a revised forecast for both these projects, depending on the agreed options, priorities and the agreed way forward.

  - The business case for the project to Improve Security at Fire Stations needs to be re-validated. This may result in the project being removed from the programme, or in delays to delivering this project.

  - The Lambeth River Station has been identified as a site requiring refurbishment. This is not currently included in the capital programme, therefore further funding may need to be requested/re-directed from other projects if deemed a priority. This is also the case for a number of other sites including the fire stations at North Kensington, Biggin Hill and Bromley.

  - Farynor and Home Fire Safety Database  - Delays could occur in the delivery of the Farynor and Home Fire Safety Database projects  as it has been considered prudent to consider the outcome of the independent Review of Building Regulations and Fire Safety being led by Dame Judith Hackett. The review has made recommendations that will ensure that there is sufficient robust regulatory system for the future. The report has now been published (17th May 2018) and due consideration is being given to the findings which will impact the final specification of these two projects. Accordingly, the exact time frame for these projects are uncertain at present.

  - Public Services Network (ICT)   - The PSN budget (£707k) has been removed from the capital programme.  The budget was a contingency to fund work in relation to the Emergency Services Network (ESN) code of connection (CoCo). Work to adhere to the ESN CoCo was funded from the Home Office by grant award. Work continues but no further external funding is available. There remains a risk that there may be a new further funding in the future, subject to the final conditions of the ESN CoCo.

  - The design and specification of the replacement vehicles and equipment is now underway following the commencement of the contract in November 2014. Key risks relate to the contractor sourcing appropriate vehicle build options within a timeframe that meets fleet replacement requirements and which may in turn impact the LFC’s cash flow. The forecast cash expenditure for 2018/19 and future years is based on the current assessment of the stage payment requirements for the pump replacement and aerial appliance replacement programme, which represents nearly 50% of the forecast Vehicles and Equipment expenditure in that period, and the delivery timings for the balance of the fleet replacement programme.  In addition, the impact of Brexit could significantly affect the future replacement costs for a number of fleet items.

- Property Services

  - Security costs – There could be a small increase in expenditure on security should the planned disposal of old Mitcham not be completed or there is a delay in handing over the Pegasus site to the main contractor.

  - Energy budgets - An outturn overspend of £256k is being reported on energy based on a ‘normal ‘ winter scenario. There is a risk that this forecast could vary should there be severe or mild weather conditions experienced during the Quarter 4.

  - There is potential for further refunds in 2018/19 for new business rate appeals on 2010 rateable values if successful. Officers are awaiting confirmation of actual values from the Estates Management Consultant.

  - The water and sewerage budget was overspent by £71k in 2017/18 mainly due to deregulation of market increasing costs. A new contract for water service commenced in December 2018 and the first billing is awaited to assess impact to expenditure. No variance is currently being forecast but there is potential for this budget to be overspent at outturn.

- Contractual Pressures/ Risks

  - Significant demand continues to be placed on the Information and Communications Technology Department to meet new requirements and aid in the development of smarter systems for the LFC. This is at a time where resources are limited and as a result there is a risk that development of information technology solutions may be constrained.

- Changes to Income

  - Telecommunications income in respect of radio masts may be reduced in the future due to a reduction in the number of operators in the industry and a potential change to legislation on access to land by operators.

  - There is a review of LFB enterprises on-going and the outcome will be reported to CB in due course. Dependent on the outcome there may be a financial impact on this year budget. The current forecast outturn includes £70k of income from the company for the reimbursement of staff time, against a budget of £170k.

Financial Regulation 9:

“(b) With the agreement of the Director of Corporate Services, a Head of Service may transfer up to £50,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget, but if those budget heads are in different Directorates the agreement of the appropriate Director or Commissioner is also required.

(c) With the agreement of the Director of Corporate Services, Directors may transfer up to £150,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget.

(e) The Director of Corporate Services shall report all transfers under (b) and (c) to the Commissioner as part of the quarterly Financial Position reports.”

No transfers were processed in Quarter 3 that require reporting.

The chart below shows the amount of outstanding LIFT debts over the last 18 months, with £100k outstanding at the end of December 2018. The graph shows a downward trend in the level of outstanding debt.

The table below shows the top five (worst) outstanding debtors for LIFT income.

|  | £ outstanding | Average Age in days | No of invoices |
| --- | --- | --- | --- |
| PEABODY TRUST | 9,522 | 218 | 24 |
| AFFINITY SUTTON | 4,795 | 107 | 12 |
| GALLION HOUSING ASSOCIATION | 4,656 | 462 | 12 |
| LONDON BOROUGH OF ISLINGTON | 4,396 | 74 | 11 |
| PERSIMMON PLC | 4,315 | 489 | 11 |
| Total | 27,684 | 261 | 70 |

Review of the top five debtors

Peabody Trust:

A final reminder letter has been sent to Peabody trust on 20th December 2018.

Affinity Sutton:

A final reminder letter has been sent to Affinity Sutton and currently in the process of being referred to General Counsel.

Gallion Housing Association:

Outstanding debts for Heather Homes Services Ltd has been referred to General Counsel for recovery action.

London Borough of Islington:

Outstanding debts were recently chased on 7th January 2019 and a third reminder letter is scheduled to be sent.

Persimmon PLC

Outstanding debts for Persimmon PLC has been referred to General Counsel for recovery action.

Summary of changes from Q2 forecast

| Revised Forecast | 2018/19 | 2019/20 | 2020/21 | 2021/22 |
| --- | --- | --- | --- | --- |
| Capital | 0 | 600,000 | 5,963,000 | 0 |
| Revenue | 4,285,494 | 4,936,894 | 5,181,394 | 5,409,894 |
| Reserve Funded | 962,624 | 948,000 | 0 | 0 |
| Total | 5,248,118 | 6,484,894 | 11,144,394 | 5,409,894 |
| Forecast Spend in Q2 |  |  |  |  |
| Capital | 0 | 628,000 | 5,963,000 | 0 |
| Revenue | 4,239,894 | 4,936,894 | 5,181,394 | 5,409,894 |
| Reserve Funded | 1,260,598 | 608,000 | 0 | 0 |
| Total | 5,500,492 | 6,172,894 | 11,144,394 | 5,409,894 |
| Movement from previous | (252,374) | 312,000 | 0 | 0 |
| Items that have changed |  |  |  |  |
| C2 - Drones | 0 | (28,000) | 0 | 0 |
| R2 – Improved USAR kit | (60,400) | 150,000 | 0 | 0 |
| R3 - Wicking T Shirts | (232,000) | 190,000 | 0 | 0 |
| R7 - Legal Costs | 115,026 | 0 | 0 | 0 |
| R9 - Fire Safety Resources | (75,000) | 0 | 0 | 0 |
| Total Movement | (252,374) | 312,000 | 0 | 0 |

| Ref | Department | Expenditure Item | Actual Spend in 2017/18 £ | Forecast Spend in 2018/19 £ | Forecast Spend in 2019/20 £ | Forecast Spend in 2020/21 £ | Forecast Spend in 2021/22 £ |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C1 | Procurement/ Technical & Service Support | Extended Height Aerial Appliances x3 Aerial appliances are used for a range of tasks at incidents which include providing a means of escape for firefighters working inside a building, as water towers, lighting and observation platforms and rescues, as just several examples. Greater height ladders have now become available on a similar size chassis to the Brigade’s current fleet that could be effectively utilised at certain incidents within London. As part of the Brigade’s existing plan to upgrade its aerial appliance fleet as announced in March, there is a benefit to procuring such vehicles at this time. LFB have provided our vehicles and equipment contractor “Babcock” with a detailed output based specification (OBS) for three extended height aerial appliances to complement the twelve standard height aerial appliances which will be ordered at the same time. Babcock went out to the market to invite tenders for the supply of all of the new aerial appliances, this is to include the supply of both standard and extended range appliances as a single contract. The window to accept tender proposals has closed and the evaluation process of the received tender proposals has now commenced. The tender evaluation process should allow for a contract to be drawn up with the successful bidder and the expectation will then be to see delivery of the new aerial appliances occurring between mid 2019 to early 2020. | 0 | 0 | 600,000 | 3,150,000 | 0 |
| C2 | Procurement/ Technical & Service Support | Drones Drones provide an alternative option to requests for the support of police helicopters which is an extremely expensive option, is not always available, is not within our direct control and for some uses is not as effective as drones might be. Drone pilot training (x6) has been completed. PDA's for drone mobilisation have been identified and agreed with Brigade Control. | 0 | 0 | 0 | 0 | 0 |
| C3 | Procurement/ Technical & Service Support | Extended Duration Breathing Apparatus Sets LFB Standard Duration BA has a working duration of 31 minutes. Extended Duration BA has a working duration of 45 minutes. A ‘Prior information notice’ has been sent out via the emergency services blue light portal letting the market know of our intention to replace our Respiratory Protective Equipment provision which includes both standard duration and extended duration breathing apparatus and inviting manufacturers to record an expression of interest. 6 companies registered their interest and preliminary meetings to outline our timescales and the outline of our requirements have been completed. We are continuing to research the market by meeting suppliers. This will be followed by the Project Initiation Document (PID) with the user requirement projected to be sent out to suppliers. Stakeholders for the working group are currently being identified and the first meeting of this group will be convened when we have a working draft of the PID. In the interim we are reviewing how we can deliver our current EDBA provision to incidents at an earlier stage via both Fire Rescue Units and EDBA support pumps as well as the Operational Support Units. | 0 | 0 | 0 | 2,813,000 | 0 |
| R1 | Multiple Departments | Ongoing Maintenance for Capital Items above | 0 | 4,000 | 79,000 | 460,500 | 767,000 |
| R2 | Operational Policy | Improved USAR Kit USAR specific drones: To map the area and conduct localised or wide area search/casualty search. Can also enter danger areas and structures to minimise risk to crews. Drone pilot training (x6) has been completed. PDA's for drone mobilisation have been identified and agreed with Brigade Control. Arrangements are being finalised for the commencement of the drone trial, which started in October 2018. WASPs: Early Warning safety device for structural stability. Can also be used for Trench rescue and confined space working. Two units are currently on trial, available on request. These can be mobilised to an incident by the duty RSO. This unit will form part of the inventory on the next generation FRU. Pop-Up Tents: To provide welfare/shelter for crews/command team in both inclement or sunny weather. Officers are carrying out an assessment of whether this equipment is required. Half Masks: For crew welfare over long periods of use compared to full face, which can cause crews to overheat. 80 USAR personnel have been fitted for half face respirators. This will form part of the personal PPE issue when resources allow the completion of face fitting for the remaining staff. | 0 | 18,600 | 170,000 | 20,000 | 20,000 |
| R3 | Operational Policy | Wicking T-Shirts A shirt which has the ability to breathe and keep the user's skin dry from sweat. The initial cost is based on estimate of £10 per shirt and allocation of five each for all firefighter and crew manager roles. An appropriate wicking t-shirt has been identified and staff group entitlement now agreed. | 0 | 15,000 | 195,000 | 57,000 | 57,000 |
| R4 | People Services | Additional resources - Counselling and Wellbeing Team Changes in the nature of the Brigade's work have increased the workload of the C&W Team. The unprecedented nature of the Grenfell Tower fire has increased workloads on a significant and sustained basis. In addition to supporting colleagues who were impacted by the fire in the immediate aftermath, the team are supporting the collection of witness statements by the police and will be required to support individuals for months and years to come, up to and including the Public Inquiry. Four additional Counsellor posts (FRS E) are now in place. Also, to operate effectively the expanded C&W team requires administrative support. A FRS B post to support the team and maintain critical and confidential records is now in place. | 68,836 | 244,894 | 244,894 | 244,894 | 244,894 |
| R5 | Fire Stations | Increase in officer levels An increase in the Deputy Assistant Commissioner (DAC) establishment from 12 to 16 is required to provide greater resilience within the operational top management group. DACs provide strategic support at incidents that require eight or more fire engines. They are also integral to the Brigade’s wider strategic response arrangements including to Major Incidents. The additional posts will support the ongoing day to day resilience within existing departments and provide the necessary level of managerial responsibility to the Brigade’s Grenfell Investigation Team. Four additional DAC posts are now in place. | 238,500 | 424,000 | 424,000 | 424,000 | 424,000 |
| R6 | Commissioner's & Directors' | Costs of the Investigation Team The establishment of this team was set out in the report on the Grenfell Tower Inquiry – Proposed Terms of Reference (FEP 2747). The team is now in place to support work on the investigation. The number and make of the establishment is changing to meet organisational need, and now the public enquiry is under way. Additional equipment has been provided, for example to allow the review of CCTV footage. | 705,506 | 2,050,000 | 1,500,000 | 858,000 | 858,000 |
| R7 | General Counsel | Grenfell - Legal Support (External Legal Advisors) The Grenfell fire has led to the instigation of a Public Inquiry of which the Authority is expected to be a core participant. Additionally, a parallel criminal investigation into the fire is being carried out by the Metropolitan Police with support from the Authority and HSE. The Authority may be required to play an extensive role in each. This growth bid is twofold. Firstly, the costs in backfilling posts of staff required to work on the Grenfell Tower case and secondly for external legal advice and representation. Secondly, this growth bid relates to the requirement of a dedicated IT solution to enable effective management of the review and disclosure of documents for the purpose of disclosure in the legal proceedings noted above. The 2018/19 forecast has decreased significantly from the previous update primarily due to updated forecast on likely costs of Junior Counsel. Forecasts for future years remain the same. | 600,288 | 1,635,632 | 233,000 | 78,000 | 0 |
| R8 | Fire Stations | Overtime Support for Specialist Teams This is based on a 30 per cent increase in operational overtime at FRU and FRU/USAR Stations alongside overtime costs for Regulatory Fire Safety in relation to cladding inspections. For Fire Safety, the one off costs cover additional inspections in June and July 2017. | 0 | 103,000 | 103,000 | 103,000 | 103,000 |
| R9 | Fire Safety | Fire Safety resources to support and enhance the inspection programme The ongoing costs are for an additional resources to support the inspection programme. Recruitment process is currently under way. | 0 | 425,000 | 1,500,000 | 1,500,000 | 1,500,000 |
| R10 | Legal & Democratic Services | Review of staff support for Chair This was to consider whether additional support is required for the Deputy Mayor for Fire and Rescue This is no longer required, and the budget has been removed. | 0 | 0 | 0 | 0 | 0 |
| R11 | Fire Stations | Potential cost of increased sickness It is anticipated that the aftermath of recent incidents will see an increase in sickness rates for operational staff, in particular. This sets out the overtime cost that will be expected to be incurred in covering the resulting gaps. | 371,000 | 371,000 | 371,000 | 371,000 | 371,000 |
| R12 | Development and Training | Training This includes additional training requirements for: • Extended Height Appliances • Drone Piloting • Extended Duration Breathing Apparatus Sets • Improved USAR Kit • Smoke Evacuation Hoods This also includes ongoing EDBA training Requirements The spend for 2018/19 for drones training, with £5k for training already delivered. | 0 | 7,000 | 1,045,000 | 437,000 | 437,000 |
| R13 | Finance Services | Additional Borrowing Costs Items funded through the capital programme will increase the overall level of external borrowing required over the current four year planning period and increase capital financing costs by an estimated £842k per annum. | 0 | 0 | 0 | 608,000 | 608,000 |
| R14 | Operational Policy | Improved Communications for Breathing Apparatus A BA replacement project will shortly be underway to examine the next generation of BA and how this can be delivered to the LFB. Whilst telemetry is being identified as a consideration any additional communications requirements over an above the current (BARIE) sets can be included for consideration. Outline costs have yet to be determined. BA communications is now in scope of the Repertory Protective Equipment replacement project and the project is just starting. There are meetings with manufacturers scheduled through July to outline timescales. with the User requirement scheduled to go to suppliers by end of the calendar year. | 0 | 0 | 0 | 0 | 0 |
| R15 | Operational Policy | Fire Escape Hoods This budget will be used to explore the viability of the purchase of smoke hoods for all front line appliances and is for the equipment costs only and does not include any additional staffing costs that may be associated with getting this project up and running. | 0 | 89,000 | 20,000 | 20,000 | 20,000 |
| Total additional resilience requirements |  |  | 1,984,130 | 5,248,118 | 6,484,894 | 11,144,394 | 5,409,894 |