| Report title |  |
| --- | --- |
| Provisional Outturn Report for 2017/18 |  |
| Report to | Date |
| Commissioner’s Board | 20 June 2018 |
| Report by | Document Number |
| Assistant Director - Finance |  |
| NO PROTECTIVE MARKING |  |

Summary

This report reviews the provisional financial outturn for the 2017/18 financial year, sets out the position on the financial reserves and also provides an update to the approved capital programme.

Recommendations

That the Commissioner’s Board notes the revenue and capital financial outturn position as set out in the report.

Background

- This report presents the provisional financial outturn position for 2017/18. The draft Statement of Accounts was approved by the Chief Finance Officer (Director of Corporate Services) to meet the statutory deadline of 31 May, and is now subject to external audit, with final accounts to be approved by the London Fire Commissioner (LFC) and published by 31 July.

- The data set out in this report has also been used to prepare the financial element of a summary report on performance for the LFC at Appendix 7, to be submitted to the London Assembly Fire, Resilience and Emergency Planning (FREP) Committee as well as the Budget and Performance Committee (BPC).

- A summary of the financial position for the revenue budget is provided in Appendix 1, with a further breakdown of the financial position provided in Appendix 2, Appendix 3 reports on the progress against the capital programme for 2017/18, Appendix 4 shows the risks that have not been quantified in this report and continue into 2018/19, Appendix 5 provides an analysis of outstanding debt relating to charges for Shut in Lift incidents, Appendix 6 meets the requirement to disclose required budget virements within the quarter under financial regulation 9 and Appendix 7 provides the Financial Element on Performance.

Revenue Summary

- The provisional outturn position for 2017/18 on the revenue budget is an underspend of £11,878k (3.0%). However as noted above, this is subject to external audit, with final accounts to be approved by the London Fire Commissioner (LFC) and published by 31 July.

- This report shows how the underspend could be used to supplement the Budget Flexibility reserve and help to mitigate the budget deficit anticipated over the next four years. This would increase the existing Budget Flexibility reserve from £11.5m to £18.7m at the start of the 2018/19 financial year.

- The table below provides both a high level summary of the material outturn underspends and commentary to show any potential impact for future years spends.

| Underspend | Outturn Underspend £m | Comments |
| --- | --- | --- |
| Operational Salaries | 5.3 | This reflects an average of 196 vacancies in 2017/18. Although vacancies are forecast to decrease from the 2017/18 position, the 2018/19 budget includes an additional £3,724k vacancy margin above the steady state level, to reflect that there are still expected to be vacancies in 2018/19. |
| Property Rates | 3.1 | £2,017k of this underspend on property rates relates to a successful appeal that was lodged by the Estates Management Consultant for the 2010 valuations. A further £1,095k is due to surplus funding that could now be released following advice from the Estates Management Consultant. |
| FRS Staff | 1.4 | This is because recruitment to a number of key roles has taken longer than anticipated. |
| Customer and Client Receipts | 1.4 | This is due to the inclusion of £0.5m income for LIFE, cadets and borough led Community Safety initiatives not utilised this year, which is to be transferred to the Fire Safety and Youth Engagement earmarked reserve. This also includes a £0.8m adjustment to balances carried forward from previous years relating to telecommunications income, identified in 2017/18 as part of the end of year reconciliations. |
| Medical and Welfare expenses | 0.9 | This underspend on the inoculations budget has now been transferred to an earmarked reserve to cover the planned one-off spend in future years. |
| MFB Act Income | 0.8 | This income budget has been increased by £2.1m for 2018/19 to £27.7m, an increase of 8%. That reflects the 2017/18 outturn position and a 5% inflationary increase. |
| Hardware and Software | 0.6 | Delays caused by implementation issues on a number of major projects including the mobile data terminals, Windows 10 and Farynor. This underspend will be transferred into the ICT Development earmarked reserve to cover planned spend in 2018/19. |
| Professional Development | 0.6 | This is due to additional underspends on professional development due to a reduction in spend on a number of projects including delays in the commencement of Fire Safety training, as well as abatements on the training contract. |

- The revenue outturn includes additional underspends of £7,148k since the position reported at Quarter 3 (FEP2709). These additional underspends are mainly due to:

- Operational staff salaries (£1,094k) which relates to previously reported recruitment challenges, this movement represents 0.3% of the operational staff budget. The overall underspend equates to an average of 196 vacancies in 2017/18.

- FRS staff salaries (£918k) because recruitment to a number of key roles has taken longer than anticipated.

- Property rates due to surplus funding of £1,095k, that could now be released following advice received from the Estates Management Consultant.

- Customer and Client Receipts (£1,405k) due to the inclusion of £0.5m income for LIFE, cadets and borough led Community Safety initiatives not utilised this year, which is to be transferred to the Fire Safety and Youth Engagement earmarked reserve, and an £0.8m adjustment to  balances carried forward from previous years relating to telecommunications income, identified in 2017/18 as part of the end of year reconciliation.

- Professional development (£704k) due to a delay in a number of projects including a new arrangement with Babcock for a Fire Safety course, no longer provided by the Fire Protection Association (£592k) and abatements on the training contract (£112k).

- Hardware and software (£610k) due to delays caused by implementation issues on number of major projects including the mobile data terminals, Windows 10 and Farynor. This underspend will be transferred into the ICT Development earmarked reserve to cover planned spend in 2018/19.

- Operational Equipment (£391k) mainly due to spend on Firefighter new technology project that did not happen this year and also an underspend on the flood response budget.

- Vehicle and equipment contract payments (£296k), due to abatements (£134k) and vehicle passthroughs (£162k) due to spend for the Ultra Low Emission Zone (ULEZ) that has been reallocated to the 2018/19 financial year.

- The underspends summarised above are in addition to £4,730k of underspends previously reported at the end of Quarter 3, which includes items identified as risks at the beginning of the financial year.

- The previously reported variances include significant underspending of £4,160k on operational staff budgets based on the then expected operational staff numbers, given forecasts for recruitment and leavers. Previously reported underspends also include a one-off budget of £830k that was created in 2017/18 to fund costs involved in offering inoculations to staff, based on co-responding being rolled out across the Brigade - which is being transferred to an earmarked reserve to cover the planned spend in future years. An underspend was also forecast of £2,017k on property rates due to the successful appeal that was lodged by the Estates Management Consultant for the 2010 valuations - this had previously been included as a saving in 2018/19 but has now been achieved earlier than originally expected. Also previously reported was additional Metropolitan Fire Brigade (MFB) Act income (£790k) and underspends on hydrants maintenance (£181) based on lower repairs than budgeted.

- As identified in previous reporting, the above underspends are offset by overspends on premises budgets (£1,725k) following the decision to progress a backlog of works aimed at improving the overall condition of the whole estate including repairs, refurbishment and minor improvements to properties; and on compensation budgets (£231k) due to a number of large value personal injury cases.

2018/19 Budget process

- As part of the 2018/19 Budget process, a review of previous years underspends was carried out to identify underspending areas in 2017/18 that could be taken as a saving in 2018/19. This led to savings of £2.6m, with other changes reported through adjustments to the Medium Term (MT) of £8.8m. Therefore, although there was an underspend totalling £11.9m in 2017/18, a sum of £11.4m has been removed from the 2018/19 budget. Key areas of underspend which have already been reflected in the 2018/19 budget include:

- Operational staff costs (underspent by £5.3m) - a one-off saving of £3.6m has been added to the existing £1.6m vacancy margin for 2018/19. This was agreed based on expected operational staff numbers given recruitment and leaver forecasts in 2018/19.

- MFB Act income (over recovered by £0.8m) -  has been increased by £2.1m in total for 2018/19 to £27.7m, an increase of 8%. This reflects the 2017/18 outturn position and a 5% inflationary increase.

- Professional development (underspent by £0.6m) due to a delay in a number of projects and abatements on the training contract. The MTF saving reflects the fixed fee element of the Training Contract that is reducing after the first six years of the contract.

- The savings and other adjustments, totalling £11.4m, are summarised in Table 1 below

Table 1: Underspends Incorporated in the 2018/19 Budget

|  | Revised Budget | Provisional Outturn Variance |  | 2018/19 Savings | MT Savings |
| --- | --- | --- | --- | --- | --- |
|  | £k | £k | % | £k | £k |
| Operational Staff | 234,889 | (5,255) | (2.2%) | (60) | (3,565) |
| FRS Staff | 47,431 | (1,428) | (3.0%) | (317) | 0 |
| Professional Development | 21,989 | (595) | (2.7%) | 0 | (3,280) |
| Recruitment | 267 | (24) | (8.9%) | (24) | 0 |
| Medical and Welfare Expenses | 2,713 | (913) | (33.7%) | (89) | 0 |
| Firefighter Pension Scheme | 20,489 | (144) | (0.7%) | 0 | (44) |
| Energy Costs | 2,031 | 158 | 7.8% | (48) | 0 |
| Property Rates | 9,166 | (3,112) | (34.0%) | 0 | (232) |
| Vehicle and Equipment Contract | 10,784 | (225) | (2.1%) | (40) | 0 |
| Vehicle Passthroughs | 605 | (314) | (51.8%) | (26) | 0 |
| Contract Hire & Operating Leases | 1,229 | (95) | (7.7%) | (21) | 0 |
| Hydrants | 581 | (201) | (34.5%) | (75) | 0 |
| Operational Equipment | 1,731 | (14) | (0.8%) | (31) | 0 |
| Equipment Furniture and Materials | 279 | 73 | 26.3% | (4) | 0 |
| Clothing & Laundry | 2,802 | 24 | 0.9% | (159) | 0 |
| General Office Expenses | 731 | (106) | (14.5%) | (5) | 0 |
| Professional Services | 8,909 | (287) | (3.2%) | (78) | 0 |
| Communications | 3,801 | 382 | 10.0% | (43) | 0 |
| Hardware and Software | 6,564 | (630) | (9.6%) | (160) | 0 |
| Staff Reimbursements | 316 | 30 | 9.6% | (74) | 0 |
| Other Supplies and Services | 57 | 26 | 46.2% | (12) | 0 |
| Other Local Authorities | 1,624 | 407 | 25.1% | (201) | 0 |
| Central Contingency | 24 | (24) | (100.0%) | (85) | 0 |
| MFB Act Income | (25,595) | (816) | 3.2% | (390) | (1,710) |
| Customer and Client Receipts | (9,923) | (1,405) | 14.2% | (658) | 0 |
| Underspends Incorporated in the 2018/19 Budget |  |  |  | (2,597) | (8,831) |

- The key variances that have led to the overall underspend are explained in more detail from paragraph 17 below.

Capital Summary

- The provisional outturn position for 2017/18 on the capital programme, before the year end application of the allowance for over-programming, is for an underspend of £15,235k. This is an increase of £6,433k from the underspend position reported as at the end of Quarter 3 (FEP2709). This is due to budget re-phasing to 2018/19 of £6,252k and budget savings of £506k, offset by £325k for new budget requirements.

- The remaining over-programming allowance in 2017/18 of £7,106k has also now been applied at year end, which has reduced the overall budget and reduced the outturn variance to an underspend of £8,129k. After accounting for this, the total movement in the outturn variance when compared to the Quarter 3 position, is for a small increase in spend of £673k.

- Over-programming was introduced into the capital budget in 2017/18 to help manage the overall capital programme – whilst individual projects are budgeted to expected timescales, with no delays expected, once this is consolidated as a programme, inevitably delays will be experienced. A number of the capital projects span multiple financial years, with the budget profiled over those years, and therefore underspending in a particular financial year is different to underspends on annual revenue budgets. Therefore the over-programming has had a positive impact, and has also helped in managing the revenue borrowing implications of the capital programme, with the relatively small overall movement of £673k from the Quarter 3 forecast to the outturn position.

Reasons for the Revenue Position

Staff

- The provisional outturn for the  operational staff budget is for an underspend of £5,255k, an increase of £1,094k since last reported at the end of Quarter 3. This relates to previously reported recruitment challenges (£6.7m), offset by a 2% pay award from 01 July 2017 (£1.5m). The underspend reflects an average of 196 vacancies in 2017/18. A one-off saving of £3.6m has been added to the existing £1.6m vacancy margin for 2018/19. This was agreed based on expected operational staff numbers given recruitment and leaver forecasts in 2018/19.

- FRS staff budgets have underspent by £1,428k, 3.0% of the total FRS staff budget. As at the end of March, there were 114 vacancies and 74 agency staff. The underspend is due to the recruitment to a number of roles taking longer than anticipated – this includes work in departments to prepare for recruitment, and not simply the selection and appointment process. The outturn also includes the one-off impact (£205k) for pay awards.

- Control staff have overspent by £191k due to high levels of overtime covering vacant posts, and due to the pay offer of 2% being above the 1% budgeted for. At the end of March, there were 1.8 vacancies within Control, and it is expected that the overtime costs will begin to reduce in the new financial year once new staff become competent.

Employee Related

- There is an underspend of £1,103k on Employee Related Budgets including £500k on Professional Development because of delays in a number of projects including delays in the commencement of Fire Safety training where a new course is being put in place with Babcock to replace the one previously provided by the Fire Protection Association, and £100k due to abatements on the training contract. As previously reported, there is also an underspend relating to a one-off budget of £830k that was created in 2017/18 to fund costs involved in offering inoculations to staff now transferred to an earmarked reserve to cover the planned spend in future years. These are offset by an overspend on compensation of £391k, due to a number of large value personal injury cases.

Firefighter Injury Pensions

- The underspend on Firefighter Injury Pensions of £144k was as a result of mortality and medical reviews.

Premises

- The underspend of £1,039k on Premises Budgets includes an underspend of £3,112k on property rates, offset by an overspend of £1,673k on building maintenance.

- The underspend on rates includes a £2,017k underspend following a successful appeal that was lodged by the Estates Management Consultant (Don & Wright) for the 2010 valuations. This had previously been included as a saving in 2018/19 but has now been achieved earlier than originally expected. The remaining rates underspend was due to surplus funding of £1,095k that could now be released following advice received from the Estates Management Consultant. This enabled rates liabilities, raised in 2016/17 for two PFI fire stations and a provision for Union Street, to be released.

- The overspend on building maintenance (£1,673k) was as a result of the decision to progress a backlog of works aimed at improving the overall condition of the whole estate, including repairs, refurbishment and minor improvements to properties.

Transport

- There is an underspend of £440k on transport budgets, an increase of £297k from the position reported at Quarter 3, on vehicle passthroughs (£162k) due to lower numbers of repairs and an additional underspend (£133k) on the vehicle and equipment contract due to abatements.

- The previously reported position at Quarter 3 included underspends of £152k on vehicle passthroughs, due to spend for the ultra low emission zone that has been reallocated to the 2018/19 financial year, abatements on the vehicle and equipment contract of £91k and reduction in spend of £95k in the  charges for lease cars. These underspends are offset by an overspend on insurance budgets of £245k following changes to the discount rates within personal injury markets and a higher cost of insurance claims.

Supplies and Services

- There is an underspend of £1,110k on Supplies and Services mainly on Hardware and Software (£630k) with delays due to a number of implementation issues on major projects including the mobile data terminals, Windows 10 and Farynor -  this underspend is to be transferred into the ICT Development earmarked reserve to cover planned spend in 2018/19. There were also underspends on hydrants maintenance (£201k) due to a lower number of repairs than budgeted and a reduction in spend as well as an adjustment to the balances on smoke alarms carried forward from previous years as part of the end of year reconciliations (£234k). The movement of £1,385k since last reported at the end of Quarter 3 is mainly due to £391k on Operational Equipment due to spend on the Firefighter new technology project (£202k) that has slipped to the next financial year, and underspend on the flood response budget (£59k) as well as delays due to a number of implementation issues on major projects on Hardware and Software £630k.

Income

- Income budgets have over recovered by £2,164k mainly due to MFB Act Income (£816k) and on Customer and Client receipts (£1,405k) due to the inclusion of £500k of funds for LIFE, cadets and borough led Community Safety initiatives which will be  transferred to the Fire Safety and Youth Engagement earmarked reserve, as well as £800k adjustment to balances carried forward from previous years relating to telecommunications income identified in the 2017/18 end of year reconciliation.

- Appendix 5 includes an update on the position on outstanding shut in lift debt.

Reserves

- Table 2 below sets out the position on the financial reserves, resulting from the financial position reported above. The balance on the general reserve, following the movements identified below, is £14,039k, the minimum general reserve position of 3.5% of the net revenue expenditure.

Table 2. Position on Reserves

| £000s | Opening Balance at 01/04/17 | Approved Movements | Underspend/ (Overspend) in 2017/18 | Use of Reserves in 2017/18 | Total Balance as at 31/03/18 | New Payments/ Transfers | Anticipated Balance at 01/04/18 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Additional Resilience Requirements | 0 | 6,757 |  | (1,984) | 4,773 |  | 4,773 |
| Community Safety Investment Fund | 602 |  |  | (501) | 101 |  | 101 |
| Compensation | 1,000 |  |  | 0 | 1,000 |  | 1,000 |
| Emergency Services Mobile Communication Programme | 356 |  |  | (178) | 178 |  | 178 |
| Emergency Medical Response | 0 | 830 |  | 0 | 830 |  | 830 |
| Firefighters' Pension | 1,172 |  |  | 0 | 1,172 |  | 1,172 |
| Fire Safety and Youth Engagement | 338 |  |  | 570 | 909 |  | 909 |
| Hazardous Material Protection | 203 |  |  | (185) | 18 |  | 18 |
| HMICFRS inspection regime | 0 |  |  | 0 | 0 | 149 | 149 |
| Hydrants | 462 |  |  | 0 | 462 |  | 462 |
| ICT Development Reserve | 668 |  |  | 642 | 1,310 | 600 | 1,910 |
| London Resilience | 1,281 |  |  | 970 | 2,250 |  | 2,250 |
| LSP2017 Implementation | 5,000 |  |  | (365) | 4,635 |  | 4,635 |
| New Governance Arrangements | 100 | 200 |  | 0 | 300 |  | 300 |
| Pension Early Release Costs | 400 |  |  | 0 | 400 |  | 400 |
| Property PFI | 1,912 |  |  | 0 | 1,912 | (1,912) | 0 |
| Recruitment/ Outreach | 600 |  |  | (182) | 418 | 83 | 501 |
| Review of Property Services | 85 | (85) |  | 0 | 0 |  | 0 |
| Sustainability | 235 |  |  | 0 | 235 |  | 235 |
| Vehicle & Equipment Reserve | 1,163 |  |  | 0 | 1,163 |  | 1,163 |
| Watch Structure Review | 0 |  |  | 0 | 0 | 168 | 168 |
| Budget Flexibility | 0 | 5,309 |  | 6,160 | 11,469 | 7,229 | 18,698 |
| General | 21,489 | (13,011) | 11,878 |  | 20,356 | (6,317) | 14,039 |
| Total | 37,065 | 0 | 11,878 | 4,947 | 53,890 | 0 | 53,890 |

- The reserves table above includes the establishment of a Government Inspection (HMICFRS) reserve to meet the costs of additional staff to facilitate the inspection regime and £83k supplementation of the Recruitment/Outreach reserve from 1 April. The above table also includes a £600k transfer of underspend into the ICT Development earmarked reserve to cover planned spend in 2018/19 and £168k to meet the costs of the Watch Structure Review. The new watch structure will further improve the resilience of the Brigade by simplifying and strengthening the officer structure at stations, with the intention to reduce officer out duties and improve appliance availability. This work was included as a financial risk in 2018/19 budget report (FEP2825) and the £168k will be used for system update costs, the update of existing training packages and the development of new training packages. The table also reflects an additional transfer of £7,229k to the Budget Flexibility reserve. This would increase the existing Budget Flexibility reserve from £11.5m to £18.7m..

- Table 3 below shows how the proposed increased balance on the Budget Flexibility reserve could help to further mitigate the budget deficit anticipated over the next four years. This would reduce the budget gap up to 2021/22 from £10.2m to £4.4m. Although it should be noted that as reserve funding only provides a one-off solution, this would increase any budget gap in 2022/23 by £5.8m. An update on the budget position in future years will be provided to the Commissioner’s Board once the Mayor’s budget guidance has been received, which is expected to be published towards the end of the month (June 2018).

Table 3 – Balance on Budget Flexibility Reserve

|  | 2018/19 | 2019/20 | 2020/21 | 2021/22 |
| --- | --- | --- | --- | --- |
|  | £m | £m | £m | £m |
| Budget Gap March | (4.4) | 8.7 | 8.5 | 10.2 |
| Payment into / (Draw from) Budget Flexibility Reserve | 4.4 | (8.7) | (8.5) | (5.8) |
| Budget Flexibility Reserve Balance | 23.1 | 14.4 | 5.8 | 0.0 |
| Revised Budget Gap | 0.0 | 0.0 | 0.0 | 4.4 |

Capital Programme

- The provisional outturn position for 2017/18 on the capital programme, before the application of the year end allowance for over-programming,  is an underspend of £15,235k. This is an increase of £6,433k from the underspend position reported as at the end of Quarter 3 (FEP2709). This is due to budget re-phasing to 2018/19 of £6,252k, mainly on Pumping Appliances and Fleet & Equipment replacement (£1,986k), Vehicle Security (£1,333k), Water hose and reels (£1,014k) and on a number of other projects and budget savings (£506k). This was offset by £325k for new budget requirements made up of Minor works for Heston and Paddington Fire Stations (£121k) and fees relating to the disposal of surplus assets (£204k).

- The remaining over-programming allowance in 2017/18 of £7,106k has also now been applied at year end, which has reduced the overall budget and reduced the outturn variance to an underspend of £8,129k. After accounting for this the total movement in the outturn variance is for a small increase in spend of £673k.

Budget re-phased to 2018/19 – (£6,252k)

- The main Budget items  re-phased to 2018/19 are discussed in more detail below:

- Fleet Replacement  Project - The stage payments for the 2nd batch of pumping appliances have been re-phased following changes in the programme rollout. This has resulted in £480k being deferred to 2018/19. In addition, based on the current delivery times for the new equipment, £1,506k has been carried forward to 2018/19, of this £1,259k will fund the new Battery Powered Combi and Dedicated Cutter Tools for frontline and reserve Mercedes Series 1, 2 and 3 pumping appliances. There have been a number of delays in the project around costings, and accommodating additional supplier requests during the tender process resulting in extending timescales.

- Fleet Associated Projects - The CCTV, vehicle security and water hose projects are being delivered on the same rollout as the pumping appliance programme and as such £290k, £1,333k and £1,014k respectively has been carried forward to 2018/19.

- Minor works of £476k has also been re-phased to 2018/19 mainly due to works at Croydon and Wennington Fire Stations.  Croydon Fire Station -  Showers Refurbishment (£227k), has been delayed due to a value engineering exercise being undertaken to bring the project back within budget.  Wennington Fire  Station - Kitchen Refurbishment  (£132k) has been re-phased because of delays at pre-start stage for a review of the kitchen ventilation design and to ensure adequate provision and siting of temporary kitchen and mess facilities.  Works at both sites are now scheduled to commence in 2018/19.

- PEG/BDC Development - The lease agreement for the new, and combined, PEG / BDC facility (Integrated Equipment and Logistics Project - IELP) was finally signed at the end of February 2018. This resulted in delays in obtaining the landlord’s licence for the fit-out/adaptation works and completion of the tender package. £123k has been carried forward to 2018/19.

- Merton Control Centre - Data transfer (transformation grant) - The project is being developed by Capita and other partner agencies who are developing their own control systems with a target date for a working solution of late summer. The project will be completed in the next financial year and £195k has been carried forward to 2018/19 to fund the remaining works.

Future Years

- A review is being undertaken regarding the options to replace the Respiratory Protection Equipment. It is envisaged that the procurement will commence during 2018 and it is estimated that the cost is circa £2.3m. Accordingly, £2.3m has been added to the capital budget in 2018/19. The budget will be updated once the outcome of the review is known.

- The specification for the replacement of the incident grounds communications is currently being worked up. The budget has been reviewed and it is now expected that the cost of the scheme will be circa £1.8m compared to the original projection of £1.3m. The final budget will be updated once the procurement has been undertaken and the actual price determined.

Capital Receipts

- The projected capital receipt for the former Southwark fire station has been reduced to £42.2m as detailed in report FEP2832, with £21.1m being forecast to be received during 2018/19 and the remaining 50% during 2019/20 financial year. The GLA will be providing £11.8m in 2018/19 to cover the reduction in the receipt for Southwark.  In addition, the level of the projected sale receipt for the former Clerkenwell fire station has also been reviewed in light of current market conditions and the reduced value is now £7.5m, compared to the original forecast of £10m. It is also forecast that this receipt will be received during 2018/19.

- Table 4 below shows a summary of the movements from the financial position as the end of December (Quarter 3) and the impact on the capital budget in future years.

Table 4 – Summary of Movements from Quarter 3

| Budget Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Quarter 3 FEP 2709 - Resources Committee | 20,344 | 39,098 | 47,006 | 21,382 | 23,090 |  |
| ICT – Business Intelligence Solution | (54) | 54 |  |  |  | Budget slippage to 2018/19 |
| ICT Replacement of Laptops | (45) | 45 |  |  |  | Budget slippage to 2018/19 |
| ICT – Accident Reporting Solution | (62) | 62 |  |  |  | Budget slippage to 2018/19 |
| ICT – New Telephone Equipment | (42) | 42 |  |  |  | Budget slippage to 2018/19 |
| ICT – New Legacy PC’s | (41) | 41 |  |  |  | Budget slippage to 2018/19 |
| ICT – Farynor Project | (50) | 50 |  |  |  | Budget slippage to 2018/19 |
| ICT – Removal of over programming | 420 |  |  |  |  | Removal of ICT budget over programming |
| ICT Wireless LAN Controllers | (19) |  |  |  |  | Budget saving |
| Merton Control Centre - Data transfer | (195) | 195 |  |  |  | Budget slippage to 2018/19 |
| Minor Works – Battersea FS – Gates | (74) | 74 |  |  |  | Budget slippage to 2018/19 |
| Minor Works - Croydon FS – Showers | (227) | 227 |  |  |  | Budget slippage to 2018/19 |
| Minor Works - Wennington – Kitchen | (132) | 132 |  |  |  | Budget slippage to 2018/19 |
| Minor Works – Eltham Hill FS - Showers | (43) | 43 |  |  |  | Budget slippage to 2018/19 |
| Minor Works – Heston FS – Line Training Facilities | 41 |  |  |  |  | New approved projects |
| Minor Works – Paddington FS- Fitness Facilities | 80 |  |  |  |  | New approved projects |
| Window Replacements – Chiswick FS | (110) | 110 |  |  |  | Budget slippage to 2018/19 |
| Appliance Bay Doors | (188) | 188 |  |  |  | Budget slippage to 2018/19 |
| New Cross FS – Yard Works | (149) | 51 |  |  |  | Budget slippage to 2018/19 |
| Workplace Plan Improvements Union St | (133) | 60 |  |  |  | Budget slippage to 2018/19 |
| Heating at various fire stations | (104) | 61 |  |  |  | Budget slippage to 2018/19 |
| West Hampstead Cottages Refurb | (16) | 16 |  |  |  | Budget slippage to 2018/19 |
| New Training Centre | (71) | 71 |  |  |  | Budget slippage to 2018/19 |
| PEG/BDC Development | (123) | 123 |  |  |  | Budget slippage to 2018/19 |
| West Norwood New Fire Station | (45) |  |  |  |  | Refund of project costs |
| Rewiring at various fire stations | (24) |  |  |  |  | Project savings |
| Alterations to Union Street (HQ) | (27) |  |  |  |  | Project savings |
| Development costs | (163) |  |  |  |  | Project savings |
| Pumping Appliances | (480) | 480 |  |  |  | Budget slippage to 2018/19 |
| CCTV on Pumping Appliances | (290) | 290 |  |  |  | Budget slippage to 2018/19 |
| 22mm Water Hose and Reels | (1,014) | 1,014 |  |  |  | Budget slippage to 2018/19 |
| Security on Pumping Appliances | (1,333) | 1,333 |  |  |  | Budget slippage to 2018/19 |
| Other vehicle & equip replacements | (1,506) | 1,506 |  |  |  | Budget slippage to 2018/19 |
| Other savings | 2 |  |  |  |  | Project costs |
| Replacement of the incident grounds communications | 0 | 500 |  |  |  | Additional budget requirement |
| Business Management System (PMF) |  | (215) | 215 |  |  |  |
| Respiratory Protective Equipment | 0 | 2,300 |  |  |  | New budget requirement |
| Removal of over programming | 6,686 | (6,686) |  |  |  | Budget slippage to 2018/19 |
| Disposal fees for surplus assets | 204 |  |  |  |  |  |
| Capital Programme Outturn Report | 21,017 | 41,265 | 47,221 | 21,382 | 23,090 |  |
| Change | 673 | 2,167 | 0 | 0 | 0 |  |

Future Capital Budget

- Table 5 below sets out the proposed revised capital programme and funding over the period 2018/19 to 2021/22. The revised spend forecast has resulted in a potential saving in the debt charges for 2018/19 of £460k, this is due to the deferral of schemes to later years. Future borrowing requirements will be reviewed as part of the ongoing budget process.  Additional detail on these figures can be found in Appendix 3.

Table 5 – Proposed Revised Capital Programme and Funding for Future Years

| Budget Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 |
| --- | --- | --- | --- | --- | --- |
| ICT | 1,483 | 5,385 | 815 | 2,360 | 2,000 |
| Fleet | 14,183 | 23,287 | 25,290 | 10,738 | 11,680 |
| Property | 5,147 | 19,279 | 21,116 | 8,284 | 9,410 |
| Disposal Fees | 204 | 0 |  |  |  |
| Contingency | 0 | (6,686) | 0 | 0 | 0 |
| Capital Programme | 21,017 | 41,265 | 47,221 | 21,382 | 23,090 |

| Budget Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 |
| --- | --- | --- | --- | --- | --- |
| Financing Requirement | 21,017 | 41,265 | 47,221 | 21,382 | 23,090 |
| Capital Receipts | (20,842) | (29,270) | (21,245) |  |  |
| Grants | (175) | (195) |  |  |  |
| GLA Funding |  | (11,800) |  |  |  |
| Charitable Contribution |  |  | (2,500) |  |  |
| External Borrowing |  |  | (23,476) | (21,382) | (23,090) |
| TOTAL | 0 | 0 | 0 | 0 | 0 |

| Budget Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 |
| --- | --- | --- | --- | --- | --- |
| Capital Receipts C/fwd | 21,496 | 759 | 117 | 0 | 0 |
| Clerkenwell Receipt |  | 7,500 |  |  |  |
| Southwark Receipt |  | 21,128 | 21,128 |  |  |
| Sale of Fleet | 105 |  |  |  |  |
| Financing | (20,842) | (29,270) | (21,245) |  |  |
| Capital Receipts Balance | 759 | 117 | 0 | 0 | 0 |

Debtors

- An analysis of debtors relating to Shut in Lift charges is provided in Appendix 5. This includes a chart that shows the continued decrease in the amount of Shut in Lift debts outstanding over the past 18 months, with £88k outstanding at the end of March 2018. The continued joint effort by Authority staff has resulted in the positive progress made to date in recovering these debts.

Finance comments

- This report is presented by the Assistant Director - Finance and there are no further comments.

Workforce comments

- No staff-side consultations have been undertaken on this report.

Legal comments

- General Counsel has reviewed this report and has no comments.

Sustainable implications

- There are no direct sustainable implications.

Equalities implications

- This report has no equality implications.

List of Appendices to this report:

- Summary Financial Position

- Detailed Financial Position

- Capital Programme

- Risks to the Revenue and Capital Position

- Outstanding Lift debtors

- Financial Regulation 9: Budget Virements

- Financial Element on Performance

Consultation

| Name/role | Method consulted |
| --- | --- |
| Heads of Department | Departmental finance returns |

|  | Revised Budget | Provisional Outturn | Provisional Outturn Variance | Previous Forecast Outturn Variance | Movement between variance figures |
| --- | --- | --- | --- | --- | --- |
|  | £000s | £000s | £000s | £000s | £000s |
| Operational staff | 236,125 | 230,897 | (5,228) | (4,161) | (1,067) |
| Other staff | 52,740 | 51,503 | (1,237) | (360) | (877) |
| Employee related | 26,479 | 25,376 | (1,103) | (506) | (596) |
| Pensions | 20,489 | 20,345 | (144) | 84 | (228) |
| Premises | 37,097 | 36,059 | (1,039) | 325 | (1,364) |
| Transport | 15,292 | 14,852 | (440) | (143) | (297) |
| Supplies and services | 27,605 | 26,495 | (1,110) | 275 | (1,385) |
| Third party payments | 2,529 | 2,908 | 379 | 279 | 100 |
| Capital financing costs | 9,508 | 9,414 | (94) | 0 | (94) |
| Central contingency against inflation | 24 | 0 | (24) | 0 | (24) |
| Total revenue expenditure | 427,889 | 417,850 | (10,040) | (4,207) | (5,833) |
| Other income | (36,113) | (38,277) | (2,164) | (412) | (1,752) |
| Net revenue expenditure | 391,777 | 379,572 | (12,204) | (4,619) | (7,585) |
| Use of earmarked reserves | 4,376 | 4,947 | 571 | (0) | 571 |
| Financing Requirement | 396,153 | 384,519 | (11,633) | (4,619) | (7,014) |
| Financed by: |  |  |  |  |  |
| Specific grants | (13,753) | (13,997) | (244) | (111) | (134) |
| GLA funding | (382,400) | (382,400) | 0 | 0 | 0 |
| Net Financial Position | 0 | (11,878) | (11,878) | (4,730) | (7,148) |

|  | Original Budget | Revised Budget | Outturn | Outturn Variance |  | Previous Forecast Outturn Variance (Q3) | Movement between Q3 and outturn variance |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | £ | £ | £ | £ | % | £ | £ |
| Operational Staff | 233,410,405 | 234,889,172 | 229,634,377 | (5,254,794) | (2.2%) | (4,160,538) | (1,094,256) |
| Trainee Firefighters | 1,235,886 | 1,235,884 | 1,262,657 | 26,773 | 2.2% | 0 | 26,773 |
| Total Operational Staff | 234,646,291 | 236,125,056 | 230,897,035 | (5,228,021) | (2.2%) | (4,160,538) | (1,067,483) |
| FRS Staff | 45,520,950 | 47,430,877 | 46,002,982 | (1,427,895) | (3.0%) | (509,894) | (918,001) |
| Control Staff | 5,442,449 | 5,309,097 | 5,500,079 | 190,982 | 3.6% | 150,097 | 40,885 |
| Total Other Staff | 50,963,400 | 52,739,974 | 51,503,061 | (1,236,912) | (2.3%) | (359,797) | (877,115) |
| Other Pension Payments | 990,000 | 990,000 | 964,607 | (25,393) | (2.6%) | 0 | (25,393) |
| Severance | 0 | 129,392 | 210,244 | 80,852 | 62.5% | 13,566 | 67,287 |
| Professional Development | 20,911,224 | 21,988,813 | 21,393,705 | (595,108) | (2.7%) | 108,400 | (703,508) |
| Recruitment | 162,100 | 267,100 | 243,221 | (23,879) | (8.9%) | (13,597) | (10,282) |
| Employee Related Insurance | 190,000 | 197,218 | 207,590 | 10,372 | 5.3% | 15,165 | (4,793) |
| Compensation | 555,813 | 555,813 | 946,432 | 390,619 | 70.3% | 230,535 | 160,084 |
| Medical and Welfare Expenses | 2,782,076 | 2,713,071 | 1,799,680 | (913,391) | (33.7%) | (860,471) | (52,920) |
| Employee Capitalised Costs | (245,400) | (362,451) | (389,230) | (26,779) | 7.4% | (0) | (26,779) |
| Total Employee Related | 25,345,813 | 26,478,957 | 25,376,250 | (1,102,707) | (4.2%) | (506,402) | (596,304) |
| Firefighter Pension Scheme | 20,489,000 | 20,489,000 | 20,344,600 | (144,400) | (0.7%) | 84,009 | (228,409) |
| Building Maintenance | 7,241,163 | 7,011,287 | 8,683,977 | 1,672,690 | 23.9% | 1,725,240 | (52,550) |
| Grounds Maintenance | 118,382 | 132,396 | 98,617 | (33,779) | (25.5%) | 0 | (33,779) |
| Premises Security | 397,752 | 505,752 | 681,815 | 176,063 | 34.8% | 210,000 | (33,937) |
| Energy Costs | 2,031,205 | 2,031,205 | 2,189,626 | 158,421 | 7.8% | 60,000 | 98,421 |
| Rents | 7,801,412 | 7,935,163 | 8,115,180 | 180,017 | 2.3% | 181,326 | (1,309) |
| Property PFI Contract | 5,545,202 | 5,545,202 | 5,489,617 | (55,586) | (1.0%) | (60,000) | 4,414 |
| Property Rates | 9,291,368 | 9,166,368 | 6,053,895 | (3,112,473) | (34.0%) | (2,017,000) | (1,095,473) |
| Water & Sewerage Rates | 255,515 | 255,515 | 326,197 | 70,682 | 27.7% | 40,000 | 30,682 |
| Fixtures & Fittings | 332,861 | 111,980 | 192,148 | 80,168 | 71.6% | 100,568 | (20,400) |
| Cleaning and Domestic Supplies | 2,032,753 | 2,031,104 | 2,001,709 | (29,395) | (1.4%) | 250 | (29,645) |
| Premises Insurance | 372,000 | 372,000 | 304,281 | (67,719) | (18.2%) | (32,000) | (35,719) |
| Other Property Services | 1,526,726 | 1,999,524 | 1,921,930 | (77,594) | (3.9%) | 117,000 | (194,594) |
| Total Premises | 36,946,338 | 37,097,495 | 36,058,991 | (1,038,504) | (2.8%) | 325,384 | (1,363,888) |
| Running Costs | 2,092,597 | 1,717,861 | 1,963,207 | 245,346 | 14.3% | 229,243 | 16,103 |
| Vehicle and Equipment Contract | 10,783,624 | 10,783,624 | 10,558,852 | (224,773) | (2.1%) | (90,880) | (133,893) |
| Vehicle Passthroughs | 645,172 | 605,465 | 291,594 | (313,872) | (51.8%) | (151,661) | (162,211) |
| Maintenance and Repairs | 905,000 | 0 | 6,211 | 6,211 | 0.0% | 0 | 6,211 |
| Contract Hire & Operating Leases | 1,189,900 | 1,228,821 | 1,134,201 | (94,620) | (7.7%) | (88,698) | (5,922) |
| Travel | 1,122,627 | 956,655 | 898,422 | (58,233) | (6.1%) | (41,424) | (16,809) |
| Total Transport | 16,738,920 | 15,292,427 | 14,852,487 | (439,939) | (2.9%) | (143,420) | (296,519) |
| Hydrants | 600,900 | 581,492 | 380,790 | (200,702) | (34.5%) | (181,455) | (19,247) |
| Operational Equipment | 2,123,414 | 1,731,453 | 1,717,381 | (14,071) | (0.8%) | 377,334 | (391,406) |
| Smoke Alarms | 700,000 | 708,357 | 474,179 | (234,178) | (33.1%) | 11,418 | (245,596) |
| Equipment Furniture and Materials | 534,188 | 278,789 | 352,136 | 73,347 | 26.3% | 17,194 | 56,153 |
| Lost & NFWT Operational Equipment | 107,387 | 107,387 | 45,473 | (61,914) | (57.7%) | 3 | (61,917) |
| Catering | 120,104 | 318,591 | 278,610 | (39,981) | (12.5%) | (29,842) | (10,139) |
| Clothing & Laundry | 2,790,337 | 2,801,982 | 2,825,891 | 23,908 | 0.9% | (20,470) | 44,378 |
| General Office Expenses | 378,869 | 731,056 | 625,014 | (106,042) | (14.5%) | 74,634 | (180,676) |
| Professional Services | 8,550,475 | 8,909,468 | 8,622,269 | (287,198) | (3.2%) | 26,925 | (314,124) |
| Postal Services | 61,255 | 61,276 | 71,829 | 10,552 | 17.2% | (40) | 10,592 |
| Communications | 3,567,294 | 3,801,193 | 4,182,940 | 381,746 | 10.0% | 14,042 | 367,704 |
| Hardware and Software | 6,121,843 | 6,564,474 | 5,934,583 | (629,892) | (9.6%) | (19,251) | (610,641) |
| Staff Reimbursements | 450,565 | 315,764 | 345,942 | 30,178 | 9.6% | 29,415 | 763 |
| Grants and Subscriptions | 225,724 | 235,841 | 182,896 | (52,944) | (22.4%) | 1,820 | (54,764) |
| Other Insurance | 225,000 | 227,446 | 189,060 | (38,386) | (16.9%) | (39,333) | 947 |
| Advertising | 112,450 | 173,488 | 181,912 | 8,424 | 4.9% | 9,347 | (923) |
| Other Supplies and Services | 212,476 | 57,224 | 84,385 | 27,161 | 47.5% | 3,417 | 23,744 |
| Total Supplies and Services | 26,882,280 | 27,605,280 | 26,495,289 | (1,109,992) | (4.0%) | 275,160 | (1,385,152) |
| Other Agencies | 315,700 | 816,812 | 786,717 | (30,095) | (3.7%) | (30,700) | 605 |
| Other Local Authorities | 1,325,102 | 1,623,706 | 2,030,887 | 407,181 | 25.1% | 309,557 | 97,624 |
| Audit & Bank Charges | 88,600 | 88,600 | 90,425 | 1,825 | 2.1% | 0 | 1,825 |
| Total Third Party Payments | 1,729,402 | 2,529,117 | 2,908,028 | 378,911 | 15.0% | 278,857 | 100,054 |
| Debt Repayment | 5,882,000 | 5,882,000 | 5,886,534 | 4,534 | 0.1% | 0 | 4,534 |
| External Interest | 3,626,000 | 3,626,000 | 3,527,473 | (98,527) | (2.7%) | 0 | (98,527) |
| Total Capital Financing Costs | 9,508,000 | 9,508,000 | 9,414,007 | (93,993) | (1.0%) | 0 | (93,993) |
| Central Contingency | 2,198,900 | 24,023 | 0 | (24,023) | (100.0%) | 2 | (24,025) |
| Total revenue expenditure | 425,448,344 | 427,889,329 | 417,849,748 | (10,039,582) | (2.3%) | (4,206,746) | (5,832,835) |
| MFB Act Income | (25,595,000) | (25,595,000) | (26,411,400) | (816,400) | 3.2% | (789,899) | (26,501) |
| Customer and Client Receipts | (8,381,538) | (9,922,801) | (11,327,724) | (1,404,922) | 14.2% | 182,471 | (1,587,393) |
| Interest Receivable | (595,000) | (595,000) | (446,872) | 148,128 | (24.9%) | 195,000 | (46,872) |
| Bad Debts | 0 | 0 | (91,264) | (91,264) | 0.0% | 0 | (91,264) |
| Total Other Income | (34,571,538) | (36,112,801) | (38,277,260) | (2,164,458) | 6.0% | (412,428) | (1,752,030) |
| Net revenue expenditure | 390,876,806 | 391,776,528 | 379,572,488 | (12,204,040) | (3.1%) | (4,619,174) | (7,584,866) |
| Use of Earmarked Reserves | 3,748,957 | 4,376,409 | 4,946,963 | 570,554 | 13.0% | 0 | 570,554 |
| Financing Requirement | 394,625,763 | 396,152,937 | 384,519,451 | (11,633,486) | (2.9%) | (4,619,174) | (7,014,312) |
| Financed by: |  |  |  |  |  |  |  |
| Specific grants | (12,225,763) | (13,752,937) | (13,997,403) | (244,466) | 1.8% | (110,717) | (133,749) |
| GLA Grant | (382,400,000) | (382,400,000) | (382,400,000) | 0 | 0.0% | 0 | 0 |
| Net Financial Position | 0 | 0 | (11,877,952) | (11,877,952) | 0.0% | (4,729,891) | (7,148,061) |

|  | 2017-18 Capital Budget July 17 Resources | Outturn 2017/18 | Variance |  | Last position 2017/18 Quarter 3 FEP2709 | Variance |  | Savings/ Budget transfer | Transfer to 2018/19 and later years | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ICT Projects | £’000s | £’000s | £’000s |  | £’000s | £’000s |  | £’000s | £’000s |  |
| Upgrade Operating System | 98 | 0 | (98) |  | 0 | 0 |  | 0 | 0 |  |
| Business Intelligent Solution | 900 | 196 | (704) |  | 250 | (54) |  | 0 | (54) | To 2018/19 |
| Control & Mobilisation System (CAMS) | 470 | 11 | (459) |  | 0 | 11 |  | 11 | 0 |  |
| Mobile Data Terminals Replacement | 288 | 57 | (231) |  | 57 | 0 |  | 0 | 0 |  |
| Home Fire Safety Database | 130 | 0 | (130) |  | 0 | 0 |  | 0 | 0 |  |
| Replacement of laptops (FEP2462) | 131 | 289 | 158 |  | 334 | (45) |  | 0 | (45) | To 2018/19 |
| Public Services Network | 707 | 0 | (707) |  | 0 | 0 |  | 0 | 0 |  |
| Accident (event) reporting solution | 70 | 68 | 2 |  | 130 | (62) |  | 0 | (62) | To 2018/19 |
| Online Payment Facility | 70 | 0 | (70) |  | 0 | 0 |  | 0 | 0 |  |
| Audio visual equip for Union Street | 130 | 150 | 20 |  | 150 | 0 |  | 0 | 0 |  |
| Blade Farm/ Hyperconverged Server | 300 | 0 | (300) |  | 0 | 0 |  | 0 | 0 |  |
| ICT – Virtual Desktop Technology | 250 | 0 | (250) |  | 0 | 0 |  | 0 | 0 |  |
| New telephone system equipment | 157 | 115 | (42) |  | 157 | (42) |  | 0 | (42) | To 2018/19 |
| New computer terminals | 69 | 28 | (41) |  | 69 | (41) |  | 0 | (41) | To 2018/19 |
| Core Switch Modules | 300 | 0 | (300) |  | 0 | 0 |  | 0 | 0 |  |
| Wireless LAN Controllers | 198 | 101 | (97) |  | 120 | (19) |  | (19) | 0 |  |
| Station Network Rewires | 100 | 0 | (100) |  | 0 | 0 |  | 0 | 0 |  |
| Physical Server Environment | 500 | 293 | (207) |  | 300 | (7) |  | (7) | 0 |  |
| Establishing a London Co-ordination Centre | 111 | 104 | (7) |  | 111 | (7) |  | (7) | 0 |  |
| Joint Emergency Services Interoperability Programme | 266 | 71 | (195) |  | 266 | (195) |  | 0 | (195) | To 2018/19 |
| Farynor Replacement | 425 | 0 | (425) |  | 50 | (50) |  | 0 | (50) | To 2018/19 |
| Performance Management System | 190 | 0 | (190) |  | 0 | 0 |  | 0 | 0 |  |
| ICT Projects Over programming | (1,098) | 0 | 1,098 |  | (420) | 420 |  | 420 | 0 |  |
| ICT PROJECTS | 4,762 | 1,483 | (3,279) |  | 1,574 | (91) |  | 398 | (489) |  |
| ESTATE PROJECTS |  |  |  |  |  |  |  |  |  |  |
| Fire Station Refurbishment (Middx) | 100 | 0 | (100) |  | 0 | 0 |  | 0 | 0 |  |
| Alteration works to Union St HQ | 75 | 15 | (60) |  | 42 | (27) |  | (27) | 0 | Budget savings |
| West Norwood New Fire Station | 0 | (45) | (45) |  | 0 | (45) |  | (45) | 0 | Refund of project costs |
| Workplace Plan (WIP) Union Street | 240 | 107 | (133) |  | 240 | (133) |  | (73) | (60) | £60k c/fwd to 2018/19 |
| Re-develop Plumstead Fire Station | 2,500 | 0 | (2,500) |  | 0 | 0 |  | 0 | 0 |  |
| Bromley FS works | 214 | 240 | 26 |  | 240 | 0 |  | 0 | 0 |  |
| LFB Museum – Fitout | 0 | 18 | 18 |  | 18 | 0 |  | 0 | 0 |  |
| Refurbishment of Edmonton F.S. | 50 | 0 | (50) |  | 0 | 0 |  | 0 | 0 |  |
| Heating at various fire stations | 1,575 | 1,471 | (104) |  | 1,575 | (104) |  | (43) | (61) | £61k c/fwd to 2018/19 |
| Window replacement at fire stations | 300 | 30 | (270) |  | 140 | (110) |  | 0 | (110) | To 2018/19 |
| Rewiring at various fire stations | 592 | 765 | 173 |  | 789 | (24) |  | (24) | 0 | Budget savings |
| Building Energy Efficiency (BEEP2) | 789 | 755 | (34) |  | 764 | (9) |  | (9) | 0 | Budget savings |
| Minor Improvement Programme | 1,681 | 670 | (1,011) |  | 1,002 | (332) |  | 144 | (476) | £60k budget savings from Heating & £95k budget savings rear years transfer to minor works - £476k to 2018/19 |
| Corporate Property Project | 50 | 0 | (50) |  | 0 | 0 |  | 0 | 0 |  |
| Appliance Bay Doors (Phase 3) | 220 | 177 | 43 |  | 365 | (188) |  | 0 | (188) | To 2018/19 |
| Appliance Bay Floors | 250 | 0 | (250) |  | 0 | 0 |  | 0 | 0 |  |
| Asbestos Removal | 50 | 20 | (30) |  | 50 | (30) |  | (30) | 0 | Budget savings |
| Fire Safety Works at Fire Stations | 54 | 83 | 29 |  | 60 | 23 |  | 23 | 0 | Budget savings |
| Forecourts/Rear yards refurbishment | 450 | 301 | (149) |  | 450 | (149) |  | (98) | (51) | £51k c/fwd to 2018/19 |
| Asset Management Plan | 200 | 0 | (200) |  | 0 | 0 |  | 0 | 0 |  |
| West Hampstead Cottages Refurb | 0 | 4 | 4 |  | 20 | (16) |  | 0 | (16) | To 2018/19 |
| Security at Fire Stations, Offices & HQ | 200 | 0 | (200) |  | 0 | 0 |  | 0 | 0 |  |
| New Training Centre | 478 | 326 | (152) |  | 397 | (71) |  | 0 | (71) | To 2018/19 |
| PEG/BDC Development | 3,750 | 217 | (3,533) |  | 340 | (123) |  | 0 | (123) | To 2018/19 |
| Development costs | 250 | (7) | (257) |  | 156 | (163) |  | (163) | 0 | Budget savings |
| ESTATE PROJECTS | 14,068 | 5,147 | (8,921) |  | 6,648 | (1,501) |  | (345) | (1,156) |  |
| FLEET & EQUIPMENT PROJECTS |  |  |  |  |  |  |  |  |  |  |
| Replacement of Fleet & Equipment | 11,884 | 13,504 | 1,620 |  | 15,490 | (1,986) |  | 0 | (1,986) | To 2018/19 |
| Fire Initial Response Equipment system | 24 | 22 | (2) |  | 24 | (2) |  | (2) | 0 |  |
| Early Replacement of ALP & HP | 1,800 | 0 | (1,800) |  | 0 | 0 |  | 0 | 0 |  |
| CCTV on Pumping Appliances | 405 | 115 | (290) |  | 405 | (290) |  | 0 | (290) | To 2018/19 |
| 22mm Water Hose and Reel for Appliances | 1,500 | 486 | (1,014) |  | 1,500 | (1,014) |  | 0 | (1,014) | To 2018/19 |
| Vehicle Security | 1,389 | 56 | (1,333) |  | 1,389 | (1,333) |  | 0 | (1,333) | To 2018/19 |
| OTHER | 17,002 | 14,183 | (2,819) |  | 18,808 | (4,625) |  | (2) | (4,623) |  |
| Projected Underspend | (6,686) | 0 | (6,686) |  | (6,686) | 6,686 |  | 0 | 6,686 | To 2018/19 |
| Disposal fees for surplus site | 0 | 204 | 204 |  | 0 | 204 | 0 | 204 | 0 |  |
| CAPITAL EXPENDITURE TOTAL | 29,146 | 21,017 | (8,129) |  | 20,344 | 673 |  | 255 | 418 |  |

| FUTURE CAPITAL PROGRAMME | 2018-19 Budget March 18 Resources Committee | B/fwd from 2017-18 Outturn | C/fwd to 2019/20/savings New Projects | 2018-19 Budget 2017-18 OUTTURN REPORT |  | 2019/20 Budget | 2020/21 Budget | 2021/22 Budget | Prior Years Spend | Projected project Spend | Approved budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ICT Projects | £’000s | £’000s | £’000s | £’000s |  | £’000s | £’000s | £’000s | £’000s | £’000s | £’000s |
| Upgrade Operating System | 98 | 0 | 0 | 98 |  | 0 | 0 | 0 | 2,091 | 2,189 | 2,350 |
| Business Intelligent Solution | 600 | 54 | 0 | 654 |  | 600 | 360 | 0 | 196 | 1,810 | 1,810 |
| Control & Mobilisation System (CAMS) | 470 | 0 | 0 | 470 |  | 0 | 0 | 0 | 9,013 | 9,483 | 10,650 |
| Mobile Data Terminals Replacement | 71 | 0 | 0 | 71 |  | 0 | 0 | 0 | 2,029 | 2,100 | 2,100 |
| Replacement of the incident grounds communications | 1,300 | 0 | 500 | 1,800 |  | 0 | 0 | 0 | 0 | 1,800 | Q4 18-19 |
| Home Fire Safety Database (linked to Farynor Project) | 130 | 0 | 0 | 130 |  | 0 | 0 | 0 | 0 | 130 | n/a |
| Replacement of laptops (FEP2462) | 0 | 45 | 0 | 45 |  | 0 | 0 | 0 | 358 | 403 | 450 |
| Public Services Network | 707 | 0 | 0 | 707 |  | 0 | 0 | 0 | 0 | 707 | Q4 16-17 |
| ICT – Accident (event) reporting solution | 0 | 62 | 0 | 62 |  | 0 | 0 | 0 | 68 | 130 | 130 |
| Online Payment Facility | 70 | 0 | 0 | 70 |  | 0 | 0 | 0 | 0 | 70 | Q4 17-18 |
| ICT – Virtual Desktop Technology | 250 | 0 | 0 | 250 |  | 0 | 0 | 0 | 0 | 250 | TBA |
| New telephone system equipment | 0 | 42 | 0 | 42 |  | 0 | 0 | 0 | 115 | 157 | 157 |
| New computer terminals | 0 | 41 | 0 | 41 |  | 0 | 0 | 0 | 28 | 69 | 75 |
| Netscaller Replacement | 0 | 0 | 0 | 0 |  | 400 | 0 | 0 | 0 | 400 | TBA |
| Core Network 6509 Replacement | 0 | 0 | 0 | 0 |  | 0 | 1,900 | 0 | 0 | 1,900 | TBA |
| Core Switch Modules | 300 | 0 | 0 | 300 |  | 0 | 0 | 0 | 0 | 300 | TBA |
| Network Access Switches 3650 Replacement | 0 | 0 | 0 | 0 |  | 750 | 0 | 0 | 0 | 750 | TBA |
| Wireless Access Points | 853 | 0 | 0 | 853 |  | 0 | 0 | 0 | 0 | 853 | TBA |
| Data Centre Switches 3750 Replacement | 104 | 0 | 0 | 104 |  | 0 | 0 | 0 | 0 | 104 | TBA |
| Station Network Rewires | 200 | 0 | 0 | 200 |  | 100 | 100 | 0 | 0 | 400 | TBA |
| New ISP | 0 | 0 | 0 | 0 |  | 500 | 0 | 0 | 0 | 500 | TBA |
| New WAN | 0 | 0 | 0 | 0 |  | 0 | 500 | 0 | 0 | 500 | TBA |
| VM Server Environment Hosts | 0 | 0 | 0 | 0 |  | 500 | 0 | 0 | 0 | 500 | TBA |
| Network Storage | 750 | 0 | 0 | 750 |  | 0 | 0 | 0 | 0 | 750 | TBA |
| Replacement of laptops | 0 | 0 | 0 | 0 |  | 563 | 0 | 0 | 0 | 563 | TBA |
| New computer terminals - Thin Client | 0 | 0 | 0 | 0 |  | 0 | 1,150 | 0 | 0 | 1,150 | TBA |
| New audio visual equip for Stations | 0 | 0 | 0 | 0 |  | 0 | 100 | 0 | 0 | 100 | TBA |
| New computer terminals - Fat Client | 0 | 0 | 0 | 0 |  | 100 | 0 | 0 | 0 | 100 | TBA |
| Data transfer system for Joint Emergency Services Interoperability Programme | 0 | 195 | 0 | 195 |  | 0 | 0 | 0 | 71 | 266 | 266 |
| Farynor Replacement (linked to ICT Home Fire Safety Database Project) | 700 | 50 | 0 | 750 |  | 0 | 0 | 0 | 0 | 750 | £100k fees |
| Business Management System (PMF) | 215 | 0 | (215) | 0 |  | 215 | 0 | 0 | 0 | 215 | TBA |
| ICT Projects Over programming/to be allocated | (2,207) | 0 | 0 | (2,207) |  | (2,913) | (1,750) | 2,000 | 0 | (4,870) | TBA |
| ICT PROJECTS | 4,611 | 489 | 285 | 5,385 |  | 815 | 2,360 | 2,000 | 13,969 | 24,529 |  |
| ESTATE PROJECTS |  |  |  |  |  |  |  |  |  |  |  |
| Fire Station Refurbishment (Middx FS) | 100 | 0 | 0 | 100 |  | 1,167 | 2,000 | 5,260 | n/a | 3,267 | n/a |
| Workplace Improvement Plan (WIP) Union Street | 0 | 60 | 0 | 60 |  | 0 | 0 | 0 | 107 | 240 | 240 |
| Plumstead Fire Station Redevelopment | 1,500 | 0 | 0 | 1,500 |  | 4,350 | 147 | 0 | 0 | n/a | n/a |
| LFB Museum – Fit-out | 30 | 0 | 0 | 30 |  | 2,352 | 0 | 0 | 18 | 2,400 | 2,400 |
| Refurbishment of Edmonton Fire Station | 100 | 0 | 0 | 100 |  | 890 | 0 | 0 | 0 | 990 | Mar 2018 |
| Heating at various stations | 1,350 | 61 | 0 | 1,411 |  | 1,350 | 1,350 | 1,350 | n/a | n/a | n/a |
| Window replacement at various stations | 400 | 110 | 0 | 510 |  | 400 | 400 | 400 | n/a | n/a | n/a |
| Rewiring of property at various fire stations | 600 | 0 | 0 | 600 |  | 600 | 600 | 600 | n/a | n/a | n/a |
| Minor Improvement Programme | 1,467 | 476 | 0 | 1,943 |  | 1,300 | 1,300 | 1,300 | n/a | n/a | n/a |
| Appliance Bay Doors (Phase 3) | 475 | 188 | 0 | 663 |  | 200 | 200 | 200 | n/a | n/a | n/a |
| Brigade wide Survey for Asbestos & Removal | 50 | 0 | 0 | 50 |  | 50 | 50 | 50 | n/a | n/a | n/a |
| Fire Safety Works at Fire Stations | 47 | 0 | 0 | 47 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Forecourts/Rear yards Refurbishment | 0 | 51 | 0 | 51 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Improve Security at all Fire Stations, Offices & HQ | 100 | 0 | 0 | 100 |  | 1,255 | 1,250 | 0 | 0 | 2,605 | TBA |
| New Training Centre * | 7,374 | 71 | 0 | 7,445 |  | 6,872 | 737 | 0 | 446 | 15,500 | 15,500 |
| PEG/BDC Development | 3,610 | 123 | 0 | 3,733 |  | 50 | 0 | 0 | 217 | 4,000 | 4,000 |
| West Hampstead Cottages Refurb (FEP2776) | 670 | 16 | 0 | 686 |  | 30 | 0 | 0 | 4 | 720 | 720 |
| Development costs | 250 | 0 | 0 | 250 |  | 250 | 250 | 250 | n/a | n/a | n/a |
| ESTATE PROJECTS | 18,123 | 1,156 | 0 | 19,279 |  | 21,116 | 8,284 | 9,410 |  |  |  |
| FLEET AND EQUIPMENT PROJECTS |  |  |  |  |  |  |  |  |  |  |  |
| Replacement of Fleet and Operational Equipment | 11,535 | 1,986 | 0 | 13,521 |  | 22,510 | 10,488 | 11,680 | 10,813 | 69,012 | TBA |
| Respiratory Protective Equipment | 0 | 0 | 2,300 | 2,300 |  | 0 | 0 | 0 | 0 | 2,300 | TBA |
| Early Replacement of ALP & HP* | 3,750 | 0 | 0 | 3,750 |  | 1,530 | 0 | 0 | 0 | 5,280 | 5,280 |
| CCTV on Pumping Appliances * | 79 | 290 | 0 | 369 |  | 0 | 0 | 0 | 115 | 484 | 501 |
| Early Replacement of Fire Boat* | 1,000 | 0 | 0 | 1,000 |  | 1,250 | 250 | 0 | 20 | 2,520 | 2,500 |
| 22mm Water Hose and Reel for Appliances * | 0 | 1,014 | 0 | 1,014 |  | 0 | 0 | 0 | 486 | 1,500 | 1,500 |
| Vehicle Security * | 0 | 1,333 | 0 | 1,333 |  | 0 | 0 | 0 | 56 | 1,389 | 1,389 |
| OTHER | 16,364 | 4,623 | 2,300 | 23,287 |  | 25,290 | 10,738 | 11,680 | 11,490 | 82,485 |  |
| Projected Underspend | 0 | (6,686) | 0 | (6,686) |  | 0 | 0 | 0 | 0 | (6,686) | n/a |
| CAPITAL EXPENDITURE TOTAL | 39,098 | (418) | 2,585 | 41,265 |  | 47,221 | 21,382 | 23,090 |  |  |  |

- Property Services

  - The 2017/18 budget includes £630k of savings from the implementation of the Property Services Integrator, which includes an estimate of savings that can be achieved on LFC’s supply chain. This saving will be updated once the supply chain has been fully costed once the mobilisation phase is completed, with final contracts in place in 2018/19. The savings target is based on an average saving each year to meet the overall savings target agreed over the contract life. It should be noted that a growth bid is expected to be required as the costs for the mechanical, electrical and plumbing, and building fabric contracts, which are in the process of being retendered, are expected to come in higher than current costs due to market changes since it was last tendered. This cannot be confirmed until the tenders are returned later in the year.

  - The savings for 2017/18 included material savings for energy budgets. These budgets have underspent in recent years, in part because of the prudent assumptions used when calculating the budget requirement. These additional savings therefore set the budget at a less cautious level, and as a result increased the risk of overspends in subsequent years, for example because of a colder than average winter. This report includes an overspend of £158k on energy budgets, therefore the risk of overspend will continue into 2018/19.  The energy budgets will be kept under review.

- Potential Risks/ Changes to the Capital Programme

  - The capital budget is an evolving entity which is subject to change throughout the year. Initial project specification is key as it is important to keep variations to projects to a minimum, as change, once a project has been agreed and commenced will invariably result in additional costs. However even the best managed projects can be subject to re-phasing or deferral due to a number of unforeseen issues, such as contractor capacity/failure, bad weather and revised operational need. This can also impact on funding requirements that in turn have a debt charge (cost of borrowing) revenue impact.

  - All capital projects will require third party collaboration to varying degrees over the project life. The following major projects, that make up over 75% of the programme, depend heavily on external parties actions and therefore can be subject to variation with the potential for delays in project delivery and revised cash flow requirements.

Vehicle Replacement Programme

  - The key risks relate to the contractor sourcing appropriate vehicle build options within a timeframe that meets fleet replacement requirements and which in turn impact the Authority’s cash flow. The forecast cash expenditure for 2018/19 and future years is based on the current assessment of the stage payment requirements for the pump replacement programme and other vehicle replacements  which represents over 50% of the forecast Vehicles and Equipment expenditure.  Any delay and revisions to the delivery timings for the fleet replacement assets will impact the actual spend incurred in the financial year.

Control and Mobilising Solution (CAMS)

  - The Brigade implemented its new mobilising system (Vision4) in November 2015,however there are a number of other work streams within the project that are still to be delivered. Update releases have been scheduled through 2018 and 2019 for this outstanding functionality. The status of this project is Blue (closed) as reported in FEP2823.

Plumstead Redevelopment/PEG&BDC Project/New Training Centre

  - As the new site for Plumstead fire station is yet to be purchased or a lease agreed, there is therefore a risk that the project will be delayed in to later years. The LFB Training Centre project has a dependency on PEG moving out of Croydon, any delay to the PEG/BDC development may have a knock on effect on the delivery of the Training Centre programme.  The lease agreement for the new combined PEG/BDC facility (Integrated and Equipment Logistics Project – IELP) has been recently signed and the fit-out/adaptation works are to commence shortly. Should these risks in respect of site acquisition/programme delays materialise, this could result in reduced expenditure in future years compared to the current forecast budgets for these major capital projects.

The chart below shows the amount of outstanding LIFT debts over the last 18 months, with £88k outstanding at the end of March 2018. The graph shows a continuing downward trend in the level of outstanding debt.

The table below shows the top 5 (worst) outstanding debtors for LIFT income.

| Row Labels | £ outstanding | Average of Age | No of invoices |
| --- | --- | --- | --- |
| TESCO STORES LTD | 6,036 | 997 | 17 |
| NETWORK HOMES | 3,938 | 908 | 11 |
| WHITBREAD HOTEL COMPANY | 3,530 | 344 | 9 |
| OM PROPERTY MANAGEMENT | 3,114 | 1,233 | 9 |
| C/O PEVEREL RETIREMENT | 3,011 | 1,145 | 10 |
| Grand Total | 19,630 | 939 | 56 |

The top five (worst) outstanding debtors, totalling £19,630, has continued to decrease over the past years. This reached a peak of £105k at the end of September 2015 and reduced down to £48k as at the end of September 2017 but has further reduced to £20k as at the end of March 2018. The continued joint effort by Authority staff has resulted in the positive progress made to date.

Review of the Top 5 debtors

Tesco’s Store LTD:

Debt chasing letters have been sent to Tesco stores within the North West and South East Areas. A payment was expected but has not been forthcoming. A joint referral has been sent to  General Counsel’s Department for Legal action.

Network Homes:

Officers have been informed that Network Homes is now operating under a new name, and further information on the new name/owner is now being pursued.

Whitbread Hotel Company:

This company had promised to pay their outstanding invoices but has not yet done so. Whitbread Hotel debts have been referred to General Counsel’s Department for further action.

OM Property Management:

This debt has been referred to General Counsel’s Department for further action.

C/O Peverel Retirement

Officers are currently awaiting payments for all 10 outstanding invoices. Copy invoices were re-sent but no payment has yet been received. A final reminder letter has been sent.

Financial Regulation 9:

“(b) With the agreement of the Director of Corporate Services, a Head of Service may transfer up to £50,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget, but if those budget heads are in different Directorates the agreement of the appropriate Director or Commissioner is also required.

(c) With the agreement of the Director of Corporate Services, Directors may transfer up to £150,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget.

(e) The Director of Corporate Services shall report all transfers under (b) and (c) to the Commissioner as part of the quarterly Financial Position reports.“

No transfers were processed in Quarter 4 that require reporting.

| LFC Revenue (£000s) | Budget | Outturn | Variance |
| --- | --- | --- | --- |
| Operational staff | 236,125 | 230,897 | (5,228) |
| Other staff | 52,740 | 51,503 | (1,237) |
| Employee related | 26,479 | 25,376 | (1,103) |
| Pensions | 20,489 | 20,345 | (144) |
| Premises | 37,097 | 36,059 | (1,039) |
| Transport | 15,292 | 14,852 | (440) |
| Supplies | 27,605 | 26,495 | (1,110) |
| Third party | 2,529 | 2,908 | 379 |
| Capital financing | 9,508 | 9,414 | (94) |
| Contingency | 24 | 0 | (24) |
| Income | (36,113) | (38,277) | (2,164) |
| Net revenue expenditure | 391,777 | 379,572 | (12,204) |
| Use of reserves | 4,376 | 4,947 | 571 |
| Financing Requirement | 396,153 | 384,519 | (11,633) |
| Financed by: |  |  |  |
| Specific grants | (13,753) | (13,997) | (244) |
| GLA funding | (382,400) | (382,400) | 0 |
| Net Financial Position | 0 | (11,878) | (11,878) |

| LFC Capital (£000s) | Budget | Outturn | Variance |
| --- | --- | --- | --- |
| ICT Projects | 4,762 | 1,483 | (3,279) |
| Estate Projects | 14,068 | 5,147 | (8,921) |
| Other Projects | 17,002 | 14,183 | (2,819) |
| Contingency | (6,686) | 0 | (6,686) |
| Disposal fees for surplus site | 0 | 204 | 204 |
| Total capital expenditure | 29,146 | 21,017 | (8,129) |
| Financed by: |  |  |  |
| Capital Receipts | 29,146 | 20,842 | (8,304) |
| Grants | 0 | 175 | 175 |
| Borrowing | 0 | 0 | 0 |
| Total | 29,146 | 21,017 | (8,129) |

Revenue Position

The provisional outturn position is for an underspend of £11.9m and related to the following main items:

- Operational Salaries (£5.3m)

- Other staff (£1.2m)

- Employee related (£1.1m)

- Premises (£1.0)

- Supplies and Services (£1.1m)

- Additional income (£2.1)

Capital Position

The approved capital programme for 2017/18 is £29.1m and the provisional outturn is £21.0m, which is £8.1m less than the budget. This variance relates to the following main items , and are largely as a result of re-phasing between financial years.

- Fleet Associated Projects (£2.1m)

- PEG/BDC Development (£3.5m)

- Plumstead Re-development (£2.5m)