| Report title |  |  |
| --- | --- | --- |
| Financial Position as at the end of June 2017 |  |  |
| Meeting | Date |  |
| Resources Committee | 15 September 2017 |  |
| Report by | Document Number |  |
| Director of Finance and Contractual Services |  |  |
| Public |  |  |

Summary

This report presents the financial position as at the end of June 2017 (quarter 1). It provides information on financial performance against revenue and capital budgets.

Recommendation

That the report be noted.

- Introduction

- This report considers the financial position as at the end of June 2017, including a forecast of outturn at the financial year end.

- All departments review their actual income and expenditure on a regular basis, and provide an updated forecast of outturn and explanation of variances, against all their budgets, to the Finance Department. These returns then form the basis of reporting to the Corporate Management Board and from there on to the Resources Committee and the Greater London Authority on a quarterly basis.

- Background to 2017/18 Budget

- The 2017/18 budget was approved by the Authority at its meeting on 30 March 2017 (FEP 2708). The Authority’s net revenue budget is £390,708k, with a net payment of £4,062k into earmarked reserves, £12,342k funding from specific grants and savings of £7,665k.

- This report sets out a summary position on both the revenue and capital budgets, and then provides more detailed explanations of variances.

- Revenue

- The forecast outturn position for 2017/18 on the revenue budget is an underspend of £4,953k (1.3%). This forecast underspend position will continue to be monitored throughout the 2017/18 financial year. In the meantime this report shows how the underspend could be used to supplement the Budget Flexibility Reserve and help to mitigate the budget deficit anticipated over the next four years. This would increase the existing Budget Flexibility reserve from £6.2m to £11.1m.

- It should also be noted that this forecast underspend position of £5.0m excludes the impact of any pay awards above budget in 2017/18. The National Joint Council Employer’s Side has made a pay offer to operational staff for a 2% rise to be paid from 1 July 2017. This offer was rejected by the FBU ‘in its current form’ in July 2017. However discussions between the two sides are continuing. If a pay award were agreed at this level it would reduce the forecast underspend by £1.5m.

- The underspend of £4,953k is mainly  due to an underspend of £4,348k on operational staff budgets based on expected operational staff numbers given forecasts for recruitment and leavers. In addition there are underspends of £734k on computing budgets due to reduced infrastructure, server and hardware costs, £187k on hydrants maintenance due to a lower number of repairs than budgeted, £157k on the professional services budget due to service credits on the Control and Mobilising Services contract, £105k on medical & welfare budgets and £100k for clothing underspends at stations, as well as additional income of £254k from leasing space at Union Street.

- The above underspends are offset by overspends of £500k required to progress a backlog of works across the whole estate including repairs, refurbishment and minor improvements. This includes the replacement of water and heating boilers at some fire stations before the winter period, drill tower repairs, replacement of kitchen extract systems, refurbishment of camp out facilities and replacement of UPS batteries at Merton LOC. There is also £267k on insurance costs due to an increase in the cost of insurance premiums following changes to the discount rates within the personal injury markets, and a higher forecast cost of settling insurance claims, and additional expenditure on control staff of £230k due to overtime cover.

- It should be noted that this forecast does not include any additional expenditure resulting from the Commissioner’s review of resources following recent events (FEP2763). The current assumption is that these will be met from reserves. This will be kept under review as the year progresses.

- The key variances are explained in more detail from paragraph 12 below.

- Capital

- The approved capital programme for 2017/18 has a budget of £29,146k. A review of the future capital programmed was carried out in light of the 2016/17 outturn, with a revised capital programme reported to Resources Committee in July (FEP 2750). The current forecast capital spend for 2017/18 is £28,970k, which is £176k  less than the capital budget.

- The capital programme will be further reviewed as decisions are made on the Integrated Equipment and Logistics Project (as outlined in FEP 2757) and the additional resilience requirements (as outlined in FEP 2763). Further details on these items, and the change above to the capital programme are set out from paragraph 26.

- Tables and Appendices to this report

- A summary of the financial position for the revenue budget is provided in Table 1. The latest position on reserves is set out in Table 2. Appendix 1 contains additional detail on the current and forecast financial position. Appendix 2 reports on the forecast outturn on the capital programme. Appendix  3 discusses the risks to the revenue and capital position that have not been quantified. Appendix  4 meets the requirement to disclose all budget virements within the quarter under financial regulation 9 and Appendix 5 provides an analysis of outstanding debt relating to charges for Shut in Lift attendances.

Table 1. Summary Financial Position

|  | Current Budget | Current Spend | Current Variance | Revised Budget | Forecast Outturn | Forecast Outturn Variance |
| --- | --- | --- | --- | --- | --- | --- |
|  | £000s | £000s | £000s | £000s | £000s | £000s |
| Operational staff | 58,361 | 57,790 | (571) | 233,048 | 228,700 | (4,348) |
| Other staff | 12,294 | 13,772 | 1,478 | 51,026 | 51,256 | 230 |
| Employee related | 21,210 | 20,770 | (440) | 26,306 | 26,161 | (145) |
| Pensions | 5,000 | 3,283 | (1,717) | 20,489 | 20,489 | 0 |
| Premises | 17,500 | 17,349 | (151) | 36,778 | 37,255 | 477 |
| Transport | 13,441 | 13,384 | (57) | 15,352 | 15,530 | 178 |
| Supplies and services | 17,555 | 16,113 | (1,442) | 27,313 | 26,222 | (1,092) |
| Third party payments | 504 | 153 | (351) | 2,414 | 2,414 | 0 |
| Capital financing costs | 245 | 213 | (32) | 9,508 | 9,508 | 0 |
| Central contingency against inflation | 5 | 0 | (5) | 3,006 | 3,006 | 0 |
| Total revenue expenditure | 146,114 | 142,826 | (3,288) | 425,240 | 420,540 | (4,700) |
| Other income | (22,852) | (22,133) | 719 | (34,532) | (34,785) | (254) |
| Net revenue expenditure | 123,263 | 120,693 | (2,569) | 390,708 | 385,755 | (4,953) |
| Use of earmarked reserves | 0 | 0 | 0 | 4,062 | 4,062 | 0 |
| Financing Requirement | 123,263 | 120,693 | (2,569) | 394,770 | 389,816 | (4,953) |
| Financed by: |  |  |  |  |  |  |
| Specific grants | (9,912) | (9,062) | 850 | (12,342) | (12,342) | 0 |
| GLA funding | 0 | 0 | 0 | (382,428) | (382,428) | 0 |
| Net Financial Position | 113,351 | 111,632 | (1,719) | 0 | (4,953) | (4,953) |

Reasons for the Revenue Position

Staff

- The budget for operational staff is forecast to underspend by £4,348k. The 2017/18 Budget (FEP2708) included a one off saving in 2017/18 of £2,334k on operational staff based on expected staff numbers given recruitment and leaver forecasts at the time. These forecasts have now been updated and the expected number of vacancies has increased from 90 to176, with this increase mostly due to a reduction in the expected number of firefighter trainees and the number of transferees from other brigades. It is planned that the Resources Committee will receive a report at its September meeting on plans for the recruitment of further trainee firefighters in 2017/18 and 2018/19. This will include an update on recent campaigns.

- Control staff budgets are forecast to overspend by £230k. Overtime levels remain high due to additional staff cover.

- It should also be noted that this forecast underspend position of £5.0m excludes the impact of any pay awards above budget in 2017/18. The National Joint Council Employer’s Side has made a pay offer to operational staff for a 2% rise to be paid from 1 July 2017. This offer was rejected by the FBU ‘in its current form’ in July 2017. However discussions between the two sides are continuing. If a pay award were agreed at this level it would reduce the forecast underspend by £1.5m.

- Employee Related

- Professional development budgets are forecast to underspend by £49k due to an underspend on the apprenticeship levy. Starting in April 2017, all organisations with a pay bill of over £1m were required to pay HMRC 0.5% of their payroll cost as a levy that can later be used to fund apprenticeship programmes. The payments made in 2017/18 are forecast to underspend against the budget due to the number of staff vacancies. There is also a forecast underspend on medical and welfare budgets of £105k due to a lower than expected number of asbestos medical appointments, medical appeals and a lower than forecast inflationary increase.

Premises

- Premises budgets are forecast to overspend by £477k due to considerable pressure on the reactive small works and minor projects required to progress a backlog of works across the whole estate. This  includes repairs, refurbishment and minor improvements all aimed at improving the overall condition of the estate. This includes the replacement of water and heating boilers at some fire stations before the winter period, drill tower repairs, replacement of kitchen extract systems, refurbishment of camp out facilities and replacement of UPS batteries at Merton LOC.

Transport

- Transport budgets are forecast to overspend by £178k. This includes a forecast overspend on insurance budgets (£267k) following changes to the discount rates within personal injury markets and a higher forecast cost of insurance claims. There is currently an actuarial review into the appropriate level of excess, which will affect the premium. This is offset by a forecast underspend on the vehicle and equipment contract (£60k) based on a forecast abatement levels.

- Supplies and Services

- There is a forecast underspend of £1,092k on supplies and services budgets. This includes underspends on computing (£734k) including orders of £264k for the new hyper converged server infrastructure and £356k for support of server and desktop hardware that were budgeted for in 2017/18 but expenditure was charged to 2016/17. It also includes a one off underspend of £121k due to transitional arrangements associated with the implementation of the new Wide Area Network.

- The variance on supplies and services is also due to a one off underspend on professional services (£157k) due to the impact of service credits attributable to the Control and Mobilising Services contract, on hydrants maintenance (£187k) based on lower repairs than budgeted and on clothing spend at stations (£100k) due to a lower replacement rate of new workwear and reduced spend because of current vacancies. This is offset by a forecast overspend on equipment, furniture and materials (£71k) related to floor moves, office desks conversions and other associated work at union street. Note the responsibility for delivering hydrants maintenance has now moved to the Procurement department, who are carrying out a review of the existing budget.

- Income

- There is a forecast over recovery of £254k on income. This is due to expected increased income from the GLA for additional space at Union Street. This is subject to additional building works being completed by the end of July 2017 and will also be considered as part of the budget process for future years.

- 2018/19 Budget Update

- The Mayor’s Budget Guidance for 2018/19 was published on 13 June 2017 and set out the overall funding the Mayor intends to provide LFEPA over the next four financial years. A report (FEP2733) setting out the resulting processes and timetable in order to deliver a balanced budget for LFEPA in 2018/19 was presented to Authority in June 2017.

- A further Budget update report will be presented to Resources in September and Authority in October. That report will include an update to LFEPA’s medium term forecast and the resulting budget gap for the next four years up to 2021/22, based on the funding levels provided by the Mayor. This will take into account the revenue pressures highlighted in the Commissioner’s report on additional resourcing requirements as presented to the Resources Committee at its meeting in July (FEP2763).

Position on Reserves

- The forecast position on reserves is set out in Table 2 below. Movements on the reserves applied in year together with the underspend for the year, leave a balance on the general reserve at the year end of £14,817k. This is £1,142k in excess of the stated minimum level of £13,675k, which is 3.5% of the net revenue expenditure budget. This  also includes the transfer of the forecast £5.0m underspend from the general reserve to the Budget Flexibility reserve. This funding will then help to mitigate the budget deficit anticipated over the next four years.

Table 2. LFEPA Reserves for the 2016/17 Financial Year

| £000s | Opening Balance at 01/04/17 | Underspend/ (Overspend) in 2017/18 | Use of Reserves in 2017/18 | Transfers between Reserves | Anticipated Balance at 31/03/18 |
| --- | --- | --- | --- | --- | --- |
| Additional Resilience Requirements | 0 |  | 0 | 6,757 | 6,757 |
| Community Safety Investment Fund | 602 |  | (602) |  | 0 |
| Compensation | 1,000 |  | 0 |  | 1,000 |
| Emergency Services Mobile Communication Programme | 356 |  | (204) |  | 151 |
| Firefighters' Pension | 1,172 |  | 0 |  | 1,172 |
| Fire Safety and Youth Engagement | 338 |  | 0 |  | 338 |
| Hazardous Material Protection | 203 |  | (159) |  | 44 |
| Hydrants | 462 |  | 0 |  | 462 |
| ICT Development Reserve | 668 |  | (368) |  | 300 |
| London Resilience | 1,281 |  | 0 |  | 1,281 |
| LSP2017 Implementation | 5,000 |  | (441) |  | 4,559 |
| New Governance Arrangements | 100 |  | 0 |  | 100 |
| Pension Early Release Costs | 400 |  | 0 |  | 400 |
| Property PFI | 1,912 |  | 0 |  | 1,912 |
| Recruitment/ Outreach | 600 |  | (325) |  | 275 |
| Review of Property Services | 85 |  | 0 | (85) | 0 |
| Sustainability | 235 |  | 0 |  | 235 |
| Vehicle & Equipment Reserve | 1,163 |  | 0 |  | 1,163 |
| Budget Flexibility | 0 |  | 6,160 | 4,953 | 11,113 |
| General | 21,489 | 4,953 |  | (11,625) | 14,817 |
| Total | 37,065 | 4,953 | 4,062 | 0 | 46,080 |

- The reserves table above includes the establishment of an Additional Resilience reserve to meet forecast costs in 2017/18 arising from an initial assessment of the LFB resources requirement following recent events (FEP 2763). The reserve has been funded by a transfer from the general reserve of £6,757k, and work is underway to confirm the costs to be met from this reserve.

- Other drawings from earmarked reserves in 2017/18 include:

- £602k for the Community Safety Investment Fund,

- £441k for implementation of LSP2017,

- £368k to fund ICT developments,

- £325k to fund the recruitment and outreach team,

- £204k to fund the Emergency Services Mobile Communication Programme, and

- £159k from the hazmat reserve to fund new gas tight suits.

- Capital

- The capital programme for 2017/18 was agreed by the Resources Committee in July 2017 (FEP2750) with a budget of £29,146k. The current forecast capital spend for 2017/18 is £28,970, which is £176k  less than the capital budget. The overall reduction in spend of £176k relates to the following items;

- Budget re-allocation

- LFB Training Centre £176k to 2018/19m

- New Budget Requirements in future years

- LFB Training Centre £4.4m

- LFB Training Centre at Croydon – cost estimates have now been updated for this project, which has resulted in an additional budget requirement of £4.4m. The sum includes the revised estimate from the Real Fire Training Specialist for the provision of the fire house. A report was presented to the Resources Committee in July (FEP2759), and additional funding approved. In addition, the budget has now been re-phased in line with the development timetable, with £176k transferred from 2017/18 to 2018/19.

- Integrated Equipment and Logistics Project (PEG/BDC Development) –  A report was presented to the Resources Committee in July (FEP2757) on various options available, with approval provided to undertake the proposed development at a leasehold site with a capital cost not exceeding £3,795k, and with the annual rental and rates liability not exceeding £660k per annum. The capital budget will be amended once the final site/development has been agreed and the associated capital costs are known.

- The Commissioner’s report to the Resources Committee in July (FEP2763) on additional resourcing requirements included a number of capital items. The funding for these will be added to the capital programme during the year as the detailed specifications are drawn up.

- In the meantime current changes to the capital programme are set out below, and full details of the capital programme are at Appendix 2.

| Budget Year | 2017-18 £k | 2018-19 £k | 2019-20 £k | 2020-21 £k | Notes |
| --- | --- | --- | --- | --- | --- |
| July 17 Resources Com (FEP2750) | 29,146 | 66,273 | 31,549 | 26,443 |  |
| New Training Centre (FEP2759) | (176) | (2,134) | 6,506 | 205 | Additional £4.4m budget reqmt |
| Capital Programme Qtr 1 2017 | 28,970 | 64,139 | 38,055 | 26,648 |  |

| CAPITAL BUDGET | 2017/18 Capital Budget £k | 2018/19 Capital Budget £k | 2019/20 Capital Budget £k | 2020/21 Capital Budget £k |
| --- | --- | --- | --- | --- |
| Estates Projects | 9,440 | 12,557 | 4,347 | 5,700 |
| ICT Projects | 3,770 | 2,210 | 0 | 2,000 |
| Fleet | 12,285 | 20,448 | 15,445 | 8,493 |
| New Projects | 10,161 | 28,924 | 18,263 | 10,455 |
| Projected Underspend | (6,686) | 0 | 0 | 0 |
| Disposal Costs | 0 | 0 | 0 | 0 |
| PFI Projects | 0 | 0 | 0 | 0 |
| TOTAL | 28,970 | 64,139 | 38,055 | 26,648 |

Debtors

- Charging for Shut in Lift attendances started in January 2010, following which it became apparent that there were difficulties with debt collection for a number of those attendances. As a result reporting on outstanding debt, as part of the quarterly financial position reports, began in June 2014.

- An analysis of debtors relating to Shut in Lift is provided in Appendix 5. This includes a chart that shows the decrease in Shut in Lift debts over the past years and since inception of shut in lift charges. The total number of shut in lift debts has been falling gradually over the last two years, after peaking in 2015, with the overall balance reduced from £300k at the end of September 2015 to £160k at the end of April 2017.

- The continued joint effort by Authority staff has resulted in the positive progress made to date on shut in lift debts recovery. As a result it is proposed that reporting on this debt will no longer form part of the quarterly financial position reports and that it will continue to be managed as part of LFEPA’s usual debt management procedures.

Head of Legal and Democratic Services comments

- The Head of Legal and Democratic Services has reviewed this report and has no comments.

Director of Finance and Contractual Services comments

- This report is presented by the Director of Finance and Contractual Services and there are no further comments.

Sustainable Development Implications

- There are no direct sustainable development implications.

Staff Side Consultations Undertaken

- No staff-side consultations have been undertaken on this report.

Equalities Implications

- This report has no equality implications.

| List of Appendices to this report: - Financial Position, 2017/18 Forecast Outturn - Capital Programme 2017/18 - Risks to the Revenue and Capital Position - Financial Regulation 9: Budget Virements - Outstanding LIFT debtors |  |
| --- | --- |
| LOCAL GOVERNMENT (ACCESS TO INFORMATION) ACT 1985 |  |
| List of background documents - FEP2708 2017/18 Budget - FEP2750 Review of Financial Outturn for 2016/17 |  |
| Proper officer | Director of Finance and Contractual Services |
| Contact officer Telephone Email | Adrian Bloomfield 020 8555 1200 x31351 Adrian.Bloomfield@london-fire.gov.uk |

|  | Current Budget | Current Spend | Current Variance |  | Original Budget | Revised Budget | Outturn | Outturn Variance |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | £ | £ | £ | % | £ | £ | £ | £ | % |
| Operational Firefighters | 58,310,468 | 57,515,445 | (795,023) | (1.4%) | 233,410,405 | 231,811,884 | 227,463,957 | (4,347,927) | (1.9%) |
| Firefighter Trainees | 50,246 | 274,456 | 224,210 | 446.2% | 1,235,886 | 1,235,884 | 1,235,884 | 0 | 0.0% |
| Total Operational Staff | 58,360,714 | 57,789,901 | (570,813) | (1.0%) | 234,646,291 | 233,047,768 | 228,699,841 | (4,347,927) | (1.9%) |
| FRS Staff | 10,995,778 | 12,422,512 | 1,426,734 | 13.0% | 45,520,950 | 45,776,533 | 45,776,533 | 0 | 0.0% |
| Control Staff | 1,297,978 | 1,348,991 | 51,013 | 3.9% | 5,442,449 | 5,249,312 | 5,479,099 | 229,787 | 4.4% |
| Total Other Staff | 12,293,756 | 13,771,503 | 1,477,747 | 12.0% | 50,963,400 | 51,025,845 | 51,255,632 | 229,787 | 0.5% |
| Other Pensions Payment | 165,000 | 167,411 | 2,411 | 1.5% | 990,000 | 990,000 | 990,000 | 0 | 0.0% |
| Severance | 0 | (2,173) | (2,173) | 0.0% | 0 | 33,681 | 47,246 | 13,565 | 40.3% |
| Professional Development | 20,368,804 | 20,031,988 | (336,817) | (1.7%) | 20,911,224 | 22,019,835 | 21,970,596 | (49,239) | (0.2%) |
| Recruitment | 52,790 | 47,159 | (5,631) | (10.7%) | 162,100 | 212,100 | 207,713 | (4,387) | (2.1%) |
| Employee Related Insurance | 0 | 48,253 | 48,253 | 0.0% | 190,000 | 190,000 | 190,000 | 0 | 0.0% |
| Compensation | 138,953 | 60,525 | (78,429) | (56.4%) | 555,813 | 555,813 | 555,813 | 0 | 0.0% |
| Medical & Welfare Expense | 484,514 | 450,982 | (33,532) | (6.9%) | 2,782,076 | 2,782,076 | 2,676,900 | (105,176) | (3.8%) |
| Capitalised Staff Charges | 0 | (34,242) | (34,242) | 0.0% | (245,400) | (477,610) | (477,610) | 0 | 0.0% |
| Total Employee Related | 21,210,062 | 20,769,902 | (440,160) | (2.1%) | 25,345,813 | 26,305,895 | 26,160,658 | (145,237) | (0.6%) |
| Firefighter Pension Scheme | 4,999,750 | 3,282,775 | (1,716,975) | (34.3%) | 20,489,000 | 20,489,000 | 20,489,000 | 0 | 0.0% |
| Building Maintenance | 3,492,602 | 3,473,779 | (18,822) | (0.5%) | 7,241,163 | 6,788,188 | 7,263,188 | 475,000 | 7.0% |
| Grounds Maintenance | 19,144 | 9,865 | (9,279) | (48.5%) | 118,382 | 146,396 | 146,396 | 0 | 0.0% |
| Premises Security | 356,200 | 382,210 | 26,010 | 7.3% | 397,752 | 425,752 | 425,752 | 0 | 0.0% |
| Energy Costs | 249,096 | 246,232 | (2,864) | (1.1%) | 2,031,205 | 2,031,205 | 2,031,205 | 0 | 0.0% |
| Rents | 3,566,068 | 3,617,165 | 51,097 | 1.4% | 7,801,412 | 7,808,252 | 7,810,256 | 2,004 | 0.0% |
| Property PFI Contract | 5,523,164 | 5,541,577 | 18,414 | 0.3% | 5,545,202 | 5,545,202 | 5,545,202 | 0 | 0.0% |
| Property Rates | 2,093,836 | 1,887,977 | (205,859) | (9.8%) | 9,291,368 | 9,291,368 | 9,291,368 | 0 | 0.0% |
| Water & Sewerage Rates | 36,159 | 36,485 | 326 | 0.9% | 255,515 | 255,515 | 255,515 | 0 | 0.0% |
| Fixtures & Fittings | 28,962 | 35,424 | 6,462 | 22.3% | 332,861 | 97,969 | 97,969 | 0 | 0.0% |
| Cleaning and Domestic Supplies | 343,509 | 221,955 | (121,554) | (35.4%) | 2,032,753 | 2,020,097 | 2,020,097 | 0 | 0.0% |
| Premises Insurance | 0 | 90,772 | 90,772 | 0.0% | 372,000 | 372,000 | 372,000 | 0 | 0.0% |
| Other Property Services | 1,791,316 | 1,805,508 | 14,191 | 0.8% | 1,526,726 | 1,996,140 | 1,996,140 | 0 | 0.0% |
| Total Premises | 17,500,053 | 17,348,948 | (151,105) | (0.9%) | 36,946,338 | 36,778,083 | 37,255,087 | 477,004 | 1.3% |
| Running Costs | 1,149,562 | 1,459,782 | 310,220 | 27.0% | 2,092,597 | 1,651,897 | 1,919,098 | 267,201 | 16.2% |
| Vehicle and Equipment Contract | 10,783,624 | 10,709,557 | (74,068) | (0.7%) | 10,783,624 | 10,783,624 | 10,723,624 | (60,000) | (0.6%) |
| Vehicle Passthroughs | 605,465 | 269,525 | (335,941) | (55.5%) | 645,172 | 605,465 | 605,465 | 0 | 0.0% |
| Maintenance and Repairs | 0 | 0 | 0 | 0.0% | 905,000 | 0 | 0 | 0 | 0.0% |
| Contract Hire & Operating Leases | 635,232 | 657,426 | 22,193 | 3.5% | 1,189,900 | 1,228,300 | 1,194,822 | (33,478) | (2.7%) |
| Travel | 266,769 | 287,750 | 20,982 | 7.9% | 1,122,627 | 1,082,445 | 1,087,145 | 4,700 | 0.4% |
| Total Transport | 13,440,652 | 13,384,039 | (56,613) | (0.4%) | 16,738,920 | 15,351,731 | 15,530,154 | 178,423 | 1.2% |
| Hydrants | 303,162 | 256,569 | (46,593) | (15.4%) | 600,900 | 587,444 | 400,000 | (187,444) | (31.9%) |
| Operational Equipment | 429,082 | 583,863 | 154,781 | 36.1% | 2,123,414 | 2,141,814 | 2,142,443 | 629 | 0.0% |
| Smoke Alarms | 210,000 | 241,051 | 31,051 | 14.8% | 700,000 | 700,000 | 700,000 | 0 | 0.0% |
| Equipment Furniture and Materials | 177,173 | 324,804 | 147,631 | 83.3% | 534,188 | 619,055 | 689,930 | 70,875 | 11.4% |
| Lost & NFWT Operational Equipment | 85,472 | 85,474 | 2 | 0.0% | 107,387 | 107,387 | 107,387 | 0 | 0.0% |
| Catering | 96,226 | 98,015 | 1,789 | 1.9% | 120,104 | 335,497 | 336,516 | 1,019 | 0.3% |
| Clothing & Laundry | 2,234,469 | 2,566,123 | 331,654 | 14.8% | 2,790,337 | 2,760,835 | 2,661,228 | (99,607) | (3.6%) |
| General Office Expenses | 117,829 | 97,442 | (20,387) | (17.3%) | 378,869 | 356,496 | 355,908 | (588) | (0.2%) |
| Professional Services | 7,712,967 | 7,837,581 | 124,615 | 1.6% | 8,550,475 | 8,458,680 | 8,301,525 | (157,156) | (1.9%) |
| Postal Services | 55,162 | 56,626 | 1,463 | 2.7% | 61,255 | 61,255 | 61,255 | 0 | 0.0% |
| Telecommunications & Radio | 3,376,496 | 938,267 | (2,438,229) | (72.2%) | 3,567,294 | 3,745,177 | 3,762,792 | 17,615 | 0.5% |
| Computing | 2,449,783 | 2,735,544 | 285,761 | 11.7% | 6,121,843 | 6,442,014 | 5,708,452 | (733,562) | (11.4%) |
| Staff Reimbursements | 79,522 | 89,179 | 9,656 | 12.1% | 450,565 | 322,405 | 322,655 | 250 | 0.1% |
| Grants and Subscriptions | 188,099 | 94,375 | (93,724) | (49.8%) | 225,724 | 234,113 | 231,475 | (2,638) | (1.1%) |
| Other Insurance | 0 | 56,305 | 56,305 | 0.0% | 225,000 | 225,000 | 225,000 | 0 | 0.0% |
| Advertising | 24,638 | 39,297 | 14,660 | 59.5% | 112,450 | 137,307 | 136,107 | (1,200) | (0.9%) |
| Other Supplies and Services | 14,744 | 12,297 | (2,447) | (16.6%) | 212,476 | 78,976 | 78,976 | 0 | 0.0% |
| Total Supplies and Services | 17,554,824 | 16,112,813 | (1,442,011) | (8.2%) | 26,882,280 | 27,313,455 | 26,221,649 | (1,091,806) | (4.0%) |
| Other Agencies | 229,349 | 273,338 | 43,989 | 19.2% | 315,700 | 917,396 | 917,396 | 0 | 0.0% |
| Other Local Authorities | 253,102 | (137,981) | (391,083) | (154.5%) | 1,325,102 | 1,407,602 | 1,407,602 | 0 | 0.0% |
| Audit & Bank Charges | 22,000 | 17,873 | (4,127) | (18.8%) | 88,600 | 88,600 | 88,600 | 0 | 0.0% |
| Total Third Party Payments | 504,451 | 153,230 | (351,221) | (69.6%) | 1,729,402 | 2,413,598 | 2,413,598 | 0 | 0.0% |
| Debt Repayment | 0 | 0 | 0 | 0.0% | 5,882,000 | 5,882,000 | 5,882,000 | 0 | 0.0% |
| External Interest | 245,135 | 213,083 | (32,052) | (13.1%) | 3,626,000 | 3,626,000 | 3,626,000 | 0 | 0.0% |
| Total Capital Financing Costs | 245,135 | 213,083 | (32,052) | (13.1%) | 9,508,000 | 9,508,000 | 9,508,000 | 0 | 0.0% |
| Central Contingency | 4,807 | 0 | (4,807) | (100.0%) | 2,198,900 | 3,006,413 | 3,006,413 | 0 | 0.0% |
| Total revenue expenditure | 146,114,203 | 142,826,193 | (3,288,010) | (2.3%) | 425,448,344 | 425,239,788 | 420,540,032 | (4,699,756) | (1.1%) |
| MFB Act Income | (19,855,200) | (19,561,137) | 294,063 | (1.5%) | (25,595,000) | (25,595,000) | (25,595,000) | 0 | 0.0% |
| Customer and Client Receipts | (2,996,458) | (2,576,106) | 420,352 | (14.0%) | (8,381,538) | (8,341,762) | (8,595,321) | (253,559) | 3.0% |
| Interest Receivable | 0 | 71 | 71 | 0.0% | (595,000) | (595,000) | (595,000) | 0 | 0.0% |
| Bad Debts | 0 | 4,291 | 4,291 | 0.0% | 0 | 0 | 0 | 0 | 0.0% |
| Total Other Income | (22,851,658) | (22,132,881) | 718,777 | (3.1%) | (34,571,538) | (34,531,762) | (34,785,321) | (253,559) | 0.7% |
| Net revenue expenditure | 123,262,545 | 120,693,312 | (2,569,233) | (2.1%) | 390,876,806 | 390,708,026 | 385,754,711 | (4,953,315) | (1.3%) |
| Use of Earmarked Reserves | 0 | 0 | 0 | 0.0% | 3,748,957 | 4,061,572 | 4,061,572 | 0 | 0.0% |
| Financing Requirement | 123,262,545 | 120,693,312 | (2,569,233) | (2.1%) | 394,625,763 | 394,769,598 | 389,816,283 | (4,953,315) | (1.3%) |
| Financed by: |  |  |  |  |  |  |  |  |  |
| Specific grants | (9,911,863) | (9,061,713) | 850,150 | (8.6%) | (12,225,763) | (12,341,662) | (12,341,662) | 1 | (0.0%) |
| GLA funding | 0 | 0 | 0 | 0.0% | (382,400,000) | (382,427,936) | (382,427,936) | 0 | 0.0% |
| Net Financial Position | 113,350,682 | 111,631,599 | (1,719,083) | (1.5%) | 0 | 0 | (4,953,315) | (4,953,315) | 0.0% |

2017/18 CAPITAL PROGRAMME  													APPENDIX 2

| APPENDIX 2 – CAPITAL PROGRAMME | 2017/18 Budget Mar 2017 FEP2709 | B/fwd from 2016-17 Outturn | C/fwd to 2018/19/savings New Projects | Revised 2017-18 Capital Budget July 2017 |  | 2018/19 Budget | 2019/20 Budget | 2020/21 Budget | Prior Years Spend | Projected project Spend | Approved budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ICT Projects | £’000s | £’000s | £’000s | £’000s |  | £’000s | £’000s | £’000s | £’000s | £’000s | £’000s |
| Upgrade Operating System | 100 | 0 | (2) | 98 |  | 0 | 0 | 0 | 2,091 | 2,189 | 2,350 |
| Telephone System at Fire Stations | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 514 | 514 | 562 |
| Business Intelligent Solution | 810 | 190 | (100) | 900 |  | 910 | 0 | 0 | 0 | 1,810 |  |
| Control & Mobilisation System (CAMS) | 488 | (18) | 0 | 470 |  | 0 | 0 | 0 | 9,002 | 9,473 | 10,650 |
| Mobile Data Terminals Replacement | 400 | (112) | 0 | 288 |  | 0 | 0 | 0 | 1,972 | 2,250 | 2,250 |
| Personal Radio Replacements | 200 | 0 | (200) | 0 |  | 1,300 | 0 | 0 | 0 | 1,300 | Q4 15-16 |
| New WAN & ISP (FEP2313) | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1,200 | 1,200 | 1,200 |
| Home Fire Safety Database | 70 | 60 | 0 | 130 |  | 0 | 0 | 0 | 0 | 130 | n/a |
| Replacement of laptops (FEP2462) | 80 | 51 | 0 | 131 |  | 0 | 0 | 0 | 69 | 200 | 450 |
| Public Services Network | 707 | 0 | 0 | 707 |  | 0 | 0 | 0 | 0 | 707 | Q4 15-16 |
| Additional SAN storage | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 67 | 67 | 85 |
| ICT – Accident (event) reporting solution | 0 | 70 | 0 | 70 |  | 0 | 0 | 0 | 0 | 70 | TBA |
| Online Payment Facility | 70 | 0 | 0 | 70 |  | 0 | 0 | 0 | 0 | 70 | Q4 15-16 |
| New audio visual equip for Union Street | 130 | 0 | 0 | 130 |  | 0 | 0 | 0 | 0 | 130 | 130 |
| ICT – Blade Farm/ Hyperconverged Server | 0 | 300 | 0 | 300 |  | 0 | 0 | 0 | 0 | 300 | TBA |
| ICT – Virtual Desktop Technology | 250 | 0 | 0 | 250 |  | 0 | 0 | 0 | 0 | 250 | TBA |
| New telephone system equipment | 0 | 157 | 0 | 157 |  | 0 | 0 | 0 | 0 | 157 | 157 |
| New computer terminals | 25 | 44 | 0 | 69 |  | 0 | 0 | 0 | 0 | 70 | 75 |
| Netscaller Replacement | 0 | 0 | 0 | 0 |  | 0 | 400 | 0 | 0 | 400 | TBA |
| Core Network 6509 Replacement | 0 | 0 | 0 | 0 |  | 0 | 0 | 1,900 | 0 | 1,900 | TBA |
| Core Switch Modules | 0 | 0 | 300 | 300 |  | 0 | 0 | 0 | 0 | 300 | TBA |
| Wireless LAN Controllers | 0 | 0 | 198 | 198 |  | 0 | 0 | 0 | 0 | 198 | TBA |
| Network Access Switches 3650 Replacement | 0 | 0 | 0 | 0 |  | 0 | 750 | 0 | 0 | 750 | TBA |
| Wireless Access Points | 0 | 0 | 0 | 0 |  | 853 | 0 | 0 | 0 | 853 | TBA |
| Data Centre Switches 3750 Replacement | 0 | 0 | 0 | 0 |  | 104 | 0 | 0 | 0 | 104 | TBA |
| Station Network Rewires | 0 | 0 | 100 | 100 |  | 100 | 100 | 100 | 0 | 400 | TBA |
| New ISP | 0 | 0 | 0 | 0 |  | 0 | 500 | 0 | 0 | 500 | TBA |
| New WAN | 0 | 0 | 0 | 0 |  | 0 | 0 | 500 | 0 | 500 | TBA |
| Physical Server Environment | 0 | 0 | 500 | 500 |  | 0 | 0 | 0 | 0 | 500 | TBA |
| VM Server Environment Hosts | 0 | 0 | 0 | 0 |  | 0 | 500 | 0 | 0 | 500 | TBA |
| Network Storage | 0 | 0 | 0 | 0 |  | 750 | 0 | 0 | 0 | 750 | TBA |
| Replacement of laptops | 0 | 0 | 0 | 0 |  | 0 | 563 | 0 | 0 | 563 | TBA |
| New computer terminals - Thin Client | 0 | 0 | 0 | 0 |  | 0 | 0 | 1,150 | 0 | 1,150 | TBA |
| New audio visual equip for Stations | 0 | 0 | 0 | 0 |  | 0 | 0 | 100 | 0 | 100 | TBA |
| New computer terminals - Fat Client | 0 | 0 | 0 | 0 |  | 0 | 100 | 0 | 0 | 100 | TBA |
| ICT Projects Overprogramming | 0 | 0 | (1,098) | (1,098) |  | (1,807) | (2,913) | (1,750) | 0 | (9,568) | TBA |
| ICT PROJECTS | 3,330 | 742 | (302) | 3,770 |  | 2,210 | 0 | 2,000 | 14,915 | 23,686 |  |
| ESTATE PROJECTS |  |  |  |  |  |  |  |  |  |  |  |
| Fire Station Refurbishment (Middx FS) | 1,000 | 17 | (917) | 100 |  | 1,667 | 0 | 0 | n/a | 1,667 | n/a |
| Fire Station Refurbishments (tba) | 0 | 0 | 0 | 0 |  | 0 | 0 | 1,500 | 0 | 1,500 | n/a |
| Alteration works to Union St HQ | 0 | 75 | 0 | 75 |  | 0 | 0 | 0 | 625 | 700 | 700 |
| Workplace Improvement Plan (WIP) Union Street |  | 0 | 240 | 240 |  |  |  |  |  | 240 | 240 |
| Plumstead Fire Station Redevelopment | 2,500 | 0 | 0 | 2,500 |  | 3,350 | 147 | 0 | 0 | n/a | n/a |
| Bromley FS works | 169 | 45 | 0 | 214 |  | 0 | 0 | 0 | 552 | 766 | 890 |
| LFB Museum – Fitout | 350 | 50 | (400) | 0 |  | 2,400 | 0 | 0 | 0 | 2,400 | 2,400 |
| Refurbishment of Edmonton Fire Station | 940 | 0 | (890) | 50 |  | 940 | 0 | 0 | 0 | 990 | Mar 2017 |
| PFI Projects – Installation of ICT hardware at Orpington temporary station and new stations | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 232 | n/a | 507 |
| Heating at various stations | 600 | 158 | 817 | 1,575 |  | 1,350 | 1,350 | 1,350 | n/a | n/a | n/a |
| Window replacement at various stations | 300 | 0 | (160) | 140 |  | 400 | 400 | 400 | n/a | n/a | n/a |
| Rewiring of property at various fire stations | 464 | 116 | 209 | 789 |  | 600 | 600 | 600 | n/a | n/a | n/a |
| Energy Conservation/ Invest to Save Projects | 0 | (6) | 6 | 0 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Building Energy Efficiency Programme 2 (BEEP2) | 754 | 63 | (28) | 789 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Minor Improvement Programme | 1,166 | 515 | 0 | 1,681 |  | 1,300 | 1,300 | 1,300 | n/a | n/a | n/a |
| Corporate Property Project | 50 | 0 | 0 | 50 |  | 50 | 50 | 50 | n/a | n/a | n/a |
| Appliance Bay Doors (Phase 3) | 200 | 20 | 160 | 380 |  | 200 | 200 | 200 | n/a | n/a | n/a |
| Appliance Bay Floors | 250 | 0 | (250) | 0 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Brigade wide Survey for Asbestos & Removal | 50 | 0 | 0 | 50 |  | 50 | 50 | 50 | n/a | n/a | n/a |
| Fire Safety Works at Fire Stations | 0 | 54 | 53 | 107 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Purchase land at former Mitcham Fire Station | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 25 | 25 |
| Forecourts/Rear yards Refurbishment | 300 | 0 | 0 | 450 |  | 0 | 0 | 0 | n/a | n/a | n/a |
| Development costs | 250 | 0 | 0 | 250 |  | 250 | 250 | 250 | n/a | n/a | n/a |
| ESTATE PROJECTS | 9,343 | 1,116 | (1,019) | 9,440 |  | 12,557 | 4,347 | 5,700 |  |  |  |
| OTHER |  |  |  |  |  |  |  |  |  |  |  |
| Replacement of Fleet and Operational Equipment | 17,468 | 2,722 | (8,306) | 11,884 |  | 20,448 | 15,445 | 8,493 | 10,813 | 67,802 | TBA |
| Establishing a London Co-ordination Centre at HQ | 0 | 111 | 0 | 111 |  | 0 | 0 | 0 | 268 | 380 | 380 |
| Data transfer system for Joint Emergency Services Interoperability Programme | 0 | 266 | 0 | 266 |  | 0 | 0 | 0 | 0 | 267 | 267 |
| Fire Initial Response Equipment (F.I.R.E.) system | 0 | 24 | 0 | 24 |  | 0 | 0 | 0 | 96 | 185 | 185 |
| OTHER | 17,468 | 3,123 | (8,306) | 12,285 |  | 20,448 | 15,445 | 8,493 | 11,367 | 68,757 |  |
| New Proposed Projects (* = Approved) |  |  |  |  |  |  |  |  |  |  |  |
| Early Replacement of ALP & HP* | 5,280 | 0 | (3,480) | 1,800 |  | 3,480 | 0 | 0 | 0 | 5,280 | 5,280 |
| CCTV on Pumping Appliances * | 405 | 0 | 0 | 405 |  | 79 | 0 | 0 | 0 | 484 | 501 |
| Early Replacement of Fire Boat* | 100 | 0 | (100) | 0 |  | 1,000 | 1,250 | 250 | 0 | 2,500 | 2,500 |
| Asset Management Plan | 10,000 | 0 | (9,800) | 200 |  | 10,000 | 10,000 | 10,000 | 0 | 40,000 | Various |
| Farynor Replacement | 375 | 50 | 0 | 425 |  | 325 | 0 | 0 | 0 | 750 | TBA |
| Improve Security at Fire Stations, Offices & HQ | 200 | 0 | 0 | 200 |  | 2,405 | 0 | 0 | 0 | 2,605 | TBA |
| Business Management System (PMF) | 190 | 0 | 0 | 190 |  | 25 | 0 | 0 | 0 | 215 | TBA |
| New Training Centre * | 3,534 | 69 | (3,301) | 302 |  | 7,860 | 7,013 | 205 | 122 | 11,100 | 11,100 |
| PEG/BDC Development | 3,750 | 0 | 0 | 3,750 |  | 3,750 | 0 | 0 | 0 | 7,500 | TBA |
| 22mm Water Hose and Reel for Appliances * | 1,000 | 500 | 0 | 1,500 |  | 0 | 0 | 0 | 0 | 1,500 | 1,500 |
| Vehicle Security * | 981 | 0 | 408 | 1,389 |  | 0 | 0 | 0 | 0 | 1,105 | 1,389 |
| New Projects TOTAL | 25,815 | 619 | (16,273) | 10,161 |  | 28,924 | 18,263 | 10,455 | 122 |  |  |
| Projected Underspend | (6,686) |  |  | (6,686) |  | 0 | 0 | 0 | 0 | (6,436) | n/a |
| CAPITAL EXPENDITURE TOTAL | 49,270 | 5,601 | (25,901) | 28,970 |  | 64,139 | 38,055 | 26,648 |  |  |  |

- Additional Resilience Requirements

  - Following the fire at Grenfell Tower, the Commissioner carried out an initial assessment of the extra specialist equipment and support LFEPA requires to ensure the LFB is fully prepared for the challenges ahead. This initial review identified a range of items with both one-off, including revenue and capital expenditure, and ongoing costs which were subsequently set out in a report to Resources Committee on 21 July 2017 (FEP 2763). Work is ongoing to clarify the costs for 2017/18 and that exercise may impact on the forecasts included in this report.

- Firefighter and Local Government Pension Schemes

  - The Authority’s pensions auto enrolment date is set for October 2017 when all staff who were not previously enrolled as part of the June 2016 exercise will be enrolled into a pension scheme. It is currently assumed that 40% of staff who are enrolled in this way will stay in the scheme. Any variation to this forecast may have a budget impact for LFEPA.

- Pay and Inflation

  - LFEPA has made a budget provision for a 1% pay award for all staff for 2017/18.

  - Due to recent events in London there may be additional overtime staff costs incurred. This is currently being assessed.

- Changes to Income

  - The 2017/18 budget included material savings for income generated through the MFB act. This budget has recovered more income than budgeted and caused an underspend in recent years, in part because of the prudent assumptions used when calculating the budget requirement. Additional savings were included in the 2017/18 budget and as a result this will increase the risk of overspends this year.

  - Both the cost recovery and expenditure budgets related to mutual assistance charges are being reviewed to ensure that they are as accurate as possible. Any budgetary pressure resulting from this review will be reported in future Budget Update reports.

- Property Services

  - The 2017/18 budget includes £630k of savings from the implementation of the Property Services Integrator, which includes an estimate of savings that can be achieved on LFEPA’s supply chain. This saving will be updated once the supply chain has been fully costed after mobilisation phase is completed in March 2018.  The savings target is based on an average saving each year to meet the overall savings target agreed over the contract life.

  - The saving proposals for 2017/18 included material savings for energy budgets. This budget has underspent in recent years, in part because of the prudent assumptions used when calculating the budget requirement. These additional savings will therefore set the budget at a less cautious level, and as a result this will increase the risk of overspends in subsequent years, for example because of a colder than average winter.

  - There is a potential overspend on security budgets if the disposal of sites (Clerkenwell, Mitcham, Southwark) are not completed in 17/18. The 2017/18 budget also included a saving of £192k from commercial income for the grotto site, which will be dependent on planning approval and agreement between all parties being reached.

- Capital Expenditure and Financing

  - The capital budget is subject to change during the year. Initial project specification is key as it is important to keep variations to projects to a minimum, as change once a project has been agreed and commenced may result in additional costs. However even a well managed project can be subject to re-phasing or deferral due to a number of unforeseen issues, such as failure or default on the part of the contractor or exceptionally adverse weather conditions. This can also impact on funding requirements which in turn may have a debt charge (cost of borrowing) revenue impact.

  - All capital projects will require third party collaboration to varying degrees over the project life. The programme depends heavily on external factors and therefore can be subject to variation with the potential for delays in project delivery and revised cash flow requirements. The capital programme is managed on a monthly basis and is reported quarterly to the CAPS group (Capital, Approval, Planning and Strategy Group, chaired by the Director of Finance & Contractual Services) where all changes to the programme are reviewed and substitution projects or re-financing proposals are assessed and agreed.

  - The Capital Programme for 2017/18 currently includes a forecast capital receipt for the sale of Clerkenwell Fire Station. If this property is not sold in 2017/18 this could result in an increased borrowing requirement and resulting capital financing costs estimated at £857k. This is based upon the current forecast capital programme and doesn’t take account of any re-phasing or slippage that might occur.

  - The design and specification of the replacement vehicles and equipment is now underway following the commencement of the new contract in November 2014. Key risks relate to the contractor sourcing appropriate vehicle build options within a timeframe that meets fleet replacement requirements and which may in turn impact the Authority’s cash flow. The forecast cash expenditure for 2017/18 and future years is based on the current assessment of the stage payment requirements for the pump replacement programme which represents 48% of the forecast Vehicles and Equipment expenditure in that period and the delivery timings for the balance of the fleet replacement programme.

  - The Brigade successfully cutover to the Replacement Mobilising Solution (VISION4 mobilising system & DS3000 ICCS) as planned on 17 November 2015. The legacy systems were decommissioned in January 2016 and there are a number of other work streams within the project that are still to be delivered. Update releases have been scheduled through 2017 and 2018 for this outstanding functionality. The status of this project is Green as reported in FEP2702.

  - The Asset Management Plan (2017) was approved in March 2017 (FEP2714), which has identified new priorities for investment over the next 5 years across the LFB estate, which includes fire station replacement, redevelopment and refurbishments which will enable the property portfolio to meet the needs of a 21st century fire service. It is difficult to source suitable new sites for purchase to replace those stations where investment to improve their condition or functionality is uneconomic, as the Authority  has to compete with other sectors, in particular residential development.  The Asset Management budget £10m per annum is set aside to fund new developments as and when these opportunities arise.

  - As the new sites for Plumstead and the combined PEG / BDC facility (Integrated and Equipment Logistics Project) are yet to be purchased or a lease agreed, there is a risk that the acquisition of the preferred sites and the respective project programmes will be substantively delayed. As the LFB Training Centre project has a dependency on PEG moving out of Croydon, a delay to acquiring a site for PEG / BDC may have a knock on effect on the Training Centre programme. This would be additional to the current reported delays on the Training Centre, which are not linked. Should these risks in respect of site acquisition materialise, this would result in reduced actual expenditure in future years compared to the current forecast costs for these major capital projects.

  - The debt charges arising from the capital programme have been calculated using the current forecast Public Works Loans Board (PWLB) rates. No allowance has been made in the capital programme for potential future capital grants or contributions and LFEPA will bid for any available capital resources as and when such opportunities arise.

- Contractual Pressures/ Risks

  - Significant demand continues to be placed on the Information and Communications Technology Department to meet new requirements and aid in the development of smarter systems for the Authority. This is at a time where resources are limited and as a result there is a risk that development of information technology solutions may be constrained.

  - The company that provides and supports the Authority’s Command Support Unit system software went into administration in early May and have since ceased trading. The software and its customer base were sold on to a 3rd party and we are entering discussions with them regarding the continued support of the product.

Financial Regulation 9:

“(f) With the agreement of the Director of Finance and Contractual Services, a head of department may transfer up to £50,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget, but if those budget heads are in different Directorates the agreement of the appropriate Directors is also required.

(g) With the agreement of the Director of Finance and Contractual Services, the Commissioner, the Directors and the Head of Legal and Democratic Services may transfer up to £125,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget.

(h) The Director of Finance and Contractual Services shall report all transfers under (f) and (g) to the relevant committee as part of the quarterly monitoring reports.“

No transfers were processed in Quarter 1 that require reporting.

The chart below shows the decrease in Shut in Lift debts over the past years and since inception of shut in lifts charge.

The total number of shut in lifts debts has been falling gradually over the last two years after peaking in 2015,  with overall balance reduced from £300k at the end of September 2015 to £160k at the end of April 2017.

In 2016/17, we have seen major debtors settle their debts. Significant payments that have been received during the year included:

- London Borough of Tower Hamlets - £71,924

- Metropolitan Housing – £29,304

- London Borough of Lambeth -  £25,071

- London Borough of Hackney - £17,694

- Sanctuary Housing - £16,698

- London Borough of Lambeth - £14,071

- London Borough of Islington £13,130

- Peabody Trust - £11,690

- Swan Housing - £10,564

- London Borough of Tower Hamlets - £6,259

- Marks and Spencer - £5,851

- Homes for Islington - £3,130

The continued joint effort from Authority staff has resulted in the positive progress made to date on shut in lift debts. As a result it is proposed that reporting on this debt will no longer form part of the quarterly financial position reports and that it continues to be managed as part of LFEPA’s debt management procedures.