| Report title |  |  |
| --- | --- | --- |
| Financial Position as at the end of September 2017 |  |  |
| Meeting | Date |  |
| Resources Committee | 3 November 2017 |  |
| Report by | Document Number |  |
| Director of Finance and Contractual Services |  |  |
| Public |  |  |

Summary

This report presents the financial position as at the end of September 2017 (quarter 2). It provides information on financial performance against revenue and capital budgets.

Recommendation

That the committee:

- Notes the content of the report.

- Agrees the transfer of £560k from travel and standby overtime budgets to the direct standbys budget, to reflect the new direct standby agreement with the London FBU detailed in paragraph 13.

- Agrees that the Authority’s carol service is part funded by Bristol Uniforms Ltd through sponsorship and that the remaining £14k can be funded from within the overall 2017/18 budget.

- Notes the £872k gross cost of the Mobile Data Terminals and Tablet Devices to be transferred from capital to revenue in year. The reasons for this change in classification of the cost are explained from paragraphs 62 to 69.

- Introduction

- This report considers the financial position as at the end of September 2017, including a forecast of outturn at the financial year end.

- All departments review their actual income and expenditure on a regular basis, and provide an updated forecast of outturn and explanation of variances, against all their budgets, to the Finance Department. These returns then form the basis of reporting to the Corporate Management Board and from there on to the Resources Committee and the Greater London Authority on a quarterly basis.

- Background to 2017/18 Budget

- The 2017/18 budget was approved by the Authority at its meeting on 30 March 2017 (FEP 2708). The Authority’s net revenue budget is £390,708k, with a net payment of £4,062k into earmarked reserves, £12,342k funding from specific grants and savings of £7,665k.

- This report sets out a summary position on both the revenue and capital budgets, and then provides more detailed explanations of variances.

- Revenue

- The forecast outturn position for 2017/18 on the revenue budget is an underspend of £5,285k (1.4%), largely due to variances previously reported on operational staff budgets £4,348k. This is  based on the expected operational staff numbers given forecasts for recruitment and leavers.

- The forecast underspend of £5,285k has increased by £332k since last reported to the Resources Committee in September (FEP 2772). The increase is mainly due to a one-off budget of £830k that was created in 2017/18 to fund costs involved in offering inoculations to staff, as a result of co-responding being rolled out across the brigade. This is no longer forecast to be spent in this financial year and the budget will now be transferred to an EMR reserve to cover the planned spend in 2018/19. There is also an additional income of £605k from Metropolitan Fire Brigade (MFB) Act income due to an increase in the value of insured properties in London. A forecast decrease in operational staff spend of £355k is made up of three separate movements, including a reduction in the forecast cost of pension contributions (£1,000k) in part due to the decision that the auto-enrolment of employees will not happen in this financial year and an increase in the underspend from vacancies (£855k). These are offset by an additional pressure (£1,500k) based on a pay award of 2% to operational staff. In September the national Fire Brigades Union (FBU) ballot rejected the pay offer from the National Joint Committee (NJC). The NJC pay offer was for a two per cent rise to be paid from 1 July 2017 and for discussions around the broadening role of firefighters to continue with the aim of developing a longer term deal. However negotiations are continuing and it is considered prudent at this stage to retain the provision.

- The above underspends are offset by a forecast reduction in the underspend on hardware and software budgets (£550k) which now includes the £419k net impact of the transfer from capital to revenue spend on the Mobile Data Terminals (MDT) project. There is also a reduction in interest receipts (£195k) due to a reduction in balances available to invest and short term interest rates continuing to remain flat, as set out in the LFEPA Treasury Management Mid-Year Report for 2017-18 also on today’s agenda. An additional overspend is forecast on building maintenance to progress a backlog of works across the whole estate including repairs, refurbishment and minor improvements (£175k). The planned use of community safety contributions/funding (£174k) is forecast to be reduced and funds received carried forward to next financial year, with spend in 2017/18 instead being funded by underspends within Fire Safety. Overspends are also now forecast on the training contract based on the current planned number of courses (£150k) and on premises security at three sites that were expected to be sold in 2017/18 (£113k).

- The key variances are discussed in more detail from paragraph 12 below.

- Capital

- The approved capital programme for 2017/18 is £29,146k. The current forecast capital spend for 2017/18 is £17,995k, which is £11,151k less than the approved capital budget and £10,975k less than the financial position reported to the Resources Committee in September (FEP 2772).

- The key variances are discussed in more detail from paragraph 33.

- Tables and Appendices to this report

- A summary of the financial position for the revenue budget is provided in Table 1. The latest position on reserves is set out in Table 2. Appendix 1 contains additional detail on the current and forecast financial position. Appendix 2 reports on the forecast outturn on the capital programme. Appendix 3 discusses the risks to the revenue and capital position that have not been quantified. Appendix 4 meets the requirement to disclose all budget virements within the quarter under financial regulation 9 and Appendix 5 provides an analysis of outstanding debt relating to charges for Shut in Lift attendances.

- Table 1. Summary Financial Position

|  | Current Budget | Current Spend | Current Variance | Revised Budget | Forecast Outturn | Forecast Outturn Variance | Previous Forecast Outturn Variance | Movement between variance figures |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | £000s | £000s | £000s | £000s | £000s | £000s | £000s | £000s |
| Operational staff | 116,324 | 114,627 | (1,697) | 233,758 | 229,055 | (4,703) | (4,348) | (355) |
| Other staff | 24,946 | 26,014 | 1,067 | 51,624 | 51,774 | 150 | 230 | (80) |
| Employee related | 22,767 | 22,269 | (498) | 26,259 | 25,431 | (828) | (145) | (683) |
| Pensions | 10,275 | 9,902 | (373) | 20,489 | 20,279 | (210) | 0 | (210) |
| Premises | 24,702 | 26,049 | 1,347 | 36,783 | 37,631 | 849 | 477 | 372 |
| Transport | 14,152 | 14,248 | 96 | 15,180 | 15,089 | (91) | 178 | (269) |
| Supplies and services | 20,646 | 21,703 | 1,058 | 29,090 | 28,590 | (500) | (1,092) | 591 |
| Third party payments | 1,227 | 1,062 | (166) | 2,598 | 2,784 | 186 | 0 | 186 |
| Capital financing costs | 1,150 | 1,150 | (0) | 9,508 | 9,508 | 0 | 0 | 0 |
| Central contingency against inflation | 0 | 0 | 0 | 2,963 | 2,963 | 0 | 0 | 0 |
| Total revenue expenditure | 236,190 | 237,024 | 834 | 428,252 | 423,105 | (5,147) | (4,700) | (447) |
| Other income | (30,525) | (31,132) | (607) | (35,035) | (35,159) | (124) | (254) | 129 |
| Net revenue expenditure | 205,664 | 205,891 | 227 | 393,217 | 387,945 | (5,271) | (4,953) | (318) |
| Use of earmarked reserves | 0 | 0 | 0 | 2,995 | 2,995 | (0) | 0 | (0) |
| Financing Requirement | 205,664 | 205,891 | 227 | 396,211 | 390,940 | (5,271) | (4,953) | (318) |
| Financed by: |  |  |  |  |  |  |  |  |
| Specific grants | (10,721) | (12,517) | (1,796) | (13,783) | (13,797) | (14) | 0 | (14) |
| GLA funding | 0 | 0 | 0 | (382,428) | (382,428) | 0 | 0 | 0 |
| Net Financial Position | 194,944 | 193,374 | (1,569) | 0 | (5,285) | (5,285) | (4,953) | (332) |

Reasons for the Revenue Position

Staff

- The budget for operational staff is forecast to underspend by £4,703k, an increase in the underspend of £355k from the position reported at Quarter 1. The forecast underspend has increased due to a decrease in the forecast cost of pension contributions of £1,000k in part as a result of the decision by the Pensions Regulator that auto-enrolment of employees will not happen in this financial year and because of a decrease in the average pension contributions as employees opt out of the scheme or are transferred to the new firefighter scheme with lower contribution rates. The forecast impact of the number of vacancies has also been updated based on latest projected firefighter trainee numbers, transferees from other brigades and leavers and this has increased the forecast underspend by £855k. These two items are offset by the inclusion of a pressure of £1,500k based on a pay award of 2% to operational staff. In September the national Fire Brigades Union (FBU) ballot rejected the pay offer from the National Joint Committee (NJC). The NJC pay offer was for a two per cent rise to be paid from 1 July 2017 and for discussions around the broadening role of firefighters to continue with the aim of developing a longer term deal. However negotiations are continuing and it is considered prudent at this stage to retain the provision

- On 6 March, a new direct standby agreement went live following agreement between the Authority and London FBU. This agreement introduced an on shift allowance and therefore fares for on shift standbys are no longer paid from petty cash. This agreement was reached on the basis that any changes would be cost neutral and it has had the effect of reducing expenditure on travel and standby overtime by £560k and increasing direct standby payments to staff by the same amount. Members are asked to agree the transfer of £560k from travel and standby overtime budgets to direct standbys budget, to reflect the new direct standby agreement with the London FBU.

- Control staff budgets are forecast to overspend by £150k, a reduction of £80k since last forecast. Overtime levels remain high due to additional staff cover and additional staff are being recruited to alleviate this overspend.

- Employee Related

- Training contract budgets are forecast to overspend by £98k, an increase of £148k from the position reported at Quarter 1. This increase is based on the current level of spend and expected number of training courses that will be run in 2017/18. This is offset by the previously reported forecast underspend on the apprenticeship levy of £50k.

- There is also a forecast underspend on the inoculations budget within the medical and welfare expenses budget of £899k, an increase of £793k from the position reported at Quarter 1. A budget of £830k was created for 2017/18 to fund costs involved in offering hepatitis B inoculations to staff, if co-responding was rolled out across the Brigade. However this is no longer forecast to be spent in this financial year and the budget will be transferred to an EMR reserve to cover the potential cost in 2018/19. The remainder of the underspend of £105k is largely due to lower than expected numbers of asbestos medical appointments, medical appeals and a lower than forecast inflationary increase as previously reported.

Premises

- Premises budgets are forecast to overspend by £849k, an increase of £372k from the previously reported overspend. The additional overspend is due to a decision being taken to progress a backlog of works aimed at improving the overall condition of the whole estate including repairs, refurbishment and minor improvements to properties (£175k). This is in addition to a £475k overspend that was included in the Quarter 1 report. The remainder of the additional overspend is for the cost of security at three sites that were expected to be sold in 2017/18 (£113k) and a forecast overspend on option appraisal fees for major capital projects (£70k), this is a new requirement and a growth proposal has been included in the Budget Update report also on today’s agenda.

Transport

- Transport budgets are forecast to underspend by £91k, a reduction in spend of £269k from the position reported at Quarter 1. The movement in the forecast includes an additional underspend of £151k on vehicle passthroughs due to the spend for the ultra low emission zone that has been reallocated to 2018/19 financial year to match the modification program, reduction in spend on transport budgets and fuel costs at Fire Stations of £53k and £37k respectively and an increase in abatements on the vehicle and equipment contract of £31k.

- The above movement is offset by a forecast overspend on insurance budgets of £284k following changes to the discount rates within personal injury markets and a higher forecast cost of insurance claims, previously reported in (FEP2772).

- Supplies and Services

- There is a forecast underspend of £500k on supplies and services budgets. This includes a reduction in the underspend of £591k since last reported. The movement is due to the transfer of capital spend to revenue on the Mobile Data Terminals (MDT) project (£419k net), as discussed in detail from paragraph 62 below , additional spend on hardware and software budgets due to unforeseen expenses in connection with the wireless upgrade and implementation of the Cloud solution (£131k) and a forecast overspend on staff reimbursements because the savings on members allowances included in the 2017/18 budget are not achievable in this financial year due to the delay in the abolition of LFEPA (£48k).

- As previously reported to the Resources Committee in September (FEP2772), the overall forecast underspend is mainly due to a revised underspend on hardware and software (£734k) as some orders that were budgeted for in 2017/18 have been charged to 2016/17 and due to transitional arrangements associated with the implementation of the new Wide Area Network. In addition there were also underspends on hydrants maintenance (£187k) based on lower repairs than budgeted, on the Control and Mobilising Services contract (£180k) due to the impact of abatements and on clothing spend at stations (£113k) due to a lower replacement rate of new workwear and reduced spend because of current vacancies. These are offset by forecast overspends on legal professional services (£72k) based on the current caseload and office furniture (£54k) related to floor moves, office desks conversions and other associated work at Union Street.

- Third Party Payments

- There is a forecast overspend on third party payments of £150k as the savings included in the 2017/18 budget on the GLA shared service for member services are not achievable in this financial year due to the delay in the abolition of LFEPA.

- Income

- There is a forecast over recovery of £124k on income. This is a reduction in the amount of income forecast to be received of £129k since last reported in Quarter 1. This includes a reduction in forecast interest receipts (£195k) due to a reduction in balances available to invest as a result of delays in the sale of the Clerkenwell and Southwark sites and short term interest rates continuing to fall, despite an optimistic market forecast in November 2016 outlined by the GLA treasury team in the last mid year report (FEP 2662). Average investment rates since last financial year have now fallen by over 0.1% from 0.55% as at 31 March 2017 to 0.44% as at 30 September 2017. Forecast average rate outturn for the year is now 0.40%.  The budget pressure in the medium term forecast will be kept under review, as the duration of the historically low interest rates continues to be extended. The reduction in income also includes a forecast reduction in the amount of community safety contributions that will be applied in this financial year with any income received being carried forward to support activities in future years (£175k), a reduction in costs recovered from LFB enterprises because of the resignation of a full time member of staff (£100k) as arrangements are reviewed following the appointment of a new LFBe Chair and a reduction in the number of charges raised to attend shut in lift due to reduction in call outs (£79k). These changes are offset by additional income of £605k of Metropolitan Fire Brigade (MFB) Act charges due to an increase in the value of insured properties in London. This is in addition to the budgeted increase of £2,070k in 2017/18. Further increases of £1,310k have been budgeted for 2018/19, a 5% increase on the 2017/18 forecast outturn. The remainder of the forecast over recovery is due to expected increased income from the GLA for additional space at Union Street (£262k) as reported in at quarter 1 (FEP 2772).

- 2018/19 Budget Update

- The Mayor’s Budget Guidance for 2018/19 was published on 13 June 2017 and set out the overall funding the Mayor intends to provide LFEPA over the next four financial years. A report (FEP2733) setting out the resulting processes and timetable in order to deliver a balanced budget for LFEPA in 2018/19 was presented to Authority in October 2017.

- The Budget Update report (FEPXXXX) which is also on today’s agenda, provides an update to the 2018/19 budget process and the proposed budget submission to the Mayor.

- Position on Reserves

- The forecast position on reserves is set out in Table 2 below. Movements on the reserves applied in year together with transfer of £356k of the underspend from the general reserve into the Budget Flexibility reserve, leave a balance on the general reserve at the year end of £13,763k, this is at the stated minimum level which is 3.5% of the net revenue expenditure budget.

- The Budget Flexibility reserve was set up in the 2017/18 Budget (FEP2708) report with funds of £6.2m, to help mitigate the budget deficit anticipated over the next four years. This reserve now includes an additional transfer of £5.3m from the general reserve to the Budget Flexibility reserve, which will reduce the general reserve down to the stated minimum level.

Table 2. LFEPA Reserves for the 2017/18 Financial Year

| £000s | Opening Balance at 01/04/17 | Approved Movements | Underspend/ (Overspend) in 2017/18 | Use of Reserves in 2017/18 | New Payments/ Transfers | Anticipated Balance at 31/03/18 |
| --- | --- | --- | --- | --- | --- | --- |
| Additional Resilience Requirements | 0 | 6,757 |  | (1,034) |  | 5,723 |
| Community Safety Investment Fund | 602 |  |  | (602) |  | 0 |
| Compensation | 1,000 |  |  | 0 |  | 1,000 |
| Emergency Services Mobile Communication Programme | 356 |  |  | (200) |  | 155 |
| Emergency Medical Response | 0 |  |  | 0 | 830 | 830 |
| Firefighters' Pension | 1,172 |  |  | 0 |  | 1,172 |
| Fire Safety and Youth Engagement | 338 |  |  | (200) |  | 138 |
| Hazardous Material Protection | 203 |  |  | (203) |  | 0 |
| Hydrants | 462 |  |  | 0 |  | 462 |
| ICT Development Reserve | 668 |  |  | (268) |  | 400 |
| London Resilience | 1,281 |  |  | 0 |  | 1,281 |
| LSP2017 Implementation | 5,000 |  |  | (409) |  | 4,591 |
| New Governance Arrangements | 100 |  |  | 0 | 200 | 300 |
| Pension Early Release Costs | 400 |  |  | 0 |  | 400 |
| Property PFI | 1,912 |  |  | 0 |  | 1,912 |
| Recruitment/ Outreach | 600 |  |  | (250) |  | 350 |
| Review of Property Services | 85 | (85) |  | 0 |  | 0 |
| Sustainability | 235 |  |  | 0 |  | 235 |
| Vehicle & Equipment Reserve | 1,163 |  |  | 0 |  | 1,163 |
| Budget Flexibility | 0 | 4,953 |  | 6,160 | 356 | 11,469 |
| General | 21,489 | (11,625) | 5,285 |  | (1,386) | 13,763 |
| Total | 37,065 | 0 | 5,285 | 2,995 | 0 | 45,344 |

- The reserves table above includes the establishment of an Additional Resilience reserve to meet forecast costs in 2017/18 arising from an initial assessment of the LFB resources requirement following recent events (FEP 2763). The reserve has been funded by a transfer from the general reserve of £6,757k. This report includes a use of £858k for funding of the investigation team, £106k to fund an increase in officer levels and £70k to fund the cost of staff counsellors in this financial year. It also includes the establishment of a reserve for Emergency Medical Response of £830k to fund the potential cost of staff inoculations in 2018/19, as discussed in paragraph 16.

- The New Governance Arrangements reserve was originally set up with a value of £100k in December 2016 (FEP2709) to meet the costs associated with the abolition of the Authority, which is now expected to happen at the end of March 2018. It is now proposed that this reserve is supplemented by a further £200k. This funding will support the outcome of the review work that has been ongoing internally and with GLA officers to ensure that the relevant reporting mechanisms, governance doctrine, and decision-making structures are ready for implementation in 2018/19.

- Other drawings from earmarked reserves in 2017/18 include:

- £602k for the Community Safety Investment Fund,

- £409k for implementation of LSP2017,

- £268k to fund ICT developments,

- £250k to fund the recruitment and outreach team,

- £203k from the hazmat reserve to fund new gas tight suits,

- £200k to fund fire safety and youth engagement work, and

- £200k to fund the Emergency Services Mobile Communication Programme.

Carol Concert

- In March 2012  budget savings for the Communications Department included provision to make the carol service cost neutral by achieving alternative funding through sponsorship (FEP1891). This year’s service is being held at Westminster Cathedral and is costed at £16k. Officers have secured £2k in sponsorship monies from Bristol Uniforms Ltd. To comply with Authority’s Code of Practice on Sponsorship, this report now seeks formal approval for the Authority’s carol service to be supported by Bristol Uniforms Ltd through sponsorship and for members to agree that the remaining £14k can be funded from within the overall 2017/18 budget. A screening process has taken place (in accordance with paragraph 5 of the Sponsorship Code of Practice) in respect of Bristol Uniforms Ltd and officers are of the opinion there is no reason why this organisation cannot act as a sponsor.

Risks

- There are a range of risks and opportunities to the financial position which are as yet unquantified in the forecasts in this report, and these are attached as Appendix 3. Since last reported, the following risks have been updated:

  - Additional Resilience Requirements – a reserve of £6.8m has been set up to cover the costs in 2017/18 of the items reported to the Resources Committee (FEP 2763). Work is on-going to confirm the requirement of this reserve in this and future financial years.

  - Pension auto enrolment – the auto enrolment date for all staff who were not previously enrolled as part of the June 2016 exercise has now been cancelled and this can be removed as a risk from future reports. The 2017/18 budget included £274k to account for 40% of staff remaining in the scheme and this is now forecast to underspend.

  - Overtime costs – a risk had been included for the potential overtime costs for operational staff following recent events in London. These costs have now been included in the forecast outturn and the risk removed from the report.

  - Disposal of sites – savings have been included on security based on the disposal of three sites in 2017/18. These savings are now forecast not to be achieved and this has been reflected in the forecast outturn in this report. The risk has been removed from the report.

  - MFB income – this report includes additional income forecast above the budget based on returns received from insurance companies set out in paragraph 23 above. This risk has therefore been removed from the report.

  - Insurance costs – The forecasts in this report reflect the recent decrease in the discount rate used to calculate premium payments. These forecasts will be reviewed if there is any further change to the discount rate as part of the insurance sectors challenge to Government, which is being considered.

Capital

- The capital programme for 2017/18 was agreed by the Resources Committee in July 2017 (FEP2750) with a budget of £29,146k. Following the deferral of the projected capital receipts for the former Clerkenwell and Southwark fire stations to 2018/19, a detailed review was undertaken of the 2017/18 capital programme to see whether savings could be achieved or projects deferred to later years. This has resulted in a reduction in the  forecast capital spend for 2017/18 of £11,151k. The last reported forecast in September (FEP 2772) was £28,970k and the overall reduction in spend of £10,975k relates to the main items set out below.

- It should be noted that £7.7m of this relates to three key projects, Plumstead fire station, the new site for the  co-location of PEG and the BDC service and the replacement of aerial appliances. The revenue debt charges budget has been adjusted with the revised capital financing requirements, detailed in the Budget Report which is also on today’s agenda.

- Budget re-phasing to 2018/19 and later years - (7,490k)

- ICT Farynor System - £375k

- ICT Business Management Solution - £650k

- ICT Performance Management Framework - £190k

- ICT – Control & Mobilising System  - £370k

- ICT – Public Services Network - £707k

- ICT – Virtual Desktop Technology - £250k

- ICT – Online Payment Facility - £70k

- ICT – Upgrade Operating System £98k

- ICT – Home Fire Safety System  - £130k

- ICT – Core Switch Modules £300k

- ICT – Station Network Rewires £100k

- ICT – Physical Server Environment £200k

- ICT – Over programming (£600k)

- Estates – Middlesex Fire Stations Refurbishments - £100k

- Estates – Plumstead New Fire Station - £2,500k

- Estates – Edmonton Fire Station Refurbishment - £50k

- Estates – Security at all Fire Stations - £200k

- Fleet - Replacement of ALP & HP Aerials - £1,800k

- Budget re-phasing from 2018/19 - £557k

- Stage payments for fire appliances - £455k

- Purchase of three training vans - £102k

- Budget Savings – (£4,244k)

- ICT – Blade Farm Server - £300k

- Estates – PEG/BDC Development - £3,410k

- Estates – Minor Works - £251k

- Estates – Asset Management Plan - £200k

- Estates – Union Street Reconfiguration - £33k

- Estates – Corporate Property Project - £50k

- Budget Additions – £180k

- ICT – Replacement of laptops - £100k

- West Hampstead Cottages - £20k

- ICT – Accident Reporting System - £60k

- Capital budget re-phasing to 2018/19 and later years  – (£7,490k)

- Farynor System – The scoping of the project has been carried out and the project timeframe has been revised. It is envisaged that the specification will be completed by the end of the year, with delivery commencing in the new financial year, with the system becoming operational during 2019/20. £375k has therefore been carried forward to the 2018/19 financial year.

- Business Intelligence Solution (BIS) and Performance Management Framework (PMF) - This has slipped due to resourcing issues required to deliver these projects. Staff have now been employed to deliver the  BIS project and a permanent project sponsor is being sought to lead project delivery for the PMF project. The budget has been re-profiled with £650k slipping to later years for the BIS and £190k to 2018/19 for the PMF.

- Home Fire Safety System – This scheme has now been deferred to 2018/19 and may be incorporated into the scope of Farynor System in the future -  £130k

- Control and Mobilising System (CAMS) - In order to meet critical deadlines, the mobilising system went live with the core functions as described in the specification. Other functionality was deferred to post go-live and this is being worked on at present. It is now envisaged that this functionality will be implemented during 2018/19 and accordingly £370k has been deferred to 2018/19.

- The Public Services Network (PSN) is the government’s high-performance network which supports public sector organisations working together, reduce duplication and share resources. No decision has been made on LFB’s requirement for PSN compliance. However the Emergency Services Network (ESN) project requires a similar standard of security accreditation which is grant funded. On this basis, the ESN project is undertaking works which largely satisfy the PSN requirement from an LFB perspective. However the scope of the grant funding for ESN may be restricted to control room services only. Should this occur, funding may be required to finalise the PSN works brigade-wide. The capital budget contingency of £707k for this has been deferred to 2018/19, when more information regarding the grant funding will be known.

- Virtual Desktop Technology – The specification for this project is now complete and it is envisaged that the procurement process will take around nine months. £250k budget has been deferred to match this timing.

- The ICT budget (£70k) for the proposed online payment facility project has been deferred to 2018/19, whilst an upgrade to the financial system (masterpiece) is undertaken. In addition, a review of the current finance system and future system requirements will be carried out. This will determine whether this proposal will progress. A decision will be made by the end of this financial year.

- ICT – Upgrade of the Operating System Project (Windows System and Sharepoint) -  Detailed user requirements for the records management solution for Sharepoint  are still to be fully defined by the lead user department. As a consequence the project is not yet at a stage where a procurement can be undertaken and it is now felt that there is insufficient time in the current financial year for expenditure to occur. The requirement is still however valid and as such the budget of £98k is to be carried forward to 2018/19.

- ICT- Core Switch Modules and Station Network Rewires  - These projects require significant resources from the network team. Security upgrades to the Firewall infrastructure and the work to implement Wireless LAN Controllers together with the work associated with the re configuration of Union Street has taken priority. Accordingly £300k and £100k respectively has been deferred to 2018/19 for these projects.

- ICT – Physical Server Environment - Work pressures arising from the upgrade of security infrastructure following the high profile incidents affecting other organisations earlier in the year and the consequent Home office compliance requirements alongside numerous business imperatives such as mobile working have had an impact on the resources available to the Technical design team. Plans have had to be re-assessed in the light of this and an element of this project has been re-phased to 2018/19 -£200k.

- The associated over-programming budget for the ICT Core Switch Modules, Station Network Rewires and the Physical Server Environment £600k has also been deferred to 2018/19.

- Plumstead New Fire Station Development - a site (Nathan Way) has provisionally been offered by Peabody on a purchase basis.  Officers have been seeking updates from Peabody on the sale of the site, but details from Peabody have not been forthcoming. Officers are therefore reporting that the sale of the site is unlikely to go through in the 2017/18  financial year and accordingly the budget of £2.5m has been re-phased to later years.

- A feasibility study is currently being undertaken into the Middlesex and Edmonton fire stations refurbishment project to assess the various options available, prior to the selection of the preferred option to be progressed. It is currently anticipated that there will be no capital expenditure in 2017/18 and therefore £100k and £50k respectively has been deferred to 2018/19.

- The project to increase security at all fire stations and other LFB buildings requires an operational threat assessment to determine the property scope of works required. Each premise will require differing levels of security upgrade depending on existing building and surrounds i.e. barriers/ access control and the operational threat assessment will suggest additional measures should the security threat level be set at highest level i.e. CCTV/fencing. This is unlikely to be resolved in the current financial year hence the forecast expenditure (£200k) in 2017/18 has been deferred to later years.

- The replacement of aerial appliances had progressed to the best and final offers. However the current procurement was stopped whilst a review of the aerial appliance capability requirements is completed. This has resulted in £1,800k being deferred to later years. The outcome of the review is that 10 standard height aerial appliances will be purchased together with 5 extended aerial appliances. The cost of the new proposal is £12,850k, this is £2,950k more than the existing budget of £9,900k which was for 15 standard height aerial appliances. This is as detailed in the Vehicle and Equipment Contract Update (FEP 2778) reported on 15 September. It should also be noted that a donation has been offered of £2,500k for the extended aerial appliances.

- Capital budget re-phasing from 2018/19 - £557k

- The timing/value of the stage payments for the second batch of pumping appliances has been revised following negotiations with the supplier. This is due to the value of the stage payments changing, although overall the price is as previously agreed. In the first batch of 53 appliances, the crew cab was not fitted until the base unit arrived into the UK, for the next 73 appliances the crew unit is fitted before it arrives in the UK, which has increased the value of the 1st stage payment by £36k per vehicle thereby resulting in £455k being brought forward from 2018/19. In addition, the purchase of three vans have also been brought forward from 2018/19 at a cost of £102k. Two fire safety vans require replacement  and one Community Fire Safety van  due to age.

- Capital budget Savings – (£4,244k)

- Blade Farm Server – The server was purchased in March 2017 and financed from the revenue budget. Accordingly, the capital budget of £300k will not be spent and is a saving to the programme.

- The original budget allocation for the PEG / BDC development project was £7.50m and based on a site purchase and fit out. Assessments in early 2017 established that leasehold options were more advantageous and capital funding of £3.45m was secured at July 2017 Resources Committee (FEP2757) to fit out leased premises, which represented a budget saving of £4.05m (£3.41m in 2017/18 and £640k in 2018/19).  A preferred leasehold site has been identified, but remains subject to finalising an agreement for lease (anticipated early November 2017). It is currently anticipated that the capital expenditure in 2017/18 will be £340k and limited to acquisition costs, consultant project management and design. The reason for this change is that both negotiations with the prospective Landlord and appointment of the consultant design team are now at a more advanced stage.

- There is a saving of £511k in the Minor Works programme. This is partly due a delay  to the planned accommodation works at Homerton fire station in order to see how a partial scheme might minimise disruption. There  is also  a delay in the planned refurbishment of the showers at Southall fire station, as further structural and drainage investigations are required. If these projects progress further, they will be funded from the 2018/19 Minor Improvements budget. £260k of the saving will be re-allocated to the replacement of the Appliance Bay Door project to fund the projects at Shoreditch and Wimbledon fire stations where the tender prices have come in higher than the pre tender estimate. This reduces the reported saving to £251k.

- The Asset Management Plan project is a programme of works that have been identified following the approval of the Asset Management Plan (FEP2714) in March 2017.  A review is being undertaken to identify the detailed scope of works required to various fire stations and it is envisaged that budgets for these works will be requested once the requirements for each project have been specified. Therefore, £200k has been identified as a saving for 2017/18 and the future capital budgets of £10m per annum have been removed from the capital programme.

- There has been a saving of £33k in the cost of the Union Street project in relation to the modifications required to relocate the mailroom. This has enabled additional space to be rented out to the GLA.

- The Corporate Property Project was used to encompass initial design and survey fees for various new developments. These costs will now be directly charged to revenue if the scheme does not progress. This would result in a saving of £50k per annum.

- Capital budget Additions – £180k

- Resources Committee approved (FEP2462) the replacement of the previous generation laptops at maximum cost of £450k. The first phase of replacement programme is underway and the new laptops are being rolled out across the Authority at a cost of £200k. The second phase is the replacement of the mobile data terminal laptops which will cost £100k.It is envisaged that these products can be purchased and installed in the current financial year. Although this sum was not included in the original budget for the current year, the funds are within the approved budget for the whole project.

- The refurbishment of West Hampstead Cottages (£720k) was approved at the September Resources Committee (FEP2776). The cottages are to be refurbished to provide eight single person quarters which will be let out to London Fire Brigade employees. The estimated spend for 2017/18 is £20k.

- ICT – Accident Reporting System – the tender prices for this project exceeded the projected budget by £60k, bringing the cost of the project to £130k. The system will meet the legal requirements for LFEPA to record and report all accidents in the workplace, including the Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR). The additional budget requirement was approved under delegated authority.

- The Commissioner’s report to the Resources Committee in July (FEP2763) on additional resourcing requirements included a number of capital items. The funding for these will be added to the capital programme during the year as the detailed specifications are drawn up.

- The full details of the capital programme is provided in Appendix 2.  The future capital programme is detailed in the budget report which is also on today’s agenda.

- Theft of MDT Equipment

- In September 2014 the Resources Committee approved a project (FEP2314) to refresh and upgrade mobile data equipment in all Brigade appliances. This includes a new ‘fixed’ front of cab mobile data terminal (MDT), two tablet devices in the rear of all pumping appliances/FRUs and a SatNav device in every appliance. Project delivery has been delayed due to a range of technical issues including a decision to deploy Windows 10 on all devices to improve security (in the light of cyberattacks over the last year), the need to secure compliance with Airwave radio infrastructure, and the need to coordinate roll-out of devices with the appliance replacement programme.

- In August 2017 there was a theft of 130 new front of cab MDT devices, which were in storage at Southwark Training Centre. These devices were awaiting the agreed software build, prior to deployment as part of the refresh project. The purchase value of the equipment stolen was £280k. The theft was reported to the Police and an insurance claim has been submitted, which is now being assessed.

- An order has been placed for 130 replacement MDTs to replace the ones stolen and the supplier has advised that there is a sixteen week lead time for production and delivery. The MDT project timelines are being reset to take this lead time into account, which means roll-out will not now commence until February 2018 and is expected to be completed by June 2018.

- The delay as a consequence of the MDT theft, the deployment of the Windows 10 operating system and a number of other technology related delays, will also have a further knock-on effect on the project. The 338 tablet devices (two per pump/FRU) purchased for the rear of the appliances in June 2015 at a cost of £592k have a three year life (the MDT devices have a five year life). By the time the roll-out is completed in June 2018 the tablet devices will be within 6 months of their ‘end of life’ and would no longer meet the Brigade’s specification.They will therefore need to be replaced.

- The decision to deploy two tablets in each pump/FRU was on the basis that the tablets would have some of the software applications available on the fixed MDT (e.g. ‘Crash’ which helps crews with the cutting of vehicles for extrication purposes) together with a range of LFB ‘apps’ that would support crews working away from the appliance. The initial LFB ‘apps’ include a premises risk assessment for data collection by crews during outside duty visits and, in due course, would include an ‘apps’ to support, for example, data collection at home fire safety visits. These LFB ‘apps’ will not be available when the tablets are rolled out by June 2018, so in replacing the devices procured in September 2015, officers are recommending that only one tablet needs to be provided in appliances for the time being. Once tablets with a range of ‘apps’ are being used, it will be possible to determine whether two are required. It is therefore  proposed to review the requirement after one year. In the meantime a buy-back option is available for the unused ‘end of life’ tablets and the intention is to take advantage of this to re-procure 171 of the tablet devices (on the basis of one per pump/FRU and 15 spares).

- The financial impact of the theft of the MDTs will mean that the £280k capital cost will need to be removed from the capital programme and instead charged to revenue, reducing capital spend and increasing revenue spend. As noted above an insurance claim has been submitted which may offset the £280k revenue cost. The revenue forecasts will be updated to reflect the net impact of this once the insurance claim is decided and then included in future reports on the financial position. The capital repurchase cost of the replacement MDTs will be offset by the reduction in spend following the recharge of the initial cost to revenue.

- As the 338 tablets for the rear of the appliances are close to the  end of their useful life, the £592k cost will now be treated as revenue expenditure instead of capital and will be offset in part by the £172k estimated buy back for the tablets.

- This means that the total revenue impact will be a gross transfer of £872k fromcapital expenditure to revenue, offset by additional forecast insurance income of £280k and the buy back income of £172k, for a net impact of £419k of additional revenue spend. The £393k to purchase 171 new tablets will be charged to the capital programme and is within the approved budget for this scheme.

Debtors

- An analysis of debtors relating to Shut in Lift is provided in Appendix 5. This includes a chart that shows the continued decrease in the amount of Shut in Lift debts outstanding over the past 18 months, with £137k outstanding at the end of September 2017. The continued joint effort by Authority staff has resulted in the positive progress made to date on shut in lift debts recovery.

Head of Legal and Democratic Services comments

- The Head of Legal and Democratic Services has reviewed this report and has no comments.

Director of Finance and Contractual Services comments

- This report is presented by the Director of Finance and Contractual Services and there are no further comments.

Sustainable Development Implications

- The move to more direct standby’s is expected to reduce commuting distances of staff undertaking standby’s when compared to attending their base station first, and completes one of the actions set out in the Sustainable Development Strategy 2016-20 (FEP 2580). There are no further implications to note.

Staff Side Consultations Undertaken

- No staff-side consultations have been undertaken on this report.

Equalities Implications

- This report has no equality implications.

| List of Appendices to this report: - Financial Position, 2017/18 Forecast Outturn - Capital Programme 2017/18 - Risks to the Revenue and Capital Position - Financial Regulation 9: Budget Virements - Outstanding LIFT debtors |  |
| --- | --- |
| LOCAL GOVERNMENT (ACCESS TO INFORMATION) ACT 1985 |  |
| List of background documents - FEP2708 2017/18 Budget - FEP2750 Review of Financial Outturn for 2016/17 - FEP2772Financial Position as at the end of June 2017 |  |
| Proper officer | Director of Finance and Contractual Services |
| Contact officer Telephone Email | Adrian Bloomfield 020 8555 1200 x31351 Adrian.Bloomfield@london-fire.gov.uk |

|  | Current Budget | Current Spend | Current Variance |  | Original Budget | Revised Budget | Forecast Outturn | Forecast Outturn Variance |  | Previous Forecast Outturn | Movement from Previous Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | £ | £ | £ | % | £ | £ | £ | £ | % | £ | £ |
| Operational Firefighters | 116,148,209 | 114,225,879 | (1,922,330) | (1.7%) | 233,410,405 | 232,522,332 | 227,819,363 | (4,702,969) | (2.0%) | (4,347,927) | (355,042) |
| Firefighter Trainees | 175,965 | 400,811 | 224,846 | 127.8% | 1,235,886 | 1,235,884 | 1,235,884 | 0 | 0.0% | 0 | 0 |
| Total Operational Staff | 116,324,174 | 114,626,690 | (1,697,484) | (1.5%) | 234,646,291 | 233,758,217 | 229,055,247 | (4,702,969) | (2.0%) | (4,347,927) | (355,042) |
| FRS Staff | 22,321,694 | 23,317,922 | 996,228 | 4.5% | 45,520,950 | 46,374,419 | 46,374,419 | 0 | 0.0% | 0 | 0 |
| Control Staff | 2,624,656 | 2,695,756 | 71,100 | 2.7% | 5,442,449 | 5,249,311 | 5,399,408 | 150,097 | 2.9% | 229,787 | (79,690) |
| Total Other Staff | 24,946,350 | 26,013,678 | 1,067,328 | 4.3% | 50,963,400 | 51,623,730 | 51,773,827 | 150,097 | 0.3% | 229,787 | (79,690) |
| Other Pensions Payment | 412,500 | 424,135 | 11,635 | 2.8% | 990,000 | 990,000 | 990,000 | 0 | 0.0% | 0 | 0 |
| Severance | 0 | 47,246 | 47,246 | 0.0% | 0 | 33,681 | 47,246 | 13,565 | 40.3% | 13,565 | 0 |
| Professional Development | 20,867,706 | 20,432,052 | (435,655) | (2.1%) | 20,911,224 | 21,965,242 | 22,063,603 | 98,361 | 0.4% | (49,239) | 147,600 |
| Recruitment | 122,610 | 125,140 | 2,530 | 2.1% | 162,100 | 212,100 | 178,622 | (33,478) | (15.8%) | (4,387) | (29,091) |
| Employee Related Insurance | 190,000 | 255,225 | 65,225 | 34.3% | 190,000 | 190,000 | 190,000 | 0 | 0.0% | 0 | 0 |
| Compensation | 277,907 | 134,176 | (143,731) | (51.7%) | 555,813 | 555,813 | 555,813 | 0 | 0.0% | 0 | 0 |
| Medical & Welfare Expense | 969,028 | 885,472 | (83,557) | (8.6%) | 2,782,076 | 2,782,076 | 1,883,575 | (898,501) | (32.3%) | (105,176) | (793,325) |
| Capitalised Staff Charges | (72,961) | (34,242) | 38,718 | (53.1%) | (245,400) | (469,898) | (477,610) | (7,712) | 1.6% | 0 | (7,712) |
| Total Employee Related | 22,766,791 | 22,269,203 | (497,587) | (2.2%) | 25,345,813 | 26,259,014 | 25,431,249 | (827,764) | (3.2%) | (145,237) | (682,528) |
| Firefighter Pension Scheme | 10,275,500 | 9,902,066 | (373,434) | (3.6%) | 20,489,000 | 20,489,000 | 20,279,000 | (210,000) | (1.0%) | 0 | (210,000) |
| Building Maintenance | 4,554,778 | 5,205,506 | 650,728 | 14.3% | 7,241,163 | 6,792,688 | 7,442,688 | 650,000 | 9.6% | 475,000 | 175,000 |
| Grounds Maintenance | 45,035 | 54,327 | 9,292 | 20.6% | 118,382 | 146,396 | 146,396 | 0 | 0.0% | 0 | 0 |
| Premises Security | 425,752 | 596,375 | 170,623 | 40.1% | 397,752 | 425,752 | 538,752 | 113,000 | 26.5% | 0 | 113,000 |
| Energy Costs | 751,690 | 739,427 | (12,263) | (1.6%) | 2,031,205 | 2,031,205 | 2,031,205 | 0 | 0.0% | 0 | 0 |
| Rents | 5,589,761 | 5,711,255 | 121,495 | 2.2% | 7,801,412 | 7,808,252 | 7,859,936 | 51,684 | 0.7% | 2,004 | 49,680 |
| Property PFI Contract | 5,541,578 | 5,541,577 | (0) | (0.0%) | 5,545,202 | 5,545,202 | 5,485,202 | (60,000) | (1.1%) | 0 | (60,000) |
| Property Rates | 4,635,830 | 4,996,002 | 360,172 | 7.8% | 9,291,368 | 9,291,368 | 9,291,368 | 0 | 0.0% | 0 | 0 |
| Water & Sewerage Rates | 92,367 | 131,947 | 39,580 | 42.9% | 255,515 | 255,515 | 255,515 | 0 | 0.0% | 0 | 0 |
| Fixtures & Fittings | 53,855 | 60,619 | 6,764 | 12.6% | 332,861 | 97,969 | 97,969 | 0 | 0.0% | 0 | 0 |
| Cleaning and Domestic Supplies | 839,195 | 779,603 | (59,592) | (7.1%) | 2,032,753 | 2,020,097 | 2,020,097 | 0 | 0.0% | 0 | 0 |
| Premises Insurance | 285,000 | 304,281 | 19,281 | 6.8% | 372,000 | 372,000 | 372,000 | 0 | 0.0% | 0 | 0 |
| Other Property Services | 1,887,418 | 1,928,327 | 40,909 | 2.2% | 1,526,726 | 1,996,140 | 2,090,140 | 94,000 | 4.7% | 0 | 94,000 |
| Total Premises | 24,702,259 | 26,049,247 | 1,346,988 | 5.5% | 36,946,338 | 36,782,583 | 37,631,267 | 848,684 | 2.3% | 477,004 | 371,680 |
| Running Costs | 1,516,575 | 1,709,107 | 192,532 | 12.7% | 2,092,597 | 1,652,522 | 1,882,361 | 229,839 | 13.9% | 267,201 | (37,362) |
| Vehicle and Equipment Contract | 10,709,557 | 10,716,116 | 6,559 | 0.1% | 10,783,624 | 10,783,624 | 10,692,744 | (90,880) | (0.8%) | (60,000) | (30,880) |
| Vehicle Passthroughs | 360,952 | 311,867 | (49,085) | (13.6%) | 645,172 | 605,465 | 453,804 | (151,661) | (25.0%) | 0 | (151,661) |
| Maintenance and Repairs | 0 | 0 | 0 | 0.0% | 905,000 | 0 | 0 | 0 | 0.0% | 0 | 0 |
| Contract Hire & Operating Leases | 1,018,222 | 991,596 | (26,626) | (2.6%) | 1,189,900 | 1,233,925 | 1,204,567 | (29,358) | (2.4%) | (33,478) | 4,120 |
| Travel | 546,563 | 518,934 | (27,629) | (5.1%) | 1,122,627 | 904,718 | 855,972 | (48,746) | (5.4%) | 4,700 | (53,446) |
| Total Transport | 14,151,868 | 14,247,620 | 95,751 | 0.7% | 16,738,920 | 15,180,254 | 15,089,448 | (90,806) | (0.6%) | 178,423 | (269,229) |
| Hydrants | 483,616 | 484,177 | 561 | 0.1% | 600,900 | 587,444 | 400,000 | (187,444) | (31.9%) | (187,444) | 0 |
| Operational Equipment | 1,148,704 | 1,008,572 | (140,132) | (12.2%) | 2,123,414 | 2,197,788 | 2,182,035 | (15,753) | (0.7%) | 629 | (16,382) |
| Smoke Alarms | 420,000 | 604,399 | 184,399 | 43.9% | 700,000 | 700,000 | 700,000 | 0 | 0.0% | 0 | 0 |
| Equipment Furniture and Materials | 136,521 | 210,204 | 73,682 | 54.0% | 534,188 | 271,127 | 269,007 | (2,120) | (0.8%) | 75 | (2,195) |
| Lost & NFWT Operational Equipment | 92,777 | 85,474 | (7,303) | (7.9%) | 107,387 | 107,387 | 107,387 | 0 | 0.0% | 0 | 0 |
| Catering | 164,022 | 168,479 | 4,458 | 2.7% | 120,104 | 320,412 | 309,559 | (10,853) | (3.4%) | 1,019 | (11,872) |
| Clothing & Laundry | 2,407,993 | 2,776,099 | 368,106 | 15.3% | 2,790,337 | 2,795,884 | 2,682,971 | (112,913) | (4.0%) | (99,607) | (13,306) |
| General Office Expenses | 360,523 | 468,470 | 107,946 | 29.9% | 378,869 | 710,704 | 765,042 | 54,338 | 7.6% | 70,212 | (15,874) |
| Professional Services | 7,933,868 | 8,356,621 | 422,753 | 5.3% | 8,550,475 | 8,501,723 | 8,406,185 | (95,538) | (1.1%) | (157,156) | 61,618 |
| Postal Services | 55,325 | 56,775 | 1,450 | 2.6% | 61,255 | 61,255 | 61,255 | 0 | 0.0% | 0 | 0 |
| Communications | 3,480,239 | 1,915,937 | (1,564,302) | (44.9%) | 3,567,294 | 3,787,345 | 3,803,460 | 16,115 | 0.4% | 17,615 | (1,500) |
| Hardware and Software | 3,296,419 | 4,874,838 | 1,578,419 | 47.9% | 6,121,843 | 7,847,539 | 7,663,956 | (183,583) | (2.3%) | (733,562) | 549,979 |
| Staff Reimbursements | 159,982 | 170,490 | 10,508 | 6.6% | 450,565 | 317,205 | 350,466 | 33,261 | 10.5% | 250 | 33,011 |
| Grants and Subscriptions | 196,209 | 125,657 | (70,552) | (36.0%) | 225,724 | 234,113 | 232,135 | (1,978) | (0.8%) | (2,638) | 660 |
| Other Insurance | 225,000 | 225,947 | 947 | 0.4% | 225,000 | 225,000 | 225,000 | 0 | 0.0% | 0 | 0 |
| Advertising | 49,075 | 130,796 | 81,721 | 166.5% | 112,450 | 135,307 | 139,512 | 4,205 | 3.1% | (1,200) | 5,405 |
| Other Supplies and Services | 35,313 | 40,551 | 5,238 | 14.8% | 212,476 | 289,726 | 291,560 | 1,834 | 0.6% | 0 | 1,834 |
| Total Supplies and Services | 20,645,587 | 21,703,486 | 1,057,899 | 5.1% | 26,882,280 | 29,089,958 | 28,589,529 | (500,429) | (1.7%) | (1,091,806) | 591,378 |
| Other Agencies | 537,623 | 551,717 | 14,094 | 2.6% | 315,700 | 917,396 | 917,396 | 0 | 0.0% | 0 | 0 |
| Other Local Authorities | 606,253 | 439,635 | (166,618) | (27.5%) | 1,325,102 | 1,591,838 | 1,777,838 | 186,000 | 11.7% | 0 | 186,000 |
| Audit & Bank Charges | 83,500 | 70,321 | (13,179) | (15.8%) | 88,600 | 88,600 | 88,600 | 0 | 0.0% | 0 | 0 |
| Total Third Party Payments | 1,227,375 | 1,061,673 | (165,702) | (13.5%) | 1,729,402 | 2,597,834 | 2,783,834 | 186,000 | 7.2% | 0 | 186,000 |
| Debt Repayment | 0 | 0 | 0 | 0.0% | 5,882,000 | 5,882,000 | 5,882,000 | 0 | 0.0% | 0 | 0 |
| External Interest | 1,149,839 | 1,149,839 | (0) | (0.0%) | 3,626,000 | 3,626,000 | 3,626,000 | 0 | 0.0% | 0 | 0 |
| Total Capital Financing Costs | 1,149,839 | 1,149,839 | (0) | (0.0%) | 9,508,000 | 9,508,000 | 9,508,000 | 0 | 0.0% | 0 | 0 |
| Central Contingency | 0 | 0 | 0 | 0.0% | 2,198,900 | 2,963,445 | 2,963,445 | 0 | 0.0% | 0 | (0) |
| Total revenue expenditure | 236,189,743 | 237,023,502 | 833,758 | 0.4% | 425,448,344 | 428,252,034 | 423,104,847 | (5,147,187) | (1.2%) | (4,699,756) | (447,431) |
| MFB Act Income | (25,595,000) | (26,355,766) | (760,766) | 3.0% | (25,595,000) | (25,595,000) | (26,200,000) | (605,000) | 2.4% | 0 | (605,000) |
| Customer and Client Receipts | (4,835,299) | (4,708,672) | 126,627 | (2.6%) | (8,381,538) | (8,845,293) | (8,559,491) | 285,802 | (3.2%) | (253,559) | 539,362 |
| Interest Receivable | (95,000) | (71,893) | 23,107 | (24.3%) | (595,000) | (595,000) | (400,000) | 195,000 | (32.8%) | 0 | 195,000 |
| Bad Debts | 0 | 4,125 | 4,125 | 0.0% | 0 | 0 | 0 | 0 | 0.0% | 0 | 0 |
| Total Other Income | (30,525,299) | (31,132,206) | (606,907) | 2.0% | (34,571,538) | (35,035,293) | (35,159,491) | (124,198) | 0.4% | (253,559) | 129,362 |
| Net revenue expenditure | 205,664,444 | 205,891,296 | 226,851 | 0.1% | 390,876,806 | 393,216,741 | 387,945,356 | (5,271,385) | (1.3%) | (4,953,315) | (318,070) |
| Use of Earmarked Reserves | 0 | 0 | 0 | 0.0% | 3,748,957 | 2,994,568 | 2,994,568 | (0) | (0.0%) | 0 | (0) |
| Financing Requirement | 205,664,444 | 205,891,296 | 226,851 | 0.1% | 394,625,763 | 396,211,309 | 390,939,924 | (5,271,385) | (1.3%) | (4,953,315) | (318,070) |
| Financed by: |  |  |  |  |  |  |  |  |  |  |  |
| Specific grants | (10,720,805) | (12,517,008) | (1,796,203) | 16.8% | (12,225,763) | (13,783,373) | (13,796,948) | (13,575) | 0.1% | 1 | (13,575) |
| GLA funding | 0 | 0 | 0 | 0.0% | (382,400,000) | (382,427,936) | (382,427,936) | 0 | 0.0% | 0 | 0 |
| Net Financial Position | 194,943,639 | 193,374,288 | (1,569,351) | (0.8%) | 0 | 0 | (5,284,960) | (5,284,960) | 0.0% | (4,953,315) | (331,645) |

The table below shows a summary of the movements since the July 2017 budget report and the impact on the capital budget in future years.

| Budget Year | 2017-18 | 2018-19 | 2019-20 | 2020-21 | Notes |
| --- | --- | --- | --- | --- | --- |
| Sept 2017 Resources Com QTR 1 | 28,970 | 64,139 | 38,055 | 26,648 |  |
| ICT – Farynor System | (375) | 375 |  |  | Budget c/fwd to 2018/19 |
| ICT – Business Intelligent Solution | (650) | (310) | 600 | 360 | Budget c/fwd to later years |
| ICT – Online Payment Facility | (70) | 70 |  |  | Budget c/fwd to 2018/19 |
| ICT – Home Fire Safety System | (130) | 130 |  |  | Budget c/fwd to 2018/19 |
| ICT – Performance Management System | (190) | 190 |  |  | Budget c/fwd to 2018/19 |
| ICT – CAMS | (370) | 370 |  |  | Budget c/fwd to 2018/19 |
| ICT – Public Services Network | (707) | 707 |  |  | Budget c/fwd to 2018/19 |
| ICT – Virtual Desktop Technology | (250) | 250 |  |  | Budget c/fwd to 2018/19 |
| ICT – Upgrade Operating System | (98) | 98 |  |  | Budget c/fwd to 2018/19 |
| ICT – Core Switch Modules | (300) | 300 |  |  | Budget c/fwd to 2018/19 |
| ICT – Station Network Rewires | (100) | 100 |  |  | Budget c/fwd to 2018/19 |
| ICT – Physical Server Environment | (200) | 200 |  |  | Budget c/fwd to 2018/19 |
| ICT – Over programming | 600 | (600) |  |  | Budget c/fwd to 2018/19 |
| ICT – Blade Farm Server | (300) |  |  |  | Budget saving |
| ICT – Replacement of laptops | 100 |  |  |  | Additional budget requirement within approved budget |
| ICT – AV Equipment | 20 |  |  |  | Additional budget requirement |
| ICT – Accident Reporting System | 60 |  |  |  | Additional budget requirement |
| Plumstead New Fire Station | (2,500) | (1,850) | 4,203 | 147 | Budget c/fwd to later years |
| LFB Museum | 18 | (2,370) | 2,352 |  | Budget c/fwd to 2018/19 |
| Fire Station (Middx) Refurb | (100) | (1,567) | 1,167 | 500 | Budget c/fwd to 2018/19 |
| Refurbishment of Edmonton F.S. | (50) | (840) | 890 |  | Budget c/fwd to 2018/19 |
| Security at Fire Stations & HQ | (200) | (2,305) | 1,255 | 1,250 | Budget c/fwd to 2018/19 |
| Asset Management Plan | (200) | (10,000) | (10,000) | (10,000) | Budget savings |
| PEG/BDC Development | (3,410) | (690) | 50 |  | Budget savings £4,050k |
| Alteration works to Union St HQ | (33) |  |  |  | Budget Savings |
| Corporate Property Project | (50) | (50) | (50) | (50) | Budget Savings |
| Other savings | (16) |  |  |  | Budget Savings |
| Minor Improvements | (251) |  |  |  | Budget Savings |
| Minor Improvements | (260) |  |  |  | Budget re-allocation |
| Appliance Bay Doors | 260 |  |  |  | Budget re-allocation |
| West Hampstead Cottage Refurb | 20 | 670 | 30 |  | New requirements FEP2776 |
| Early Replacement of ALP & HP* | (1,800) | 270 | 1.530 |  | Re-phasing of budget |
| Extended Aerial Appliances | 0 | 0 | 200 | 250 | Additional cost |
| Pumping Appliances | 455 | (455) |  |  | Budget brought forward |
| 3 Training Vans | 102 | (102) |  |  | Budget brought forward |
| General Fleet Vehicles | 0 | (5,185) | 950 | 3,425 | Budget b/fwd £810k to 2021/22 |
| General Fleet Vehicles | 0 | 129 | 0 | 0 | New Requirements |
| Capital Programme Qtr. 2 | 17,995 | 41,674 | 41,232 | 22,530 |  |
| change | (10,975) | (22,465) | 3,177 | (4,118) |  |

| APPENDIX 1 – 2017/18 CAPITAL PROGRAMME | 2017-18 Capital Budget July 2017 Resources Committee | Current Forecast 2017/18 Qtr. 2 | Change |  | Last reported position 2017/18 Qtr. 1 | Variance | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ICT Projects | £’000s | £’000s | £’000s |  | £’000s | £’000s |  |
| Upgrade Operating System | 98 | 0 | (98) |  | 98 | (98) | To 2018/19 |
| Business Intelligent Solution | 900 | 250 | (650) |  | 900 | (650) | To later years |
| Control & Mobilisation System (CAMS) | 470 | 100 | (370) |  | 470 | (370) | To 2018/19 |
| Mobile Data Terminals Replacement | 288 | 288 | 0 |  | 288 | 0 |  |
| Home Fire Safety Database | 130 | 0 | (130) |  | 130 | (130) | To 2018/19 |
| Replacement of laptops (FEP2462) | 131 | 231 | 100 |  | 131 | 100 | Within existing approval |
| Public Services Network | 707 | 0 | (707) |  | 707 | (707) | To 2018/19 |
| Accident reporting solution | 70 | 130 | 60 |  | 70 | 60 | Add budget requirement |
| Online Payment Facility | 70 | 0 | (70) |  | 70 | (70) | To 2018/19 |
| Audio visual equip for Union Street | 130 | 150 | 20 |  | 130 | 20 | Add budget requirement |
| Blade Farm/ Hyperconverged Server | 300 | 0 | (300) |  | 300 | (300) | Budget saving |
| ICT – Virtual Desktop Technology | 250 | 0 | (250) |  | 250 | (250) | To 2018/19 |
| New telephone system equipment | 157 | 157 | 0 |  | 157 | 0 |  |
| New computer terminals | 69 | 69 | 0 |  | 69 | 0 |  |
| Core Switch Modules | 300 | 0 | (300) |  | 300 | (300) | To 2018/19 |
| Wireless LAN Controllers | 198 | 198 | 0 |  | 198 | 0 |  |
| Station Network Rewires | 100 | 0 | (100) |  | 100 | (100) | To 2018/19 |
| Physical Server Environment | 500 | 300 | (200) |  | 500 | (200) | To 2018/19 |
| ICT Projects Over programming | (1,098) | (498) | 600 |  | (1,098) | 600 | To 2018/19 |
| ICT PROJECTS | 3,770 | 1,375 | (2,395) |  | 3,770 | (2,395) |  |
| ESTATE PROJECTS |  |  |  |  |  |  |  |
| Fire Station Refurbishment (Middx) | 100 | 0 | (100) |  | 100 | (1080) | To 2018/19 |
| Alteration works to Union St HQ | 75 | 42 | (33) |  | 75 | (33) | Budget savings |
| Workplace Plan (WIP) Union Street | 240 | 240 | 0 |  | 240 | 0 |  |
| Re-develop Plumstead Fire Station | 2,500 | 0 | (2,500) |  | 2,500 | (2,500) | To 2018/19 |
| Bromley FS works | 214 | 240 | 26 |  | 214 | 26 | Add budget requirement |
| LFB Museum – Fitout | 0 | 18 | 18 |  | 0 | 18 | Transfer from 2018/19 |
| Refurbishment of Edmonton F.S. | 50 | 0 | (50) |  | 50 | (50) | To 2018/19 |
| Heating at various fire stations | 1,575 | 1,575 | 0 |  | 1,575 | 0 |  |
| Window replacement at fire stations | 300 | 140 | (160) |  | 140 | 0 | £160k to Appliance Bay Doors |
| Rewiring at various fire stations | 592 | 789 | 197 |  | 789 | 0 | £197k from Appliance bay floors |
| Building Energy Efficiency (BEEP2) | 789 | 764 | (25) |  | 789 | (25) | Budget Savings |
| Minor Improvement Programme | 1,681 | 1,170 | (511) |  | 1,681 | (511) | £251k budget savings & £260k to Appliance Bay Doors |
| Corporate Property Project | 50 | 0 | (50) |  | 50 | (50) | Budget savings |
| Appliance Bay Doors (Phase 3) | 220 | 640 | 420 |  | 380 | 260 | £160k from Window Replacements & £260k from Minor Improvements |
| Appliance Bay Floors | 250 | 0 | (250) |  | 0 | 0 | £53k to Fire Safety Projects & £197k to FS rewiring |
| Asbestos Removal | 50 | 50 | 0 |  | 50 | 0 |  |
| Fire Safety Works at Fire Stations | 54 | 107 | 53 |  | 107 | 0 | £53k from Appliance bay floors |
| Forecourts/Rear yards refurbishment | 450 | 450 | 0 |  | 450 | 0 |  |
| Development costs | 250 | 233 | (17) |  | 250 | (17) | Budget Savings |
| ESTATE PROJECTS | 9,440 | 6,458 | (2,982) |  | 9,440 | (2,982) |  |
| OTHER |  |  |  |  |  |  |  |
| Replacement of Fleet & Equipment | 11,884 | 12,441 | 557 |  | 11,884 | 557 | B/fwd from 2018/19 |
| Establishing a London Co-ordination Centre at HQ | 111 | 111 | 0 |  | 111 | 0 |  |
| Data transfer system for Joint Emergency Services Interoperability Programme | 266 | 266 | 0 |  | 266 | 0 |  |
| Fire Initial Response Equipment (F.I.R.E.) system | 24 | 24 | 0 |  | 24 | 0 |  |
| OTHER | 12,285 | 12,842 | 557 |  | 12,285 | 557 |  |
| New Proposed Projects |  |  |  |  |  |  |  |
| Early Replacement of ALP & HP* | 1,800 | 0 | (1,800) |  | 1,800 | (1,800) | To 2018/19 |
| CCTV on Pumping Appliances * | 405 | 405 | 0 |  | 405 | 0 |  |
| Asset Management Plan | 200 | 0 | (200) |  | 200 | (200) | Savings £200k |
| West Hampstead Cottages Refurb | 0 | 20 | 20 |  | 0 | 20 | FEP2776 |
| Farynor Replacement | 425 | 50 | (375) |  | 425 | (375) | To 2018/19 |
| Security at Fire Stations, Offices & HQ | 200 | 0 | (200) |  | 200 | (200) | To 2018/19 |
| Performance Management Sys (PMF) | 190 | 0 | (190) |  | 190 | (190) | To 2018/19 |
| New Training Centre * | 478 | 302 | (176) |  | 302 | 0 |  |
| PEG/BDC Development | 3,750 | 340 | (3,410) |  | 3,750 | (3,410) | Budget Saving |
| 22mm Water Hose and Reel for Appliances * | 1,500 | 1,500 | 0 |  | 1,500 | 0 |  |
| Vehicle Security * | 1,389 | 1,389 | 0 |  | 1,389 | 0 |  |
| New Projects TOTAL | 10,337 | 4,006 | (6,331) |  | 10,161 | (6,155) |  |
| Projected Underspend | (6,686) | (6,686) |  |  | (6,686) | 0 |  |
| CAPITAL EXPENDITURE TOTAL | 29,146 | 17,995 | (11,151) |  | 28,970 | (10,975) |  |

- Pay and Inflation

  - The 2017/18 Budget includes a provision for a 1% pay award for all staff for 2017/18. This report now includes a £1.5m pressure based on the latest offer to operational staff. As this offer has been rejected, any additional award would further reduce the underspend.

- Changes to Income

  - Both the cost recovery and expenditure budgets related to mutual assistance charges are being reviewed to ensure that they are as accurate as possible. Any budgetary pressure resulting from this review will be reported in future Budget Update reports.

- Property Services

  - The 2017/18 budget includes £630k of savings from the implementation of the Property Services Integrator, which includes an estimate of savings that can be achieved on LFEPA’s supply chain. This saving will be updated once the supply chain has been fully costed after mobilisation phase is completed in March 2018. The savings target is based on an average saving each year to meet the overall savings target agreed over the contract life. It should be noted that a growth bid has been submitted for 2018/19  as the costs for the mechanical, electrical and plumbing and building fabric contracts, which are in the process of being retendered, are expected to come in higher than current costs due to market changes since it was last tendered. This cannot be confirmed until the tenders are returned later in the year.

  - The saving proposals for 2017/18 included material savings for energy budgets. This budget has underspent in recent years, in part because of the prudent assumptions used when calculating the budget requirement. These additional savings will therefore set the budget at a less cautious level, and as a result this will increase the risk of overspends in subsequent years, for example because of a colder than average winter.

- MDT Theft

The theft of MDT is covered in detail from paragragh 61. The spend on the stolen MDTs will be charged to revenue and would be offset by the insurance income. There is a risk that the claim would not meet the full cost and any difference resulting in additional overspend.

- Capital Expenditure and Financing

  - The capital budget is subject to change during the year. Initial project specification is key as it is important to keep variations to projects to a minimum. However even a well managed project can be subject to re-phasing or deferral due to a number of unforeseen issues, such as failure or default on the part of the contractor or exceptionally adverse weather conditions. This can also impact on funding requirements which in turn may have a debt charge (cost of borrowing) revenue impact.

  - All capital projects will require third party collaboration to varying degrees over the project life. The programme depends heavily on external factors and therefore can be subject to variation with the potential for delays in project delivery and revised cash flow requirements. The capital programme is managed on a monthly basis and is reported quarterly to the CAPS group (Capital, Approval, Planning and Strategy Group, chaired by the Director of Finance & Contractual Services) where all changes to the programme are reviewed and substitution projects or re-financing proposals are assessed and agreed.

  - Discussions are continuing regarding the sale of the two former fire stations, Clerkenwell and Southwark, and as a result the forecast capital receipts for these sites have been deferred by a year to 2018/19. The capital financing costs have been updated to reflect the re-phasing of the capital receipts, although if these sales are delayed any further, the level of external capital financing will increase together with the associated debt charges. This situation will continued to be monitored.

  - The design, specification and build of the replacement vehicles and equipment is now underway following the commencement of the new contract in November 2014. Key risks relate to the contractor sourcing appropriate vehicle build options within a timeframe that meets fleet replacement requirements and which may in turn impact the Authority’s cash flow. The forecast cash expenditure for 2017/18 and future years is based on the current assessment of the stage payment requirements for the pump replacement programme which represents about half the forecast Vehicles and Equipment expenditure in that period and the delivery timings for the balance of the fleet replacement programme.

  - The Brigade successfully cutover to the Replacement Mobilising Solution (VISION4 mobilising system & DS3000 ICCS) as planned on 17 November 2015. The legacy systems were decommissioned in January 2016 and there are a number of other work streams within the project that are still to be delivered. Update releases have been scheduled through 2017 and 2018 for this outstanding functionality. The status of this project is Green as reported in FEP2702.

  - The Asset Management Plan (2017) was approved in March 2017 (FEP2714), which has identified new priorities for investment over the next 5 years across the LFB estate, which includes fire station replacement, redevelopment and refurbishments which will enable the property portfolio to meet the needs of a 21st century fire service. It is difficult to source suitable new sites for purchase to replace those stations where investment to improve their condition or functionality is uneconomic, as the Authority  has to compete with other sectors, in particular residential development.  Initially a budget of £10m per annum was set aside to fund new developments as and when these opportunities arise.  Following a review of the programme, it was decided that the budgets for the works resulting from the asset management plan would be requested once the requirements for each project have been specified. Therefore £200k,has been identified as a saving for  2017/18 and the future capital budgets of £10m per annum have been removed from the capital programme.

  - As the new sites for Plumstead and the combined PEG / BDC facility (Integrated and Equipment Logistics Project) are yet to be purchased or a lease agreed, there is a risk that the acquisition of the preferred sites and the respective project programmes will be substantively delayed. As the LFB Training Centre project has a dependency on PEG moving out of Croydon, a delay to acquiring a site for PEG / BDC may have a knock on effect on the Training Centre programme. This would be additional to the current reported delays on the Training Centre, which are not linked. Should these risks in respect of site acquisition materialise, this would result in reduced actual expenditure in future years compared to the current forecast costs for these major capital projects.

  - The debt charges arising from the capital programme have been calculated using the current forecast Public Works Loans Board (PWLB) rates. No allowance has been made in the capital programme for potential future capital grants or contributions and LFEPA will bid for any available capital resources as and when such opportunities arise.

  - The spend on stolen Mobile Data Terminals will be charged to revenue and would be offset by the insurance income. There is a risk that the claim would not meet the full cost and any difference resulting in additional overspend.

- Contractual Pressures/ Risks

  - Significant demand continues to be placed on the Information and Communications Technology Department to meet new requirements and aid in the development of smarter systems for the Authority. This is at a time where resources are limited and as a result there is a risk that development of information technology solutions may be constrained.

  - The company that provides and supports the Authority’s Command Support Unit system software went into administration in early May and have since ceased trading. Whilst there is now a new supplier in place supporting the system and interim arrangements have been agreed there is no formal arrangement yet in place to support the deployed version other than on a time and materials basis.

Financial Regulation 9:

“(f) With the agreement of the Director of Finance and Contractual Services, a head of department may transfer up to £50,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget, but if those budget heads are in different Directorates the agreement of the appropriate Directors is also required.

(g) With the agreement of the Director of Finance and Contractual Services, the Commissioner, the Directors and the Head of Legal and Democratic Services may transfer up to £125,000 from a budget head within that department’s approved budget to a budget head within another department’s approved budget.

(h) The Director of Finance and Contractual Services shall report all transfers under (f) and (g) to the relevant committee as part of the quarterly monitoring reports.“

No transfers were processed in Quarter 2 that require reporting.

The chart below shows the amount of outstanding LIFT debts over the last 18 months. Note the below graph shows a slight increase in outstanding debt for the month ending September 2017. This appears to be a seasonal trend and also occurred in September 2016, possibly as a result of staff taking leave over the summer.

The chart below shows the top 5 (worst) outstanding debtors for LIFT income.

|  | Amount outstanding (£) | Average Age of Invoices in days | No of invoices |
| --- | --- | --- | --- |
| London Borough of Lambeth | 16,517 | 74 | 42 |
| Royal Borough of Greenwich | 13,272 | 184 | 34 |
| London Borough of Croydon | 7,303 | 649 | 20 |
| Sainsbury’s Supermarkets PLC | 5,742 | 792 | 16 |
| London Borough of Hackney | 5,510 | 19 | 14 |
| Total | 48,344 | 280 | 126 |

The top five (worst) outstanding debtors, totallingf £48,344, above includes £5,477 of invoices still within the 30 days payment period, and are therefore not yet overdue for payment. The Authority’s internal debt control process is currently ongoing to recover these debts.

The top five (worst) debtors has continued to decrease over the past years. This reached a peak of £105k at the end of September 2015, but has now reduced to £48k as at the end of September 2017. The continued joint effort by Authority staff has resulted in the positive progress made to date.

London Borough of Lambeth:

Outstanding debt for LB Lambeth has been referred to Finance by the South West Area team. The required checks have been carried out by Finance and these debts have been referred to the Legal department for action. Payment has been promised shortly by LB of Lambeth.

Royal Borough of Greenwich:

A final chase letter has been sent by the South East Area team, giving 14 days to pay. It is anticipated that this letter should result in payment because previous old invoices were settled following a final chase letter. However if no payment is received by early November, debts will be referred to Finance/Legal for further action.

London Borough of Croydon:

A final chase letter was been sent by the South East Area team on 12 October 2017, giving 14 days to pay. This has followed a period where work was carried out by the Borough Commander with the

LB Croydon to put new measures in place, including the offer of an amnesty. This has resulted in some payments being made previously, however some additional charges have now been incurred. If no payment is received following the final chase letter, the debt will be referred to Finance/Legal for further action.

Sainsbury’s Supermarkets PLC

There are currently difficulties experienced with regards to outstanding payments by Sainsbury as a whole. Although Sainsbury’s is the named debtor, invoices are raised against the individual store where the shut in life releases occurred, which has made it more challenging to secure payment. The Sainsbury’s invoices also present further challenges as they cover the London-wide area and do not come under the responsibility of any one area.

Area teams have now referred outstanding invoices to Finance for further action. The required checks have been carried out by Finance and these debts have now been referred to Legal department for action. Further consideration will be given to the role Sainsbury’s HQ should play in the debt recovery process.

London Borough of Hackney

The outstanding debts for LB Hackney have now been settled.

The table below shows the total outstanding outstanding debt for LIFT income for Boroughs by area.

| Area | Borough | Amount Due £ |
| --- | --- | --- |
| North East | London Borough Of Waltham Forest | 1,822 |
| North East | London Borough Of Tower Hamlets | 670 |
| North East | London Borough Of Islington | 4,718 |
| North East | London Borough Of Newham | 394 |
| North East | London Borough Of Hackney | 5,510 |
| North East | London Borough Of Barking & Dagenham | 1,181 |
| North East | London Borough Of Havering | 787 |
| Total North East |  | 16,188 |
| North West | London Borough Of Ealing | 354 |
| North West | London Borough Of Camden | 354 |
| North West | London Borough Of Hounslow | 715 |
| Total North West |  | 1,423 |
| South East | London Borough Of Croydon | 7,303 |
| South East | Royal Borough Of Greenwich | 13,272 |
| Total South East |  | 19,078 |
| South West | London Borough Of Lambeth | 16,517 |
| Total South West |  | 16,517 |
| Grand Total |  | 53,597 |