- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/25 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 340 kgs/head | 310 kgs/head | 395 kgs/head | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | 756 kgs/hh | 706 kgs/hh | 617kgs/hh | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | 66 kgs/head | 50 kgs/head | 77 kgs/head | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70% Unavoidable food waste in residual: 30%. Avoidable food waste recycled: 44% Unavoidable food waste recycled: 56%. If you would like to apply these figures, you would need to know the percentage of both your residual waste and your recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 21 % | 30 % | 22.4%* (*24.96% including recycled Incinerator Bottom Ash metals) | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 23 % | 35 % | 22%** (**24.31% including recycled Incinerator Bottom Ash metals) | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/25 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 4 % | 100 % | 100 % | 100 % | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100 % | 100 % | 100 % | 100 % | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 12 % | 100 % | 85% | 95% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100 % | 100 % | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0 % | 100 % | 90% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100 % | 100 % | 100 % | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100 % | 100 % | 100% | 100% | Borough to take from own info. |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| WCC 1.01 | Commercial waste reductions | - Producers of commercial waste are already incentivised to reduce their waste by the savings they can make on waste collection and disposal as part of the council’s Fees and Charges for commercial waste. - Much will depend on the implementation of RWS which will overhaul how commercial waste is managed inc EPR for packaging waste. | - On track / part complete | - In 2024, the night shift additional recycling project collected 2,211 tonnes of mixed recycling and 47.4 tonnes of food waste. - Year to date (21 July 2025), the night shift recycling project collected 1,309 tonnes of mixed recycling and 274.44 tonnes of food waste - Delivered a range of outreach and educational activities for Simpler Recycling and compliance by businesses - 17% more food waste collected from businesses in 2024/25 compared to 2023/24 - 24% more source segregated paper/cardboard collected for recycling from businesses in 2024/25 | - In 2024/25 there was a 1% reduction in total commercial waste tonnage compared to 2023/24. |
| WCC 1.02 | Household waste restrictions | - Restricting residual waste in purpose-built flats by incentivising use of recycling bins through lower hire charges for general rubbish bins and provision of free of charge recycling bins - updated waste storage guidance, mansion block rationalisation work will include updating the current database and increasing recycling improvement infrastructures in these blocks. - The housing estates local incentive “In it to Win It” scheme incentivises residents to recycle more in through the opportunity for their estate to win community prizes. Winners are judged on kg/hh per estate and number of contamination reports to ultimately reduce that amount of general waste in the recycling and encourage residents to recycle more. | - On track / part complete - On track / part complete | - To clarify this section encompasses both purpose-built flats and housing estates. - Purpose-built flats waste storage guidance is on public portal - Westminster City Council. Waste Storage Planning Guidelines – Completed .For further information: www.westminster.gov.uk/recycling-and-rubbish/waste-storage-planning-advice - Mansion Block Waste Bin Infrastructure review works are in progress. - “In it to Win it” programme has been kept on hold until smart sensors trials are completed and deployed in the bins for accurate data and collections. - The sensors trials are in progress however with contract relet works, the sensor project is now expected to be rolled out in 2027/28. However the in it to win it rewards scheme , will start from 2026/27 using the manual monitoring data. | - Incorporated food waste service provisions in the waste storage guidance necessitate the service as part of standard waste storage for new purpose-built blocks. – Completed - Housing estate infrastructure project: estimated 2000 tonnes of CO2e be saved per annum with the roll out of this project. Please also see WCC 2.03. - Results shown 44% increase in recycling participation and 25% reduction in reported contamination incidents. With 100% increase in quality. This project is a success. |
| WCC 1.03 | Household waste restrictions | - Containerisation of household waste – 60% of household waste is already containerised via communal bins. The remaining 40%, is mostly unsuitable due to lack of off-street outside storage or located within Conservation Areas. The remainder of properties could have containerised collections but because changes to fleet and resourcing levels will be required it is best considered during procurement. In the past, benefits from the flexibility of standardised fleet & communications outweighed having a small minority of kerbside properties using 2 wheeled bins. | - On track / part complete | - Containers were trialled in Ilbert Street (Queen’s Park ward) from 2022. This trial is now complete. Containers were then delivered to three wards (Queen’s Park/ Harrow Road/ Westbourne) between July and October 2024. This achieved an average of approx.. 15% increase in residents participating with the recycling service, approx.. 23% increase in residents participating with the food waste service and a decrease in abandoned waste reports by 25%. - We are waiting for Cabinet Member confirmation to proceed with Phase 2 of the roll-out in four wards (Maida Vale, Little Venice, Abbey Road and Regent’s Park). These will occur between October 2025 and July 2026. | - The roll-out across the 3 wards (Queen’s Park, Harrow Road and Westbounre) achieved an average of approx.. 15% increase in residents participating with the recycling service, approx. 23% increase in residents participating with the food waste service and a decrease in abandoned waste reports by 25%. - We completed a door knocking exercise and engaged 24% of residents (of 6,779 suitable properties) and 18% of those undertook a survey. 65% of respondents were pleased with the new service and provided positive feedback. |
| WCC 1.04 | Household waste reductions | - Reducing the number of on-street waste bins by removing sites with dumping problems. | - On track / part complete | - The on-street waste and recycling (BBB-MRC) are extremely popular among residents with limited storage spaces, as these enable them to clear waste outside of scheduled line collections. However, with local ward Cllrs intervention waste team have successfully removed 5 BBB sites to improve waste presentation / dumping issues. This is an ongoing work. - Officers are conducting city wide BBB audits to identify further sites with similar issues. Audits expected to complete Nov 2024 with actions taking place from March /April 2025 – In total 7 BBB/MRC sites have been removed since the RRP to increase D2D participation and reduce flytipping incidents. | - Significant improvement has been registered across the BBB sites following enforcement and educational activities. Resulting in more line collection / D2D participation - New bin housing pods to be introduced across potential MRC/BBB sites to increase participation, reduce contamination and flytipping. This has resulted form the success of housing unit infrastructure project. |
| WCC 1.05 | Household waste collection reductions | - Alongside roll out of a weekly food waste recycling service during 2022, kerbside properties where suitable had one weekly rubbish collection substituted for a weekly food waste recycling collection. Residents however have option to register to have their second rubbish collection reinstated. | - Delayed / on-hold / no progress to date | - Kerbside collection changes (in relation) were completed by winter 2022. - However, following local elections in 2022 a change in approach was followed and some areas now have 2nd weekly rubbish collections reinstated due to the volume of individual second weekly rubbish collection requests submitted. - No changes since last RRP update July 2024. | - Difficult to assess impact as household rubbish tonnage is not available per ward/ area. |
| WCC 1.06 | Garden/ food waste | - Promotion of discounted home composters on council website and on Recycle for Westminster Facebook page. 50 home compost bins distributed per annum | - On track / part complete | - Due to staff resources and focussing efforts on the food waste recycling roll out/ BAU activities – this area of work has not been a focus in terms of high levels of promotion. Some social media activity undertaken. - Further promotion will be undertaken in 2025/26 | - Target Number not achieved in 2024/2025 (under 10) |
| WCC 1.07 | Reusable nappies | - Westminster City Council joined the Real Nappies for London voucher scheme in April 2022 for the first time. - Voucher scheme will be promoted on council channels as much as possible and promotion of scheme at baby groups has started. - Scheme to be promoted as recycling stands | - On track / part complete | - WCC held 3 Give and Take events in the year 2024/25. The Paddington Children’s Library event had the highest number of residents engaged at 15. - 3 reusable nappy demonstrations completed which resulted in more people finding out about the data. - In 2025/26, voucher sign-ups come with optional questionnaires which should help WCC to understand people's behaviours. - WCC has continued it commitment to working with Real Nappies for London for another year in 2025/26 with a target to issue and have 100 vouchers used. - This is ongoing work. | - The data work completed meant that WCC targeted different areas to increase voucher sign-up. - This meant that 88 vouchers were given out to residents compared to 67 in the year 2023/24. |
| WCC 1.08 | Food waste reduction | - Promotion of LoveFoodHateWaste campaign with leaflets provided at events, website and via social media. - Westminster City Council has joined Pan London Food Waste & Diet Campaign with ReLondon. - Participate in Food Waste Action Week in 2023 (webinar, social media activity, engagement stands) | - On track / part complete | - Agreed to provide continued funding at silver level for another year for the Pan London food waste reduction campaign - Eat Like a Londoner. - Promoted Food Waste Action Week on our social media channels. - Unfortunately, the Eat Like A Londoner campaign was paused but will be restarting in 2025/26 and however, WCC has indicated to London Councils it will continue to Support if the campaign goes ahead. | - Successful cook Low Waste workshop held during Food Waste Action week. - Promoted Food Waste Action Week on our social media channels. |
| WCC 1.09 | Reduction events- textiles | - Regular Give and Take events held at libraries, along with repair and upcycle workshops | - On track / part complete | - In 2024/25 we held 3 give and take events to do with real nappies for London to promote waste reduction. - We’ve held low waste kitchen workshops. - We’ve had clothes mending workshops at our Community Mobile Recycling Centre (CMRC) events. Along with bike repair services at every CMRC, and e-waste repair services at certain CMRCs (where the location is suitable) – for further info: www.westminster.gov.uk/recycling-and-rubbish/reusing-and-other-recycling-services/community-mobile-recycling-centre - Have had new engagement stands for Reusable period products | - 67 bags of clothes for charity from our CMRC events instead of being thrown away - Around 15 people per clothes mending workshop event in our CMRCs which helped reduce the number of items being recycled - It is difficult to determine impact from residents acquiring theses new skills and the impact on how they repair their clothes in future. - Please also see impact listed for WCC 4.03. |
| WCC 1.10 | Reduction events- upcycled craft workshops | - Hold/support upcycled craft workshops at WCC libraries that promote reuse and engage with residents to educate on waste reduction. | - On track / part complete | - Focus has been on our CMRC events where we have Dr Bike fixing bikes, SunnyJar helping to reuse textiles and to help residents acquire textile repair skills. | - Our textiles workshops and Bike repairs at our CMRCs events are very successful which has resulted in textiles being upcycled/reused. - Please also see impact listed for WCC 4.03. |
| WCC 1.11 | Circular economy projects | - WCC participated in Circular Economy Week 2022 with a community event at Church Street focussed on re-use/ re-cycling/ repair. - Officers are currently scoping projects for the remaining CE budget, which will likely include working with Libraries to bring the Library of Things to Westminster. - We also anticipate setting a clearer direction on public water fountains and taking advantage of more pan-London/ national schemes. | - On track / part complete | - This work has been incorporated into our new Community Mobile Recycling Centres initiative (where WCC includes bike repair services, a swap shop and provides opportunities to reuse). - No changes since last RRP update 2024. | - Please also see impact listed for WCC 4.03. |
| WCC 2.01 | Residential food waste recycling service | - Food waste recycling trial (approx. 7000 hhs) ran from Autumn 2019 until February 2022 (over 700 tonnes of food waste collected) - Since March 2022 permanent food waste recycling service has been expanded to suitable kerbside and mansion blocks and estates - Service provision will include: kerbside service, communal bin service (for housing estates and mansion blocks), on-street micro-recycling centre bins and an on demand doorstep collection service for properties in the West End. | - On track / part complete | - Since March 2022 the food waste recycling service has been rolled out to the majority of residential properties in the City of Westminster. WCC provide 4 types of food waste service (weekly kerbside, communal, on-street neighbourhood and an on-demand booking service). - To date over 5,300 tonnes of food waste has been collected as part of this service. - A main challenge WCC faces is with a number of managing agents/ property managers are refusing to engage with WCC on introducing the service/ or are rejecting the offer of the food waste service. | - To date (since March 2022) over 5,300 tonnes of food waste has been collected as part of this service |
| WCC 2.02 | Household recycling service provision - All households and institutions/organisations generating household waste e.g. schools, religious buildings etc. already receive a collection of the minimum level for household dry recycling (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays) & also liquid food/drink cartons | - Annual communication plan focus on promoting the use of the dry mixed recycling service. Use of ReLondon communication templates when suitable. - Various media channels used – engagement, social media, print etc - Focus on increasing recycling via door to door campaigns, behaviour change projects, increased residential engagement activities and providing further recycling communications information (including translations and disability-friendly formats) so that is clear for residents on how to recycle. - Initial behaviour change project will be launched in Spring 2023 - work is starting in early 2023 to plan and scope this project. | - On track / part complete | - Focus has been on BAU communications activities. This included an annual recycling leaflet included in our Council Tax packs, supporting all appropriate London-wide and national recycling and waste reduction campaigns. In addition to this WCC undertake a large Christmas communications campaign (as this is the only bank holiday during the year where collections are changed). - All initiatives/ projects also have their own communications plans- for example for our CMRCs, the north container expansion project (Ilbert Street blue and black bins). - All available communication channels are used- social, printed, e-newsletters, engagement stands, etc. | - Contribute to increasing household recycling rate |
| WCC 2.03 | Estates recycling | - Adoption of best practice outcomes from ReLondon flats project to improve recycling facilities at flats via capital funding bids. This infrastructure project could potentially involve 16,400 households from medium to high rise blocks of flats flats. - Collaborate with estates services department on waste enforcement on housing land and increase recycling knowledge of residents through targeted communications including letters and posters | - Complete | - New bespoke estate recycling bin housing units/ infrastructure has been developed and will be installed across all suitable housing estates and mansion blocks from Aug 2024; these units will have simple clear communication message that will prompt residents to recycle more. The required capital works will commence form July 24 with an aim to complete the full rollout by June 2025. - The 289 new housing pods have been installed across all council owned housing estates, private housing to have the same pods installed by end of 2025/26. | - Linked to WCC 1.02 - Results shown 44% increase in recycling participation and 25% reduction in reported contamination incidents. With 100% increase in quality. This project is a success. - Bespoke communications and engagement events completed and a working group with housing is now established to trouble all operational and engagement challenges. |
| WCC 2.04 | Management of communal recycling infrastructure in purpose built private flats / converted mansion blocks | - Planning guidance designed to encourage source segregation, engagement with gatekeepers/porters, managing agents, analysis of fair provision for residual waste, bin hire contracts already offer financial incentive for landlords/managing agents to recycle i.e. recycling bins are free to hire whilst rubbish bins are charged for. - Review existing bin infrastructure across all mansion blocks and purpose-built houses by end of 2023-24 and enhance recycling capacity where feasible. - Corporate policy on provision of enforcement is underway. | - On track / part complete | - Two large collection rounds participation and performance data has been analysed and bespoke communication plan along with engagement activities have been planned and developed. The project is expected to be delivered by end of 2026. This project had minor delays due to waste relet contract works and other urgent priorities. | - In addition to increasing the recycling service participation, the new bespoke targeted communication will also focus on recycling high carbon intensity items like textiles and small WEEE along with Reuse. |
| WCC 2.05 | Delivery of contamination action plan to ensure high quality recycling | - Contamination reporting by crews, targeted communications to worse offenders, installation of 'transparent' bins, transparent recycling sacks, helping commercial customers improve internal management of wastes. - Contamination action plan redrafting underway - Investigate if any new technological solutions are available for the on-street bins to reduce contamination. | - On track / part complete | - The artificial intelligence (AI) system trial to spot contamination couldn’t deliver the anticipated outcome however conversations are back on track with IT teams to investigate the AI systems to spot contamination and hazardous waste. | - Contamination action plans and measures to address the behaviours are now live and are being used at both Social Housing and MOP- Manson blocks. - Measures around on-street recycling capital infrastructure improvement works are delivered to a greater level. The housing unit expansion is now rolled out to recycling bring banks with an aim to complete the rollout my March 2026. |
| WCC 2.06 | Management of 1200 recycling litter bins to enable residents/visitors to recycle on the go. | - Ongoing management of infrastructure includes maintenance, replacement, site suitability reviews, signage, emptying, provision of bulking infrastructure, street sweeper incentive scheme. - The City Council has successfully installed 60 new litterbins across the city since lifting the lockdown and won WRAP Bin infrastructure funding 2021/22 which enabled WCC to develop a bespoke litterbin and install an additional 21 new duo litterbins. | - Complete | - New model litterbin has been developed with capturing recycling on-the-go in mind, the 1500 new model litter bins will be installed in the city from Sept 24 and rollout should be completed by June/July 2025 - Sweeper waste and recycling will be captured and stored in bespoke sweeper bins called SSB. These SSB be collected using the regular large electric vehicles for recycling. - Crews and Sweepers are all trained to collect both streams separately and recycling as much as possible by separating at the point of pickup. Sweeper dedicated training have been developed and delivered to raise the service profile and make them the ambassadors of the service. | - 1700 on-the-go- recycling litterbins have been installed across the city and with 30% diversion rate and 10% contamination rate the project proved to be a great success. Multiple Street Sweeper Bins (SSBs) have been installed and sweepers training completed. An estimated 10% of the total street litter is now recycled. |
| WCC 2.07 | Comprehensive commercial waste recycling service available to 40,000 businesses, includes source segregated collections of paper (3,300 tpa), glass (6,600 tpa) & food (3,000 tpa) plus mixed recycling (paper, glass, metals, plastics & cartons). | - Introduction of new source segregated recycling services in 2018/2019 for glass, paper and food - A project is being developed to capture more glass, food waste and cardboard from hospitality businesses in a trial area who present their waste for collection at night when there is no recycling service. | - On track / part complete | - All materials mandated under Simpler Recycling are collected other than flexible plastics which will be implemented as of April 2027 pending having a treatment outlet for this material. | - The commercial waste recycling rate increased from 20.13% in 2023/24 to 21.16% in 2024/25 - The municipal waste (total waste) recycling rate increased from 23.07% in 2023/25 to 25.04% in 2024/25. |
| WCC 2.08 | Coffee cup recycling service/trial | - Introduction of new trial coffee cup recycling service for businesses in 2019 whereby businesses can purchase separate coffee cup collections as part of their commercial waste collection contract. - Limited update since start of the pandemic due to flexible working arrangements. | - Complete | - Coffee cups are now collected as part of dry mixed recycling after confirmation from our MRF operator that these are accepted as input material and recycled as part of the mixed paper stream. | - Completed |
| WCC 3.01 | Waste Large Fleet – ULEZ Compliance and Street Cleansing Fleet – Zero emission operations Westend and CityWide | - The City council actively using planning policy and sustainable infrastructure to promote clean air - Reducing Westminster City Council’s own vehicle fleet emissions - By introducing electric vehicles for council use. - To switch from current diesel street cleansing fleet to fully electric cleansing fleet - To switch current diesel-powered ULEZ compliant waste and recycling fleet to fully electric by 2024/25 | - On track / part complete | - Delays in securing the planning approvals for the second waste depot meant, the electrification of the second half of the fleet is still pending however plans are in place to electrify 95% of the fleet by April 2027. | - Westminster fleet is 100% ULEZ complaints, however City Councils aspirations are to go beyond the ULEZ and have a fleet of zero tailpipe emissions, which is now expected to be completed by April 2027 subject to securing planning permissions for a second waste depot. |
| WCC 3.02 | Supporting BIDS (and other similar commercial organisations) to set up waste consolidation schemes so there are fewer vehicle movements in the city for collecting waste e.g. HOLBA serviced by WCC Commercial Waste Services. | - Continue to promote and support best practice for waste consolidation schemes. Ensure the City Council bids for all tender opportunities to further reduce the number of vehicles movements around waste collections- progress of this depends on outcome of the pandemic and outcome of RWS consistency consultation | - Delayed / on-hold / no progress to date | - There is no progress on DEFRA’s work around commercial waste market reform as part of the Resources & Waste Strategy. The lack of legislative context limits the city council’s opportunities and ability around establishing commercial waste consolidation schemes. - The city council maintains its relationships with those BIDs that offer a preferred waste supplier scheme. | - Commercial waste market reform will deliver a cleaner public realm, less system inefficiency/ duplication, less nuisances for residents, better recycling performance, eliminates perverse incentives by private waste collectors and reductions in HGV emissions leading to cleaner air. |
| WCC 3.03 | Emissions Performance Standard (EPS) | - The council has modelled predicted improvements in recycling as a result of the actions in this plan. WCC’s disposal routes are fixed until at least 2031- therefore the ability to reduce our EPS is limited (for example the EPS calculation assumptions for energy-from-waste disposal routes will mean it is difficult to improve WCC’s EPS rating). | - Delayed / on-hold / no progress to date | - No progress to date | - No progress to date |
| WCC 4.01 | Management of wastes | - The current waste disposal contract ensures all waste generated is treated or transferred in Greater London in the first instance i.e. dry mixed recyclables are sent to a MRF in Southwark before being sent for further treatment outside of London, source segregated recycling is bulked at a waste transfer station in London before being sent for reprocessing or recycling - Next treatment contract to be tendered on similar principles, from 2024. | - Delayed / on-hold / no progress to date | - In 2023/24 84% of the primary treatment of the city council’s total waste took place in greater London. - In 2024/25 89% of the primary treatment of the city council’s total waste took place in greater London. - 99% of all waste collected by the city council was received by waste delivery/transfer/receiving points within greater London. | - Dependent on new contract in 2027 - No further update. |
| WCC 4.02 | Provision and improvement of over 100 micro recycling centres sites (MRC) within Westminster | - Conduct annual audits of MRC sites to ensure the bins and communications information are updated. Regular enforcement of sites, provision of see-through bins and bins with secure locks to tackle fly tipping and contamination - Signage improvements underway at MRC sites to ensure residents understand how to use bins. - Reverse lidded bins with larger aperture were deployed at targeted sites to address flipping of cardboard and contamination. - Increase WEEE and textile bins to suitable sites; provide food waste housing units to sites in line with food waste expansion service where feasible. | - Complete | - Officers are conducting city wide MRC bin audits to identify further sites with dumping / contamination issues. Audits expected to complete Nov 2024 with actions taking place from March /April 2025 - Following audits capital works around new bin signage, bin keepers and new reverse lock lids with see through panels will be deployed to address the contamination, increase recycling and make the site pleasing for the neighbourhood. - Ongoing review will ensure at least 2 new small WEEE and 5 new Textile banks are installed by end of 2025/26. The relaunch of these two services are planned for 2024/25 where clear and effective new communications brandings will be developed and installed across all bins by end of 2024. | - Project has been delivered successfully; 160 MRC sites now have secure bins with lockable lids and see through bins at trouble site to spot contamination. Capital spends included better signage and with new housing pods, the MRC sites will have even better infrastructure - Small WEEE and Textile bins have been increased by two each however due to ongoing antisocial behaviours these units are under constant review. |
| WCC 4.03 | Pop-up recycling centres | Re-establish a mobile/pop-up recycling centre at suitable locations- dependent on contract relet | - Complete | - During 2024/25 5 Community Mobile Recycling Centres (CMRCs) were held across the City (meeting our internal target for the year). - At the CMRCs provision includes: bulky waste drop-off services, recycling drop off (including hard-to-recycle items such as books/ electrical items/ textiles/ batteries, bulbs etc) swap shop (electrical items are PAT tested). Depending on the location other services include free bike repair services, textile repair services (and workshops) and electrical appliance repair services. The CMRCs also allow residents to pick up recycling bags or food waste liners. - In May 2024 the CMRC won the (Local Authority Recycling Initiative, Awards for Excellence May 2024 - The CMRCs are successful and are running as a business-as-usual initiative. 6 CMRCs (including at new locations) are planned for 2025/2026. | - Increase in items that can be recycled that are not collected via residential dry mixed recycling collection stream (electrical, textile, book, and energy-saving light bulbs). - The CMRCs contribute to raising resident awareness about our services and contribute to WCC’s household recycling rate. - During 2024-25 around 700 residents attended the CMRCs. - Over 100 bags of textiles/ toys/ books/ household items in good condition were donated to local charity partners - Near 6 tonnes of items such as textiles/ books/ toys were diverted from energy-from-waste disposal via reuse and recycling. - Nearly 200 bikes were repaired |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| 6.01 | Household collections (excluding film)- mixed recycling | - WCC already collects glass, metal, plastic, paper and card. From residential properties - WCC plans to continue to co-collect card and paper with other dry recyclables on a general basis and has completed an eTEEP assessment to support this operational decision | - eTEEP assessment has been conducted and results suggest current practice is most appropriate for Westminster and there is no need for a Written assessment to be completed. - WCC’s eTEEP document can be shared if required. - Key outcome is to co-collect paper and card with other streams using current methods. However, Westminster our planning to go beyond it and improve quality by collecting paper and card separately at some communal locations in addition to current segregated on-street micro-recycling centre sites where possible, excluding large housing estates by April 2028. | - March 2026 |
| 6.02 | Residential food waste collections | - Please see RRP action WCC 2.01 | - Please see RRP action WCC 2.01 | - Please see RRP action WCC 2.01 |
| 6.03 | Residential garden waste collections | - Household garden waste trial launched in June 2025 in two wards for around 6.5k households - Trial service is free and follows an opt-in, bi-weekly collection model. - Up to 2 x 90 litre reusable sacks are provided to residents who sign up to the trial (additional sacks can be provided upon request once the resident starts to use the service). | - From the results of the trial a decision will be made in Autumn 2025 regarding the permanent service model (to ensure service launch by March 2026) | - March 2026 |