Part 1 –Reduction and Recycling Plan (RRP) April 2023 to March 2025

- London Borough of Lewisham:

The London Borough of Lewisham is passionate about creating a cleaner, greener, more environmentally sustainable borough and making Lewisham a place where everyone is proud to live, work and study in, and visit. The council is working with its partners to adapt their services to consumers needs following the waste hierarchy which gives priority to preventing waste and encourages reducing and reusing resources. This will support our ambition of moving towards a more circular economy – which keeps resources in use for longer. Lewisham already meets the mayor’s minimum recycling collection requirements, as the 6 main items plus a weekly food collection for kerbside properties is already in place. Lewisham commenced with a new food waste disposal contract via anaerobic digestion in April 2022.

The London Borough of Lewisham is an inner London borough with a highly transient population. The recycling rate in Lewisham is currently 28% (2021/22). This is impacted upon by our current and future housing stock. It is generally accepted that recycling is more difficult for residents in flats and there is a high proportion of flats in the borough.  Lewisham’s London Plan has set the housing target of 1667 new homes per year. Most new build housing developments are expected to be flatted developments which means that achieving recycling levels comparable with outer London boroughs with a lower proportion of flats will be challenging.

Lewisham has only one small reuse and recycling centre located in the North of the borough where residents are able to dispose of their household waste. The centre does not accept any DIY or commercial waste at this location due to the size of the centre.

- Key strategic documents linked to this plan:

This RRP has been developed in line with the London Borough of Lewisham’s:

Waste Strategy -  https://councilmeetings.lewisham.gov.uk/documents/s92378/Waste%20Strategy%20Final%20Design.pdf

Climate Emergency Action Plan - https://councilmeetings.lewisham.gov.uk/documents/s81350/Climate%20Emergency%20Action%20Plan.pdf

Local Plan - https://lewisham.gov.uk/-/media/files/imported/corestrategyadoptedversion.ashx

Corporate Strategy - https://lewisham.gov.uk/-/media/files/lewisham-council-corporate-plan-2022-2026.ashx

Park & Open Space Strategy - https://lewisham.gov.uk/-/media/parksandopenspacestrategy2020.ashx?la=en

- RRP Dashboard

| Set Common Performance Targets | Baseline Performance (2019/20) | Performance Target 2024/25 | Metric Guidance / Data source | Target Guidance |
| --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | 319.05 | 280 | Defra stats (Ex BVPI84a) | Borough sets own targets, informed by ReLondon /WRAP good practice. |
| Total annual household residual waste collected per household (kgs/household) | 555.59 | 450 | Defra stats (Ex NI191) | Borough sets own targets, informed by ReLondon/WRAP good practice. |
| Total annual household avoidable (edible) food waste (kgs/head) | 73 | 69 | Borough to estimate based on own or WRAP food waste composition data. Estimates should be based on avoidable food waste produced (i.e., not just food waste collected). | Based on estimated avoidable food waste produced. Borough to set own targets, informed by ReLondon/WRAP good practice and support programmes (e.g., Trifocal). |
| Annual household waste recycling rate (% by weight) | 27% | 40% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP Route Map modelling and other good practice. The GLA will use the borough recycling benchmarking table in the Route Map modelling as a reference point when assessing local authority targets set in the RRP process (See Appendix 2 of the London Environment Strategy, page 111: https://www.london.gov.uk/sites/default/files/les_appendix_2_-_evidence_base_0_0.pdf) |
| Annual LACW recycling rate (% by weight) | 24% | 40% | Defra stats | Borough sets own targets, informed by ReLondon/WRAP good practice. Targets should at least match household recycling targets, going beyond the mayor’s 50 per cent LACW recycling target by 2025 where possible. |
| Proportion (%) of properties receiving the mayor’s minimum level of service for household recycling: |  |  |  |  |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | Borough to take from own info. Separate food waste does not include co-mingled with garden waste | Borough sets own target, informed by ReLondon/WRAP good practice. Separate food waste does not include co-mingled with garden waste |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) | 100% | 100% | Borough to take from own info (Nb included for boroughs that are unable to provide food waste collections due to long term contractual issues). | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 90% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays). | 100% | 100% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)) and separate food waste collection | 0% | 30% | Borough to take from own info. | Borough sets own target, informed by ReLondonL/WRAP good practice and FAS data. |
| % of flats above shops (FAS) collecting six main dry materials (glass, cans, paper, card, plastic bottles and mixed rigid plastics (pots, tubs and trays)). | 100% | 100% | Borough to take from own info. | Borough sets own target, informed by ReLondon/WRAP good practice and FAS data. |
| Proportion (%) of waste fleet heavy vehicles that are ULEZ compliant | 100% | 100% | See www.tfl.gov.uk/modes/driving/ultra-low-emission-zone | Borough should aim to operate a fully ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. Please include baseline and target % of waste vehicles that are zero emission where applicable |
| Performance of LACW activities against the Mayor's EPS (tonnes of CO2eq per tonne of waste managed). | -0.069 | -0.084 | Use tool found here Boroughs to set by uploading WDF data into the GLA tool. | Borough to run their own scenarios using GLA tool to determine planned service changes (DSO borough) or new contract options against the EPS for target years (2024/5). See London Environment Strategy Proposal 7.3.2.b |

- RRP Actions:  Part one

| Ref | Theme - Waste Reduction - Maximising Recycling - Reducing Environmental Impact - Maximising local waste sites | Action title | Action Description | Expected Target / Impact | Timescale for action | WCA/WDA |
| --- | --- | --- | --- | --- | --- | --- |
| Lewisham 1 | Maximising Recycling Waste Reduction | Food service collection roll out to estates borough wide | - Trial of different food waste bins/housing units on Lewisham Homes & Pinnacle estates. - Procure food caddies, internal and external. - Provision of 180ltr residual waste bins to ground floor residents - Removal of excess 1280ltr recycling bins. - Ongoing targeted education/ engagement with residents on estates. | - All estate properties to receive food waste collections. - 100% coverage by March 2024 - Diversion from incineration, increase in food waste tonnages. Increase of 2.5% in recycling target | - March 2024 - Food waste Communications: October 2023 to May 2024 | UA |
| Lewisham 2 | - Maximising Recycling | Food service collection roll out to flats borough wide | - Residents in flatted properties currently do not have a food waste collection. Once the roll out to estates has been completed, Officers will work with Managing agents to trial bins/housing units to identify suitable containers for flatted properties. - Officers will meet with other local authorities to investigate possible collection solutions for flats - Ongoing targeted education/ engagement with residents. - Officers will work closely with colleagues in Lewisham Homes to maximise the effectiveness and reach of communications. - Audit on bin numbers to be carried out per block to reduce the number of general waste bins once food waste collection has been implemented. | - All flatted properties to receive food waste collections. - 100% coverage by March 2025 - Diversion from incineration, increase in food waste tonnages. Increase of 5% in recycling target | - March 2025 - Food waste Communications: October 2023 to May 2025 | UA |
| Lewisham 3 | - Maximising Recycling | Food service collection roll out to flats above shops borough wide | - Residents in flatted properties currently do not have a food waste collection. Once the roll out to flats has been completed, Officers will work with Managing agents to trial bins/housing units to identify suitable containers for flats above shops. - Officers will meet with other local authorities to investigate possible collection solutions for flats above shops. - Officers will look to work with boroughs that have trialled this service in order to build on existing knowledge and to identify best practice - Ongoing targeted education/ engagement with residents. | - All flats above shops to receive food waste collections. - 30% coverage by March 2025 - Diversion from incineration, increase in food waste tonnages. Increase of 1% in recycling target | - March 2025 - Food waste Communications: October 2023 to May 2025 | UA |
| Lewisham 4.1 | - Waste Reduction - Maximising Recycling | Waste Strategy objectives – Residual Waste Reduction/Contamination | - Implement a range of waste awareness campaigns such as swap shops, Cleaner Lewisham and right thing, right bin” campaign to reduce and discourage contamination and promote what waste goes in which bin. - Investigate the possibility of purchasing digital messaging for refuse trucks. - New Polices to be agreed and implemented on side waste and lid down – this will outline our policy of crews collecting good quality recyclable side waste and not collecting residual waste from bins that cannot be closed - New service standards to be agreed and implemented, Delivery of service standard to coincide with the serving of Section 46 notice. - Effective education, engagement, and communication plan- detailing attendance at events, schools’ community groups and resident associations. - New bin tags for all types of waste bins to be issued to crews. | - All bins to be re-stickered with updated information relating to recycling and food waste. - Service Standards to be approved and re-issued. - Attend 45 schools outreach events - Attend 8 Community event per year | - Ongoing events to be held by March 2025 - Service standards to be re-issued by February 2023 - New leaflets, sticker & bin tags to be created and produced by April 23 | UA |
| Lewisham 4.2 | - Waste reduction - Maximising Recycling | Waste Strategy Objectives – Food Waste Reduction | - Implement a range of food waste awareness campaigns and initiatives such us Love Food Hate Waste, Food recycling-use your bin, home composting. - Explore partnership working and local promotion of apps such as To Good to Go, Olio and Refill - New food waste stickers to be created for all residual and recycling bins - Home composting campaigns to be introduced along with workshop to encourage the home composting | - Minimum of 4 food reduction events per year. - Promotion of apps - Participation in the Pan London food campaign. - Hold 4 Compost works shops per year - Increase in the number of home compost bins purchased to previous year | - Pan London food campaign to run for 2 years, commences 2023 | UA |
| Lewisham 5 | - Maximising Recycling | Increased participation in garden waste service | - Targeted communications to encourage greater participation in the garden waste scheme. | - Number of new subscriptions – Target 13,500 by April 2025 | - Communications plan to align with growing seasons i.e., leading into Spring - Ongoing | UA |
| Lewisham 6 | - Maximising Recycling | External Funding | - Officers to investigate and apply for external funding to help support key campaigns - Funded activities to assist in outreach and engagement, improving education around waste minimisation and recycling | - Number of successful funding applications | - Ongoing | UA |
| Lewisham 7 | - Waste Reduction | Investigate the possibility of opening a Re-use shop/stall | - Investigate the possibility of opening a re-use shop or stall at Deptford Market. - Visit other Local Authorities to see how they opened their re-use sites. - Investigate the possibility of opening a virtual reuse shop. - Look at possibilities of working with eBay for textiles and furniture - Hold 3 Swap Shops per year | - Waste reduction | - Investigate reuse shop/stall Summer 2023 - Investigate working with eBay Summer 2025 - Swap shop on going event | UA |
| Lewisham 8 | - Waste Reduction - Maximising recycling | Improved recycling and waste reduction on markets | - Engagement with stall holders at the licensing stage promoting waste reduction - Engagement with stall holders by market officers promoting waste reduction on the market - Investigate the possibility of reducing plastic bag usage from market stalls - Implementation of cardboard recycling - Investigate the possibility of providing food waste collection service | - Waste reduction in tonnages collected from markets - Increase in cardboard recycling - Food waste diverted from incineration to anaerobic digestion, an expected increase of 3% in waste sent to AD. | - Summer 2024 | UA |
| Lewisham 9 | - Maximising Recycling | Working with Private Sector Housing Team re HMO’s | - Targeted communication detailing landlord responsibility to be provided. - Targeted communication to tenants. On how to use services provided. - Look to tighten up waste management procedures regarding HMO licenses. Work with the Strategic Housing Team to incorporate waste management into the landlord licensing process | - Waste reduction - Reduced complaints | - Ongoing periodically | UA |
| Lewisham 10 | - Maximising recycling | Expand the range of kerbside collections | - Investigate the feasibility in providing pop up electrical, textile, battery, and coffee pod collections | - Increase in recycled tonnage | - March 2025 | UA |
| Lewisham 11 | - Maximising recycling | Target campaigns | - Following the completion of the participation and compositional survey, target areas for improved recycling, increased garden waste collections and food waste. Including flats and estates to reduce the level of contamination | - Reduction of contamination - Improved recycling | - March 2024 | UA |
| Lewisham 12 | - Maximising recycling | Improved Textile recycling | - Refurbished textile banks across the borough. - QR codes on all banks – this will allow residents to easily get information about services relating to textile recycling/reuse and to identify the purpose of the banks - Investigate the possibility of doorstep textile collections - Donation station at more convenient local locations - Investigate the provision of locker drop textile service working in partnership with contractor | - Increase in materials sent for recycling and re-use. Increase in re-use material expected to increase by 2% | - March 2024 | UA |
| Lewisham 13 | - Waste Reduction | Reuse and Repair activities & events | - Officers to arrange 6 Give and Take day across the borough per year. - Investigate the possibility within shopping centres / libraries for pop up reuse and repair events. - Work with partners to establish alternative bulky waste collections for reuse | - Reduction in waste collection. - Work with partners re bulky waste collection | - Summer 2023 | UA |
| Lewisham 14 | - Maximising Recycling - Waste Reduction | Commercial waste collections | - Officers will make use of engagement tools in order to promote the recycling service to businesses. - Implement time banding across the borough and enforce | - Expected increase of commercial business waste to be sent for recycling by 25% - Reduction in commercial waste fly tips | - Ongoing | UA |
| Lewisham 15 | - Maximising Recycling | Schools’ food waste collection | - Trial food waste collections at a number of primary schools - Investigate the possibility of rolling out a commercial waste food collection service for schools. | - Expected increase of 4% in food waste sent for anaerobic digestion. | - Primary schools’ collection July 2023 - Secondary school collections March 2025 | UA |
| Lewisham 16 | - Maximising Recycling | Commercial waste recycling policy | - New Service standards to be created and implemented for commercial businesses - This policy will align with Lewisham’s commitment to maximising recycling, commercial waste officers will prioritise and promote recycling services when dealing with customers. - Food waste collections will be rolled out to businesses - Commercial waste officers will provide businesses with information relating to waste reduction. | - Improved waste management with businesses | - June 2023 | UA |
| Lewisham 17 | - Maximising Recycling | Council Tax letter | - Officers to ensure that information relating to waste and recycling is sent out with Council Tax letters | - Improved awareness | - Ongoing | UA |
| Lewisham 18 | - Maximising Recycling | Parks & Open Space Strategy – recycle waste from Parks | - Work closely with relevant internal departments and key partners to investigate the possibility of recycling waste from Parks - Educational campaign planned to encourage park visitors to reduce their use of single-use plastics and encourage the use of reusable items - Investigate the possibility of providing food waste collections to food facilities within parks and open spaces. - Work with the parks team and events team to ensure there is a policy in place to recycle waste from events e.g., London Marathon, Blackheath Festival, Peoples Day | - Increase in recycling 1% - Improved waste management at events - Improved education | - Ongoing | UA |
| Lewisham 19 | - Maximising Recycling | Cleaner Lewisham | - Implement a Low Plastic Zone in phases to businesses and market traders, encouraging commercial customer to sign up to plastic pledge reduction. - Part of the campaign will be providing information on correct means of waste disposal, including information on recycling locations for soft plastic, WEEE and batteries | - Reduced single used plastics - Positive PR for council - Increase business participation | - December 2024 | UA |
| Lewisham 20 | - Waste Reduction | Food Waste Reduction | - Campaign to be launched promoting the reduction of food waste, messaging will be in line with campaigns such as ‘Love Food Hate Waste’ - Messaging to be promoted at community events, schools, Goldsmiths University, and residents’ associations - Work will be done with our internal communications team to develop this campaign | - Minimum of 4 food events carried out per year. - Reduction in food waste by 4 kg per head | - ongoing | UA |
| Lewisham 21 | - Maximising Recycling - Waste Reduction | Lewisham Homes Estate Project | - Work will be done to roll out these projects to more estates in the borough - Engagement with residents concerning proper use of the recycling bins - Work with managing agents to reinforce this messaging - Survey of waste disposal facilities in place on the estate - Continue the roll out of improved recycling facilities on estates through the MetroSTOR waste containerised project. - Improved communication - Embed recycling message through Envirocrime pilot - Investigate the possibility of introducing compost areas to engaged community group gardens / pilot area / sheltered blocks. - Officers will investigate the possibility of implementing ReLondon’s Flat Recycling Package to a number of Lewisham Homes estates in order to support these targets – the implementation of this package will be subject to budgetary constraints | - Reduction in contamination on trial estates by 10% - Reduction in fly tipping | - Ongoing | UA |
| Lewisham 22 | - Waste Reduction - Reducing Environmental Impact | Local Plan | - Lewisham is currently working on its Local Plan; this document will guide Lewisham’s planning decisions through 2040 - The document is currently in the drafting stage, changes are being made based on a recent consultation - Circular economy principles will be prioritised in the borough. - Development projects will be net-zero waste; they will need to submit a Circular Economy Statement in line with the requirements of the draft London Plan policy s17. - Development proposals must be designed to ensure adequate on-site provision for the sorting of recyclable material, composting of organic material and the disposal of general waste during the occupation stage. | - Local plan to be approved - Improved engagement with planning officers | - March 2023 |  |
| Lewisham 23 | - Reducing Environmental Impact | Zero Carbon City | - The Council is committed to working towards a zero-carbon city and zero emission transport network by 2050 - The Council is committed to becoming a carbon neutral borough by 2030 - Ensuring contractors use ULEZ compliant vehicles and minimise the movement of vehicles - Include CO2 emission KPI’s in contracts - Deliver a carbon reduction and energy efficiency program in the Council’s social housing stock - Implement a decentralised energy strategy for the borough - Investigate the possibility of using energy generated by SELCHP to charge electric vehicles | - 100% ULEZ compliant vehicles in use - Procurement of new vehicles - Contribute towards Mayor of London /Lewisham zero carbon city by 2030 | - Ongoing |  |
| Lewisham 24 | - Reducing Environmental Impact | Electric Vehicles | - Officers will seek funding for the trial of electric fleet vehicles - Officers will trial alternative collections vehicles to reduce the number of collection vehicles within the borough - Investigate the possibility of utilising electricity from SELCHP at LB Westminster site for electrical vehicles | - 100% ULEZ compliant vehicles in use - Procurement of new vehicles - Contribute towards Mayor of London /Lewisham zero carbon city by 2030 - Contribute to Lewisham air quality target | - Dec 2023 |  |
| Lewisham 25 | - Maximising Local Waste Sites | CA Site Communications Campaign | - Produce new literature promoting the CA Site - Improve signage at the Site - Review opening times of the site to make it more accessible to residents - Implement single stream bring bank area | - Improved access - Wider material acceptance | - Review of RRC items to be completed by September 2023 |  |