- RRP Dashboard update:

| Performance Targets | Baseline Performance 2019/20 | Performance Target 2024/251 | Actual performance 2023/24 | Metric Guidance / Data source |  | Target Guidance |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total annual household waste per head (kgs/head) | kgs/head 319.05 | kgs/head 280 | kgs/head 314.18 | Defra stats (Ex BVPI84a) |  | Borough sets own targets, informed by ReLondon /WRAP good practice. |  |
| Total annual household residual waste collected per household (kgs/household) | kgs/hh 555.59 | kgs/hh 450 | kgs/hh 518.74 | Defra stats (Ex NI191) |  | Borough sets own targets, informed by ReLondon/WRAP good practice. |  |
| Total annual household avoidable (edible) food waste (kgs/head) | kgs/head 77kg | kgs/head 77kg | kgs/head 77kg | Borough to estimate based on own waste composition data. Estimates should be based on estimated total avoidable food waste produced, i.e. from both residual and food kerbside schemes. |  | A baseline figure of 77kg/capita/year is provided in WRAP guidance. Following a waste composition analysis published in 2020, WRAP have suggested the following splits for households: Avoidable food waste in residual: 70% Unavoidable food waste in residual: 30% Avoidable food waste recycled: 44% Unavoidable food waste recycled: 56% If you would like to apply these figures, you would need to know the percentage of both your residual waste and you’re recycling which was food. If you don’t have this data, please continue to use the 77kg/capita/year figure. |  |
| Annual household waste recycling rate (% by weight) | 27% | 40% | 26.8% | Defra stats |  | Borough sets own targets. |  |
| Annual LACW recycling rate (% by weight) | 24% | 40% | 23% | Defra stats |  | Borough sets own targets. |  |
| Performance Targets | Baseline Performance 2019/201 | Performance Target 2024/251 | Actual performance 2023/24 | Anticipated performance by 1 April 2026 | Metric Guidance / Data source |  | Target Guidance |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays) and separate food waste | 100% | 100% | 100% | 100% | Borough to take from own info. |  | BAorough sets own target, informed by ReLondon/WRAP good practice |
| % of kerbside properties (all households on a kerbside collection) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)* | 100% | 100% | 100% | 100% | Borough to take from own info (*n.b. included for boroughs that have historically been unable to provide food waste collections due to long term contractual issues e.g. ELWA constituent boroughs). |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials and separate food waste | 0% | 90% | 30% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats (communal collections, excluding flats above shops) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)) and separate food waste collection | 0% | 30% | 10% | 90% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| % of flats above shops (FLASH) collecting six main dry materials (glass, cans, paper, card, plastic bottles, and mixed rigid plastics (pots, tubs, and trays)). | 100% | 100% | 100% | 100% | Borough to take from own info. |  | Borough sets own target, informed by ReLondon/WRAP good practice and FLASH data. |
| Proportion (%) of waste fleet heavy vehicles that are LEZ / ULEZ compliant | 100% | 100% | 100% | 100% | Borough to take from own info |  | Borough should aim to operate a fully LEZ / ULEZ compliant waste fleet as a minimum, with aspirations to introduce zero emission vehicles where practicable. |

- 2024/25 RRP Action update:

| Ref # (use # from original RRP) | Action title (copy from original RRP) | Action description (copy from original RRP) | Status: - Complete - On track / part complete - Delayed / on-hold / no progress to date - Cancelled | Action progress update Please include: - Progress made in 2024/25 against this action - How this action is going to be further delivered across 2025/26 (if applicable) - Reason for part completion, delay, hold, no progress or cancellation (if applicable) | Impact of action Please include: - What was the impact of this action being delivered in 2024/25, against the ‘Expected Target / Impact’ set out in the original RRP? |
| --- | --- | --- | --- | --- | --- |
| Lewisham 1 | Food service collection roll out to estates borough wide | - Trial of different food waste bins/housing units on Lewisham Homes & Pinnacle estates. - Procure food caddies, internal and external. - Provision of 180ltr residual waste bins to ground floor residents - Removal of excess 1280ltr recycling bins. - Ongoing targeted education/ engagement with residents on estates. | - On track / part complete | - We have held a Managing Agent Forum, to bring agents up to date with the food waste collection service that will be rolled out in the borough, 7 MA’s attended the event.. - Second Managing Agent meeting arranged for Dec 2025. - 10 Food waste collection trials have now been completed. - Food waste collections have continued at these locations. - Procurement for food caddies in progress. - The procurement of several types of food bins for estates/ has been completed. - Targeted messaging on Social media, informing residents of estates/flats of upcoming changes for food waste collection roll out. - We have removed excess 1280l recycling bins on 6 estates to date. All ground floor properties, where space is available, have been provided with 180l residual bins and 240l recycling bins. - New Communication & Behaviour Change Officer has been appointed to assist with the ongoing targeted education. - Currently recruiting Waste Advisors to assist with the roll out of food collection and to improve the quality of recycling from estates. - Delays due to limited resources. | - Forums improved stakeholder engagement and early buy-in from managing agents, helping to ensure smoother implementation across estates. - Trial’s provided valuable insights into operational challenges and resident behaviour, informing borough-wide rollout plans. - The trials were successful with participation averaging out at 70% across the monitoring period. - The procurement of different types of food bins enables a tailored solutions for different estate layouts, improving accessibility and participation. |
| Lewisham 2 | Food service collection roll out to flats borough wide | - Residents in flatted properties currently do not have a food waste collection. Once the roll out to estates has been completed, Officers will work with Managing agents to trial bins/housing units to identify suitable containers for flatted properties. - Officers will meet with other local authorities to investigate possible collection solutions for flats. - Ongoing targeted education/ engagement with residents. - Officers will work closely with colleagues in Lewisham Homes to maximise the effectiveness and reach of communications. - Audit on bin numbers to be carried out per block to reduce the number of general waste bins once food waste collection has been implemented. | - On track / part complete | - We have held a Managing Agent Forum to bring agents up to date with the food waste collection service that will be rolling out in the borough, 7 MA’s attended the event.. - Second Managing Agent meeting arranged for Dec 2025 - We have conducted site visits some MA to discuss potential placement location for the communal food bins and identify what type of containers which will be suitable. - Food waste collection trials have now been completed. - Food waste collections have been implemented at these locations. - Procurement for food caddies in progress. - The procurement of various types of food bins for estates/ has been completed. - Targeted messaging on Social media, informing residents of estates/flats of upcoming changes for food waste collection roll out. - The audit on the number of bins for all estate blocks in the borough is now completed. - New Communication & Behaviour Change Officer has been appointed to assist with the ongoing targeted education. - Currently recruiting Waste Advisors to assist with the roll out of food collection and to improve the quality of recycling from flats. | - Forums improved stakeholder engagement and early buy-in from managing agents, helping to ensure smoother implementation across estates. - Trial’s provided valuable insights into operational challenges and resident behaviour, informing borough-wide rollout plans. - The trials were successful with participation averaging out at 70% across the monitoring period. - The procurement of different types of food bins enables a tailored solutions for different estate layouts, improving accessibility and participation. |
| Lewisham 3 | Food service collection roll out to flats above shops borough wide | - Residents in flatted properties currently do not have a food waste collection. Once the roll out to flats has been completed, Officers will work with Managing agents to trial bins/housing units to identify suitable containers for flats above shops. - Officers will meet with other local authorities to investigate possible collection solutions for flats above shops. - Officers will look to work with boroughs that have trialled this service in order to build on existing knowledge and to identify best practice. - Ongoing targeted education/ engagement with residents. | - Delayed / on-hold / no progress to date. | - We have rolled out a trial of food collections at Blackheath started in December 2023. - New Communication & Behaviour Change Officer has been appointed to assist with the ongoing targeted education. - Currently recruiting Waste Advisors to assist with the roll out of food collection and to improve the quality of recycling from FLASH. - Procured suitable food housing bins/units that can be either installed on the public highway or fitted to fencing, walls or columns. - Rollout to Flats above shops has not yet been achieved due to limited resources and budgets. - This will be part of simpler recycling Food collection by 2026. | - Trial at Blackheath has provided early data and resident feedback which can inform wider rollout strategies. Helps identify operational challenges and community engagement needs. - Use of ReLondon resources will help plan and promote the roll out of food waste service. |
| Lewisham 4.1 | Waste Strategy objectives- Residual Waste/ Waste Reduction/Contamination | - Implement a range of waste awareness campaigns such as swap shops, Cleaner Lewisham and right thing, right bin” campaign to reduce and discourage contamination and promote what waste goes in which bin. - Investigate the possibility of purchasing digital messaging for refuse trucks. - New Polices to be agreed and implemented on side waste and lid down – this will outline our policy of crews collecting good quality recyclable side waste and not collecting residual waste from bins that cannot be closed. - New service standards to be agreed and implemented, Delivery of service standard to coincide with the serving of Section 46 notice. - Effective education, engagement, and communication plan- detailing attendance at events, schools’ community groups and resident associations. - New bin tags for all types of waste bins to be issued to crews. | - On track / part complete | - We were part of the Pan London ‘Eat Like a Londoner’ food campaign and have carried out a local food waste campaign. - We have one RCV which has a digital messaging board for recycling awareness. Currently investigating cost to provide digital messaging on all our refuse trucks. - We have implemented new policies on side waste and lid down collections from crews. - New Services standards have been written and in the process of being printed. Service standards will be delivered to all properties within the borough and will be available on the website. - We have conducted a small number of presentations and educational events for schools but not achieved the attendance as per the target. - New bin tags have been created and are now in use. - We are now promoting the use of Anglo Doorstep collections to encourage re-use. - A total of 2 ‘Bring and Fix’ workshops have been carried out during 2024 /25 and a further 2 have been held in 2025/26. - A total of 14 Mending workshops were carried out in 2024 /25 and a further 17 have been held to date. - A total of 8 Compost workshops were held during 2024/25, and a total of 2 have been held to date. | - The Pan-London ‘Eat Like a Londoner’ & Local Food Waste Campaign raised awareness of food waste reduction and sustainable eating habits. - Digital display on RCV, improved messaging to the public on key issues. - New Side Waste & Lid Down Policies have helped to reduce side waste with general waste. It’s estimated that the kg of household waste per head has reduced by 6.13kg per head and the kg of residual waste per household has reduced by 12.4kg per household. - School Presentations & Educational Events helps to deliver key messages. - The workshops have empowered residents to reduce waste through repair, mending, and composting, supporting the borough’s circular economy and sustainability goals. A total of 277 garments were repaired and diverted from disposal between Sept 2024 – July 2025 - Compost workshops have encouraged residents to purchase compost bins, a total of 106 bins purchased in 2024/25, on average reducing compostable waste by approx. 16 tonnes |
| Lewisham4.2 | Waste Strategy Objectives- Food Waste Reduction | - Implement a range of food waste awareness campaigns and initiatives such us Love Food Hate Waste, Food recycling-use your bin, home composting. - Explore partnership working and local promotion of apps such as To Good to Go, Olio and Refill - New food waste stickers to be created for all residual and recycling bins. - Home composting campaigns to be introduced along with workshop to encourage the home composting. | - On track / part complete | - We were part of the Pan London ‘Eat Like a Londoner’ food campaign and have carried out a local food waste campaign. We have not achieved the number of events we planned due to limited resources and budgets. - We have not explored partnership to work with local promotion apps due to limited resources. - New food waste leaflets and signage created and are gradually being rolled out. - A total of 8 Compost workshops were held during 2024/25, and a total of 2 have been held to date. - Events attended to promote food waste reduction by providing advice on how to store food items, how to reduce food wastage and recipes on how to use left over food. | - The Pan-London ‘Eat Like a Londoner’ & Local Food Waste Campaign raised awareness of food waste reduction and sustainable eating habits. - A total of 5 food waste reduction events with an average of 40 attendees spoken to at each event, have been carried out during 2024/25, this has helped reduce the amount of waste being thrown away - Compost workshops have encouraged residents to purchase compost bins, a total of 106 bins purchased in 2024/25, on average reducing compostable waste by approx. 16 tonnes |
| Lewisham 5 | Increased Participation in garden Waste services | Targeted communications to encourage greater participation in the garden waste scheme. | - Complete | - We have targeted communications by encouraging greater participation and achieved the target set. - Increase of approx. 2500 subscriptions since 2024/25 | - Increase of approx. 2500 subscriptions since 2024/25 |
| Lewisham 6 | External Funding | - Officers to investigate and apply for external funding to help support key campaigns. - Funded activities to assist in outreach and engagement, improving education around waste minimisation and recycling | - Complete | - We have applied for a number of external funding, with some successful monies received for certain projects. For example: WEE bring banks based around the Borough, chewing gum litter and smoking related litter. - The funded activities to assist in outreach and engagement are ongoing. | - WEEE funding funded 27 new small electrical banks across the borough, we saw an increase of 653% in items collected in 2024/25 compared to the previous year. |
| Lewisham 7 | Investigate the possibility of opening a Re-use shop/stall | - Investigate the possibility of opening a re-use shop or stall at Deptford Market. - Visit other Local Authorities to see how they opened their re-use sites. - Investigate the possibility of opening a virtual reuse shop. - Look at possibilities of working with eBay for textiles and furniture. - Hold 3 Swap Shops per year | - On track / part complete | - We have not investigated the possibility of opening a re-use or shop in Deptford Market. However, we are currently looking at the possibility to move our Household Waste & Recycling centre to a larger site, if successful a re-use shop will be opened. Report is expected to go to M&C on December 25 - We have visited other Local Authorities to see how they opened their re-use sites. - We have not investigated Ebay for textiles and furniture due to limited resources. - A total of 2 ‘Bring and Fix’ workshops have been carried out during 2024 /25 and a further 2 have been held in 2025/26. - A total of 14 Mending workshops were carried out in 2024 /25 and a further 17 have been held to date. - We have held one give and take event but have not held the 3 swap shops per year due to limited resources. | - The investigation into opening a reuse shop or stall was not delivered in 2024/25 - The workshops have empowered residents to reduce waste through repair, mending, and composting, supporting the borough’s circular economy and sustainability goals. A total of 277 garments were repaired and diverted from disposal between Sept 2024 – July 2025 - Compost workshops have encouraged residents to purchase compost bins, a total of 106 bins purchased in 2024/25, on average reducing compostable waste by approx. 16 tonnes |
| Lewisham 8 | Improved Recycling and waste reduction on Markets | - Engagement with stall holders at the licensing stage promoting waste reduction. - Engagement with stall holders by market officers promoting waste reduction on the market. - Investigate the possibility of reducing plastic bag usage from market stalls. - Implementation of cardboard recycling - Investigate the possibility of providing food waste collection service. - Following on from the successful outcome at Lewisham Market, Officers will explore the possibility to roll out the cardboard and organic waste collection at all markets within the borough | - Delayed / on-hold / no progress to date | - Due to limited resources, we have been unable to engage with Traders to promote waste reduction. However, a new Marketing Manager has been appointed and is looking at the licensing and cost for waste disposal to encourage waste reduction. - We have implemented card segregation recycling. - We installed food bin collection service to Lewisham Market. - We have not yet investigated the roll out to further markets in the borough. | - No engagement with Traders to promote waste reduction took place in 2024/25. - Food recycling from food waste collected at the market saw an increase of 35 tonnes in 2024/25 compared to the previous year whereas the carboard recycling remained the same at 224 tonnes. |
| Lewisham 9 | Working with Private Sector Housing Team re HMO’s | - Targeted communication detailing landlord responsibility to be provided. - Targeted communication to tenants. On how to use services provided. - Look to tighten up waste management procedures regarding HMO licenses. - Work with the Strategic Housing Team to incorporate waste management into the landlord licensing process | - On track / part complete | - We have provided information to registered landlords on their responsibilities and their tenants’ responsibilities for waste disposal. More ongoing communications needs to be implemented. - Attended private landlords meeting, provided information on landlord’s responsibility. - Regular meetings with the Strategic Housing team to provide updates or concerns. - New service standards and new web page for landlords and managing agents providing advice on responsibilities and how to manage waste to go live December 2025 | - 2 landlord meeting attended. Forums improved stakeholder engagement and early buy-in from managing agents, helping to ensure smoother implementation across estates. |
| Lewisham 10 | Expand the range of kerbside collections | Investigate the feasibility in providing pop up electrical, textile, battery, and coffee pod collections | - Delayed / on-hold / no progress to date | - We have not investigated the feasibility of pop up electrical, textile, battery and coffee pod collections due to limited resources. | - No investigation took place during 2024/25, so no impact. |
| Lewisham 11 | Target campaigns | - Following the completion of the participation and compositional survey, target areas for improved recycling, increased garden waste collections and food waste. - Including flats and estates to reduce the level of contamination | - On track / part complete | - We have carried out a campaign of food waste and WEEE waste. Further campaigns. - New Communication and Behaviour Change Officer appointed new campaigns to be rolled out for food and waste reduction 2025/26. - Compositional survey for flats/estates and kerbside properties due Dec/Jan 26, to identify high levels of contamination. Recycling Advisors to target these areas. | - WEEE waste saw an increase of 653% - Food waste campaign saw an increase in request for food bins but no increase in tonnage |
| Lewisham 12 | Improved Textile recycling | - Refurbished textile banks across the borough. - QR codes on all banks – this will allow residents to easily get information about services relating to textile recycling/reuse and to identify the purpose of the banks. - Investigate the possibility of doorstep textile collections. - Donation station at more convenient local locations - Investigate the provision of locker drop textile service working in partnership with contractor | - Complete - On track / part complete | - We had new textile banks delivered in August 2024 and installed into the borough. - QR codes are on the textile banks. - We have not investigated doorstep textile collections; locker drop or donation stations due the current textile market dropping. However, we have rolled out larger textile banks at key locations across the borough. | - Following the implementation of 17 new banks we saw an increase of 48% in tonnage during 2024/25 compared to the previous year. |
| Lewisham 13 | Reuse and Repair activities & events | - Officers to arrange 6 Give and Take day across the borough per year. - Investigate the possibility within shopping centres / libraries for pop up reuse and repair events. - Work with partners to establish alternative bulky waste collections for reuse | - On track / part complete | - We have only held one Give and Take days within 2024/25 due to limited resources. - A total of 2 ‘Bring and Fix’ workshops have been carried out during 2024 /25 and a further 2 have been held in 2025/26. - A total of 14 Mending workshops were carried out in 2024 /25 and a further 17 have been held to date. - A total of 8 Compost workshops were held during 2024/25, and a total of 2 have been held to date. | - The workshops have empowered residents to reduce waste through repair, mending, and composting, supporting the borough’s circular economy and sustainability goals. A total of 277 garments were repaired and diverted from disposal between Sept 2024 – July 2025 - Compost workshops have encouraged residents to purchase compost bins, a total of 106 bins purchased in 2024/25, on average reducing compostable waste by approx. 16 tonnes |
| Lewisham 14 | Commercial waste collections | - Officers will make use of engagement tools in order to promote the recycling service to businesses. - Implement time banding across the borough and enforce | - On track / part complete | - Delays in promoting the recycling service during 2024/25 due to limited resources. - New Marketing Manager appointed. Currently promoting commercial waste recycling services, Simpler Recycling and garden waste service to all businesses and schools. - New market manager joined August 2025, working with Traders to reduce waste and increase recycling. - We have implemented time banding at one location in the borough further locations are to be rolled out. Report going to M&C in December to seek approval to roll out time banding in key locations across the borough. | - Limited promotion of recycling services during 2024/25 |
| Lewisham 15 | Schools’ food waste collection | - Trial food waste collections at a number of primary schools - Investigate the possibility of rolling out a commercial waste food collection service for schools. | - Complete | - We have successfully implemented food waste collection service to all primary schools within the borough and 11% of secondary schools. | - Approx 84 primary schools signed up for food collection service |
| Lewisham 16 | Commercial waste recycling policy | - New Service standards to be created and implemented for commercial businesses. - This policy will align with Lewisham’s commitment to maximising recycling, commercial waste officers will prioritise and promote recycling services when dealing with customers. - Food waste collections will be rolled out to businesses. - Commercial waste officers will provide businesses with information relating to waste reduction. | - Complete | - New service standards due to go live December 2025. - Food waste collections service is available to all commercial businesses within Lewisham. Currently recruiting 2 new sales officers to target businesses for food and recycling waste contracts. | - No Impact during 2024/25 |
| Lewisham 17 | Council Tax letter | Officers to ensure that information relating to waste and recycling is sent out with Council Tax letters | - Complete | - Waste and Recycling information was sent with Council Letters this year 2024 and 2025 | - All properties received recycling information in their council tax packs, which help reinforce key messages around recycling, food waste, and service changes, helping to reduce confusion and increase compliance. |
| Lewisham 18 | Parks & Open Space Strategy – recycle waste from Parks | - Work closely with relevant internal departments and key partners to investigate the possibility of recycling waste from Parks. - Educational campaign planned to encourage park visitors to reduce their use of single-use plastics and encourage the use of reusable items. - Investigate the possibility of providing food waste collections to food facilities within parks and open spaces. - Work with the parks team and events team to ensure there is a policy in place to recycle waste from events e.g., London Marathon, Blackheath Festival, Peoples Day | - Complete | - We have liaised with internal departments and implemented recycling in parks. - Campaign has been carried out to encourage park users to recycle. - No investigations have taken place yet for food waste collections in the parks. - We have worked with the parks team for events such as London Marathon | - Campaign has helped raise awareness and promoted correct recycling behaviour in leisure settings. - Recycling in parks has helped increase recycling but unable to quantify. |
| Lewisham 19 | Cleaner Lewisham | - Implement a Low Plastic Zone in phases to businesses and market traders, encouraging commercial customer to sign up to plastic pledge reduction. - Part of the campaign will be providing information on correct means of waste disposal, including information on recycling locations for soft plastic, WEEE and batteries. | - On track / part complete | - Work on Low Plastic Zone in phases for businesses, market stall holders etc to sign up to a plastic pledge reduction. This was not carried out in 2024/25 due to limited resources. However, compositional survey on all waste bins and a survey on single use plastics has recently been carried out in all council buildings. Campaign to reduce single use plastic has now commenced. - New posters and stickers for commercial properties have been created to clearly display acceptable items for each waste route. | - No action carried out in 2024/25 - Survey of council buildings helped identify the need for improved messaging. Most members of staff are Lewisham residents. |
| Lewisham 20 | Food Waste Reduction | - Campaign to be launched promoting the reduction of food waste, messaging will be in line with campaigns such as ‘Love Food Hate Waste’. - Messaging to be promoted at community events, schools, Goldsmiths University, and residents’ associations. - Work will be done with our internal communications team to develop this campaign. | - On track / part complete | - We were part of the Eat Like a Londoner campaign promoting waste reduction and sustainable diets. - We did not provide messages to community events, schools due to limited resources and budget during 2024/25. However, during 2025/26 to date we have used social media to promote food reduction campaign, attended 5 residents association, 4 ward assemblies and a number of messages have been promoted on the school’s platform were carried out in 2025/26. | - The Pan-London ‘Eat Like a Londoner’ & Local Food Waste Campaign raised awareness of food waste reduction and sustainable eating habits. - We did not provide messages to community events, schools due to limited resources and budget during 2024/25 |
| Lewisham 21 | Lewisham Homes Estate Project | - Work will be done to roll out these projects to more estates in the borough. - Engagement with residents concerning proper use of the recycling bins. - Work with managing agents to reinforce this messaging. - Survey of waste disposal facilities in place on the estate - Continue the roll out of improved recycling facilities on estates through the MetroSTOR waste containerised project. - Improved communication - Embed recycling message through Envirocrime pilot. - Investigate the possibility of introducing compost areas to engaged community group gardens / pilot area / sheltered blocks. - Officers will investigate the possibility of implementing ReLondon’s Flat Recycling Package to a number of Lewisham Homes estates in order to support these targets – the implementation of this package will be subject to budgetary constraints | - On track / part complete | - A number of trials have been carried out at locations across the borough to trial different food bins and recycling bins. Trials have now been completed. - Officers now working with Lewisham Housing to roll out the food waste to estates across the borough. - Survey of waste disposal facilities being completed as locations confirmed for food waste roll out. - Ongoing roll out of metro store housing units for recycling and food to Lewisham Housing estates - Once recruited, Waste advisors will engage with residents on estates/flats to encourage waste reduction, recycling and provide information on the upcoming food waste collection being rolled out. - Recycling advisors will use ReLondon toolkits and case studies to support the roll out of food waste and improve recycling on estates/flats. | - Trial’s provided valuable insights into operational challenges and resident behaviour, informing borough-wide rollout plans. - The trials were successful with participation averaging out at 70% across the monitoring period. - The procurement of different types of food bins enables a tailored solutions for different estate layouts, improving accessibility and participation. |
| Lewisham 22 | Local Plan | - Lewisham is currently working on its Local Plan; this document will guide Lewisham’s planning decisions through 2040. - The document is currently in the drafting stage; changes are being made based on a recent consultation. - Circular economy principles will be prioritised in the borough. - Development projects will be net-zero waste; they will need to submit a Circular Economy Statement in line with the requirements of the draft London Plan policy s17. - Development proposals must be designed to ensure adequate on-site provision for the sorting of recyclable material, composting of organic material and the disposal of general waste during the occupation stage. | - On track / part complete | - On the 3rd of November 2023 Lewisham Council submitted the Lewisham Local Plan and its supporting documents to the Secretary of State for its independent examination. The Council will now await the appointment of an independent examiner by the Secretary of State. - As part of the plan, development proposals should apply circular economy principles in order to conserve resources and improve resource efficiency, with reference to London Plan policy SI7 (Reducing waste and supporting the circular economy - Major development proposals should aim to be net zero-waste. Development proposals that meet the threshold for being referable to the Mayor of London must submit a Circular Economy Statement, as part of the Sustainable Design Statement, in line with London Plan policy SI7. - Meetings are being held within the council in the development of circular economy principles. | - The Council is now awaiting the appointment of an independent examiner by the Secretary of State to review the submitted Local Plan and its supporting documents. |
| Lewisham 23 | Zero Carbon City | - The Council is committed to working towards a zero-carbon city and zero emission transport network by 2050. - The Council is committed to becoming a carbon neutral borough by 2030. - Ensuring contractors use ULEZ compliant vehicles and minimise the movement of vehicles. - Include CO2 emission KPI’s in contracts. - Deliver a carbon reduction and energy efficiency program in the Council’s social housing stock. - Implement a decentralised energy strategy for the borough. - Investigate the possibility of using energy generated by SELCHP to charge electric vehicles | - On track / part complete | - The Council’s commitment to climate action and towards working towards a zero-carbon city and zero emissions transport network are set out in the Council’s Climate Action Plan Lewisham Council Climate Action Plan updated 2024 - Lewisham Council declared a climate emergency in 2019 and set an ambition for the borough to be net zero carbon by 2030. The Council reports annually on the delivery of its Climate Action Plan most recently in June 2025, Lewisham Climate Action Plan 2025 progress report - Lewisham's Sustainable Procurement Guide 2025-2030 sets out the following Transportation of goods Transportation is a significant contributor to carbon emissions, impacting on air quality and quality of life for residents. Specifications and method statements are opportunities to minimise the environmental impact of goods delivery by reducing the need for transportation and prioritising sustainable options where relevant. Emphasis is to be placed on sourcing goods and services locally wherever possible, reducing emissions from long-distance freight. Where applicable suppliers are encouraged to use electric vehicles, cargo bikes or public transport. Where applicable, suppliers for goods, services, and construction projects will be required to set out in their Carbon Reduction Plan their approach to transitioning any remaining petrol and diesel vehicles to electric. Suppliers are encouraged to consolidate deliveries and adopt efficient logistics models to reduce the frequency of vehicle trips in the borough delivering environmental benefits and potentially financial savings. - Lewisham's Sustainable Procurement Guide 2025-2030 sets out the following: Our commitment for the next four years is to ensure that environmental impacts form a key consideration of social value. The Council will undertake an assessment of carbon emissions from across our supply chain and use this analysis to target interventions and support a dialogue with suppliers. Where applicable, we will require suppliers for goods, services, and construction projects, to submit a Carbon Reduction Plan (CRP), producing a CRP for the contracted project, with input from our climate implications tool where necessary. Before the end of this strategy, tenders for contracts with an annual value of £5 million or more must monitor and report on their organisational carbon footprints, to comply with government CRP requirements. Construction or infrastructure projects must meet Planning policies, and buildings are expected to meet targets for net zero operational carbon with low energy requirements that are 100% powered by renewable energy. - The baseline for scope 3 emissions from the Council’s procurement of goods and services is expected to be complete by the end of 2025/26. This will be used to prioritise engagement activity with commissioning teams and suppliers. The Council is committed to working towards a zero-carbon city and zero emission transport network by 2050 The Council’s commitment to climate action and towards working towards a zero-carbon city and zero emissions transport network are set out in the Council’s Climate Action Plan Lewisham Council Climate Action Plan updated 2024 The Council is committed to becoming a carbon neutral borough by 2030 Lewisham Council declared a climate emergency in 2019 and set an ambition for the borough to be net zero carbon by 2030. The Council reports annually on the delivery of its Climate Action Plan most recently in June 2025, Lewisham Climate Action Plan 2025 progress report Ensuring contractors use ULEZ compliant vehicles and minimise the movement of vehicles Lewisham's Sustainable Procurement Guide 2025-2030 sets out the following Transportation of goods Transportation is a significant contributor to carbon emissions, impacting on air quality and quality of life for residents. Specifications and method statements are opportunities to minimise the environmental impact of goods delivery by reducing the need for transportation and prioritising sustainable options where relevant. Emphasis is to be placed on sourcing goods and services locally wherever possible, reducing emissions from long-distance freight. Where applicable suppliers are encouraged to use electric vehicles, cargo bikes or public transport. Where applicable, suppliers for goods, services, and construction projects will be required to set out in their Carbon Reduction Plan their approach to transitioning any remaining petrol and diesel vehicles to electric. Suppliers are encouraged to consolidate deliveries and adopt efficient logistics models to reduce the frequency of vehicle trips in the borough delivering environmental benefits and potentially financial savings. Include CO2 emission KPI’s in contracts Lewisham's Sustainable Procurement Guide 2025-2030 sets out the following: Our commitment for the next four years is to ensure that environmental impacts form a key consideration of social value. The Council will undertake an assessment of carbon emissions from across our supply chain and use this analysis to target interventions and support a dialogue with suppliers. Where applicable, we will require suppliers for goods, services, and construction projects, to submit a Carbon Reduction Plan (CRP), producing a CRP for the contracted project, with input from our climate implications tool where necessary. Before the end of this strategy, tenders for contracts with an annual value of £5 million or more must monitor and report on their organisational carbon footprints, to comply with government CRP requirements. Construction or infrastructure projects must meet Planning policies, and buildings are expected to meet targets for net zero operational carbon with low energy requirements that are 100% powered by renewable energy. The baseline for scope 3 emissions from the Council’s procurement of goods and services is expected to be complete by the end of 2025/26. This will be used to prioritise engagement activity with commissioning teams and suppliers. Deliver a carbon reduction and energy efficiency program in the Council’s social housing stock Lewisham Climate Action Plan 2025 progress report sets out the following (Action 2.1.1) The Council’s Housing Retrofit Strategy was approved by Mayor and Cabinet in March 2025. The next phase of work includes establishing a delivery roadmap for retrofit measures across Council homes prioritising the least energy-efficient properties. The Strategy includes a detailed assessment of the work required to decarbonise the Council’s housing stock and sets out actions to improve fabric, decarbonise heating, increase low carbon energy generation, battery storage and flexible use of energy and engage with tenants and leaseholders on retrofit to raise awareness and shape future programme. Implementation efforts in 2025 will focus on delivering retrofit to high priority properties. Engagement with tenants will be a priority to ensure retrofit measures address both energy efficiency and resident needs. In 2024/25 the Council has been delivering a retrofit programme funded with £2.5m from the Social Housing Decarbonisation Fund Wave 2.1. This programme will retrofit over 250 properties by September 2025. Works completed to date include the Hermitage a 1940s block in a conservation area installing new windows, ventilation and solar panels alongside a range of other works to improve the fabric of this Art Deco block of 28 properties. In 2025 the Council secured an additional £7.1m funding under the Social Housing Fund Wave 3 that will support a 3-year programme of retrofit works across Lewisham’s housing stock that will improve a minimum of 700 homes. Implement a decentralised energy strategy for the borough. The Council published a Lewisham Strategic Heat Decarbonisation Study 2020 and since then has delivered techno-economic assessments of heat networks in Catford, Lewisham Town Centre and North Lewisham. The Council has technical guidance for developers in key heat demand areas and is working with the Greater London Authority and neighbouring boroughs on a sub regional Local Area Energy Plan that will further embed a strategic approach to decentralised energy for the borough.. | - The estimate of consumption emissions for Lewisham has fallen by 29% between 2001 and 2020 - The latest published data for Lewisham Council corporate carbon emissions is 12,379 tCO2 a year and covers the period 2022/23. This was compiled from energy, water and fuel data for corporate buildings, schools, leisure centres, streetlighting and the Council’s fleet. These are the Council’s direct emissions, which align to the Greenhouse Gas Protocol for scope 1 and 2 emissions. The Council’s reported emissions have reduced by just over 25% in the 5-year period covered by the data. - A number of guides took affect 2025, No data available for 2024/25 yet. |
| Lewisham 24 | Electric Vehicles | - Officers will seek funding for the trial of electric fleet vehicles. - Officers will trial alternative collections vehicles to reduce the number of collection vehicles within the borough. - Investigate the possibility of utilising electricity from SELCHP at LB Westminster site for electrical vehicles | - Delayed / on-hold / no progress to date | - The council trialled three electric waste collection vehicles, with one still in use for cardboard recycling at Lewisham Market. However, further rollout of larger electric vehicles is currently on hold due to two main challenges: the lack of charging infrastructure and the uncertainty surrounding the proposed Bakerloo Line extension, which has delayed approval for necessary upgrades. - We are looking to trial a larger food waste collection vehicle. - We have investigated the possibility for utilising electricity from SELCHP but no budget is currently available - The council has trialled RCV’s with electric backs, and this is the proposal along with the use of HVO in the fleet strategy which goes to M&C in Dec. | - Reduced carbon emission by using electrical vehicle |
| Lewisham 25 | CA Site Communications Campaign | - Produce new literature promoting the CA Site - Improve signage at the Site. - Review opening times of the site to make it more accessible to residents. - Implement single stream bring bank area | - complete | - We have completed new literature for promoting the CA site. - We haven’t updated the signage at the CA site. - We are reviewing the opening times, to close site Monday and Tuesday and to remain open at the weekends. Report to go to M&C in December to seek approval for the change in hours. | - New signage has helped improves navigation and clarity for users, reducing confusion and misuse. - Change in opening hours Aligns operational hours with peak usage patterns, potentially improving efficiency and reducing staffing costs. |

- New RRP Actions for 2025/6:

- Add any new actions planned for delivery in the 2025/6 financial year, which weren’t included in the 2023 to 2025 RRP.

| Ref (follow on from original RRP #) | Action title | Action Description | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Lewisham 26 | Waste Audit of Council offices | - ​To gain a baseline understanding of recycling habits and waste generated by Laurence House staff - To introduce a methodology for engaging with staff on reducing plastics use and waste | • To commit to actions towards the London Councils Plastics Pledge, which seeks to eliminate problematic single use plastics in all council operations by 2030 • To help raise awareness of repercussions of waste, and to inform an internal Comms campaign to embed circularity principles internally To increase recycling rates, and reduce rates of waste, especially from single-use plastics | November 2026 |

- Simpler Recycling Preparedness:

- Add any plans or actions taken to date on how the authority is aligning its collection services with national Simpler Recycling requirements.

| Ref (follow on from original RRP #) | Action title / Area of Simpler Recycling reforms | Action Description / How the authority is preparing for this | Expected Target / Impact | Timescale for action |
| --- | --- | --- | --- | --- |
| Lewisham 27 | Communications & Behaviour Change | - Appointed a Communications & Behaviour Change Officer. - Waste Advisors being recruited to support education and rollout - Information literature being created on changes - Social Media, JCD advertising boards Lewisham Life etc to be used to promote roll out of food waste collections | Increase resident understanding and participation. Improve recycling quality and reduce contamination | Officer due to start November; Advisors recruitment ongoing in 2025. |
| Lewisham 28 | Infrastructure & Bin Provision | - Procured food waste housing units at several locations for flexible installation. - Procured varying sizes of food bins and caddies - Arrangement still to be made to lease additional vehicles and staff for the delivery of bins. | Improve accessibility and compliance. Support rollout to diverse housing types. | Units available; ongoing phased. deployment through Jan - March–2026 |
| Lewisham 29 | Education & Community Engagement | - School presentations and events being delivered. - Compost, Bring & Fix, and Mending workshops held. Further events being planned - Ongoing attendance at events, TRA, assemblies. - Focus Groups will be carried out - On going communication via a number of different means. | Promote waste reduction and reuse. Promote food waste reduction | Ongoing Comm’s will be over a phased period informing residents what is coming, then providing more information on dates of roll out, then reminders on how to use the service, followed by reminders to use your food bin. |

Insert data from original 23-25 RRP in this column

Insert anticipated performance information here for when Simpler Recycling legislation comes into effect on 1 April 2026