## Cover
Transport Committee Information Request
Dated: 13th May 2011
Contents:
1) London Underground Investment Summary - Track Renewal / Refurbishment, Stations Enhanced, Escalator and Lift Refurbs
2) Tube Lines Limited Investment Summary - Track Renewal / Refurbishment, Stations Enhanced, Escalator and Lift Refurbs
3) LU Network Step-Free Access and Capacity Enhancements
4) A summary of Upgrade Capability and Capacity Uplifts
5) A summary of major upgrade and investment programme milestones completed to date
6) A summary of major upgrade and investment programme future milestones
7) A forecast breakdown of train kilometres

## LU Investment Summary
London Assembly Request For Information - dated 13th May 2011
LU data requested for London Assembly Transport Committee of 14th June 2011
LU - BCV Asset Renewal & Refurbishment
YEAR |  | 2003/2004 | 2004/2005 | 2005/2006 | 2006/2007 | 2007/2008 | 2008/2009 | 2009/2010 | 2010/2011 | Total 03/04 - 10/11 | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 20118/2019 | 2019/2020 | 2020/2021 | Total Forecast 11/12 - 20/21
Bakerloo | Track (km)
| Full renewal | 0.334 | 0.181 | 1.265 | 1.071 | 0.543 | 0.251 | 0.222 | 0.712 | 4.579 | 0.743 | 0.994 | 0.842 | 0.199 | 0.347 | 1.087 | 0.25 | 0.599 | 0.526 | 1.177 | 6.764
| Refurbished / life extension | 0 | 0 | 0 | 0 | 2.307 | 0.695 | 1.277 | 0.367 | 4.646 | 0.61 | 0.195 | 0.2 | 0.437 | 0.164 | 0 | 0 | 0 | 0 | 0 | 1.606
| Total track | 0.334 | 0.181 | 1.265 | 1.071 | 2.85 | 0.946 | 1.499 | 1.079 | 9.225 | 1.353 | 1.189 | 1.042 | 0.636 | 0.511 | 1.087 | 0.25 | 0.599 | 0.526 | 1.177 | 8.37
0
| Stations enhancements completed | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 2 | 0 | 0 | 6
0
| Escalator replacement or major refurbishment | 5 | 3 | 2 |  | 4 | 3 | 3 | 3 | 23 | 5 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 3 | 0 | 14
0
| Lift replacement or major refurbishment | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 5
Central | Track (km)
| Full renewal | 5.822 | 9.296 | 10.325 | 8.163 | 2.518 | 2.666 | 3.433 | 2.743 | 44.966 | 4.419 | 3.028 | 2.682 | 1.423 | 5.755 | 2.322 | 0.13 | 3.066 | 3.047 | 1.307 | 27.179
| Refurbished / life extension | 0 | 0 | 0.953 | 2.134 | 5.612 | 2.734 | 1.366 | 0.778 | 13.577 | 0.767 | 1.427 | 0.496 | 0 | 1.053 | 0 | 0 | 1.7 | 6 | 6.5 | 17.943
| Total track | 5.822 | 9.296 | 11.278 | 10.297 | 8.13 | 5.4 | 4.799 | 3.521 | 58.543 | 5.186 | 4.455 | 3.178 | 1.423 | 6.808 | 2.322 | 0.13 | 4.766 | 9.047 | 7.807 | 45.122
0
| Stations enhancements completed | 0 | 0 | 3 | 6 | 8 | 7 | 3 | 1 | 28 | 0 | 0 | 0 | 0 | 2 | 3 | 9 | 1 | 0 | 0 | 15
0
| Escalator replacement or major refurbishment | 4 | 5 | 4 | 3 | 4 | 2 | 6 | 8 | 36 | 5 | 1 | 4 | 0 | 1 | 2 | 5 | 0 | 1 | 0 | 19
0
| Lift replacement or major refurbishment | 0 | 0 | 0 | 4 | 0 | 0 | 3 | 0 | 7 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 8
Victoria | Track (km)
| Full renewal | 0.365 | 0.47 | 1.003 | 0.366 | 2.275 | 3.443 | 0.369 | 0 | 8.291 | 0 | 0.561 | 0.56 | 0.422 | 0.561 | 1.119 | 2.758 | 0.599 | 0.69 | 3.02 | 10.29
| Refurbished / life extension | 3.113 | 1.557 | 0.915 | 6.479 | 2.197 | 2.908 | 2.051 | 0 | 19.22 | 0 | 0 | 0 | 1.677 | 0 | 1.9 | 0 | 0 | 0 | 0 | 3.577
| Total track | 3.478 | 2.027 | 1.918 | 6.845 | 4.472 | 6.351 | 2.42 | 0 | 27.511 | 0 | 0.561 | 0.56 | 2.099 | 0.561 | 3.019 | 2.758 | 0.599 | 0.69 | 3.02 | 13.867
0
| Stations enhancements completed | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 6
0
| Escalator replacement or major refurbishment |  | 3 | 3 | 3 | 1 | 1 | 2 | 3 | 16 | 3 | 2 | 4 | 3 | 4 | 3 | 1 | 2 | 0 | 0 | 22
0
| Lift replacement or major refurbishment | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 4
Waterloo & City | Track (km)
| Full renewal | 0 | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refurbished / life extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total track | 0 | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Stations enhancements completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Escalator replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total BCV | Track (km)
| Full renewal | 6.521 | 13.347 | 12.593 | 9.6 | 5.336 | 6.36 | 4.024 | 3.455 | 61.236 | 5.162 | 4.583 | 4.084 | 2.044 | 6.663 | 4.528 | 3.138 | 4.264 | 4.263 | 5.504 | 44.233
| Refurbished / life extension | 3.113 | 4.957 | 1.868 | 8.613 | 10.116 | 6.337 | 4.694 | 1.145 | 40.843 | 1.377 | 1.622 | 0.696 | 2.114 | 1.217 | 1.9 | 0 | 1.7 | 6 | 6.5 | 23.126
| Total track | 9.634 | 18.304 | 14.461 | 18.213 | 15.452 | 12.697 | 8.718 | 4.6 | 102.079 | 6.539 | 6.205 | 4.78 | 4.158 | 7.88 | 6.428 | 3.138 | 5.964 | 10.263 | 12.004 | 67.359
0
| Stations enhancements completed | 0 | 0 | 3 | 6 | 10 | 10 | 3 | 3 | 35 | 0 | 0 | 1 | 2 | 3 | 3 | 12 | 6 | 0 | 0 | 27
0
| Escalator replacement or major refurbishment | 9 | 11 | 9 | 6 | 9 | 6 | 11 | 14 | 75 | 13 | 3 | 8 | 4 | 6 | 6 | 7 | 4 | 4 | 0 | 55
0
| Lift replacement or major refurbishment | 2 | 1 | 0 | 6 | 2 | 2 | 3 | 0 | 16 | 2 | 0 | 4 | 0 | 2 | 2 | 3 | 3 | 1 | 0 | 17
Notes
1) Station enhancement work varies in scope depending on the size, complexity and current condition of the station. The volume is recorded against the forecast Delivery Into Service completion milestone
2) The future station programme for BCV / SSL is highly indicative as of May 2011, with design work about to commence on the 74 stations not enhanced under the PPP.
LU - SSL Asset Renewal & Refurbishment
YEAR |  | 2003/2004 | 2004/2005 | 2005/2006 | 2006/2007 | 2007/2008 | 2008/2009 | 2009/2010 | 2010/2011 | Total 03/04 - 10/11 | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 20118/2019 | 2019/2020 | 2020/2021 | Total Forecast 11/12 - 20/21
Circle and Hammersmith & City | Track (km)
| Full renewal | 0.429 | 0 | 0 | 3.366 | 0.581 | 0.369 | 2.814 | 2.266 | 9.825 | 0.591 | 1.023 | 2.3 | 1.9 | 3.7 | 2.55 | 4.25 | 4 | 0 | 0 | 20.314
| Refurbished / life extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 1.5
| Total track | 0.429 | 0 | 0 | 3.366 | 0.581 | 0.369 | 2.814 | 2.266 | 9.825 | 0.591 | 1.023 | 2.3 | 1.9 | 3.7 | 2.55 | 4.25 | 4 | 1.5 | 0 | 21.814
0
| Stations enhancements completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 1 | 6 | 1 | 0 | 0 | 13
0
| Escalator replacement or major refurbishment | 8 | 1 | 3 | 3 |  | 2 | 11 | 1 | 29 | 0 | 0 | 0 | 5 | 2 | 3 | 1 | 2 | 1 | 0 | 14
0
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 1 | 10 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 5
District | Track (km)
| Full renewal | 2.042 | 3.641 | 4.425 | 1.404 | 6.487 | 13.067 | 15.897 | 9.213 | 56.176 | 9.02 | 6.795 | 9.1 | 7.5 | 6.2 | 4.55 | 3.85 | 0 | 0.5 | 0 | 6.764
| Refurbished / life extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.103 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 8.7 | 1.606
| Total track | 2.042 | 3.641 | 4.425 | 1.404 | 6.487 | 13.067 | 15.897 | 9.213 | 56.176 | 9.02 | 7.898 | 9.1 | 7.5 | 6.2 | 4.55 | 4.05 | 0 | 0.5 | 8.7 | 8.37
0
| Stations enhancements completed | 0 | 0 | 4 | 4 | 1 | 6 | 1 | 1 | 17 | 0 | 0 | 0 | 4 | 0 | 4 | 12 | 0 | 0 | 0 | 6
0
| Escalator replacement or major refurbishment | 0 | 2 | 0 | 1 | 3 | 0 | 2 | 1 | 9 | 0 | 0 | 1 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 14
0
| Lift replacement or major refurbishment | 2 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 10 | 0 | 2 | 1 | 3 | 0 | 3 | 1 | 0 | 0 | 0 | 5
Metropolitan | Track (km)
| Full renewal | 2.161 | 0 | 0 | 7.393 | 8.681 | 4.994 | 2.562 | 6.426 | 32.217 | 4.902 | 3.372 | 2.5 | 5.65 | 5.9 | 8.95 | 4.2 | 6.1 | 0 | 0 | 41.574
| Refurbished / life extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.993 | 0.993 | 0 | 0.693 | 0 | 0 | 0.8 | 2 | 1 | 0 | 2.75 | 2.15 | 9.393
| Total track | 2.161 | 0 | 0 | 7.393 | 8.681 | 4.994 | 2.562 | 7.419 | 33.21 | 4.902 | 4.065 | 2.5 | 5.65 | 6.7 | 10.95 | 5.2 | 6.1 | 2.75 | 2.15 | 50.967
0
| Stations enhancements completed | 0 | 0 | 4 | 3 | 4 | 2 | 0 | 2 | 15 | 0 | 0 | 1 | 0 | 8 | 4 | 0 | 1 | 0 | 0 | 14
0
| Escalator replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
0
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
Total SSL | Track (km)
| Full renewal | 4.632 | 3.641 | 4.425 | 12.163 | 15.749 | 18.43 | 21.273 | 17.905 | 98.218 | 14.513 | 11.19 | 13.9 | 15.05 | 15.8 | 16.05 | 12.3 | 10.1 | 0.5 | 0 | 109.403
| Refurbished / life extension | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.993 | 0.993 | 0 | 1.796 | 0 | 0 | 0.8 | 2 | 1.2 | 0 | 4.25 | 10.85 | 20.896
| Total track | 4.632 | 3.641 | 4.425 | 12.163 | 15.749 | 18.43 | 21.273 | 18.898 | 99.211 | 14.513 | 12.986 | 13.9 | 15.05 | 16.6 | 18.05 | 13.5 | 10.1 | 4.75 | 10.85 | 130.299
0
| Stations enhancements completed | 0 | 0 | 8 | 7 | 5 | 8 | 1 | 3 | 32 | 0 | 0 | 1 | 7 | 10 | 9 | 18 | 2 | 0 | 0 | 47
0
| Escalators replaced or refurbished | 8 | 3 | 3 | 4 | 3 | 2 | 13 | 2 | 38 | 0 | 0 | 4 | 6 | 5 | 4 | 1 | 2 | 1 | 0 | 23
0
| Lifts replaced or refurbished | 2 | 4 | 0 | 4 | 0 | 6 | 5 | 1 | 22 | 0 | 2 | 1 | 3 | 3 | 3 | 2 | 1 | 0 | 2 | 17
Notes
1) Station enhancement work varies in scope depending on the size, complexity and current condition of the station. The volume is recorded against the forecast Delivery Into Service completion milestone
2) The future station programme for BCV / SSL is highly indicative as of May 2011, with design work about to commence on the 74 stations not enhanced under the PPP.

## TLL Investment Summary
London Assembly Request For Information - dated 13th May 2011
Tube Lines data requested for London Assembly Transport Committee of 14th June 2011
YEAR |  | 2003/2004 | 2004/2005 | 2005/2006 | 2006/2007 | 2007/2008 | 2008/2009 | 2009/2010 | 2010/2011 | Total 03/04 - 10/11 | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 20118/2019 | 2019/2020 | 2020/2021 | Total Forecast 11/12 - 20/21
Jubilee Line | Track (km)
| Full renewal | 3.72 | 4.63 | 3.085 | 0.409 | 0.485 | 0 | 0.002 | 1 | 13.331 | 4.703 | 1.731 | 0.37 | 0.48 | 0 | 0 | 0.285 | 1.2206 | 1.2206 | 1.2206 | 11.2308
| Refurbished / life extension | 1.145 | 3.588 | 1.736 | 0 | 0 | 0.714 | 0 | 0.61 | 7.793 | 0.757 | 1.58 | 0 | 2.278 | 0.598 | 2.277 | 3.4729 | 1.0125 | 1.0125 | 0.57563 | 13.5635
| Total track | 4.865 | 8.218 | 4.821 | 0.409 | 0.485 | 0.714 | 0.002 | 1.61 | 21.124 | 5.46 | 3.311 | 0.37 | 2.758 | 0.598 | 2.277 | 3.7579 | 2.2331 | 2.2331 | 1.7962 | 24.7943
| Stations enhancements completed | 0 | 2 | 1 | 3 | 2 | 4 | 6 | 6 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Escalator replacement or major refurbishment | 0 | 1 | 4 | 3 | 8 | 7 | 5 | 8 | 36 | 9 | 5 | 7 | 5 | 2 | 6 | 4 | 1 | 3 | 1 | 43
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 5 | 5 | 5 | 4 | 2 | 4 | 6 | 3 | 39
Northern Line | Track (km)
| Full renewal | 2.416 | 5.328 | 4.692 | 9.54 | 0 | 0.533 | 0.753 | 0.467 | 23.729 | 1.855 | 2.83 | 0.284 | 4.011 | 1.079 | 1.17 | 3.198 | 3.4793 | 3.4793 | 3.4793 | 24.8648
| Refurbished / life extension | 0.791 | 5.086 | 14.507 | 4.344 | 0 | 5.8475 | 2.439 | 5.274 | 38.2885 | 1.848 | 3.677 | 8.912 | 3.114 | 10.374 | 1.18 | 0 | 4.2974 | 4.2974 | 4.2974 | 41.9971
| Total track | 3.207 | 10.414 | 19.199 | 13.884 | 0 | 6.3805 | 3.192 | 5.741 | 62.0175 | 3.703 | 6.507 | 9.196 | 7.125 | 11.453 | 2.35 | 3.198 | 7.7766 | 7.7766 | 7.7766 | 66.8619
| Stations enhancements completed | 0 | 3 | 4 | 2 | 11 | 6 | 8 | 5 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Escalator replacement or major refurbishment | 5 | 7 | 6 | 3 | 7 | 3 | 2 | 1 | 34 | 0 | 3 | 5 | 5 | 5 | 2 | 0 | 5 | 1 | 2 | 28
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 0 | 0 | 0 | 2 | 2 | 3 | 5 | 7 | 4 | 1 | 24
Piccadilly Line | Track (km)
| Full renewal | 5.024 | 1.902 | 6.069 | 8.0892 | 0.645 | 0.107 | 0.237 | 0.481 | 22.5542 | 0.446 | 0 | 2.007 | 0.639 | 3.402 | 0.97 | 0.35 | 3.8182 | 3.8182 | 3.8182 | 19.2686
| Refurbished / life extension | 1.418 | 2.918 | 1.506 | 3.1295 | 0.893 | 3.5545 | 0 | 3.093 | 16.512 | 1.676 | 0.814 | 1.08 | 1.486 | 2.165 | 2.277 | 3.036 | 1.5739 | 1.5739 | 1.5739 | 17.2556
| Total track | 6.442 | 4.82 | 7.575 | 11.2187 | 1.538 | 3.6615 | 0.237 | 3.574 | 39.0662 | 2.122 | 0.814 | 3.087 | 2.125 | 5.567 | 3.247 | 3.386 | 5.3921 | 5.3921 | 5.3921 | 36.5242
| Stations enhancements completed | 0 | 3 | 7 | 6 | 5 | 7 | 4 | 3 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Escalator replacement or major refurbishment | 0 | 5 | 1 | 4 | 3 | 4 | 5 | 2 | 24 | 3 | 2 | 2 | 1 | 3 | 3 | 1 | 4 | 1 | 1 | 21
| Lift replacement or major refurbishment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 2 | 2 | 3 | 1 | 1 | 2 | 0 | 20
Total JNP | Track (km)
| Full renewal | 11.16 | 11.86 | 13.846 | 18.0382 | 1.13 | 0.64 | 0.992 | 1.948 | 59.6142 | 7.004 | 4.561 | 2.661 | 5.13 | 4.481 | 2.14 | 3.833 | 8.5181 | 8.5181 | 8.5181 | 55.3642
| Refurbished / life extension | 3.354 | 11.592 | 17.749 | 7.4735 | 0.893 | 10.116 | 2.439 | 8.977 | 62.5935 | 4.281 | 6.071 | 9.992 | 6.878 | 13.137 | 5.734 | 6.5089 | 6.8838 | 6.8838 | 6.4469 | 72.8163
| Total track | 14.514 | 23.452 | 31.595 | 25.5117 | 2.023 | 10.756 | 3.431 | 10.925 | 122.2077 | 11.285 | 10.632 | 12.653 | 12.008 | 17.618 | 7.874 | 10.3419 | 15.4018 | 15.4018 | 14.9649 | 128.1804
| Stations enhancements completed | 0 | 8 | 12 | 11 | 18 | 17 | 18 | 14 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Escalators replaced or refurbished | 5 | 13 | 11 | 10 | 18 | 14 | 12 | 11 | 94 | 12 | 10 | 14 | 11 | 10 | 11 | 5 | 10 | 5 | 4 | 92
| Lifts replaced or refurbished | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 4 | 1 | 8 | 10 | 9 | 9 | 10 | 8 | 12 | 12 | 4 | 83
Notes
1) Station enhancement work varies in scope depending on the size, complexity and current condition of the station. The volume is recorded against the forecast Delivery Into Service completion milestone
2) The future station programme for TLL records no volumes as all stations were enhanced during Review Period 1 of the PPP.

## Capacity & SFA
LU Network Step- Free Access Enhancements |  |  |  |  | LU Network Station Capacity Projects
| Cells this colour have delivered |  |  |  |  | Cells this colour have delivered
| Year | Station | Lines served | Deliverer(s) |  | Year | Station | Lines served | Deliverer(s)
| 2004/05 | Earl's Court | District | LU |  | 2004/05 | Elephant & Castle | Bakerloo / Northern | LU
| 2005/06 | Wembley Park | Metropolitan / Jubilee | LU |  | 2005/06 | Wembley Park | Metropolitan / Jubilee | LU
|  | Brixton | Victoria | LU |  |  | Brixton | Victoria | LU
| 2006/07 |  |  |  |  | 2006/07
| 2007/08 | Heathrow Terminal 5 | Piccadilly | BAA |  | 2007/08 | Walthamstow Central | Victoria | LU
|  | Oakwood | Piccadilly | Tube Lines
| 2008/09 | Pinner | Metropolitan | LU |  | 2008/09 | Covent Garden | Piccadilly | LU
|  | Acton Town | Piccadilly | Tube Lines
|  | Finchley Central | Northern | Tube Lines
|  | Hendon Central | Northern | Tube Lines
|  | Roding Valley | Central | LU
| 2009/10 | Edgware | Northern | Tube Lines |  | 2009/10 | Shepherd's Bush | Central | LU
|  | High Barnet | Northern | Tube Lines |  |  | Wood Lane | Circle & H&C | Westfield
|  | Wood Lane | Circle & H&C | Westfield
|  | Golders Green | Northern | Tube Lines
|  | Hainault | Central | LU
| 2010/11 | Southfields | District | LU |  | 2010/11 | King's Cross St Pancras | Circle / H&C / Metropolitan / Piccadilly / Northern / Victoria | LU
|  | Kingsbury | Jubilee | LU
|  | Euston Square (Westbound) | Circle / H&C / Metropolitan | LU
|  | King's Cross St Pancras | Circle / H&C / Metropolitan / Piccadilly / Northern / Victoria | LU
| 2011/12 | Green Park | Piccadilly / Jubilee / Victoria | LU |  | 2011/12 | Blackfriars | District / Circle | Network Rail
|  | Blackfriars | District / Circle | Network Rail |  |  | Farringdon | Circle / H&C / Metropolitan | Network Rail
|  | Farringdon | Circle / H&C / Metropolitan | Network Rail |  |  | Highbury & Islington (new exit concourse) | Victoria | LU
[7 empty] | Cannon Street | District / Circle | Hines UK
[7 empty] | Stratford | Central / Jubilee | LU / Westfield
| 2012/13 |  |  |  |  | 2012/13 | Finsbury Park (spiral stairs to LU platforms) | Piccadilly / Victoria | LU
| 2013/14 | Paddington H&C | H & C | LU |  | 2013/14 | Paddington H&C | H & C | LU
| 2014/15 |  |  |  |  | 2014/15
| 2015/16 | Bank* | W&C | LU/Bloomberg |  | 2015/16 | Bank* | W&C | LU / Bloomberg
| 2016/17 | Bond Street | Jubilee / Central | LU |  | 2016/17 | Bond Street | Jubilee / Central | LU
|  | Tottenham Court Road | Northern / Central | LU |  |  | Tottenham Court Road | Northern / Central | LU
| 2017/18 |  |  |  |  | 2017/18
| 2018/19 | Victoria | Circle / District / Victoria | LU |  | 2018/19 | Victoria | Circle / District / Victoria | LU
|  | Whitechapel | District / H & C | Crossrail |  |  | Whitechapel | District / H & C | Crossrail
|  | Barbican | Circle / H&C / Metropolitan | Crossrail |  |  | Vauxhall** | Victoria | LU
|  | Ealing Broadway | District / Central | Crossrail
|  | Vauxhall ** | Victoria | LU
| 2019/20 |  |  |  |  | 2019/20
| 2020/21 | Finsbury Park | Piccadilly / Victoria | LU |  | 2020/21 | Finsbury Park | Piccadilly / Victoria | LU
|  | Bank | Northern (incl DLR interchange) | LU |  |  | Bank | Circle / District / Central / Northern | LU
| Notes |  |  |  |  | Notes
| * Bank W&C - delivery date subject to developer's implementation programme |  |  |  |  | * Bank W&C - delivery date subject to developer's implementation programme
| ** Vauxhall - forecast completion reflects the latest planning assumption. |  |  |  |  | ** Vauxhall - forecast completion reflects the latest planning assumption.
Note on K7: allanthomson: An LU project with Tube Lines as main delivery contractor
Note on K15: allanthomson: LU Project with Tube Lines as delivery contractor

## Upgrade Capability_Capacity
Line Upgrades - Capability and Capacity Increases
Line | Upgrade Delivery | Capacity Increase | Aggregate Capability Increase | Train km - 2011 (million) | Forecast Train km post upgrade | % Increase in train km
Bakerloo (Deep Tube Programme) | In development phase |  |  | 3.4607 | TBC | TBC
Piccadilly (Deep Tube Programme) |  |  |  | 11.5971 | TBC | TBC
Central | - | - | - | 11.5261 | - | -
Victoria | 2012 | 21% | 18% | 5.1683 | 6.6096 | 27.89%
Waterloo & City | delivered in 2006 | 25% | - | 0.28577 | - | -
Jubilee | 2011 | 33% | 21% | 6.9545 | 10.3098 | 48.25%
Northern | 2014 | 20% | 20.4% | 10.6375 | 15.0893 | 41.85%
Circle/Hammersmith & City | 2018 | 65% | 17.6% | 19.5237 | 25.1489 | 28.81%
Metropolitan | 2018 | 27%
District | 2018 | 24%
Notes
The Sub-Surface Upgrade is due to complete in 2018, however many of the journey time and capacity improvements will be realised earlier than this
The Journey Time Capability increase forecast on the Sub-Surface Upgrade is an average of the increase of the SSL North and South sections
Train kilometres on the Sub-Surface lines are forecast as a total for all sub-surface lines
The timing and exact scope of the Bakerloo and Piccadilly line upgrades are under development as part of the Deep Tube Programme

## Completed Milestones
London Underground Investment Programme Major Milestones
Completed milestones - achievements to 2010/11
Waterloo & City Line Upgrade |  | Wembley Park Station
2006 | 25% additional capacity and journey times reduced by approximately 12% | 2006 | Modernisation and capacity enhancement completed to meet the demands of the new stadium
Enhanced reliability and a smoother ride for LU customers
King's Cross St. Pancras Station Development
Jubilee Line 7th Car Project |  | 2009 | New Northern line ticket hall opened
2006 | A seventh car was added to all Jubilee line trains, providing 17% additional capacity | 2010 | Station now fully accessible with opening of a lift to Northern line platforms
|  | 2010 | Station size now quadrupled and capacity increase to meet 100,000 peak demand during Olympics
District line train refurbishment
2008 | Full refurbishment of existing District line trains completed | Covent Garden
|  | 2007 | Completion of congestion relief project
Victoria Line Upgrade
2011 | Over three quarters of the Victoria line's new trains are now in customer service | Heathrow Terminal 5
2011 | New Victoria line control centre in operation | 2008 | Heathrow Terminal 5 station on the Piccadilly line completed
2011 | Victoria line signalling replaced
Wood Lane
Sub-Surface Upgrade |  | 2008 | Wood Lane, the first new Tube station on an existing line in 70 years, opened
2009 | New service pattern on Circle and Hammersmith & City lines introduced, increasing service frequency to Hammersmith and enabling the line to operate more reliably
2010 | First new air-conditioned trains running on the Metropolitan line | Shepherd's Bush Station Refurbishment
2011 | Victoria line signalling replaced | 2008 | Shepherd's Bush Central line station fully rebuilt with new and enlarged ticket hall
Infrastructure Renewal |  | Stratford (Regional) station
2011 | Over 200km of track replaced between 2003 and January 2011 | 2011 | Complete redevelopment of station including new entrances, ticket halls, subways, concourses, lifts and platforms
2011 | Over 180 escalators and lifts replaced or refurbished between 2003 and January 2011
Station Modernisations / refurbishments
Connect Radio |  | 2011 | More than half of LU's 270 stations have now been modernised or refurbished
2008 | New communication system rolled out across all LU lines, delivering a more resilient system, better customer information and improved safety
Step-free Access
|  | 2011 | 62 LU stations are now step-free from street to platform

## Future Major Milestones
London Underground Investment Programme Major Milestones
Line Upgrades - Future Outline Programme |  | Outline Programmes of key enablers - major station capacity schemes and tunnel cooling
Victoria Line Upgrade |  | Paddington Station Congestion Relief
2011 | Start to control Victoria line operations from the new service control centre | 2012 | Start on site - station fit out final scheme
2011 | Full service operation for 09 Tube stock | 2013 | Completion (DfT target)
2012 | Demonstration of line upgrade capability
2013 | Victoria line upgrade programme completion (DfT Target) | Tottenham Court Road Station Congestion Relief
|  | 2011 | Completion of the Northern line blockade
Jubilee Line Upgrade |  | 2015 | Complete Phase 1 (partial opening of new plaza ticket hall)
2011 | J5 section commissioned and revenue service started | 2016 | Delivery into service (DfT Target)
Northern Line Upgrade |  | Bond Street Station Congestion Relief
2011 | Complete negotiations with Thales to enable placing of new Supplemental Agreement or propose new strategy | 2012 | Start structural demolition works
|  | 2013 | Start of main tunnelling operations (DfT Target)
Deep Tube Programme (Bakerloo and Piccadilly line upgrades) |  | 2015 | Tunnelling set up decommissioned
2011 | Completion of testing and trials strategy | 2017 | Completion (DfT Target)
2015 | Delivery of prototype for low energy, higher capacity train for Piccadilly and Bakerloo lines
Victoria Station Upgrade
SSR Upgrade |  | 2011 | Elliott House demolition starts
Trains and Signalling |  | 2014 | Northern ticket hall - civils complete (including removal of traffic management)
2011 | Trains - S7 test train delivered to London and available for testing | 2016 | Southern ticket hall - station operations room complete
2011 | Automatic Train Control - appoint contractor | 2016 | Northern ticket hall - access to Victoria line and London Fire and Emergency Planning Authority shaft, delivery into service (DfT Target)
2013 | Roll out of new air-conditioned trains on Metropolitan line complete (DfT target) | 2018 | Bring into Use (DfT Target)
2014 | Roll out of new air conditioned trains on Circle, Hammersmith & City lines complete (DfT Target)
2016 | Roll out of new air conditioned trains on District line complete (DfT Target) | Bank Congestion Relief (Northern Line)
2018 | Full signalling upgrade across the Sub-Surface network complete (DfT Target) | 2012 | RIBA D design accepted phase complete
|  | 2012 | Transport Works Act Order submission
Power Upgrade |  | 2015 | Start on site
2011 | Package 1a (Neasden Depot) - available to supply traction power | 2021 | Bring into Use (DfT Target)
2011 | Eastcote transformer rectifier 2 - commissioned and energised
2011 | Sub Surface Railway main power supply upgrade - completion of concept design for all implementation sites | Cooling the Tube Programme (Victoria line)
2013 | P8M substation full beneficial use (All S7 Sites) | 2011 | All Victoria line tranche 3 mid-tunnel vent shafts - all fans and associated equipment available
2013 | Package 2 (Circle and Hammersmith & City lines traction) | 2012 | All Victoria line tranche 3 mid-tunnel vent shafts - sites brought into beneficial use
2014 | Package 4 (new bulk supply point at Edgware Road) delivered | 2012 | Out of service fans phase 4 – all fans available for beneficial use
2014 | Package 3B (Circle line traction to enable Automatic Train Control)
2015 | Package 3A (District line east) - delivered
2018 | Sub-Surface lines power works complete (DfT Target)

## Train km forecast breakdown
Train km forecast by line (million)
Line | 2011/12 | 2012/13 | 2013/14 | 2014/15
Bakerloo | 3.5084 | 3.5363 | 3.5583 | 3.5708
Central | 11.6427 | 11.7442 | 11.8673 | 11.9062
Victoria | 5.6515 | 6.3091 | 6.5883 | 6.6096
Waterloo & City | 0.2861 | 0.28693 | 0.28657 | 0.28724
Jubilee | 8.0098 | 10.1513 | 10.2633 | 10.3098
Northern | 11.0884 | 11.2956 | 11.4864 | 15.0893
Piccadilly | 11.7608 | 11.9195 | 11.9792 | 12.018
Circle/Hammersmith & City | 20.4651 | 21.1957 | 21.8474 | 22.6561
Metropolitan
District
Note: The line-by-line train km forecasts reconcile to the full Network total forecast in the TfL Business Plan. The forecasts are based on the network forecast for % of scheduled service operated, and may by line vary on a year-by-year basis.