## Stakeholder Analysis
Stakeholder Analysis
Stakeholder Name | Department / Category | Interest / Stake | Power / Influence | Supportiveness | Success Criteria and Needs | Communication Needs | Concerns | Knowledge and Expertise (How can they help?) | Resistance to change | Priority | Action (What do you need to do?)
LBTH Planning Team | Working Group | Need the successful completion of the project to continue with roll-out of the FRP. | High | High | Completed outcomes from set out in Project Brief. | Working group meetings, direct communication with Project Manager. | Successful delivery of the FRP upgrades work. Improvements in the waste and recycling performance of the Opportunity Area. | Understand the requirements for the project, knowledge of Tower Hamlets contacts. | n/a | High | Set up regular catch-ups with Project Manager and working group meetings
LBTH Waste Team | Working Group | Need the successful completion of the project to continue with roll-out of the FRP. | High | High | Completed outcomes from set out in Project Brief. | Working group meetings, direct communication with Project Manager. | Successful delivery of the FRP upgrades work. Improvements in the waste and recycling performance of the Opportunity Area. | Understand the requirements for the project, knowledge of Tower Hamlets contacts. | n/a | High | Set up regular catch-ups with Project Manager and working group meetings
Tower Hamlets Housing Forum | Housing | Achieve the housing vision, including sub-groups for Public Realm & Asset Management. | Medium | Medium | Meet the needs of the people who live in their estates, improving the quality of facilities. | Formal communications, expect slow replies due to the numerous different members. | May have concerns of the outcome of the study which could have financial implications. | Understand the key stakeholders across the Executive Membership, their support will be key to successful engagement with other Housing Associations & managing agents. | This can be overcome by explaining the benefits of the project | Medium | Engage with the Housing Forum early on in the process, as due to their contacts, they may be able to facilitate successful engagement with landlords and managing agents.
GLA | Working Group | Need the successful completion of the project to continue with roll-out of the FRP. | High | High | Completed outcomes from set out in Project Brief | Working group meetings, direct communication with Project Manager. | Ensuring the Mayor's environmental vision / strategy is met. | Understand the requirements for the project, knowledge of Tower Hamlets contacts. | n/a | High | Set up regular catch-ups with Project Manager and working group meetings
Collection crews | Operations | Need the successful completion of the project to continue with roll-out of the FRP, creating better conditions for bin stores and better collections. Improved H&S implications due to better waste storage. | Low | High | Completed outcomes from set out in Project Brief | Formal communications from the Waste Team about changes to the bin stores/ bin areas. | May have concerns over a number of additional bins requiring collections, or new bins being placed in areas and the crews not being informed. | Knowledge of historical issues with certain blocks and understands collection requirements. | n/a | Low | Hold toolbox talks with relevant crews in advance of the improvements to achieve their buy-in.
Councillors/ Members | Council | Need the successful completion of the project to continue with roll-out of the FRP. | High | High | Completed outcomes from set out in Project Brief. | Regular updates so that they are abreast of work being done should their residents query them. | May have concerns of the outcome of the study which could have financial implications. | Understand the requirements for the project, knowledge of Tower Hamlets contacts. | This can be overcome by explaining the benefits of the project. | High | Regular communications such as meetings, briefing notes and reports on the status of the FRP rollout.
LBTH Communications Team | Operations | Effective communications to residents about the FRP and changes to their service. | Medium | Medium | Successful engagement with residents and landlords. | Regular updates and discussions regarding planning and progress of the communications plan. |  | Help choose the best methods of communication and promote the FRP so that it reaches the residents. | n/a | Low | Engage with communications team early on in the process to plan the communications campaign with them. Hold regular meetings to plan and monitor progress and engagement with the communications materials.
Managing Agents/Landlords | Housing | Achieve the housing vision. | High | High | Meet the needs of the people who live in their buildings, improving the quality of facilities. | Formal communications, expect slow replies due to the numerous different members. | May have concerns of the outcome of the study which could have financial implications. | Understand the key stakeholders across the buildings, their support will be key to successful engagement with residents. | This can be overcome by explaining the benefits of the project. | Medium | Compile list of landlords and plan priority target list to engage with initially. Make contact and chase those who have not responded. Utilise the landlord excels provided to help with engagement and buy-in - couch FRP as a means to benefit them both financially and with resident satisfaction levels.
Residents | External | Need the successful completion of the project to have FRP level bin stores and bin areas to utilise. | Medium | Medium | Improved bin stores / areas to utilise, which help facilitate their full engagement in the recycling service. | Communications throughout the whole process about the changes being made and what to expect. | Ease of use for the waste and recycling services. | Providing feedback on the FRP and championing changes with the landlords/managing agents. | n/a | Medium | Regular communications with residents about the changes and feedback on the FRP. Communication will need to be on-going to transient nature of the population.

## Stakeholder Matrix
High
| Opponents | Allies
| engage & consult | Manage closely
| pay attention | include in governance
| aim to move to right | & decision-making
Power & Influence
| Apathetics | Defenders
| Monitor | Keep informed
| Inform via general | anticipate and meet needs
Low | communications
| Low | High
Supportiveness